# StreamNet

BPA Project Number 198810804

Fiscal Year 2000

Third Quarter Progress Report

April 1, 2000 through June 30, 2000

Submitted to:

Bonneville Power Administration

Submitted by:

Pacific States Marine Fisheries Commission

Table of Contents

Introduction………………………………………………………………………..………	Page   2

## Objective 1.   Data Development…………………………………………………..……	Page   3

### Task 1.1.  Anadromous Fish………………………………………………….....	Page   3

### Task 1.2.  Resident Fish and Other Aquatic Species…………………..…….	Page 10

### Task 1.3.  Habitat…………………………………………………………..……..	Page 14

### Task 1.4.  Facilities……………………………………………………….………	Page 15

### Task 1.5.  Habitat Restoration / Improvement Projects………………..……..	Page 17

### Task 1.6.  Sub-Basin Planning………………………………………….………	Page 18

### Objective 2.  Data Management…………………………………………...……………	Page 19

### Objective 3.   Library……………………………………………………………………..	Page 31

### Objective 4.  Service to Fish and Wildlife Program Activities………………………..	Page 34

### Objective 5.  Project Management / Coordination…………………………………….	Page 38

### Work Planned for Next Quarter………………………………………………………….Page 45

Introduction

This report presents accomplishments of the StreamNet project for the third quarter of Fiscal Year 2000.  The report is organized to clearly link accomplishments by the project participants to the tasks and responsibilities detailed in the annual Statement of Work.  It is organized by task for all project participants rather than by individual project participant as in previous years.  This report also represents a new approach that provides greater flexibility and the ability to produce reports in several formats.  It is based on a relational database containing the details of the Work Statement and the accomplishments by each project participant.  This allows rapid compilation of a report for the entire project as well as the ability for each participant to develop a report specific to their activities.  Since not all tasks are addressed each quarter and the project participants often work on different tasks, some tasks do not show activity in the third quarter.

Project participants contributing to the StreamNet project were Columbia River Intertribal Fisheries Commission (CRITFC), US Fish and Wildlife Service (FWS), Idaho Department of Fish and Game (IDFG), Montana Fish, Wildlife and Parks (MFWP), Oregon Department of Fish and Wildlife (ODFW), Pacific States Marine Fisheries Commission (Region), Shoshone-Bannock Tribes (SBT), and Washington Department of Fish and Wildlife (WDFW).

Page 2 of 45

Objective	1	Data Development

Increase the knowledge base concerning the region’s fish and wildlife resources through the acquisition of new information that responds to

emerging needs as well as the updating and enhancement of production and survival trends and other existing information.

Objective	1	Data Development

Task	1	Anadromous Fish

Acquire data sets related to salmon, steelhead and, where data are readily available, other anadromous fish populations from the multiple agencies, tribes

and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.a	Distribution, Life History (use type), and Barriers

Document the occurrence and distribution of anadromous species, related barriers to migration, and life history characteristics

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Develop an associated barriers database. Available, existing 	Identified and attached constraints (barrier types) to preliminary barriers

information on natural barriers is particularly lacking, so the 	for anadromous fish. The database is still not ready for exchange, but the

barriers dataset should be expected to be incomplete.	constraints is one more piece that is required.

ODFW	1	Populate the FishBarrier table by rectifying all anadromous 	Continued internal efforts to populate the FishBarrier table as new

distribution with the barriers database:	distribution and barrier information was identified and performed QA/QC on

In the Lower Columbia HUCs (below the Willamette). 	the database.

In the Mid-Columbia HUCs (between the Willamette & John Day

basins).

In the Upper Columbia HUCs (upstream of the John Day)

ODFW	2	Update, maintain, and correct the 100k distribution event tables	Ongoing.

for Oregon as needed and applicable.

ODFW	3	Update the 100k distribution event tables:	Performed extensive q/a on all anadromous salmonid distribution event

For the Willamette basin using documentation records derived	data.  Identified and fixed all distribution event records that either overlap,

from the W-DESH 2 project.	fall just shy of being adjacent or that are adjacent, but have the same

For the John Day basin	usetype. Also reviewed were cases where the end measure of the event

For the NE Oregon basins	exceeds the length of the stream and inconsistent measures across HUC

boundaries.

Objective	1	Task	1.a	Fiscal Year 2000 Third Quarter 	Page 3 of 45

ODFW	4	Test an automated approach to populate the FishBarrier table by 	Continued to refine the process of distribution and barrier data rectification.

rectifying all anadromous distribution with the barriers database

using the Tillamook basin

ODFW	5	Populate the FishBarrier table for the Willamette basin by	Completed during second quarter.

rectifying all anadromous distribution with the barriers database.

ODFW	7	Develop a database to capture fish presence survey data to help 	Continued to develop the Fish Presence Survey Database in MS Access to

populate the DistPresence table.	capture Oregon’s upper fish distribution and culvert information collected

by ODF/ODFW surveyors.  To date, 792 Records have been entered in the

Columbia basin.

ODFW	8	Develop a database for capturing incidental species observations 	Continued to make enhancements to the database structure. Currently, 28

not routinely reported in agency documents.	of the 80 records in the database are for Col. Basin streams.

ODFW	9	Locate documentation information in the Willamette (W-DESH 2 	Completed during the first quarter.

Project) in order to populate the DistPresence table.

ODFW	10	Assist in identifying appropriate references for anadromous fish 	Ongoing.

distribution data in order to populate the DistPresence table.

ODFW	11	Assist project staff with identifying appropriate references for 	Ongoing.

anadromous fish distribution.

ODFW	12	Assist in adding new barrier records to the Barriers database 	Efforts this quarter involved identifying information sources to populate

including providing references for any information in the database.	missing information for existing barrier records.

ODFW	14	Using project camera, photograph Columbia basin barriers that	Reviewed the list of 195 photographs that StreamNet has for Oregon in

are maintained in the database and provide to PSMFC.	order to compile a list of photos that are still needed. Due to staff

vacancies, no further effort is anticipated on this task.

ODFW	16	Transfer all 250K Lamprey distribution data into the 100K data 	Completed during second quarter.

structure using data from ORIS.

ODFW	17	Assist as needed with tabular data collection and compilation	Ongoing. Worked with regional SN staff to reconcile LLID differences

tasks in order to help produce anadromous salmon distribution 	between ODFW and StreamNet data.

coverages.

ODFW	19	Update the Barrier database with information obtained during 	Updated the master barrier database to 2000.2 format and made efforts to

conduct of other project activities and submit updated	identify information sources to populate missing data fields for existing

information to PSMFC.  Four updates anticipated.	barrier records.

Objective	1	Task	1.a	Fiscal Year 2000 Third Quarter 	Page 4 of 45

Region	1	Compile distribution updates (tabular events) as they arrive.  	1)  Compiled and QA'd anadromous distribution updates from ODFW.

Create distribution GIS coverages from these event tables, and 	Generated new GIS coverages from these events and posted these to the

post the shape files to the StreamNet website as downloadable 	StreamNet website as shape files for the query system and downloadable

GIS coverages	GIS coverages for public access.

2)  Developed a procedure to summarize total anadromous distribution

(salmon/steelhead) by cataloging unit (HUC).  Created a GIS coverage and

metadata of the results and posted these files to the StreamNet web site.

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.b	Adult Abundance

Escapement, redd counts, trap counts, dam counts

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Compile 1999-field season redd count data into Idaho's existing 	Added new information from 1999 field season into the IDFG StreamNet

database.	anadromous redd count database.

IDFG	2	The data will then be migrated to the current version of the PNW 	Migration of adult abundance data into the IDFG StreamNet database

1:100,000-scale hydrography.	management system awaits completion of  the system and the associated

100K LLID hydrography.

IDFG	3	Write new routines to convert the redd count data to the 	Work to prepare data exchange routines is awaiting completion of the IDFG

StreamNet data exchange format (2000.1) and submit to PSFMC.	 StreamNet database management system.

ODFW	1	Update StreamNet abundance and indices data (escapement,	CREP documents were organized and reviewed for relevant data to

redd counts, trap counts, peak/other spawning counts, etc.) 	for StreamNet.  Due to the departure of our abundance database staff person,

OR populations within the Columbia Basin (updated through	and the anticipated delays in filling the position, it is likely that no future

1998). Three updates planned.	updates will be submitted to regional StreamNet this fiscal year.

ODFW	2	Compile some* of the Columbia basin abundance field data 	Continued to update existing trends to the 2000.2 data exchange format.

gathered by the CREP crews into the SN abundance dataset.	Due to the departure of our abundance database staff person, and the

anticipated delays in filling the position, it is likely that no future updates will

be submitted to regional StreamNet this fiscal year.

ODFW	3	Update existing abundance trends to the new 2000.1 exchange 	Updated the abundance database and interface to conform to the latest

format standards as trends are updated through 1998.  Three 	accepted exchange format  - DEF 2000.2.

updates planned.

ODFW	4	Revise and enhance the Abundance data entry interface to suit 	Due to the departure of our abundance database staff person, no efforts

project needs.	were made during this quarter.

Objective	1	Task	1.b	Fiscal Year 2000 Third Quarter 	Page 5 of 45

ODFW	5	Opportunistically review all 60K series trends for Oregon and 	Continued to update existing trends to the 2000.2 data exchange format

transfer to 50K series trends or delete them if they cannot be 	and some trends were updated through 1998.  Due to the departure of our

validated.	abundance database staff person, and the anticipated delays in filling the

position, it is likely that no future updates will be submitted to regional

StreamNet this fiscal year.

ODFW	6	Review all Oregon trends with personal communication	Due to the departure of our abundance database staff person, no efforts

references in the Abundance database and update to hardcopy	were made during this quarter.

reports if possible.

WDFW	1	Update and exchange hatchery returns through 1998 in the 	LLID assignment was finished for hatchery facilities as a precursor for

StreamNet data exchange format (2000.1).	conversion and exchange of the return data, which are ready.

WDFW	2	Update and exchange natural spawner data through 1998 (CR, 	1) 1998-99 Hanford Reach spring, fall chinook natural spawning data

PS)	completed, ready for conversion and exchange.

2) 1998-99 PS chum updated in the internal database; ready for conversion

and exchange.

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.c	Juvenile Data

Sample records, abundance indices (as available)

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Incorporate the IDFG General Parr Monitoring (GPM) data into	The IDFG General Parr Monitoring database has been preliminarily migrated

the IDFG database.	into the IDFG StreamNet database management system. Final migration is

awaiting completion of bringing the 100K hydrography into the system.

Cross-reference of species codes have been completed. Point locations of

approximately 80% of the  GPM transects have been linked to the 100K

LLID hydrography and measures determined. Additional work is needed to

identify additional locations and to link to the hydrography.

IDFG	2	If possible, convert the IDFG GPM (juvenile fish) data into 	Conversion of the IDFG General Parr Monitoring data to StreamNet is

exchange format and submit to PSMFC.	awaiting final migration into the IDFG StreamNet database management

system and adoption of a data exchange format by StreamNet.

ODFW	1	Prepare and submit recommended modifications of the draft 	Due to the departure of our abundance database staff person, no efforts

Juvenile abundance portion of the DEF.	were made during this quarter.

ODFW	2	Update Oregon's 10 existing juvenile abundance records to 	New DEF has yet to be proposed or adopted. No efforts were made this

approved DEF standards.	quarter.

Objective	1	Task	1.c	Fiscal Year 2000 Third Quarter 	Page 6 of 45

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.d	Harvest

In-river, terminal, and other harvest, as available

Project	Work Element	Accomplishments, Third Quarter

ODFW	1	Provide statewide 1997 tributary sport harvest from angler	Acquired, compiled, and maintained in-season updates of catch estimates

harvest cards.	by species in Columbia River sport and commercial fisheries.

WDFW	1	Update and exchange salmon harvest data through 1998, 	Columbia River commercial terminal and zonal harvest figures updated,

beginning with Columbia River commercial, sport and treaty 	ready for conversion and exchange.

harvest.

WDFW	2	Update and exchange steelhead harvest through 1997 if	Assisted in review of new steelhead Catch Record Card area coding

feasible.	scheme for 2000-2001 and preparation of cross-reference table while

awaiting final release of 1997 catch statistics.

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.e	Hatchery Production

Releases, disposition, straying

Project	Work Element	Accomplishments, Third Quarter

FWS	2	Transform into format 32	Answered Western Washington FRO inquiries regarding submitted data

IDFG	1	Compile IDFG 1999-field season hatchery returns data into	Added new information from 1999 field season into the IDFG StreamNet

Idaho's existing database.	anadromous hatchery returns database.

IDFG	2	Migrate the data to the PNW 1:100,000-scale hydrography,	Work to prepare data exchange routines is awaiting completion of the IDFG

write new routines to convert the data to the StreamNet data	StreamNet database management system.

exchange format (2000.1), and submit to PSFMC.

ODFW	1	Develop the ability to remotely access the Portland mainframe 	Worked with Portland information systems staff to get access to the

hatchery data and download hatchery return data consistent	Portland mainframe hatchery data.

with the StreamNet contract.

ODFW	2	Compile 1997 egg-take data and submit to PSMFC	Worked with HIMS data manager to get the hatchery return data from the

mainframe

ODFW	3	Develop an automated procedure to update egg-take data and	Worked with HIMS data manager to get the hatchery return data from the

to capture and incorporate historic data into the StreamNet	Mainframe

database.

Objective	1	Task	1.e	Fiscal Year 2000 Third Quarter 	Page 7 of 45

ODFW	4	Compile data on returns to ODFW hatchery facilities (updated	Worked with HIMS data manager to get the hatchery return data from the

for 1997 and part of 1998 returns).	mainframe

Region	1	Assist StreamNet partners with acquisition, development, 	Assisted ODFW in cleaning up the hatchery releases database by

formatting and submission of data.	identifying hatchery release trends (time-series) that failed to be assigned

the appropriate coding ('300,000 trends')

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.f	Natural Production

Survival, production factors, spawner recruit

Project	Work Element	Accomplishments, Third Quarter

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.g	Age

Age/sex composition for returning adults

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Compile IDFG 1999-field season age and sex composition	Added new information from 1999 field season into the IDFG StreamNet

data into our existing database.	anadromous age/sex composition database.

IDFG	2	Migrate the data to the PNW 1:100,000-scale hydrography,	Migration of age/sex composition  data into the IDFG StreamNet database

write new routines to convert the data to the data exchange	management system awaits completion of  the system and the associated

format (2000.1), and submit to PSFMC.	100K LLID hydrography.

ODFW	1	Compile age frequency data (updated for natural spring	Completed during second quarter.

chinook in 1997, available time series for natural steelhead in

OR portion of the Columbia basin).

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.h	Genetics

Areas where genetics data exists and the sources of these data

Project	Work Element	Accomplishments, Third Quarter

Objective	1	Task	1.h	Fiscal Year 2000 Third Quarter 	Page 8 of 45

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.I	Populations

Population delineation, as determined by others

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Incorporate the standard population/run type designations into	Anadromous populations, known as cells or runtypes, in IDFG have been

the IDFG database.	preliminarily linked to the 100K LLID hydrography and incorporated into the

IDFG StreamNet database management system. Finalization of these data

await the final work on the 100K LLID hydrography for the information

system.

IDFG	2	If possible, convert IDFG population/run type data and submit	There is no StreamNet data exchange format for submitting population or

to PSMFC.	runtype geospatial data to StreamNet.

ODFW	1	Produce a cross-reference table of ODFW designated Gene 	StreamNet subbasin delineations have not been modified to sinc with

Conservation Groups (GCG) by subbasin.	ODFW GCGs and it appears unlikely that this will happen this fiscal year.

Therefore, it is not anticipated that any further efforts will be made this

year.

WDFW	1	Compile and exchange Washington SaSI stock status data for 	Compared the upper extent of the SaSI stock status GIS coverage with

anadromous fish using newly developed 2000.1 Data Exchange 	updates made last quarter to the anadromous fish presence and use

Format (DEF)(see Task 2.3).	layers. Identified and eliminated inconsistencies.

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.j	Historic Range

As available at the watershed-level.  Compilation at the reach level is an option if these data are available

Project	Work Element	Accomplishments, Third Quarter

Objective	1	Task  1.j	Fiscal Year 2000 Third Quarter 	Page 9 of 45

Objective	1	Data Development

Task	2	Resident Fish and Other Aquatic Species

Acquire data sets related to resident fish species, and where specifically identified other aquatic species, from the multiple agencies, tribes and

organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.a	Distribution and Life History

Document species occurrence and distribution and life history characteristics

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	As new information becomes available, update and maintain	Collecting permit data continue to be entered into the IDFG StreamNet

the existing IDFG StreamNet distribution dataset for resident	database management system for references. We have not summarized

salmonids and other species of concern that is attached to the	these data, yet, into updated fish distribution geospatial layers.

PNW 1:100,000-scale hydrography.  Include collecting permit

records and annual reports.

MFWP	1	Convert MRIS from the River Reach Numbering system to an	Completed conversion to a temporary " LLID" system to reference streams

"LLID system" (temporary use of MFWP water code).	in MRIS. Added StreamNet measure fields to provide for use of route

measures. Completed initial data gathering and meeting with field biologists

for the 2000 MRIS updates.  Unable to enter data by routes until PNW

hydrography and NHD are completed.

ODFW	1	Produce GIS coverages illustrating rainbow and redband trout 	Processed upper fish distribution point data for the Lower Columbia in an

distribution where available for Columbia basin streams.	effort to enhance existing distribution information.

ODFW	2	Transfer Lahonton cutthroat and white sturgeon 250K resident 	Converted Lahontan Cutthroat distribution data to StreamNet format.

distribution data from ORIS into the 100K data structure and

compare with the current 100K distribution and update

accordingly.

WDFW	1	Update and exchange bull char distribution data at 100K	1) Redesigned the bull char database to reflect new USFWS bull char

resolution if multi-agency agreement on distribution criteria	status, presence, and use category needs. Designed new field maps

can be reached (see Task 2.3).	reflecting both 24K and 100K streams layers. Created new instruction

sheets for field biologists who will participate in the bull char presence and

use update.

2) Generated new maps showing existing bull char presence data, added

maps from WCC mapping parties, and delivered update kits and training

materials to field biologists.

Objective	1	Task	2.a	Fiscal Year 2000 Third Quarter 	Page 10 of 45

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.b	Adult Abundance

Escapement, redd counts, trap counts, dam counts

Project	Work Element	Accomplishments, Third Quarter

MFWP	1	Collect stream fisheries survey data collected for population 	Collected population trend and other survey data up through the 1999 field

trends; genetics and escapement, redd counts, trap count and 	season and all new genetic records from University of Montana Genetics

other counts during visits to biologists.  	Lab.  Entered all genetics data and began entering survey data.

MFWP	2	Collect references for each survey.	References were gathered for each survey when available. Some of the

surveys are not and will not be written in any formal report(i.e., DJ report)

and therefore will be given their own reference ID number and other

required StreamNet documentation by MRIS staff.

ODFW	1	Update existing abundance trends to the new exchange format 	Continued to update existing trends to the 2000.2 data exchange format.

standards as trends are updated through 1998.  Three updates 	Due to the departure of our abundance database staff person, and the

planned.	anticipated delays in filling the position, it is likely that no future updates will

be submitted to regional StreamNet this fiscal year.

ODFW	2	Review all Oregon trends with personal communication	Due to the departure of our abundance database staff person, no efforts

references in the Abundance database and update to hardcopy	were made during this quarter.

reports if possible.

ODFW	3	Update StreamNet abundance and indices data holdings (redd 	Continued to update existing trends to the 2000.2 data exchange format

counts, trap counts, peak/other spawning counts, etc.) for OR 	and some trends were updated through 1998.  Due to the departure of our

populations within the Columbia Basin (updated through 1998).  	abundance database staff person, and the anticipated delays in filling the

Three updates planned.	position, it is likely that no future updates will be submitted to regional

StreamNet this fiscal year.

ODFW	4	Opportunistically review all 60K series trends for Oregon and 	Due to the departure of our abundance database staff person, no efforts

transfer to 50K series trends or delete them if they cannot be 	were made during this quarter.

validated.

Objective	1	Task	2.b	Fiscal Year 2000 Third Quarter 	Page 11 of 45

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.c	Angler Use

Fishing pressure, creel census

Project	Work Element	Accomplishments, Third Quarter

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.d	Hatchery Production

Hatchery production (releases and outplants) for salmonids

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	IDFG resident fish stocking data currently uses an IDFG specific 	Continue to build cross-references of IDFG stocking catalog numbers with

stream and lake locator (Catalog Number). IDFG SN will develop	100K LLID hydrography. The catalog numbers do not have a direct

an ArcInfo compatible event table to cross-reference the catalog 	correspondence with reach numbers, therefore the work is slow and

numbers to LLIDs.	tedious. It involves a lot of on-screen visual examination to ensure accuracy.

IDFG	2	Migrate the IDFG stocking data into the IDFG StreamNet	This component is now waiting completion of a cross-reference between

database, write new routines to convert the data to the data	IDFG stocking catalog numbers and the 100K LLID hydrography.

exchange format (2000.1), and submit to PSMFC.

ODFW	1	Acquire 1997 trout release data  (by species, location, and	Coordinated with ODFW hatchery data staff to develop a process to export

facility) and compile into SN exchange format.	the required information into StreamNet format.  The current bottleneck

seems to be that the ODFW system has a limited number of programming

routines that it can store, and there is no room for any new ones at this time.

WDFW	1	Complete conversion and exchange resident fish stocking data 	1) Continued cleansing duplicate entries found in the pre-1982 resident fish

from 1930-1981, once location coding has been standardized	stocking records. Sent WRIA 62 records to Region 1 fish biologist for

and verified.	intensive comparison to field ledgers maintained in the Regional Office.

2) Began assigning standard location codes (LLIDs) to stocking sites

(streams and lakes).

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.e	Genetics

Areas where genetics data exists and the sources of these data

Project	Work Element	Accomplishments, Third Quarter

MFWP	1	Update genetic spatial and tabular databases that contain the 	Genetic spatial and tabular components were updated through June 2000.

results of genetic analysis of populations of Montana's species	Westslope Cutthroat Trout Genetic Maps by drainage were sent out to

of special concern	state and federal biologists in April 2000.

Objective	1	Task	2.e	Fiscal Year 2000 Third Quarter 	Page 12 of 45

Objective	1  Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.f	Population

Population delineation, as determined by others

Project	Work Element	Accomplishments, Third Quarter

MFWP	1	Maintain spatial delineation of bull trout populations, core and	Updated bull trout core areas with most recent data from MFWP.  Produced

nodal habitat.  Enhance layer with population risk field.  	map depicting changes and sent to past requestors.  Will send new

coverage to StreamNet next quarter.

MFWP	2	Determine westslope cutthroat trout priority areas as part 	Created Westslope Cutthroat Trout Priority Area coverage in April 2000; it

Westslope Cutthroat Conservation Agreement.	has been reviewed and should be finalized next quarter.

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.g	Historic Range

As available at the watershed-level

Project	Work Element	Accomplishments, Third Quarter

MFWP	1	Explore the development of historic range coverages for all of 	Started creation of Historic Distribution by HUC.  Used existing MRIS data

Montana's native species.	and The Nature Conservancy data as a starting block.

MFWP	2	Submit arctic grayling, westslope and Yellowstone cutthroat	Submitted Arctic Grayling, Westslope and Yellowstone Cutthroat Trout

trout historic distribution to StreamNet by June 1.	historic coverages to StreamNet in May 2000. Received historic coverage

of Montana's native fish species from project conducted by TNC.  Will

review and make recommendations to StreamNet as to an exchange format

next quarter.

Region	1	Compile distribution updates (tabular events) as they arrive.  	Formatted metadata for MFWP submission of historic grayling and cutthroat

Create distribution GIS coverages from these event tables, and 	distribution data, and posted this (GIS) data and metadata as

post the shape files to the StreamNet website as downloadable 	downloadable files to the StreamNet website.

GIS coverages

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.h	Status

Population stability index

Project      Work Element								Accomplishments, Third Quarter

Objective	1	Task  2h	Fiscal Year 2000 Third Quarter 	Page 13 of 45

Objective  1   	Data Development

Task	3	Habitat

Acquire data sets related to fish habitat from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in

standardized, consistent formats for the following categories:

Objective  1   	Data Development	Task   3   Habitat

Task	3.a	Stream / Watershed Habitat

Incorporate applicable stream and watershed level habitat and stream survey data, as these become available

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	IDFG StreamNet will incorporate the IDFG General Parr	No new work has been accomplished on stream habitat in the IDFG

Monitoring (GPM) habitat data into its database.	General Parr Monitoring database. We are awaiting completion of the 100K

LLID hydrography and the IDFG StreamNet database management system

(see item 1.1c).

IDFG	2	If possible, convert the IDFG GPM habitat data into regional	Awaiting migration of IDFG General Parr Monitoring data into the IDFG

format and submit to PSMFC.	StreamNet database management system and a StreamNet data exchange

format.

MFWP	1	Determine what type of habitat data and at what scale Montana 	Met with MFWP and Federal biologists on what habitat data is gathered.

state and federal fisheries biologists are collecting during	Most of the habitat data is gathered by federal biologists by several

regional visits.	different methods.  Currently, we are working on a standardized stream

form that could potentially facilitate gathering this habitat data in the future.

Objective	1	Data Development	Task   3   Habitat

Task	3.b	Water Quality

Incorporate existing Clean Water Act 303(d) data and other water quality data as applicable

Project	Work Element	Accomplishments, Third Quarter

Region	1	Create GIS water quality data coverages from the 303(d) data	Compiled metadata for 303(d) water quality data and developed a web

and post to the StreamNet web site.	page (http://www.streamnet.org/303d.html) to distribute this data &

metadata on the StreamNet web site

Region	3	Georeference (assign LLIDs) to the stream nutrient data	Georeferenced approximately 50% of the stream nutrient data (work

ongoing).

Objective	1	Task	3.b	Fiscal Year 2000 Third Quarter 	Page 14 of 45

Objective	1	Data Development	Task   3   Habitat

Task	3.c	Miscellaneous Habitat Data

Project	Work Element	Accomplishments, Third Quarter

MFWP	2	Update and incorporate MFWP water leasing and dewatered 	Updated Instream Flow and Water Leasing databases and incorporated

stream list data into MRIS.	into MRIS.  Also updated this information on the MRIS web site.

ODFW	1	Update key stream management area designations for OR	No changes have been made to these data layers therefore no efforts

including FEMAT key watersheds, AFS aquatic diversity areas,	were made this quarter.

ODFW coho source river reaches, ODSL Essential Salmon

Habitat and Priority Areas.

Objective	1	Data Development

Task	4	Facilities

Acquire data sets related to fishery-related facilities and structures from the multiple agencies, tribes and organizations within the Columbia Basin and

compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   4   Facilities

Task	4.a	Dams and Fish Passage Facilities

Enhance the existing StreamNet dams data set by updating relevant data from the Pacific Northwest Hydropower Database and Analysis System (NWHS)

and the National Inventory of Dams

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Add enhanced data from the National Inventory of Dams to the 	Worked to obtain code definitions to enhanced dams database from Idaho

IDFG StreamNet information system.	Department of Water Resources and National Inventory of dams. Made

additional table structure and programming modifications to the dam

component of the IDFG StreamNet database management system.

IDFG	2	Write export routines and submit the dams data to PSMFC in 	Still awaiting final completion of IDFG StreamNet database management

StreamNet Data Exchange Format.	system before developing routines to exchange dam information with

central StreamNet.

ODFW	1	Update the dam database with information obtained during the 	Added updated RRNs and LLIDs, imported NIDDamID, RRN, and Prop field

conduction of other project activities.  Four updates planned	data from the NID into the Dam table and added an OwnerType lookup

table.

Region	1	Convert remaining 250K Dams information in StreamNet	Georeferenced all dams, where possible, with non-stream coordinates

database to the 100K system. Create a 100K Dams and Fish	based on longitude/latitude for use by the StreamNet query system.  Tied

Passages facilities GIS coverage and distribute it via the	WA & OR dams to 1:100k stream locations, where possible, and submitted

StreamNet website.	these results to ODFW and WDFW for their review.

Objective	1	Task	4.a	Fiscal Year 2000 Third Quarter 	Page 15 of 45

Objective	1	Data Development	Task   4   Facilities

Task	4.b	Hatcheries

Update and maintain a dataset on anadromous and resident hatchery facilities containing information on location, design, management and authorization

Project	Work Element	Accomplishments, Third Quarter

FWS	1	Continue checking for submitted FWS update records, update 	Submitted updated hatchery facilities file

records when appropriate, submit to StreamNet

IDFG	1	IDFG StreamNet has attached the IDFG hatchery database to	Hatchery facilities is complete and linked to 100K LLID hydrography.

the current 1:100,000-scale PNW hydrography. The data will be 	Awaiting final adoption of hydrography into IDFG StreamNet database

incorporated into the IDFG database and submitted to PSMFC.

IDFG	2	Supporting hatchery structures, such as weirs and traps, will be 	No new work on supporting hatchery structures, such as weirs and traps.

added to the hatcheries database.

ODFW	1	Locate at least one public domain photo of each hatchery in 	Reviewed the list of 195 photographs that StreamNet has for Oregon in

Oregon and provide to PSMFC.	order to compile a list of photos that are still needed. Due to staff

vacancies, no further effort is anticipated on this task.

ODFW	2	Update OR hatchery facilities data to the 99 version of the 	Imported the latest version of the Hatchery table and began the process of

exchange format and submit to PSMFC.	updating it.

Region	1	Convert hatcheries data to the 100K system.  Create a regional 	Georeferenced all hatcheries, where possible (OR & WA only), with non-stream

hatcheries GIS coverage and distribute it via the StreamNet 	coordinates based on longitude/latitude for use by the StreamNet query

website.	system.  Tied Oregon hatcheries to 1:100k stream locations, where possible,

and submitted these results to ODFW for their review.

WDFW	1	Provide standard geo-spatial coordinates (Longitude-Latitude)	Reviewed and corrected LLID assignments to hatchery facilities based on

for each facility.	hatchery returns and hatchery facilities data work. Added LLIDs for

facilities not in the returns dataset.

Objective	1	Data Development	Task   4   Facilities

Task	4.c	Diversion/screening

Develop a dates for water diversions and screening

Project	Work Element	Accomplishments, Third Quarter

ODFW	1	Identify fish screening data that is appropriate for the StreamNet 	No exchange format has been developed, therefore no efforts were made

site and submit test records once an exchange format has been 	this quarter.

adopted.

ODFW	2	Develop a database structure Oregon's fish screening data	Worked with Screening Program staff to build a crude, basic database

and submit a draft data exchange format to SC for adoption.	structure for fish screening data maintained on paper.

Objective	1	Task	4.c	Fiscal Year 2000 Third Quarter 	Page 16 of 45

Objective	1	Data Development

Task	5	Habitat Restoration/Improvement Projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations within the Columbia Basin and

compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   5   Habitat Restoration/Improvement Projects

Task	5.a	Fish and Wildlife Program Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects related to the Fish and Wildlife Program

Project	Work Element	Accomplishments, Third Quarter

Objective	1	Data Development	Task   5   Habitat Restoration/Improvement Projects

Task	5.b	Other Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects other than related to the Fish and Wildlife Program

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	IDFG StreamNet will continue to compile information from	Compiled an extensive database of non-FWP projects obtained from the

non- FWP restoration projects into the PSMFC projects	Idaho Conservation Data Center. Many of these projects consisted only of

database and interface and submit to PSMFC.	land purchases or changes in management, rather than fencing and

restoration, but we captured this information while we had the data in front

of us.

MFWP	1	Data will be updated for FWP Projects during FY-00; a spatial	MFWP staff updated the restoration project database for Montana after

data layer of project location will be checked by regional staff	StreamNet staff made several modifications to edit/entry.  Working on DEF

and the possibility of adding other agency/FWP divisions will be	to exchange Montana's data this fiscal year.

explored during regional visits.

ODFW	2	Provide technical assistance to GWEB and StreamNet staff as 	Coordinated a data update for StreamNet on 40 projects in OWEB’s

needed to make compilation of ODFW habitat 	Mitigation/Restoration database.  Provided technical assistance to OWEB

restoration/improvement projects in the Columbia basin more 	staff, answering MS Access questions to make compilation of ODFW

efficient.	mitigation and restoration data more efficient.

Objective	1         Task   5.b	Fiscal Year 2000 Third Quarter 						Page 17 of 45

Objective	1	Data Development

Task	6	Sub-basin Planning

Develop consistent data sets and information that are particularly suitable and useful for regional sub-basin planning and make them readily available for

planners

Objective	1	Data Development	Task   6   Sub-basin Planning

Task	6.a	Provide data for Sub-basin Planning

Organize and distribute the available fish, wildlife and habitat data in a standardized format for use in Sub-basin Planning or other regional planning efforts

Project	Work Element	Accomplishments, Third Quarter

MFWP	1	Coordinate with MT CBFWA rep and provide available fish,	Discussed Montana's role with Montana CBFWA representative, MFWP

wildlife and habitat data in a standardized format for Sub-basin 	Fisheries Division staff and attended NWPPC meeting in Helena in May

Planning or other regional planning.  	concerning amendment process and sub-basin planning process. Will

provide input as process continues.

ODFW	2	Participate in discussions concerning data needs to support 	Consulted with ODFW staff who are preparing the Hood and Fifteen Mile

sub-basin planning or other processes adopted by the amended 	subbasin summaries about data gaps and ways StreamNet might be able to

Fish & Wildlife Program. Modify data plan and priorities as	help. Provided Oregon's input to the "Availability of Fisheries Data from

needed to be responsive.	StreamNet For Use with the Subbasin Assessment Template" document.

Region	1	Meet with sub-basin planners to discuss data types that may	Participated in the planning meetings for rolling provincial reviews in the

be needed, data sources, and to plan integration methods of	Intermountain and Columbia Gorge provinces.  Discussed data needs and

the various data sets.	StreamNet data availability for Subbasin Summaries.

SBT	1	Assist StreamNet cooperators with data needs as they are 	Sub-basin planning was put on hold until sub-basin assessments are

developed by Fish and Wildlife Program managers from sub-	complete.  Sub-basin assessment parameters

basin planning sessions.

WDFW	2	Coordinate data compilation from other WDFW Units as needed	 1) Participated in the subbasin assessment data compilation for the Gorge

to respond to the above needs, using StreamNet data exchange 	 Province by providing escapement, harvest, hatchery returns data, graphs,

experience.	 basin descriptions and maps for the Wind River, Little White Salmon River,

and White Salmon River basins.

2)Provided a list of StreamNet data categories and coverages pertinent to

the InterMountain Province subbasin assessment team in preparation for

their data meetings.

Objective	1	Task	6.a				Fiscal Year 2000 Third Quarter 						Page 18 of 45

Objective	1	Data Development	Task   6   Sub-basin Planning

Task	6.b	Capture information from Sub-basin Planning

Acquire information developed during subbasin planning to update anadromous fish, resident fish, and wildlife data sets

Project	Work Element	Accomplishments, Third Quarter

ODFW	1	Determine the Subbasin Planning generated data types that	Began reviewing draft subbasin summaries to identify new data types that

are not contained in StreamNet and adjust staff work plans to	StreamNet might consider compiling.

capture new data if appropriate

Objective	2	Data Management and Delivery

Provide high quality data management services, with specific emphasis on the creation of regionally consistent data sets and the timely delivery of

data to users in formats that meets their policy, planning, and management needs

Objective	2	Data Management and Delivery

Task	1.	Database Management

Maintain functional database programs at the state and regional levels to make consistent data sets for anadromous fish, resident fish and to a lesser

extent wildlife available through the StreamNet online database system.  At both the regional and state levels, provide database management and

administration necessary for accomplishing StreamNet Objectives, to include: 1) maintaining regional and state-level StreamNet data sets, 2) processing

exchange data into the regional database, 3) transporting data to the SQL environment, 4) enhancing StreamNet database structures and capabilities, and

5) providing programming services to project participants to allow for efficient data entry and transfer.

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Implement a new information management system that will	Continued to develop an IDFG StreamNet database management system for

facilitate input of IDFG data and output the data in SN Data	use by IDFG personnel to enter and manage fisheries data. Emphases

Exchange Format for inclusion in the regional database.	have been on cleaning remaining glitches in 100K LLID hydrography, user

interface forms, and table structures. The hydrography, taxonomy, and supporting

tables are in beta-testing mode. The reference system is in production and

being actively used by Fishery Bureau and StreamNet staff.  The lakes

component was independently extracted and supplied to IDFG fishery staff

for testing. Stream survey, hatcheries, and dams components are still in

development, but nearing completion. Fishery Bureau staff have coordinated

with StreamNet to develop a regulations component for the system.  With our

help, they have linked fishing regulations to the 100K LLID hydrography.

Objective	2	Task  1.	Fiscal Year 2000 Third Quarter 							Page 19 of 45

IDFG	2  Update existing data sets with 1998 field data	We have not migrated our old StreamNet anadromous fish databases into

the new database management system. We anticipate the hydrography

being completed, cleaned and approved shortly and then this will be our

first task.

IDFG	3	Update existing data sets as described in Task 1 and provide	Immediately upon final clearance of the 100K LLID hydrography into the

data to the regional StreamNet office in DEF.  Provide data as	new IDFG StreamNet database management system, we will transfer our

sub-sets are updated rather than waiting for entire data to be	existing anadromous StreamNet data for the 1998 and 1999 field seasons

complete.	and submit to PSMFC in data exchange format.

ODFW	1	Provide state-level StreamNet database management / 	Wrote procedures for validating distribution event data.

administration / development.  Enhance StreamNet and ODFW 	Tested and commented on the StreamNet Access user interface.

database structure and capabilities as possible.	Scoped the development of a composite database which will be used to

capture a variety of different survey information

ODFW	2	Modify/update the EventMapper tools with updated event data 	Worked with StreamNet regional staff to resolve problems with the new

and/or background GIS layers.	EventMapper coverages and provided the new coverages to OWEB and

ODFW staff members.

ODFW	3	Maintain and update state-level StreamNet data sets, database 	Converted master image database to 2000.2 DEF standard.

structures, and interfaces.

ODFW	4	Develop custom GIS projects and database structures that help 	Technical assistance was provided to several ODFW data collection

improve data management transfer with ODFW field staff.	projects which will aid in greater data availability and more efficient data

transfer to StreamNet.

ODFW	5	Develop custom database products in support of project data 	Reviewed additional information on the Riparian Lands Tax Incentive

compilation efforts as described in 3.1 below.	Program sent from the Portland ODFW office.  Completed development of

the first draft of the database structure and the interface and submitted

version 1.0 to Habitat Division for review and comments.

ODFW	6	Investigate and summarize the pros and cons of distributed vs. 	Completed the initial investigation and summarization of the pros and cons

centralized information systems	of a centralized vs. a distributed information system for Oregon's natural

resource data and a preliminary report was prepared.

ODFW	7	Update existing data sets as described in Task 1 and provide	Ongoing.

data to the regional StreamNet office in DEF.  Provide data as

sub-sets are updated rather than waiting for entire data to be

complete.

Objective	2	Task	1.	Fiscal Year 2000 Third Quarter 	Page 20 of 45

Region	1	Maintain and manage the StreamNet database so information /	1)  Maintained the StreamNet database.

data are available internally to project participants and externally	2)  Posted the 1990 smolt density model data files on the StreamNet web

via Internet.	site at http:/www.streamnet.org/f&w_subbasin.html.  These files are in the

form of spreadsheets summarizing subbasin habitats, percent of stream

lengths used, and smolt carrying capacities.

Region	2	Add data submitted to the StreamNet regional office into the SN 	1)  Loaded new data from ODFW related to trends, dams, barriers and

database within ~30 days of receipt from the project partners.	fish barriers tables.

2)  Updated hatchery facility records from WDFW.

Region	3	Assist data-providing agencies with error checking of data sets.	Reported errors to data compilers as encountered.

Region	7	Document all additions/changes to data structure, exchange 	Ongoing

formats, interface tools, etc.

Region	8	Develop metadata for spatial data sets posted to the StreamNet 	Developed metadata for new spatial data sets posted to the StreamNet GIS

GIS web page.	Web page and updated existing metadata when updates to the related

spatial data sets occurred.  Performed minor database cleanup and

updates.  For example, added new lookup codes, reworded some codes,

created a Publishers table, cleaned up the Reference table's Authors field.

Region	10	Provide programming services to project participants to assist	1)  Updated the Trends (time-series) data input interface.  This effort was

with efficient data entry and data transfer	designed to assist the StreamNet partners in their efforts on Tasks 1.1.b,

1.1.d, 1.1.e, 1.2.b, 1.2.c, and 1.2.d.

2)  Examined the existing StreamNet database, which uses RRN-based

georeferencing, to determine which data types had not been updated to

the LLID system.  We found that the Smolt Density Model and Protected

Areas tables could not be converted to the LLID system, due to imprecise

descriptions of geographic locations used in those tables.  We also

determined that georeferencing in the Trend, Dam, and Hatchery tables

must be accuracy-checked (this is being addressed by the StreamNet

partner agencies).  Smolt Density Model data and Protected Areas data will

remain queriable on the StreamNet web page, but their geographic

referencing will not be converted to the 1:100,000-scale LLID hydrography

due to the sometimes vague textual descriptions of location.

Objective	2	Task	1.	Fiscal Year 2000 Third Quarter 	Page 21 of 45

WDFW	1	Washington state data maintenance and exchange support 	Worked on developing a means to export data from our Paradox-based

services, including updated exchange format system, support for 	system into the MS Access-based TrendUI data entry tool. Installed

MS Access 97, and support for new data categories and fields.	TrendUI, ran into several compatibility problems with Access version

2000m and worked to repair problems.

WDFW	2	Update existing data sets as described in Task 1 and provide	1) Converted and exchanged hatchery facilities tabular dataset with

data to the regional StreamNet office in DEF.  Provide data as	StreamNet. Spatial dataset should be ready next quarter.

sub-sets are updated rather than waiting for entire data to be	2)Sent a list of LLID corrections PSMFC-StreamNet staff need to make to

complete.	the copy of the regional release database they maintain.

3)Spent time reviewing the 60000 series trends in the existing StreamNet

database (Washington state escapement and hatchery returns data added

by Duane Anderson years back) looking to separate duplicates from good

data.

Objective	2	Data Management and Delivery

Task	2.	Data Plan

Update and maintain a project data plan that identifies 1) current data holdings at the regional level, 2) data items to be incorporated in the current contract

period and in future years, and 3) expectations for data development and delivery from participating organizations within the current contract period

Project	Work Element	Accomplishments, Third Quarter

CRITFC	1	Provide input to the data plan to keep it responsive to subbasin 	NPPC executed a contract with several consultants to develop data for

planning and Framework needs and schedules.	watershed assessments. We are tracking these activities and will work at

the regional level to insure effective, efficient management of these data

sets. Specific discussions and actions will begin in the fourth quarter and

extend into the next contract period.

Objective	2	Task	2.	Fiscal Year 2000 Third Quarter 	Page 22 of 45

Objective	2	Data Management and Delivery

Task	3.	Data Exchange Standards

Establish and maintain data exchange standards that ensure consistent format and content of data that originated from the multiple agencies and data

sources in the basin.  Included will be proposed and adopted data exchange formats, metadata and location look-up tables for specific data items as

described under Objective 1.  At the regional level, this task will provide technical assistance regarding standard codes and exchange formats for Fish

and Wildlife Program and ESA- related projects, and for applicable tribal data compilation activities.  At the state level, this task will provide similar technical

assistance for state agency data activities applicable to StreamNet.

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	IDFG StreamNet will participate in the design, development	Participated via the StreamNet Steering Committee on adoption of data

and maintenance of standard codes and data exchange formats.	exchange formats.

This will occur through involvement on the Steering Committee

and technical work groups. There is no set schedule for this task,

because it is highly dependent on issues facing the Steering

Committee. Potential new data exchange standards may include

juvenile abundance, genetics, stream habitat, stream temperature

and resident fish releases.

ODFW	1	Participate in the design, development and maintenance of 	Reviewed and commented on the 2000.2 DEF, including the restoration

standard codes and data exchange formats. This will occur 	projects data category, distribution standards and definitions

through involvement on the Steering Committee and technical

work groups. There is no set schedule for this task, because it

is highly dependent on issues facing the Steering Committee.

Potential new data exchange standards may include juvenile

abundance, genetics, stream habitat, stream temperature and

resident fish releases.

Region	1	Work with the project database managers to identify needed 	Developed a listing of needed changes and additions to the DEF.

modifications to the Data Exchange Format (DEF) to

accommodate changing data needs

Region	2	Formally adopt changes to the DEF through the SN Steering 	Updated the StreamNet Data Exchange Format.  Created a major new

Committee	version of the exchange format, number 2000.1, which was approved by

the Steering committee.  Subsequently developed version 2000.2, which is

an error-fix of version 2000.1.

Objective	2	Task	3.	Fiscal Year 2000 Third Quarter 	Page 23 of 45

Region	3	Document all adopted changes to the DEF	Distributed a printed version of the new DEF to all Steering Committee

members

Region	4	Develop a description of the DEF process and guidelines for 	A protocol for proposing and adopting changes to the StreamNet data

modification	exchange format was developed and documented within version 2000.2 of

the DEF.  This protocol will be tested as it is implemented, and modified as

necessary.  It is anticipated that more well-defined procedures will result in

greater efficiency, easier tracking of proposed changes, and ensure

complete review before adoption of changes.

WDFW	4	Move toward complete adoption of LLIDs as the standard	1) Continued to correct LLID assignments, in some cases assigning

stream referencing code by reviewing and completing the	"closest LLID'd stream" and using a code to help us identify these cases.

RRN-to-LLID conversion, addressing supercode issues,	2) Started work on a proposal for site coding to the StreamNet Steering

and assuring that LLIDs are assigned to all locations where	Committee that takes a more generalized approach. This is based on having

StreamNet data exist.	to deal with lake and marine areas, facilities on small streams that are not

on the 100K streams layer, and sites that aren't on water at all.

Objective	2	Data Management and Delivery

Task	4.	GIS Data System

Establish and implement procedures for coordination of StreamNet-related spatial data activities among participating organizations, to include regular

meetings and or other communication links among participating GIS specialists. Designate and maintain metadata format for spatial data to be used by

StreamNet participants. Prepare map products in hardcopy and/or electronic format for use in Program-related aquatic resource policy, planning, and

management.  Provide for distribution of spatial data in GIS and tabular format and as GIS products.

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Maintain and enhance a geographic information system (GIS) 	We have continued to maintain, enhance and utilize our StreamNet GIS

related to regional and state-level StreamNet goals and	system. Our new IDFG StreamNet database management system, while

Objectives.	itself in SQL Server, is directly linkable to our GIS data.

IDFG	2	Prepare data and map products from StreamNet data on	We used our GIS for answering many information requests and for

request	providing GIS services to our fisheries staff (See item 2.7 below for a

summary of the data and map requests).

MFWP	1	Maintain a state level GIS program (state and StreamNet 	MFWP administrators reviewed and prioritized GIS layers that MFWP

funded)	StreamNet staff maintains; 71 coverages are currently being maintained by

staff.

MFWP	2	Prepare map products in hardcopy and/or electronic format for	Provided map products and GIS analysis to support the Fisheries Division

use in Program-related aquatic resource policy, planning, and 	native species management program, genetic sampling program, westslope

management.	cutthroat priority areas, updated bull trout distribution and core areas, and

updated USFS with fish present, hydrography and genetics data.

Objective	2	Task	4.	Fiscal Year 2000 Third Quarter 	Page 24 of 45

ODFW	1	Participate in planning and coordination meetings for state-level	Attended OGIC Hydro subcommittee meeting covering 100k / 24k issues.

24k hydrography layer to ensure compatibility with the PNW  	Met with David Graves, regional GIS specialist, to discuss alternative

100k hydrography.	solutions to problems that have arisen in the 100k to 24k LLID transfer

process that USFS and BLM employees are implementing.

ODFW	2	General maintenance activities associated with the GIS data 	Ongoing.

system

ODFW	3	Develop a lakes coverage for Oregon.	Provided Oregon lakes coverage with LLID's and names to SN regional

staff.

ODFW	5	Develop, maintain, and update metadata for Oregon StreamNet	Updated distribution metadata.

GIS products

Region	1	Maintain and enhance a geographic information system (GIS) 	1)  Maintained a geographic information system related to regional

related to regional StreamNet goals and Objectives.	StreamNet goals and Objectives.

2)  Created a regional (Pacific Northwest) GIS coverage of lakes and

reservoirs by combining GIS coverages from Washington, Oregon, and

Idaho.  Developed associated metadata and distributed these files on the

StreamNet website.  Developed related information in the StreamNet

database to allow georeferencing  of StreamNet data to lakes and reservoirs

and utility of this new capacity by the online query system.

3)  Investigated the cause of problems with incorrect subbasin X stream cross

references.  Referred to the 1990 subbasin plans to determine correct subbasin

definitions, and found that we had some errors in our GIS coverage.  These

errors are being addressed as the updated subbasin definitions are created.

Region	2	Prepare GIS data and map products from StreamNet data.	Prepared GIS data and map products from StreamNet data, as needed.

Responded to all requests from the public and prepared GIS data, maps, and

other products for 10 public requests.  Requests were from a variety of sources

including private citizens, environmental consulting firms, government agencies,

educators, and students.  Prepared more detailed map products for requests

from the NWPPC and associates for use in reports, etc.  Examples included

maps of fish species distribution and BPA-funded hatchery projects.

Region	3	Integrate the functioning of the GIS system with the StreamNet 	Integrated the functioning of the GIS system with the StreamNet fisheries

fisheries and habitat database, in support of the query system.  	and habitat database.  Maintained and updated cross tables of our LLID

Create cross tables and queriable maps used via the StreamNet 	stream locations by county, subbasin, hydrologic cataloging unit, state, and

web interface.	region in support of the query system.  Created queriable GIS coverages

of updated fish distribution and hydrography for the StreamNet web

interface.  Determined downstream stream tributary information for most

1:100k streams (approx. 60,000 total) for use by the query system.

Objective	2	Task	4.	Fiscal Year 2000 Third Quarter 	Page 25 of 45

Region	6	Develop a tool to rapidly assign LLID location identifiers to data	Developed a method to update the event mapper base 1:100,000 scale

hydrography and created an updated version for use with the event

mapper application

WDFW	1	Create approved reference documents for all exchanged spatial 	Began generating standardized "memos to file" to document dates, places,

data sets.	and participants in the mapping parties for all of the anadromous fish

presence/use field maps we've compiled.

Objective	2	Data Management and Delivery

Task	5	StreamNet Internet Site

Continue to maintain and enhance the existing client-server system to provide access to StreamNet data products through the Internet.  The StreamNet

home page will continue to be recognized as the project's primary data delivery vehicle.  Priority will be given to incorporating data developed through

Objective 1 and providing access to reference materials secured through Objective 3.  Appropriate training on the use of the system will be provided

through a combination of on-line help and in-person training sessions.

Objective   2	Data Management and Delivery	Task   5   StreamNet Internet Site

Task	5.a	Maintain the StreamNet Client Server system

Project	Work Element	Accomplishments, Third Quarter

ODFW	1	Provide review and comment on system function to the Regional 	Provided comments to regional StreamNet staff on the format and content

program	of data displayed in the new query system.

Region	1	Maintain, upgrade as needed, and administer the StreamNet	Performed ongoing maintenance and administration of the StreamNet web

web servers.	servers, including:  Maintenance of the server computers;  Maintenance of

the StreamNet web site.  Created the ability to query for habitat restoration

project data on-line.

Region	2	Convert the query system from the RRN to the LLID system	The on-line query system was modified to function with LLIDs rather than

where possible.	with the River Reach Numbers (RRN) and made available for internal

testing within the project.  The new query system was not implemented

publicly during the quarter.  This effort was part of a major undertaking to

convert the database to the use of LLIDs for georeferencing.  Given the

magnitude of this change, additional work on this effort will be required in

subsequent quarters as this new query system is brought on line.

Objective	2	Task	5.a	Fiscal Year 2000 Third Quarter 	Page 26 of 45

Objective  2  Data Management and Delivery	Task   5   StreamNet Internet Site

Task	5.b	Enhance and improve the StreamNet website

Maintain and enhance components of the StreamNet home page and incorporate new features that complement existing components

Project	Work Element	Accomplishments, Third Quarter

CRITFC	2	Identify changes and new features which will improve delivery of 	Management of the library portion of the website will be more effectively

Library services	managed if it is separated from (but linked to) the main servers. The

logistics of doing this are being identified.

ODFW	1	Recommend and/or take part in review of new products and 	1) Reviewed and commented on the StreamNet Test Query site.

features.  Provide feedback on content, suitability, navigability	2)Began work on a preseason report on salmon, steelhead, and sturgeon

and data currency issues.	stock status and Columbia River fall fisheries which will be posted on the

SN website when completed.

Region	1	Develop and conduct an online survey of users to determine the 	Researched methods of conducting an on-line user survey.   Decided on a

need for modifications to the site, the data or the project.	survey approach and developed a prototype for testing by StreamNet staff

prior to deployment.  Developed a 'frequently asked questions' page for

use with the survey when it is conducted.

Region	2	Review the website for clarity, organization and ease of use.  	Began review of the website as an ongoing exercise rather than

Recommend and implement changes to maximize utility for	approaching it as an 'all at once' review.

people accessing the site to obtain information

Region	3	Implement an improved and remodeled website based on the 	Made a variety of adjustments, corrections and improvements to the

review.	website as problems were identified.

Region	4	Plan to enhance the website content by adding additional kinds	Enhanced the GIS Data portion of the web site by adding an additional

of information that would support the Fish and Wildlife Program.  	download format (.shp files) and compressing all downloadable files for

Develop concept for increased information by coordinating with 	quicker access.

regional data users

Region	7	Modify the query system to function with revisions to the DEF	Began revision of the query system to fit the revised DEF, version 2000.1,

which was adopted by the StreamNet Steering Committee.  The new

protocol for implementing DEF changes specifies that the changes should

be built into the query system then reviewed by project staff at the regional

and cooperator level, and then brought online 90 days after the Steering

Committee approval.

WDFW	1	Take part in review of new products and features. Provide 	Staff spent time reviewing new Online Query tool and approach, evaluating

feedback on content, suitability, navigability and data currency 	success of the database conversion to 2000.1 on the Web site, and visiting /

issues, especially issues related to providing static or dynamic 	reacting to the new GIS products section of the StreamNet Web site.

map capabilities. -ALL

Objective	2	Task	5.b	Fiscal Year 2000 Third Quarter 	Page 27 of 45

Objective	2	Data Management and Delivery

Task	6.	1:100,000-scale Hydrography

Maintain the 1:100,000-scale PNW hydrography for purposes of attaching StreamNet data.  Coordinate with efforts to prepare a National Hydrographic

Dataset (NHD). Develop a standardized method for incorporating lake hydrography and attribute information.

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Continue to maintain the Idaho portion of the 1:100,000-scale	Continue to correct errors found in the 100K hydrography as we find them

PNW hydrography for purposes of attaching StreamNet data.	in our efforts to build an IDFG StreamNet database management system.

IDFG	2	Participate in coordination of the National Hydrographic Dataset 	Reviewed the National Hydrography Dataset (NHD), particularly in its

(NHD) through review and evaluation of the NHD.	applicability to link StreamNet data. Provided input to StreamNet Steering

Committee and GIS staff on the NHD.

IDFG	3	Continue to enhance the 1:100,000-scale PNW hydrography for 	Continued to work out bugs in our application of the 100K LLID

use in IDFG's information management system. This will include 	hydrography to the IDFG StreamNet database management system. Bugs

integrating the PNW hydrography with lakes, dams, and other 	include routing errors, errors in coding 16 digit reach numbers, and errors

hydrographic related features. All modifications will be made 	in establishing relationships among the streams, lakes, dams, and other

according to regional standards established for the 	hydrographic related features.

1:100,000-scale PNW hydrography.

IDFG	4	Submit all modified PNW hydrography to PSMFC for inclusion	Submission of final Idaho hydrography to PSMFC is still awaiting final

in the regional PNW hydrography data.	clearance into the IDFG StreamNet database management system. I

anticipate that being completed in the final quarter of the current fiscal

year.

MFWP	1	Support the efforts of the NHD and convert Montana	For Montana east of divide, NHD is moving at glacial speed but Western

hydrography to NHD upon receipt.	Montana HUC's are in the flow direction QA/QC process and we anticipate

a product to begin checking and routing next quarter.  NRIS has received a

grant to maintain the NHD coverage, which will aid in the work needing to

be performed.

MFWP	3	Use the PNW prior to release of NHD for western Montana 	Continued to work with David Graves on creating a routed coverage for

following the assignment of LLIDs by StreamNet regional staff	western Montana including LLID's.  Completed inclusion of USFS work into

in winter 2000.	1:100 K product, sent to David, who has assigned all remaining LLID's.

Performed QA/AC and sent back for final work from David.  Will complete

and route next quarter.

Objective	2	Task	6.	Fiscal Year 2000 Third Quarter 	Page 28 of 45

ODFW	1	Submit issues and corrections to 100K stream coverage as 	Modified stream routes in the Hood River subbasins.

identified during other data compilation activities.

ODFW	2	Review Duane's RRN-LLID cross-reference table for errors and 	Worked to get correct LLIDs, Supercodes and WaterbodyIDs assigned.

incorporate LLIDs into Oregon's abundance records	Prepared and sent the records for incorporation into the StreamNet regional

database.

ODFW	3	Review and provide an evaluation of the NHD test CU's.	Completed during second quarter.

ODFW	4	Participate in technical and policy discussions concerning	Ongoing.

adoption of the NHD 100K framework for the Northwest.

Region	1	Continue to maintain the regional 1:100,000-scale PNW 	Maintained the regional 1:100,000 scale PNW hydrography.  Corrected

hydrography.	errors on an ongoing basis as they were reported or found through regular

use.  Developed a method to update the event mapper base 1:100,000

scale hydrography and created an updated version for use with the event

mapper application.

Region	2	Implement updates to the 1:100,000-scale PNW hydrography	Synchronized the PNW reach files with updates made by ODFW to their

from state cooperators.	Oregon regional set.

Region	3	Update and serve a regional web version of the 1:100,000-scale 	Developed a semi-automated procedure for updating all PNW hydrography

PNW hydrographic set from the StreamNet website.	to the StreamNet website for distribution in multiple formats.  Updated and

delivered a regional web version of the 1:100,000 -scale PNW

hydrography on the StreamNet website (see

http://www.streamnet.org/pnwr/pnwrhome.html).  Responded via e-mail or

phone to all public requests for information about the PNW hydrography

and assisted users of the hydrography with ancillary products (tables, GIS

coverages, etc.)

Region	4	Assess future uses of the National Hydrography Dataset (NHD) 	Submitted a proposal to maintain the NHD to the USGS & EPA.  NHD will

and if adopted, coordinate the replacement of the PNW Reach	likely become the national standard approach to hydrography, and

files with the NHD as the StreamNet hydrography layer.	coordination and parallel updates with the PNW hydrography is imperative.

Region	5	Update Montana hydrography with LLID routing as updates are 	Developed complete LLID-based routes for Montana hydrography in the

received from MFWP.	following cataloging units (i.e. HUCs):  17010101, 17010102, 17010103,

17010104, 17010201, 17010202, 17010203, 17010204, 17010205,

17010212, and 17010213.

Objective	2	Task	6.	Fiscal Year 2000 Third Quarter 	Page 29 of 45

Objective  2    Data Management and Delivery

Task	7.	Data Requests

Receive and respond to requests for data, source materials, and custom products.  Response to requests will be honored within the limits of available

resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.  Other priorities will include implementation

of the Endangered Species Act and federal, state, and tribal natural resource management activities.

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Continue to respond to requests for information in the IDFG 	1) 55 requests for site specific species list of fish presence/absence via

StreamNet database, including requests for fishery information	the Idaho Conservation Data Center.

that comes into the Idaho Conservation Data Center (Natural	2) 6 map products for IDFG personnel showing fish distributions.

Heritage Program), other IDFG programs and personnel, and	3) 1 list of sensitive fish in Idaho

outside agencies and consultants.	4) 13 requests for geospatial data involving fish distributions.

MFWP	1	Receive and respond to requests for data, source materials,	Filled 73 GIS/ArcView technical support request for the MFWP Information

and custom products.  Respond to requests within the limits of 	Services Unit; 26 for fisheries requests.

available resources, with priority given to information requests

having direct relevance to the FWP.

ODFW	1	As requested, consistent with other deliverables in this contract, 	A total of 7 data,  81 document,  2 map/GIS related, and  12 other requests

receive and respond to requests for data, source materials, and 	were answered during this quarter. A detailed list by requester and

custom products.	request type can be made available upon request.  Also, 3,025 data

downloads were made from the ODFW FTP site during this quarter.

ODFW	2	As requested, provide training and instruction on the use of the 	Instruction on the use of the StreamNet web site was provided to a few

StreamNet website data delivery system.	individuals via phone conversation.

Region	1	Respond within one day whenever possible to all user requests 	1)  Responded to all StreamNet GIS/map user requests within one day of request.

received via email, phone, or other medium.  Typical requests 	Answered all questions, where possible, about data, maps, GIS products, and

received include help using the query system, complex data 	miscellaneous requests. Requests were from a variety of sources including

requests not easily done with the query system, and requests	private citizens, environmental consulting firms, government agencies, educators,

for GIS coverages and maps.	and students.  Prepared GIS data or maps for public requests when feasible

(see task 2.4- region (2)- Prepare GIS data & maps from StreamNet data).

2)  Fulfilled data requests for the NWPPC Annual Report.

3)  Created a summary of contents of the StreamNet database for use in

Sub-basin Summaries / Assessments and provided to Sub-basin teams at the

Intermountain and Columbia Gorge Provincial Review meetings and to NWPPC.

4)  We were not able to determine the exact number of visitors to the StreamNet

web site.  We logged 55,986 visits during the quarter, but many were search

robots.  We estimated 2,696 query sessions during the quarter. Over 20 special

requests for assistance were received and answered in addition to NWPPC.

WDFW	1	Generate maps, data reports, electronic copies of datasets as 	56 maps, 4 digital datasets and three reports were generated from spatial

requested.	and tabular StreamNet databases and provided to agency staff, other state,

tribal and local jurisdictions, and University staff.

Objective	2	Task	7.	Fiscal Year 2000 Third Quarter 	Page 30 of 45

Objective	3	Library / Reference Services

Provide a full service regional library for fish (and to some degree wildlife) literature (published and gray), including documentation of all data in the

StreamNet database.

Objective	3	Library / Reference Services

Task	1.	Collection Development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document data source materials, Fish

and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies, interested parties, and other libraries.

Project	Work Element	Accomplishments, Third Quarter

CRITFC	1	Coordinate source material submissions for data compiled under 	Received and cataloged approximately 75 StreamNet reference

Objective 1. Develop standards for document submissions	documents.  Submitted list of publishers for Reference table picklist.

CRITFC	2	Collect and catalog documents prepared by contractors	Continued to work with the BPA publications office to ensure a complete

(including final products published by BPA and draft documents	collection of annual reports from the Fish and Wildlife Program.  Also

suitable for public release) under the Fish and Wildlife Program.	continued to discuss the publications that are only produced electronically.

Work with Publications distribution for better publication

notification and deposit system.

CRITFC	3	Collect and catalog documents from the Council's Fish and	Received 12 boxes of materials from NPPC.  Have processed

Wildlife Program-related collection.	approximately 50% of the collection.

CRITFC	4	Collect and catalog additional books, journals, agency reports,	Added 1000 new records for documents to the library catalog.  Received

gray literature, research reports, and documents that are	and sent documents through Duplicate exchange.  Requested placement

applicable to management of the region's aquatic resources.	on more mailing lists for Natural Resources publications.

IDFG	1	IDFG StreamNet will continue to collect documents used as	No new source materials were sent to the StreamNet library.

source materials for data in Objectives 1 and 2.  Documents will

be assigned reference numbers and forwarded to the StreamNet

library as per established StreamNet guidelines

MFWP	1	Provide an update to the electronic version of documents used	MFWP Fisheries Division support staff continue to enter all new documents

as source materials for data compiled in Objective 1.  Make a 	into the INMAJIC library cataloging system.  Will provide updated version to

determination about acquiring the hard copy documents from 	StreamNet regional librarian in September.

Montana to the StreamNet Library.

Objective	3	Task	1.	Fiscal Year 2000 Third Quarter 	Page 31 of 45

ODFW	1	Provide originals/copies of all documents and reports referenced	Submitted 6 documents associated with updated abundance trends to the

in the compilation of new StreamNet data holdings, but not	StreamNet Library during the third quarter.  An error was made in Oregon's

already housed in the StreamNet Library.	second quarter submission in that 34 documents were submitted during

the second quarter.

ODFW	2	Update the set of historic Oregon Fish Commission and Game 	This effort is on hold till our Library tracking software is updated (see Task

Commission reports and provide to the StreamNet library as 	3.2).

available.

ODFW	3	Update library bibliography of ODFW, Fish Commission, and	This effort is on hold till our Library tracking software is updated (see Task

Game Commission reports with 99 ODFW publications and	3.2).

make bibliography available to the StreamNet Library for reference.

Objective	3	Library / Reference Services

Task	2.	Provide Access to Collection

Provide user access to the materials described in Task 3.1 by providing facilities for storage of paper and electronic copies of documents, an online

catalog of all documents in collections, and staff to answer location questions and respond to requests.

Project	Work Element	Accomplishments, Third Quarter

CRITFC	2	Catalog, organize and maintain the collection for appropriate 	Continued to streamline collections by integrating the StreamNet reference

on-site use.	documents, NPPC and classified collection.  Over 300 records were

processed.

ODFW	1	Investigate existing approaches and recommend adoption or 	Ordered InMagic software for use by the library to allow better tracking of

develop a custom library interface and bibliography that allows 	information requests and documents.

tracking of information requests, key word searches, and easy

comparison to the StreamNet Library holdings.

Objective	3	Task	2.	Fiscal Year 2000 Third Quarter 	Page 32 of 45

Objective	3	Library / Reference Services

Task	4.	Library Services

Manage the StreamNet Library and provide library services to the StreamNet user community and the general public.

Project	Work Element	Accomplishments, Third Quarter

CRITFC	1	Provide access guide to outline services for patrons. 	Updated Access Guide to show new journal runs.

CRITFC	2	Assist users to locate information by providing reference,	Assisted clients with over 40 requests for information.

referral, and computer based search services.

CRITFC	3	Provide document delivery services, including inter-library	Approximately 253 interlibrary loan requests were generated by clients.

lending and borrowing.	We lent 30 items to other libraries.

ODFW	1	Respond to requests for ODFW documents and other source 	Provided 388 hardcopy documents and 22 electronic documents to 88

materials.	individual users during the quarter.

Objective	3	Library / Reference Services

Task	5.	Inter-library Coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other collections that will enhance the

StreamNet Library and to avoid unnecessary duplication of effort and materials

Project	Work Element	Accomplishments, Third Quarter

CRITFC	1	Collect information about other regional fish and wildlife library 	Created mailing list for the Needs Assessment. Began revisions of

collections and access policies.	previous needs assessment.

CRITFC	5	Maintain presence in related Library groups (i.e. IAMSLIC,	Renewed membership in Special Libraries Association, Environmental

NRIC)to provide access to knowledge on Best Management	Resources Management Division.

Practices for libraries and current awareness of subject-related

materials.

Objective	3	Task	5.	Fiscal Year 2000 Third Quarter 	Page 33 of 45

Objective  	4  Services to Fish and Wildlife Program Activities

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife Program projects

Objective	4	Services to Fish and Wildlife

Task	1.	Project Tracking

Assist CBFWA, BPA, and the Council in providing Internet access to the Annual Implementation Work Plan (AIWP) database and other essential information

from AIWP-related reports

Project	Work Element	Accomplishments, Third Quarter

Region	1	Update AIWP information in a timely manner as it is received,	This work component was dropped from the work plan because CBFWA

and make it available and queriable via the StreamNet web site.	has taken on the job of posting AIWP information.

Objective	4	Services to Fish and Wildlife

Task 2	Monitoring and Evaluation

Assist in the development of products that contribute to the monitoring and evaluating (M&E) of Fish and Wildlife Program effectiveness.  Specific area of

involvement will include:

Objective	4	Services to Fish and Wildlife 	Task   2   Monitoring and Evaluation

Task	2.a	M&E Participation

Participate in Program-related monitoring and evaluation work groups

Project	Work Element	Accomplishments, Third

CRITFC	1	Assist CBFWA to develop an R/M/E plan consistent with the 	Discussed R/M/E issues with Council and EDT staffs to explore differences

regional Framework (cost sharing)	between their perceptions of the various issues with those of the

resource managers. Developed detailed recommendations on these issues

for CBFWA as part of the NPPC program amendment process.

ODFW	1	Participate in discussions concerning data needs to support 	Participated in various discussions as part of other meetings. Reviewed

processes adopted by the amended Fish & Wildlife Program for 	the draft of the CBFWA Research, Monitoring and Evaluation guidelines in

Monitoring and Evaluation.	an effort to identify potential data needs in the basin.

Objective	4	Services to Fish and Wildlife 	Task   2   Monitoring and Evaluation

Task	2.b	Evaluation

Periodically re-evaluate the StreamNet data plan to ensure consistency with M&E needs

Project	Work Element	Accomplishments, Third Quarter

Objective	4	Task	2.b	Fiscal Year 2000 Third Quarter 	Page 34 of 45

Objective	4	Services to Fish and Wildlife 	Task   2   Monitoring and Evaluation

Task	2.c	M & E Reporting

Prepare reports and data products that illustrate key M&E topics

Project	Work Element	Accomplishments, Third Quarter

Objective	4	Services to Fish and Wildlife

Task	3.	Watershed Projects

Provide data and data services to Fish and Wildlife Program-sponsored watershed planning and assessment projects

Project	Work Element	Accomplishments, Third Quarter

MFWP	1	Participate in watershed and, sub-basin planning to the extent 	Discussed watershed products needed for the Mountain Columbia

requested by the Council and other regional participants.  	Province rolling review process with MFWP and Council staff. Will provide

Coordinate with Montana CBFWA representatives in the process 	products as needed.

and assure a valuable product.  Volunteer to complete a pilot

sub-basin in the process within Montana.

Objective	4	Services to Fish and Wildlife

Task	4.	Stock Assessment Projects

Provide technical assistance to the Upper Columbia Basin and Upper Snake River Basin resident fish stock assessment projects, including a) identification

of regionally consistent data exchange standards and b) Internet access to project data and other information. Specific actions will be defined in

consultation with stock assessment project managers

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	IDFG StreamNet will coordinate with the Upper Snake River	No coordination conducted this quarter with the Upper Snake River Basin

Basin Resident Fish Stock Assessment project in order to	Resident Fish Stock Assessment Project. It is our intention, and we have

incorporate that data into StreamNet and to provide technical	discussed this previously with the USRBRFSAP, to implement our new

assistance.	IDFG StreamNet database management system for their use.

WDFW	1	Provide spatial, tabular data standardization and exchange 	1) Participated in May 17 Steering Committee meeting for the JSAP Project.

consultation and assistance to participants in the BPA-funded	Delivered updated resident fish distribution data for the Blocked Area in

Joint Stock Assessment Project (JSAP).	both JSAP format and StreamNet exchange format (event tables) to

familiarize project participants with StreamNet standards.

2) Wrote WDFW 1999 Final Report for the JSAP Project, Part I:

"Coordination, Data Standards Development, and Data Sharing Activities".

Objective	4	Task	4.	Fiscal Year 2000 Third Quarter 	Page 35 of 45

Objective	4	Services to Fish and Wildlife

Task	5.	Service to Other Fish and Wildlife Program Projects and Activities

In consultation with CBFWA, the Council, and BPA StreamNet will provide technical assistance and data services to select Program projects

Project	Work Element	Accomplishments, Third Quarter

CRITFC	1	Collaborate with CBFWA, NPPC, and other fish and wildlife 	Participated in CBFWA meetings and interagency staff discussions

programs in the Columbia Basin to identify and provide technical 	regarding shortcomings in the present programs. Kept SC apprised of

and other services to the Fish and Wildlife Program (cost sharing)	issues.

IDFG	1	Provide technical and other services to other FWP projects 	1) Continued coordination with Fisheries Bureau and CBFWA

occurring in IDFG. 	representatives in regard to data needs and development of IDFG

StreamNet database management system.

2) Coordinated with FWP anadromous field projects to enhance their data

management capabilities and to capture data for StreamNet.

MFWP	1	Provide technical assistance and data services to Program 	Provided David Graves with Montana's fish distribution, bull trout core and

projects upon request.  	nodal areas, Wild and Scenic Rivers coverage, wildlife data, and hunting

district data to fill a NWPPC request for data.  Provided data list for

subbasin planning efforts.

ODFW	1	No work planned this year.	1) Provided input to the StreamNet data holdings document prepared for NWPPC.

2) Prepared information on the distribution of wildlife species as part of a

data request from the NWPPC.

3) Participated in a conference call with other StreamNet participants

concerning the upcoming Columbia River Gorge Provincial Review and how

StreamNet might be involved.  Attended the Columbia Gorge Rolling

Provincial Review meeting in The Dalles.

4) Produced, formatted, and posted in-season fishery management

information (dam counts, hydrological data, and harvest estimates) on

CRM/ODFW web page for three Columbia River Compact hearings (April 1,

2000 - June 30, 2000)

WDFW	1	No work planned; available as needed and as prioritized.	Provided EDT support by assisting a regional fish biologist and regional

habitat biologist (Vancouver area) in entering historical run size, hatchery

releases, stock information, and historical and current presence/use for

anadromous species into the EDT Model database.

Objective	4	Task	5.	Fiscal Year 2000 Third Quarter 	Page 36 of 45

Objective	4	Services to Fish and Wildlife

Task	6.	Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas dataset, b) archive the official version as a historic record, and c) in

consultation with the Council, respond to requests for information concerning Protected Areas

Project	Work Element	Accomplishments, Third Quarter

Region	1	Maintain the existing Protected Areas database.	This effort is ongoing.

Objective	4	Services to Fish and Wildlife

Task	7	Basin Data Needs

StreamNet will provide information and assistance to regional reviews of data management projects and data management needs conducted by the

NWPPC, ISRP, ISAB and other regional entities

Objective	4	Services to Fish and Wildlife 	Task   7   Basin Data Needs

Task	7.a	Data Management Needs

Provide an analysis of regional data management needs, challenges and capabilities to the Power Planning Council, CBFWA, and other regional data

review processes

Project	Work Element	Accomplishments, Third Quarter

ODFW	1	Review and contribute to the data management 'white paper'.	Continued to provide comments on the SN data management white paper.

Region	1	Organize and coordinate development of a 'white paper' report 	Coordinated input from the sub projects and developed a beginning draft.

describing the current state of regional data management and 	The information ultimately proved more useful in the form of a letter to the

future options	ISRP than as a white paper.

Region	2	Publish and distribute the data management 'white paper'.	Revised the draft white paper on data management into a letter to the ISRP

panel that reviewed the regional data management projects.  This letter

served as a follow up to the project review and was intended to provide

background and context to the review.  The draft white paper was also

modified and used in our recommendations for amendment of the NWPPC

Fish and Wildlife Program.

SBT	1	Review and contribute to the data management 'white paper'.	Reviewed and commented to Bart on draft.

Objective	4	Task	7	Fiscal Year 2000 Third Quarter 	Page 37 of 45

Objective	4	Services to Fish and Wildlife 	Task   7   Basin Data Needs

Task	7.b	Data Needs Workshop

Promote organization of a regional 'data needs workshop' to establish regional data / information needs and priorities and to develop recommendations for

roles and responsibilities for acquiring and providing the needed data / information

Project	Work Element	Accomplishments, Third Quarter

ODFW	1	Participate if requested.	Participated in preliminary planning and strategy discussions with the

Steering Committee.

Objective	5	Project Management / Coordination

Provide effective leadership that ensures the production of high quality products targeted at critical applications and the development of these

products in a timely, cost-effective manner.

Objective	5	Project Management / Coordination

Task	1.	Manage Project Activities

Administer all aspects of the project at the regional and sub-contractor levels, including oversight of budget, personnel, work statement preparation and

implementation, coordination among participating agencies, active participation in steering committee work, and project reporting

Project	Work Element	Accomplishments, Third Quarter

CRITFC	1	Provide normal supervision of StreamNet Library staff and the 	Same as in last quarter's report.

CRITFC database Programmer.

FWS	1	Participate in Steering Committee activities	Participate in StreamNet Steering Committee meeting

FWS	2	Produce quarterly reports within 1 month after the end of each 	Submitted quarterly report

quarter

IDFG	1	Participate in Steering Committee activities. Manage all aspects	1) Managed work flow, personnel, and budget issues for IDFG StreamNet.

of StreamNet in IDFG, including budget, personnel, and work 	Participated in Steering Committee meeting and activities.

management. Products will include:  Annual IDFG StreamNet	2) As the Steering Committee representative to PSMFC on personnel

work statement; Quarterly and annual reports of progress; and, 	issues, I gathered input from Steering Committee members on the project

Participation in Steering Committee activities.	manager's performance and summarized in a report to PSMFC for

performance evaluation.

3) Completed and submitted second quarter progress report.

MFWP	1	Administer all aspects of the project for Montana, including 	Provided administration to all aspects of the StreamNet program in Montana

oversight of budget, personnel, work statement preparation and 	including performance reviews for all staff, budget planning for FY2001,

implementation, coordination, and project reporting. Participate	attend steering committee meetings and provide input to SC decision

in Steering Committee.  	processes.

Objective	5	Task	1.	Fiscal Year 2000 Third Quarter 	Page 38 of 45

ODFW	1	Attend StreamNet steering committee or specific technical data 	Attended the April Steering Committee meeting in Vancouver, WA.

meetings as needed to address data issues.

ODFW	2	Summarize/compile individual staff quarterly reports into one 	Compiled and submitted the 2000-2 quarterly report.

document, including fiscal year highlights, and plans for the

next quarter.

ODFW	3	Coordination activities: Oversee and monitor personnel, budget, 	Ongoing. Once again, we spent an excruciatingly inordinate amount of time

and other project activities.	this quarter on personnel related issues and paperwork - primarily related

to recruitment for vacant positions. Reviewed and commented on our

ODFW Program  budget and add packages for the 2001-03 budget

process.

ODFW	4	Prepare for and attend StreamNet steering committee meetings	Attended April Steering Committee meeting in Vancouver.

and specific technical data meetings as needed to address data

issues.

ODFW	5	Participate / attend appropriate conferences and submit 	Attended the ESRI Conference in June.  Summary report is available to

conference agendas, proceedings, and presentations to PSMFC 	regional StreamNet staff.

upon request

ODFW	6	Produce and provide a Statement of Work and budget proposal	Provided a budget estimate to PSMFC for FY-2001 for Oregon StreamNet.

for ODFW

ODFW	7	Contribute to the Oregon portion of Quarterly and Annual reports 	All staff submitted required reports for this period.

by providing period highlights, plans for the next quarter, and a

data request/response log.

ODFW	8	Develop a mid-year status report for work items contained in 	All staff submitted mid-year status reports related to their individual

individual work plans.	Work plans.

ODFW	9	Summarize/compile individual CRM staff quarterly reports into	Completed.

one document, including fiscal year highlights, and plans for the

next quarter, and deliver to Cedric

Region	1	Provide oversight for the StreamNet Program	Conducted ongoing management of the StreamNet Project, including

regional office staff meetings and email and phone coordination with

project participants.  Hosted the quarterly StreamNet Steering Committee

meeting on April 27-28, 2000.

Region	2	Supervise and train StreamNet regional staff	1)  Continued routine supervision of regional technical staff.

2)  The Regional Data Manager completed MSCE course 833 'Implementing

a database design in MS SQL Server 7.0 the week of May 22-26, 2000.

Objective	5	Task	1.	Fiscal Year 2000 Third Quarter 	Page 39 of 45

Region	3	Develop program budgets and manage / monitor expenditures	Developed and submitted FY 2001 project renewal and budget.  The

StreamNet Program Manager Worked with PSMFC budget officer to clarify

project spending and budget.

Region	4	Coordinate with other regional data management projects to 	Participated in meeting of PSMFC data management project leaders to

coordinate and cooperate to maximize data and information flow, 	coordinate and discuss current activities.

maximize complementary aspects, and to avoid duplication.

Region	5	Coordinate with data collecting agencies and organizations to 	1) Regional staff participated with representatives of multiple agencies

determine data availability and encourage data and information 	during several meetings at the FS Regional Ecosystem Office to discuss

being made public.	availability and formats of fish habitat project data, to coordinate efforts,

and to discuss potential for a regional database of such information.

2) Staff participated in an IRICC meeting regarding data collection standards

for aquatic habitat measurement and characterization.  The water

temperature and stream classification standards were updated.

Region	7	Produce quarterly reports within 1 month after the end of each 	Developed a new format for the quarterly report that organized tasks and

quarter	accomplishments by Objective and task, allowing activities by all project

cooperators to be grouped.  This format was used to prepare the report

for the second quarter.

Region	9	Manage and serve the StreamNet Steering Committee through:  	Organized and chaired the quarterly StreamNet Steering Committee meeting

Organizing and conducting committee meetings at least quarterly; 	 on April 27-28, 2000.

Calling additional meetings as needed to address timely issues;

and, Actively consulting with Steering Committee on program

activities

Region	11	Prepare a project proposal and Statement of Work for FY 2001	Developed and submitted a project proposal to renew the project for FY

2001.

SBT	1	Produce quarterly reports within 1 month of end of quarter. 	Submitted second quarter report.

SBT	3	Participate in Steering Committee meetings	Attended April Steering Committee meeting.

WDFW	1	The WDFW StreamNet state coordinator will participate in	1) Participated in the April Steering Committee meeting at USFWS

Steering Committee activities. He will also manage all aspects	Vancouver office, generating and delivering informal WDFW project

of StreamNet in WDFW, including budget, personnel, and	progress report.

work management.	2) Generated and delivered Q2 project report in new "work plan" style.

3) Provided FY2000 budget and workplan for supplemental funds as well

as FY2001 first draft budget for BPA funded portion of StreamNet.

4) Hired a new data compiler to work with Bob Woodard in the Region 5

office (Vancouver).

Objective	5	Task	1.	Fiscal Year 2000 Third Quarter 	Page 40 of 45

Objective	5	Project Management / Coordination

Task	2.	Participate in Fish and Wildlife Program Development Activities

Organize, facilitate, and/or participate in appropriate coordination meetings with BPA, CBFWA, the Council, ESA officials, ISAB/ISRP, and/or staff and

management of participating organizations aimed at identifying ways that StreamNet might more effectively contribute to the Fish and Wildlife Program

(FWP). Participate in advisory groups, task forces, and other groups whose purpose is enhancing the effectiveness of the Fish and Wildlife Program and

its data development activities.

Project	Work Element	Accomplishments, Third Quarter

CRITFC	1	Participate in appropriate coordination meetings with BPA,	Submitted detailed recommendations to NWPPC regarding changes to the

CBFWA, the Council, ESA officials, ISAB/ISRP, and/or staff and 	present Fish and Wildlife Program to improve data management and

management of participating organizations aimed at identifying 	StreamNet effectiveness. Follow-up discussions are extensive and

ways that StreamNet might more effectively contribute to the	ongoing.

Fish and Wildlife Program.

ODFW	1	Participate in Fish and Wildlife Program advisory groups and 	Attended the Hood River Subbasin Planning information meetings in April

applicable regional policy, planning, and management forums	and provided comments on data availability and data services which

and provide a written summary of activities in quarterly progress 	StreamNet could provide.

reports.

Region	1	Participate in appropriate coordination meetings with BPA,	1)  Participated in several CBFWA and NWPPC meetings.

CBFWA, the Council, ESA officials, ISAB / ISRP, and/or staff	2)  Developed and submitted recommendations for the draft NWPPC Fish

and management of participating organizations aimed at	and Wildlife Program amendment relating to regional data management.

identifying ways that StreamNet might most effectively contribute

data / information and support to the FWP.

Region	2	Where appropriate, participate in advisory groups, task forces, 	Participated in IRICC meeting at USFS regional office in Portland.  Discussed

and other groups whose purpose is enhancing the effectiveness 	the IRICC document being developed for setting interagency data collection

of the Fish and Wildlife Program and its data development	standards for aquatic habitat measurement and characterization.

activities.  Areas of particular emphasis are a) participation in

FWP monitoring and evaluation activities, and b) exploring

opportunities for integration of StreamNet data exchange formats

into Fish and Wildlife Program contract terms and conditions.

SBT	1	Participate in appropriate coordination meetings with BPA,	Represented StreamNet issues as a member of CBFWA's Anadromous

CBFWA, the Council, ESA officials, ISAB/ISRP, and/or staff and 	Fish Committee.

management of participating organizations aimed at identifying

ways that StreamNet might more effectively contribute to the

Fish and Wildlife Program.

Objective	5	Task	2.	Fiscal Year 2000 Third Quarter 	Page 41 of 45

WDFW	1	No specific work planned; available as needed for coordination.	1) Responded to NWPPC request for data scoping and availability of

resident fish and wildlife spatial data coverages.

2) Compiled and delivered Yakima Basin and Lake Roosevelt resident fish

stocking and harvest information for the past five years in response to a

second scoping request from the NWPPC.

Objective	5	Project Management / Coordination

Task	3.	Coordinate with Other Related Activities

As needed, produce public information materials including updated versions of the project brochure, computer demonstration materials, and/or other

appropriate materials

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	Continue to coordinate with regional and state-level fish and 	Developed plan and IDFG budget enhancement for an Idaho Fish and

wildlife activities that have relevance to the goals and Objectives	Wildlife Information System that would build upon and enhance IDFG

of StreamNet.	StreamNet's capabilities to manage and distribute fish and wildlife data. The

enhancement is in IDFG's 2002 budget request and has also been

proposed directly to the Governor's office for funding.

MFWP	1	Maintain communication, help coordinate activities with Montana 	Provided guidance to NRIS staff on MRIS query system enhancements,

Department of Natural Resources, Department of Environmental 	served on selection committee for NRIS director and system administration,

Quality and the Natural Resource Information System as they	represented FWP and StreamNet on NRIS Advisory Council and served as

relate to StreamNet activities.  Participate in appropriate	staff for the FWP rep on the Montana Geographic Information Council.

conferences by preparing papers and giving presentations. 	Attended Montana/Idaho User's Group Conference in Kalispell; staff

conducted workshops on ArcView tips and tricks and Access and

ArcInfo.

ODFW	1	Establish / maintain working relationships with major data	1)  Participated in restoration data integration meetings with the Regional

collection projects within and outside ODFW to promote efficient	Ecosystem Office, BLM, USFS, and OWEB.

and beneficial data sharing.	2)  Drafted and submitted seven pages of comments on ODFW's draft

Vision 2006 Strategic Plan. Many comments related to data management

issues.

Objective	5	Task	3.	Fiscal Year 2000 Third Quarter 	Page 42 of 45

Region	1	Coordinate the efforts of the StreamNet project with other data 	1)  Met twice in Salem, Oregon with the Regional Ecosystem Office,

compilation projects occurring in the region.  Address issues of 	USFWS, ODFW, and the Oregon Watershed Enhancement Board to

data gaps, duplication of effort, data set integration, 	discuss a unified habitat restoration projects database for the Pacific

georeferencing standardization, scientific rigor, management 	Northwest.  Agreed to develop a white paper on how the various

needs, etc.	databases of this region might be integrated.

2)  Created brief visual presentation materials to demonstrate the habitat

restoration projects on-line query system output which is a component of

the new, LLID-based query system.  Wrote a general description of the

information which can be captured in the StreamNet habitat restoration

database.

3)  The StreamNet regional fisheries biologist met in Yakima with Dave Lind

and Bill Bosch (Yakama Nation fisheries biologists) and Dave Askren of

BPA.  The group discussed needs and strategies to help guide the Yakama

biologists in their desire to make the Yakima-Klickitat Fisheries Project data

available on a queriable web site.

Objective	5	Project Management / Coordination

Task	4	Prepare Public Information Materials

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities to identify means for collaborative

data collection, storage, and dissemination. Collaborative data activities will target tribal fishery programs within the Columbia Basin, federal land managers’

fishery programs, state fish and wildlife agencies, and, with respect to water use and stream development, state water resource management agencies.

Collaboration with coast-wide and private data collection/compilation efforts will be pursued when this supports overall project goals. Areas of particular

emphasis are 1) participation in Fish and Wildlife Program monitoring and evaluation activities, and 2) exploring opportunities for integration of StreamNet

data exchange formats into Fish and Wildlife Program contract terms and conditions.

Objective	5	Task  4.	Fiscal Year 2000 Third Quarter 	Page 43 of 45

Objective	5	Project Management / Coordination	Task   4   Prepare Public Information Materials.

Task	4.a	Prepare Public Information Materials

As needed, produce public information materials including updated versions of the project brochure, computer demonstration materials, and/or other

appropriate materials

Project	Work Element	Accomplishments, Third Quarter

IDFG	1	No work planned this year.	Produced a new map showing the distribution of the subspecies of

cutthroat trout in Idaho. It is currently on public display in IDFG

headquarters office.

ODFW	1	Write informational article for the ODFW Monitor or Inside Tracks	Due to the departure of project staff, and the anticipated delays in filling these

on the Fish Presence Survey database development and its utility.	positions, it is anticipated that no further efforts will be made on this task.

ODFW	2	Write informational article for the ODFW Monitor or Inside	No efforts were made this quarter. The barrier data is still being compiled

Tracks on the Barriers database development and utility	and validated.  It would be premature to publish an information article until

the bulk of our data has been completely reviewed.

ODFW	3	Write informational article for the ODFW Monitor or Inside	Due to the departure of project staff, and the anticipated delays in filling

Tracks on the development of a component information system	these positions, it is anticipated that no further efforts will be made on this

and utility.	task.

ODFW	4	Write informational article for the ODFW Monitor or Inside	No efforts were made this quarter. It was decided that the information

Tracks on distribution data development efforts.	article would be put on hold until we could develop a simplified approach to

accessing the fish distribution data.  This approach was completed this

quarter.

ODFW	5	Develop an informational PowerPoint presentation about the SN 	Due to the departure of project staff, and the anticipated delays in filling

Project.	these positions, it is anticipated that no further efforts will be made on this

task.

ODFW	6	Write informational article for the ODFW Monitor or Inside Tracks	Due to the departure of project staff, and the anticipated delays in filling

on custom database and GIS projects/products services provided	these positions, it is anticipated that no further efforts will be made on this

by the project.	task.

Region	1	Update the existing StreamNet brochure	Developed an inventory of all data in the StreamNet online database, by

species and by Province / Subbasin for use in developing Subbasin

Summaries as part of the Rolling Provincial Review process.

Objective	5	Task	4.a	Fiscal Year 2000 Third Quarter 	Page 44 of 45

Objective	5	Project Management / Coordination	Task   4   Prepare Public Information Materials.

Task	4.b	Participate in informational meetings/conferences

Participate in appropriate state, regional, and national educational and professional conferences, including, where applicable, giving presentations,

preparing poster session materials, and contributing to conference proceedings.

Project	Work Element	Accomplishments, Third Quarter

ODFW	1	Participate in appropriate meetings & conferences as	1) Attended the Oregon Plan Monitoring Review and Workshop.

opportunities arise to highlight StreamNet programs & data	2) Attended the ESRI User’s Conference in San Diego and presented an

Oregon Salmon Distribution Poster at the conference.

3) One project staffer attended a Graphics Primer class

4) One project staffer attended a 6 hour Advanced HTML course.

5) One staffer attended a two-day fish passage course.

6) One staffer attended DEQ's Willamette River Basin Water Quality Data

Summit.

Region	1	Participate in appropriate meetings to explain the StreamNet 	Participated in the initial meetings of the Rolling Provincial Reviews at the

project, solicit new data and information, or to present relevant 	Intermountain and Columbia Gorge provinces.  Described StreamNet Project

data from the SN database	capabilities and data holdings.  Distributed the inventory of data to the

subbasin summary team leaders.

#### Work Planned for Next Quarter

In the fourth quarter we anticipate routine completion of the tasks detailed in the Work Statement, with the exception of

work on abundance trends in Oregon.  The Oregon Department of Fish and Wildlife experienced an unanticipated Data

Analyst position vacancy that delayed work on a number of tasks in the third quarter.  Because of anticipated

administrative delays in filling the position, it is expected that the position will likely not be filled before the end of the fiscal

year.  This position was responsible for updating the abundance trend data (Objective 1, Task 1.b) for Oregon, and this

work will be delayed until Fiscal Year 2001.  Barring unforeseen circumstances, all of the other project participants

anticipate no delays in the fourth quarter.

Work Planned for Next Quarter	Fiscal Year 2000 Third Quarter 	Page 45 of 45