|  | StreamNet Project BPA Project No.: 198810804 FY 2003 Work Statement As Amended August, 2003 Work to be performed under base level bridge funding October 1, 2002 through September 30, 2003 |
| --- | --- |

Bruce Schmidt

Pacific States Marine Fisheries Commission

Cooperators:

Phil Roger, Columbia River Intertribal Fish Commission

Bart Butterfield, Idaho Department of Fish and Game

Janet Hess-Herbert, Montana Fish Wildlife and Parks

Cedric Cooney, Oregon Department of Fish and Wildlife

Steve Pastor, U.S. Fish and Wildlife Service

Dick O'Connor, Washington Department of Fish and Wildlife

August 5, 2003

| Table of Contents | Pg. |
| --- | --- |
| Introduction.......................................................................................... | 2 |
| Objective 1. Data Development and Update...............................….... | 4 |
| Objective 2. Data Management and Delivery...............................….. | 15 |
| Objective 3. Library / Reference Services.......................................... | 23 |
| Objective 4. Services to Fish and Wildlife Program Activities......… | 26 |
| Objective 5. Project Management / Coordination..........................…. | 27 |

Amendment

This work statement and budget were modified to reallocate expenditures among the cooperators of the project to balance funding needs with savings.  These adjustments maintained the basic elements of the work statement.  In addition, new funding was approved late in the fiscal year for new work related to data management (Letter from Doug Marker to Therese Lamb, July 22, 2003).  This modification resulted in additional jobs being added to this statement of work as well as modifications to the budget.  Both kinds of changes were made at the same time to facilitate a single contract amendment.  The new jobs have been added to this work statement in bold type.

Introduction

StreamNet is a cooperative, multi-agency data compilation and data management project authorized by the Northwest Power Planning Council’s Fish and Wildlife Program (FWP).  It is funded primarily by the Bonneville Power Administration as part of 	its program to protect, mitigate, and enhance fish and wildlife resources affected by the development and operation of hydroelectric facilities on the Columbia River and tributaries, as part of the Northwest Power Planning Council's Fish and Wildlife Program.  Other funding has been obtained in the past from agencies including the Environmental Protection Agency and the National Marine Fisheries Service.  The Pacific States Marine Fisheries Commission administers the project.

Introduction			StreamNet Statement of Work, Fiscal Year 2003	Page 2 of 36

Three fourths of the project consists of sub-projects within the state fish and wildlife agencies, Columbia River Intertribal Fish Commission and US Fish and Wildlife Service to develop databases within the respective agencies and facilitate data transfer regionally.  In addition to administratively housing the StreamNet sub-projects, these cooperating agencies also contribute in kind support.  The kind and amount of support varies between agencies.  All agencies provide at least some salary support for their StreamNet Project Leader (2 months from CRITFC, 1 month from ODFW, 3 months from IDFG, 8 months from MFWP, 10 months from FWS, and 12 months from WDFW).  Several provide use of servers or other computer equipment and services that are not covered by charges for indirect costs.  All contribute time by biologists and in some cases data entry staff to provide data to the project.  MFWP provides $65,000 worth of in-state travel, office space, computers and office supplies.

This document is the FY2003 Work Statement for the base components of the StreamNet Project.  Not all tasks identified in the Work Statement apply to all participating agencies.  Each participating agency contributes work to a subset of the project tasks, with their responsibilities detailed individually for each task.  The intent of this format is to provide clarity concerning the total activities addressing each project task and the role of each project participant.  This combined Statement of Work covers Federal Fiscal Year 2003, from October 1, 2002 through September 30, 2003.

The StreamNet Project compiles, manages and distributes information related to fish resources in the Columbia River basin, with additional information available for the rest of the Pacific Northwest.  The state, tribal and federal fish and wildlife agencies collect and utilize data related to the region’s fish and wildlife resources to meet their own mandates.  A subset of these data, primarily the annually collected types of information that are routinely used to monitor trends within fisheries and populations and provide management information, are compiled by StreamNet into regionally standardized formats and publicly distributed.  In this manner, data common to fisheries management but collected and stored in multiple formats by the individual agencies are standardized and made uniformly available basin wide.  StreamNet also ties all data to the regional 1:100,000 scale routed hydrography (GIS stream network) so that different kinds of data can be compared on a geographic basis and mapped.  The project utilizes the Internet as its primary means of data distribution, but also provides custom data services to FWP participants.  The StreamNet web site provides access to information in a queriable database and also provides maps, individual data sets not contained in the queriable database, and library references.  All data in the StreamNet database are referenced to source documents that are housed in the StreamNet Library.

Work priorities for FY 2003 include updating existing long term data sets, managing the data and infrastructure necessary to maintain and deliver data, maintaining the StreamNet Library, providing data services to regional entities associated with the Fish and Wildlife Program, and project administration.  This year the project proposal was written to describe actions already underway plus new data types and data services that could be provided if deemed of regional priority and if funded.  The Rolling Provincial Review process under which the proposal was being considered was delayed, however, so this statement of work contains only the minimum ongoing baseline activities of the project under a level funded bridge budget.  Under base funding only, the majority of work remains focused on anadromous species.  The proposal included increased emphasis on data related to resident species and on data types that the project has not been able to pursue previously due to limitations of staff time.  If the review process authorizes those activities, this baseline work statement will be amended.

Introduction			StreamNet Statement of Work, Fiscal Year 2003	Page 3 of 36

Objective	1	Data acquisition and development

Support the need for region wide fisheries data for research, monitoring, modeling, and management through acquisition

and regional standardization of new information and updates to previous information for priority fishery data types.  Data

types may be addressed by all data providing agencies, or for specific data types by a single cooperating agency on behalf

of the entire project.  This Objective addresses both anadromous and resident fish species, although priorities may differ.

The tasks under this objective are identified as high or low priority under the constraints imposed under base level funding.

Work on the low priority types will largely be limited to preliminary development or scoping unless new funding is

approved.

Objective	1	Data acquisition and development

Task	1	Anadromous distribution and life history (habitat use)

Document the occurrence, distribution and life history characteristics of anadromous fish species.  Project participants have placed a high

priority on updating these data during the fiscal year, utilizing a newly adopted Data Exchange Format (DEF).  The new DEF represents a

significant new workload, but will lead to more regionally consistent distribution information.  This is priority 1 under base funding.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

IDFG	1	Convert Idaho's existing anadromous fish distribution into the new 	9/30/03	Distribution table submitted in 	Brown

generalized fish distribution data exchange format.	data exchange format.

ODFW	1	Update (to a minimal extent), maintain, correct and exchange 	Ongoing	Errors corrected, newly 	Bowers

anadromous fish distribution and documentation information.  Also, 	discovered distribution based on

evaluate the Oregon Museum collections database for potential utility in 	documented sightings, and

enhancing our historic distribution information.	distribution and documentation

data  based on these changes is

exchanged

WDFW	1	Continue updating data as received and actively solicit data as warranted.  	12/31/02	Salmon, steelhead, bull trout 	O'Connor,

Convert tabular and spatial data to the current revised StreamNet DEF and	data exchanged	Sikora

submit to PSMFC.

Objective	1	Task:	1	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 4 of 36

Objective	1	Data acquisition and development

Task	2	Resident fish distribution and life history (habitat use)

Document the occurrence, distribution and life history characteristics of resident fish species.  This will be a lower priority, except for

Montana, under base level bridge funding.  Existing resident fish distribution will be maintained, but development of new data or data for new

species will be limited due to the funding level.  This is lower priority under base funding, except for Montana.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

IDFG	1	Participate in the Westslope Cutthroat Trout Conservation Assessment. 	9/30/03	Updated distribution data for 	Butterfield

In response to a decision by the 9th District court to require a new status 	westslope cutthroat trout.

review for westslope cutthroat trout, the states of Idaho, Montana,

Washington, and Oregon, along with the Fish and Wildlife Service and the

Forest Service, have agreed to work together to prepare the new status

review. IDFG/StreamNet will send staff to several workshops to facilitate

the capture of data that will include distribution. The data will be prepared

for inclusion into StreamNet.

IDFG	2	As a result of our participation in job 1 of this task,  we will obtain the 	9/30/03	Updated distribution data for 	Butterfield

data from a similar effort for Yellowstone Cutthroat Trout. The data will 	Yellowstone cutthroat trout.

be prepared for inclusion into StreamNet.

IDFG	3	Update the StreamNet distribution database using other sources, including 	9/30/03	Updated distribution data for 	Murdock

collection permit reports, historical survey records, and information from	species in our internal database.

published reports.

MFWP	1	Complete Distribution and Use Types dataset from data collected from 	01/01/03	Exchanged distribution data in 	Carson

biologists, documents and reports during 1999-2000 using LLID stream 	DEF format

routes.  Exchange the data to the StreamNet database in the approved

DEF format.

MFWP	2	Visit MFWP biologists in 2003 to collect 2001-2002 fish distribution and 	8/01/03	Data inputted and exchange.	Carson

supporting survey data and references.  Obtain data from federal biologists

using our developed interface.  Input all this information into the MRIS

tables.  Develop some QA/QC on data before distribution.

ODFW	1	Maintain existing resident distribution information.	Ongoing	Existing resident distribution 	Bowers

maintained and available

WDFW	1	As time and funding permits, scope data availability and work with 	Ongoing, 	Quarterly progress report, 	O'Connor,

WDFW staff to enhance existing resident distribution data collections.	quarterly	cutthroat data if possible	Sikora

Objective	1	Task:	2	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 5 of 36

Objective	1	Data acquisition and development

Task	3	Adult abundance in the wild

Develop and maintain information on adult abundance for native fish species, resident and anadromous, including escapement, redd counts,

peak spawner counts, trap counts, dam and weir counts, and resident fish populations (where calculated).  Also included in this data category

are data gathered during spawning ground surveys regarding straying of hatchery fish onto spawning areas, i.e., marked/unmarked ratio.

Priority is given to updating these data through 2001.  This is priority 1 under base funding.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Update mainstem Columbia and Snake River dam counts through 2002 	3/31/03	Updated dam count data sets 	Forrest

and provide updated data to the StreamNet database.	exchanged.

CRITFC	2	Update available tribal spawning ground survey data.	6/30/03	Updated available spawning 	Forrest

ground data sets.

IDFG	1	Complete the compilation of the 2001 field season redd count data from 	4/1/03	Redd count data for the 2001 	Brown

IDFG.  Included in these data are carcass counts and counts of live fish.  	field season submitted to the

Prepare the data for inclusion into StreamNet and submit.	StreamNet database

IDFG	2	Start compilation of 2002 field season redd count data from IDFG.  Data	9/30/03	Redd count data for the 2002 	Brown

will not be complete, however, because all reports may not be available.	field season compiled.

MFWP	1	Collect all 2002 survey data during field office visits.	05/01/03	Data collection	Carson, Hutten

MFWP	2	Input 2002 data into MFISH, including trend, count and references.  We 	06/01/03	Data inputted. DEF discussion 	Carson

will explore which DEF is appropriate for resident fish population surveys	with Steering Committee.

(Matches the Draft Juvenile Abundance Table)

ODFW	1	Update existing anadromous, resident, and non-game abundance and index 	12/31/02, 	All Columbia Basin trends where	Hurn

trends through 2001 and opportunistically collect new trend information. 	4/15/03, 	new information is available are

Compile and exchange marked-to-unmarked ratio data (relative to dam, 	9/15/03	updated with available

weir, spawning ground, etc. counts) and/or hatchery-fraction data for an 	information

undetermined location in the Oregon portion of the Columbia basin.

WDFW	1	Continue to update and enhance the existing natural spawner database 	Ongoing, 	2001 anadromous data updated	Woodard,

(escapement estimates and/or detailed counts) for available species.	8/31/03 final	Sikora, (Smith)

WDFW	2	After we enhance the dam table with more records, consult the biologists 	Ongoing, 	Quarterly progress report, plan 	Woodard,

to scope and collect any existing dam and weir counts that might not 	quarterly	to capture data	Sikora, (Smith)

already be captured in our on-going Adult Abundance collection.

WDFW	3	Capture GPS coordinates to delineate the extent of spawning grounds 	9/30/03 	Accurate GPS points of 	Woodard

for spawning ground survey reaches in key lower Columbia R. tributaries		spawning grounds

Objective	1	Task:	3	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 6 of 36

Objective	1	Data acquisition and development

Task	4	Hatchery releases

Develop and maintain information on the release of hatchery reared fish.  Priority is given to updating anadromous release records using

RMIS data for anadromous species through 2001.  Release data for resident species under base funding will be developed only where the data

are readily available (primarily Montana).  Efforts this year will focus on creating cross references between PSC release codes and LLID

stream location identifiers.  We will explore means of providing unrolled data on specific release locations rather than more general PSC

codes.   This is priority 1 under base funding

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

FWS	1	For anadromous hatchery releases, compile FWS hatchery release data, 	9/30/03	Database file in PSC format 3.2 	Pastor

with added CWT information.  Transform data to format 040.  Submit 	submitted to the database

most current release year hatchery release data to PSMFC via USFWS

WWFRO.

FWS	2	For resident fish, explore availability of release data relative to FWS 	9/30/03	Exchange of resident fish data 	Pastor

facilities.  Provide resident fish production and release data to PSMFC.	to the StreamNet database

IDFG	1	Crosswalk PSC codes for Idaho hatchery releases in the Regional Mark 	9/30/03	Table with PSC to LLID 	Butterfield

Information System (RMIS) to StreamNet’s stream georeferencing system	measures conversion.

of LLIDs and measures.

IDFG	2	Compete the crosswalk of IDFG catalog numbers to StreamNet’s stream 	9/30/03	Table with Catalog Number to 	Butterfield

georeferencing system of LLID and measures.	LLID measures conversion.

MFWP	1	Explore current DEF for hatchery releases and provide Montana data in 	12/01/02	Exchanged Data set	Hutten

exchange format.

ODFW	1	Update anadromous hatchery releases through 2001.	7/30/03	Data exchanged with Region	Herber

ODFW	2	Create a cross table to link Pacific Salmon Commission codes to LLID.	9/30/03	PSC Code to LLID cross table 	Herber

Stream based locations to provide more precise locations for releases

Region	1	Assist cooperators with cross referencing PSC codes with LLID codes.	Ongoing	Assistance provided as requested	Butcher

WDFW	1	For anadromous species, finish researching, compiling, converting existing	4/30/03	Salmon, steelhead historic and 	Sikora,

WDFW anadromous release data as detailed, "unrolled" records.  Submit 	current unrolled release data 	(Lensegrav)

the data directly to StreamNet (instead of via RMIS).	through 2001

WDFW	2	WDFW resident stocking data is fractured in several collections by year.  	Ongoing, 	Quarterly progress report, data 	Sikora,

Work at researching, compiling, and converting data for any years we 	quarterly	submission(s) if possible	(Lensegrav)

have finalized at a given time, until all collections are submitted.

(Progress with this data set relies heavily upon initial improvements to our

Lakes spatial layer).

Objective	1	Task:	4	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 7 of 36

Objective	1	Data acquisition and development

Task	5	Hatchery returns

Develop and maintain information on the return, disposition and straying of adult fish returning to hatcheries, including information on

coded wire tags.  This is an anadromous related task only.  Priority will be placed on updating total return and egg take data through 2001.

Development of disposition data is lower priority and would require additional resources.  This is priority 1 under base funding.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

FWS	1	Compile FWS hatchery return data for FWS hatcheries for the most 	9/30/03	Updated HatchRet file	Pastor

recent return year and submit to the regional database.  FWS will also

account for all adults returning to federal hatcheries.

IDFG	1	Complete compilation of the 2001 field season hatchery return data from	4/1/03	Hatchery return data for the 	Brown

IDFG and exchange with StreamNet database.	2001 field season submitted to

the database.

IDFG	2	Start compilation of the 2002 field hatchery return data from IDFG.  	9/30/03	Hatchery return data for the 	Brown

Data will be incomplete because all reports may not be available within 	2002 field season begun.

this project year.

ODFW	1	Compile data on returns to ODFW hatchery facilities (updated through 	6/30/03	Updated return data exchanged 	Herber

2001 returns where possible).	with StreamNet

WDFW	1	Continue to update and enhance the existing hatchery return database for 	3 mos. 	2001 anadromous data 	Woodard, Sikora

available species.	after new 	exchanged

DEF

finalized

Objective	1	Data acquisition and development

Task	6	Dams and Fish Passage Facilities

Develop and maintain information on dam facilities.  Primary emphasis is now on maintenance of existing information, with occasional

updates as necessary.  This is priority 1 under base funding.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

IDFG	1	Update LLID measures and geographic coordinates for Idaho dams in the 	12/30/02	Data table with updated location	Butterfield

National Inventory of Dams	values.

MFWP	1	Provided an updated Montana dams spatial coverage and associated data in	3/31/03	Updated data set, if necessary	Hutten

the StreamNet exchange format if additions, deletions or modifications

are made.

Objective	1	Task:	6	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 8 of 36

ODFW	1	Maintain and update, as needed, based on errors found in the Oregon dam 	Ongoing	Corrected dam and fish passage 	Bowers, Brodeur

and fish passage facilities information.	facility information exchanged

WDFW	1	Update the dam database adding records and improving field entries as 	7/30/03	Updates including new records 	Sikora,

warranted.	and/or field improvements	(Lensegrav)

Objective	1	Data acquisition and development

Task	7	Hatchery facilities

Develop and maintain information on anadromous and resident hatchery facilities, including information on location, design, management

and authorization.  Primary emphasis is now on maintenance of existing information, with occasional updates as necessary.  This is priority 1

under base funding.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

FWS	1	Update hatchery facility records as needed,  Update hatchery water 	9/30/03	Updated Hatchery file submitted	Pastor

records as needed.  Update FWS data sets with 2002 data and submit to 	 to the StreamNet database

PSMFC

IDFG	1	This is a maintenance item for IDFG. We will maintain this database by 	As needed	Updated data in data exchange 	Brown

making modifications for staff changes or other necessary fields. Prepare 	format.

any updates for inclusion into StreamNet.

MFWP	1	Update the StreamNet hatchery database with Montana's public and 	12/15/02	Updated database exchanged	Hutten

private facilities.  Exchange with StreamNet upon completion.

ODFW	1	Maintain and update, as needed, based on errors found in the Oregon 	Ongoing	Corrected hatchery facilities 	Bowers, Brodeur

hatchery facilities information.	information exchanged

WDFW	1	Update the hatchery database adding records and improving field entries as	As needed, 	Updates including new records 	Sikora,

warranted, including record updates for related tables (i.e. 	HatXProd 	and/or field improvements	(Lensegrav)

HatcheryXProduction data).	8/31/03

Objective	1	Data acquisition and development

Task	8	Harvest

Develop and maintain information on sport and commercial harvest.  Higher priority is assigned to anadromous species.  This is priority 1

under base funding.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Complete and update ocean and Columbia River catch data through	9/30/03	Updated harvest data sets 	Roger

2002.	exchanged.

Objective	1	Task:	8	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 9 of 36

IDFG	1	We will evaluate IDFG harvest records to determine the feasibility of 	9/30/03	Report on feasibility to include 	Brown

sending harvest data to StreamNet. If possible within our existing work 	IDFG harvest data.

plan, we will submit harvest data to for inclusion into StreamNet

ODFW	1	Compile and exchange Oregon sport harvest data through 2000, in three 	12/31/03, 	All Columbia Basin sport harvest	Hurn

submissions.	4/15/03, 	trends where new information

9/15/03	is available are updated with

available information

WDFW	1	Re-submit any existing StreamNet Washington harvest data, updating it 	1/31/03	Enhancement to existing 	Sikora

per StreamNet's current location coding format to validate and correct the	StreamNet data

conversion that was completed by non-WDFW personnel.

WDFW	2	Although we should only be in maintenance mode for this data set, WDFW	Ongoing, 	Quarterly progress reports, data 	Sikora

re-organized their data collection process several times since our last 	quarterly	submission if possible

StreamNet update (and it's still in flux) so it poses a large workload.  As

such, we need a large allotment of time before renewing this effort.  As

funding and time permits, compile freshwater harvest for key Columbia

Basin salmonid stocks for both anadromous and resident data, using

existing WDFW data sets (i.e. Angler Fish Database) and other sources.

Standardize the data (to stock if possible), convert and submit it to

PSMFC.

Objective	1	Data acquisition and development

Task	9	Habitat restoration / improvement projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations within the

Columbia Basin and compile and maintain them in standardized, consistent formats.  This data category is still being organized, but interest in

this information is growing as there is no consistent source of this information on a regional basis.  This is priority 2 under base funding, and

will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

MFWP	1	Continue to collect, centralize and maintain all stream restoration 	3/31/03, 	Updated data exchanged	Hutten

projects data for Montana using the "Future Fisheries Interface" which 	9/30/03

StreamNet staff maintains and the Fisheries Division inputs data.

Exchange data to the Region twice during the year.

ODFW	1	Maintain and update, as needed, based on errors found in Oregon's existing	Ongoing	Exchange corrected tabular 	Brodeur

tabular restoration data.  Maintenance only; no new updates are planned.	restoration data

Objective	1	Task:	9	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 10 of 36

WDFW	1	If funding and time permits, finalize conversion of  Washington's IAC's 	Ongoing, 	Quarterly progress report, data 	Sikora,

(Interactive Committee for Outdoor Recreation) PRISM database for 	quarterly	submission if possible	(Lensegrav)

WRIA 5 records and submit to StreamNet.  Build an ArcView project file

that incorporates Washington Salmon Recovery Funding Board data,

basin-specific salmon habitat limiting factors (LFA) and potentially SaSI

stock status.  Assess if this tool allows managers to effectively compare

relative expenditures (and the factors they intend to address) to identify

priority issues in the basin and the utility of creating similar products for

other basins.

Objective	1	Data acquisition and development

Task	10	Barriers and diversion/screening

Develop and maintain data sets for barriers to fish migration and diversion structures with information on screening status.  This category is

still being organized.  Existing data on adult barriers will be maintained and updated as practical.  Other sources of data will be explored.  Work

on juvenile barriers, culverts and diversion screening may require additional resources.  The primary emphasis is on anadromous species

except in non-anadromous areas.  This is priority 2 under base funding, and will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

IDFG	1	Participate in the Westslope Cutthroat Trout Conservation Assessment. 	9/30/03	New barrier data for westslope 	Butterfield

In response to a decision by the 9th District court to require a new status 	cutthroat trout exchanged

review for westslope cutthroat trout, the states of Idaho, Montana,

Washington, and Oregon, along with the Fish and Wildlife Service and the

Forest Service, have agreed to work together to prepare the new status

review. IDFG/StreamNet will send staff to several workshops to facilitate

the capture of data that will include barriers. The data will be prepared for

inclusion into StreamNet.  Delivery is dependent on the Forest Service

completing the database.

IDFG	2	As a result of our participation in work component 1 of this task, we will 	9/30/03	New barrier data for 	Butterfield

obtain the data from a similar effort for Yellowstone Cutthroat Trout. 	Yellowstone cutthroat trout

The data will be prepared for inclusion into StreamNet.  Delivery is 	exchanged

dependent on the Forest Service completing the database.

MFWP	1	Continue to collect barrier location, species affected and other fields on 	3/31/03	Data in DEF and exchanged to 	Hutten,

stream barriers in Montana.  Information will be collected on all species 	the StreamNet database	Lindstrom

regardless of life history.  Exchange Barriers data with the StreamNet database.

ODFW	1	Compile and exchange Oregon fish screening and diversion data assuming 	4/15/03	Exchanged screening/diversion 	Brodeur

a new DEF is adopted. If no DEF is approved, data will be posted on the 	information

NRIMP site and linked to StreamNet as an 'as is' submission.

Objective	1	Task:	10	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 11 of 36

ODFW	2	Update and maintain Oregon's barrier data and minimal fish barrier data 	Ongoing	Exchanged barrier location 	Bowers, Brodeur

development based on new barrier information.	information and minimal fish

barrier information, based on

new barrier location information

ODFW	3	Capture GPS coordinates for water diversions and fish screens in the 	9/30/03	Accurate coordinates for fish 	Cooney

primary Oregon Columbia River tributary subbasins.	screens and diversions

WDFW	1	As funding and time permits, review existing Washington state barriers 	Ongoing, 	Quarterly progress report, data 	Sikora,

and/or screening data and identify additions and corrections needed and 	quarterly	submission if possible	(Lensegrav)

plan for future exchanges.

Objective	1	Data acquisition and development

Task	11	Juvenile data, abundance and outmigration

Develop and maintain information on smolt production (as determined from smolt traps), juvenile abundance (as determined through snorkel,

electrofishing, and other surveys), and smolt density model estimates.  Primary emphasis will be on maintaining the existing smolt density

model data and development of a DEF for these data.  The rest of the work for this data category is still under development and will require

additional resources to accomplish.  This is priority 2 under base funding, and will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Seek to obtain tribal data on smolt abundance. Inform Steering Committee	9/30/03	Report to Steering Committee. 	Forrest

of data availability.	Available data sets exchanged

IDFG	1	Depending on the adoption of an appropriate StreamNet juvenile data 	9/30/03	Juvenile abundance data in data 	Murdock

exchange format (see Task 3.4), prepare existing IDFG juvenile trapping 	exchange format.

data for inclusion in StreamNet.

IDFG	2	Code the IDFG General Parr Monitoring database to StreamNet’s 	9/30/03	General Parr Monitoring 	Butterfield

georeferencing for streams using LLID and measures.	database with LLID and

measures attached

MFWP	1	Pursue incorporation of resident fish survey data into the juvenile 	9/30/03	Potential data exchange if DEF 	Carson

abundance DEF, if approved.	is adopted

ODFW	1	Assist in development of a DEF and exchange 10 Oregon juvenile 	9/30/03	At least 10 Oregon Juvenile 	Hurn

abundance and/or outmigration estimate records (not counts)	Abundance records exchanged, if

DEF is approved

WDFW	1	As funding and time permits, keep informed about other WDFW agency 	Ongoing, 	Quarterly progress report, data 	Sikora

staff efforts to organize the juvenile data and scope existing juvenile data 	quarterly	submission if possible

to plan future conversion and submission efforts.

Objective	1	Task:	11	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 12 of 36

Objective	1	Data acquisition and development

Task	12	Age

Develop and maintain information on age/sex composition of returning adults, primarily for anadromous species.  This is a medium priority,

with the primary focus on developing data for a few test locations as a means of testing data organization/format and utility.  Remaining

DEF issues will be resolved.  This is priority 2 under base funding, and will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Use CRITFC age data on sockeye populations and Bonneville Dam 	9/30/03	A workable DEF format for age 	Roger

sampling to evaluate and develop an age DEF.	data.

FWS	1	Update age and sex data for the most recent return year.	9/30/03	Updated Age table	Pastor

IDFG	1	Complete the compilation of the 2001 field season age data using 	4/1/03	Age composition data for the 	Brown

hatchery returns data from IDFG.	2001 field season.

IDFG	2	Start compilation of the 2002 field age data from IDFG.  Data will likely 	9/30/03	Age composition data (partial) 	Brown

be incomplete because all reports may not be available by the end of the 	for the 2002 field season.

fiscal year.

ODFW	1	Compile age frequency data for an as-yet undetermined basin or hatchery 	5/30/03	Determine target basin or 	Hurn

in the Oregon portion of the Columbia Basin as a test case for this data 	hatchery and exchange all

type.	available age data

WDFW	1	Stay in step with the other StreamNet cooperating agencies' efforts to 	9/30/03	Salmon and Steelhead Data for 	Woodard, Sikora

research, compile, convert and submit age data for natural spawner data in	one test subbasin, plan for

one prototype subbasin (probably Lower Columbia R).  This effort is to 	future work

assess any problems with the existing format and standardization with

other agencies' data , and plan for further data submittals.

Objective	1	Data acquisition and development

Task	13	Production factors and run reconstruction

Develop and maintain information on survival, production factors, spawner / recruit estimates, and run reconstruction.  This is currently a

low priority, but the existing spawner / recruit estimate data will be maintained.  This is priority 2 under base funding, and will be addressed as

time and other priorities allow.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Coordinate with ESA recovery planning and NWPPC subbasin planning 	9/30/03	Available productivity data sets.	Roger

efforts to capture available anadromous fish and bull trout productivity

data for eventual DEF testing and inclusion in StreamNet.

Objective	1	Task:	13	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 13 of 36

Region	1	Assist cooperating projects, as needed, in determining availability and 	As needed	Assistance, and work with 	Schmidt

potential acquisition of these data.	Steering Committee on decision

on how to deal with these data.

Objective	1	Data acquisition and development

Task	14	Habitat

Acquire data sets related to fish habitat (including water quality, stream/watershed habitat quality, temperature, invertebrates, and miscellaneous habitat

data) from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats

or archive them in original format, as appropriate.  This is currently a low priority under the existing contract, and data development will be pursued only

on other funding.  Data developed on other funding will be organized and included in the StreamNet database.    This is priority 2 under base funding,

and will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Coordinate with ESA recovery planning and NWPPC subbasin planning 	9/30/03	Available watershed assessment 	Roger

processes to capture watershed assessment data for DEF testing and 	data sets

eventual inclusion into StreamNet.

Region	1	Assist cooperating projects, as needed, in determining availability and 	As needed	Assistance, and work with 	Schmidt

potential acquisition of these data.	Steering Committee on decision

on how to deal with habitat data

Objective	1	Data acquisition and development

Task	15	Genetics

Develop and maintain information on genetic information and data sources for areas where genetics data exist.  Efforts this year will concentrate on

organizing existing information, and then working on a Data Exchange Format.  This is priority 2 under base funding, and will be addressed as time

and other priorities allow.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Work through the coast-wide genetics work group to update the genetics 	9/30/03	Updated genetics data catalog.	Forrest

data catalog.

MFWP	1	Obtain results from genetic analysis from the University of Montana 	Ongoing	Updated genetics database	Carson

Genetics Lab for sampled populations of Montana's species of special

concern.

MFWP	2	Update fish distribution table when new genetic samples affect fields /	Ongoing	Up-to-date distribution data	Carson

records. Finalize a GeneticSample table field to facilitate querying purity

MFWP	3	Exchange data to the StreamNet regional database when a DEF is 	When 	Exchanged genetics data	Carson

approved by the Steering Committee.	possible

Objective	1	Task:	15	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 14 of 36

Objective	1	Data acquisition and development

Task	16	Other data sets

On an opportunistic basis, conduct scoping or exploratory level work on the availability of other types of fish related data, as requested by

FWP participants.  Actual acquisition, standardization, georeferencing and distribution of these data would be dependent on funding for new

work.  This is priority 2 under base funding, and will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

IDFG	1	We will work with IDFG and other agency staff to facilitate either the 	Ongoing	Potentially various independent 	Butterfield

incorporation of their data into StreamNet or independently posting their	data sets

data on the StreamNet web site.

MFWP	1	Will explore as opportunities arise	Ongoing	Data made available as 	All staff

opportunities arise

ODFW	1	Develop data sets outside Oregon StreamNet's base efforts if requested by 	Ongoing, if 	Initial Subbasin Planning related 	Hurn

subbasin planners.	requested	data sets developed

ODFW	2	Compile and exchange Oregon's carcass placement results for 2001 as an 	8/31/03	2001 Carcass placement 	Hurn

'as-is' data set.	information accessible via

StreamNet website

Region	1	Advise and assist data developers with other data sets not currently in the 	On request	Assistance or advice to data 	Butcher, Banach

StreamNet system.  Low priority, and within current resources only.	Developers

Region	2	Acquire data sets from other entities where the data would be useful in 	Ongoing, 	Knowledge of available data 	Banach

relation to the fisheries data available in the StreamNet database and for 	opportun-	sets, and acquired data sets

regional planning and management needs.  This may include data for 	istic	posted on the StreamNet web

resident species as located through the resident fish data inventory 	site in original format.

conduced last fiscal year.  Initial efforts may be only exploratory in

nature, and will only be pursued within existing resources and as data

become available.

Region	3	Evaluate data resources discovered during FY02 that were originally 	5/1/03	Report on work required to 	Banach

obtained by the precursor projects to StreamNet (CIS and NED).  These 	recapture CID/NED data.

resources include data and reports on floppy disks, and hard copy reports.

Determine the types of data that are available in each format and that are

already included in the StreamNet database.  Determine the feasibility and

value of reclaiming lost data and the workload required.  Prepare a report

making recommendations to the Steering Committee for the possible

inclusion of those data not already included in the StreamNet database.

Objective	1	Task:	16	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 15 of 36

Objective	2	Data management and delivery

Provide high quality data management services, with specific emphasis on the creation of regionally consistent

data sets and the timely delivery of data to users in formats that meets their policy, planning, monitoring, and

management needs

Objective	2	Data management and delivery

Task	1	Maintain and enhance the tabular database systems at the project and regional levels

Maintain functional tabular database programs at the agency and regional levels to make consistent tabular data sets for anadromous and

resident fish available through the StreamNet online database system.  At both the regional and agency levels, provide database management

and administration necessary for accomplishing StreamNet objectives, to include: 1) maintaining and updating the hardware and software

systems necessary to support the StreamNet project, and 2) enhancing or optimizing StreamNet database structures and capabilities.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Develop prototype electronic data exchange procedures with the Yakama 	6/30/03	A prototype system to update 	Forrest

Nation to simplify updates of fish abundance data.	Yakama fish abundance for

StreamNet directly from tribal

Databases

IDFG	1	Complete the administrative programs to convert locally held data to 	9/30/03	Functioning program modules 	Murdock

StreamNet data exchange format. This includes: redd counts, hatchery 	that automate the transfer of

returns, hatchery facilities, and references. Depending on the adoption of 	IDFG data into StreamNet data

an appropriate StreamNet juvenile data exchange format (see Task 3.4), 	exchange format.

juvenile trap data may also be included.

IDFG	2	Prepare documentation of the Idaho Fish and Wildlife Information 	9/30/03	Documents, charts and graphs 	Murdock

System (IFWIS). IFWIS is the information system at IDFG that contains 	that document the IFWIS

the locally held and compiled StreamNet data. Documentation should 	infrastructure and database.

include resource diagrams, entity relationship diagrams, database standards

document, programming standards document, and database metadata.

IDFG	3	Maintain existing modules of IFWIS, including the spawning ground, 	Ongoing	Functioning databases and 	Murdock

juvenile trapping, collecting permit reports, and the reference programs. 	applications at IDFG/StreamNet

This includes maintenance of data integrity in the IFWIS database.

IDFG	4	Maintain the hardware and software that comprises IFWIS. Provide 	Ongoing	Functioning hardware and 	Murdock

system administration, backup and recovery, and security.	software infrastructure at

IDFG/StreamNet

Objective	2	Task:	1	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 16 of 36

IDFG	5	Build additional IFWIS components, interfaces or tools as required to 	Ongoing,	New or updated databases and 	Murdock

complete other tasks. Specific jobs will be identified on an as needed	as needed	applications for managing the

basis, but may include tools to evaluate existing trend-based data.	internal IDFG/StreamNet data.

MFWP	1	Provide a high-quality, state-level data management system, emphasizing 	Ongoing	well-coordinated and integrated 	Hess-Herbert and

coordination with StreamNet regional staff, MFWP and other state and 	data management systems	staff

federal natural resource agencies to encourage the use of consistent data

attributes and data sets among all agencies.

ODFW	1	Maintain and enhance all existing Oregon tabular database systems, 	Ongoing	Necessary development and 	Herber, Cooney,

including the ODFW Library software, the Incidental Fish Observation 	modifications to keep these 	Brodeur

Database, the Fish Presence Survey Database, and the Oregon Fish Finder 	systems functional

Database. This work includes metadata development and maintenance,

and QA/QC activities.

Region	1	Maintain and upgrade as necessary the StreamNet database servers and 	Ongoing	Functional and improved 	Kinney

software.  Administer the SQL Server database.  Maintain and optimize 	database servers and software

database structure and function.  Advise on software acquisition for the

StreamNet regional office.

WDFW	1	Work with internal WDFW staff to improve the agency data collection 	Ongoing	Consultation, tools, databases, 	Sikora, Woodard

efforts to allow more efficient compiling in the internal intermediate 	programming as warranted

WDFW StreamNet database and/or StreamNet databases.

WDFW	2	Coordinate activities to maintain all new and existing internal 	Ongoing	Tabular data, coordination, 	Sikora, Woodard

WDFW-StreamNet tabular databases, general WDFW-StreamNet 	functional database system

procedures and specifically StreamNet data submission procedures.  	including adequate

Coordination between agencies with co-compiling responsibilities (i.e. 	documentation

CRITFC's efforts in the Yakima watershed).  Maintain the hardware and

software necessary to support the database system.

Objective	2	Task:	1	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 17 of 36

Objective	2	Data management and delivery

Task	2	Maintain and enhance the GIS and hydrography database systems at the project and regional levels

Maintain functional Geographic Information System programs at the agency and regional levels to make consistent GIS layers for anadromous and

resident fish available through the StreamNet online database system.  At both the regional and state levels, provide GIS management and administration

necessary for accomplishing StreamNet objectives, to include: 1) maintaining regional and agency-level GIS systems, including hardware and software,

and 2) maintaining a regionally consistent hydrography layer at the 1:100,000 scale.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

IDFG	1	Maintain existing ArcView tools, including the data request project, the 	Ongoing	Functioning GIS applications.	Butterfield

Geographic Information Locator program, the Idaho Projector extension,

and the Fish Tools project.

IDFG	2	Maintain the hardware and software that comprise IDFG/StreamNet GIS. 	Ongoing	Functioning hardware and 	Butterfield

Provide system administration, backup and recovery, and security.	software.

IDFG	3	Build additional GIS data sets, interfaces or tools as required to complete 	Ongoing,	Potentially new ArcView 	Butterfield

other tasks. Specific jobs will be identified on as needed basis.	as needed	data sets and tools.

IDFG	4	Complete the migration to ArcGIS 8.2. We will continue to maintain and 	12/30/02	New license manager installed 	Butterfield

support ArcView 3.x.	and access to ArcGIS by all

IDFG/StreamNet and IFWIS

staff.

MFWP	1	Maintain the MFWP StreamNet GIS system.	Ongoing	Functioning GIS system	Hess-Herbert

ODFW	1	Maintain and enhance all existing Oregon GIS database systems. This 	Ongoing	Necessary development and 	Bowers

work includes metadata development and maintenance, and QA/QC 	modifications to keep these

activities.	systems functional

Region	1	Integrate the functioning of the GIS system with the StreamNet fisheries 	Ongoing	Cross tables up to date and 	Butcher

and habitat database in support of the query system.  Maintain up-to-date 	online delivery of data by

cross tables used via the StreamNet web interface to select information by 	geographic criteria

geographic area.

Region	2	Maintain functioning GIS software at the regional office (two seats) + 	Ongoing	Functional regional GIS system	Butcher

server products, including installing new software and making upgrades to

old software, fulfilling contract obligations to ESRI (software vendor), and

keeping abreast of GIS software developments that could be beneficial to

the project.

Objective	2	Task:	2	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 18 of 36

Region	3	Maintain a regionally consistent 1:100,000 hydrography layer (the PNW 	Ongoing	1:100,000 hydrography layer 	Butcher

Reach File) for internal use and for public access, through consultation 	and documentation available for

with the state stewards of the hydrography.	 project use and on line

Region	4	Maintain/improve the LLID/NHD hydrography conversion tool.  Immediate	3/31/03	Completed LLID/NHD 	Butcher

need is to complete error trapping routines and polish the final application.	conversion tool.

Region	5	Increase data usability with new GIS software and by converting from 	11/30/02	GIS database converted to 	Butcher

coverage format to geodatabase format.	geodatabase format.

Region	6	Develop an on-line mapping application for use by data compilers, 	9/30/03	Online Event Mapper functional	Butcher

agency biologists, project sponsors, watershed councils, etc. to assist

in mapping projects, assigning LLID and measures on the regional

hydrography, and entry of data.

WDFW	1	Perform any work required to spatially-enable data.   Coordinate activities	Ongoing	Spatial Layers, spatially 	Hudson, Sikora,

to maintain all new and existing WDFW internal spatial layers related to	enabling cross-references, 	(Lensegrav)

StreamNet tabular and spatial submissions including but not limited to	tabular coordination, functional

100K hydro (streams and lakes), marine areas, distribution, production	GIS system including adequate

(hatchery and dam), and release site layers. Manage regionally standard	documentation.

location codes (LLIDs) and cross-reference files that spatially enable data.

Submit any spatial layer as warranted to coordinate with tabular exchanges.

Maintain the hardware and software necessary to support all system functions.

WDFW	2	Create FGDC compliant metadata for Washington StreamNet spatial	9/30/03	Completed metadata 	Hudson

data layers

Objective	2	Data management and delivery

Task	3	Data management and coordination

This task includes GIS and tabular data management at the regional and cooperating project levels after they have been developed.  Once data

are submitted to the regional database, assure they fit established formats, perform appropriate error checks, and load the data into the

StreamNet database and perform routine management of the data.  The region and contributing agencies will collaborate to fix problems and

assure seamless loading of data into the database.  The cooperating projects will perform similar functions for their data.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

IDFG	1	On an opportunistic basis, coordinate with IDFG fishery programs to 	Ongoing	Increased coordinate and 	Butterfield

facilitate the use of data standards that are consistent with StreamNet and 	cooperation between StreamNet

other regional standards.	 and IDFG fishery projects.

IDFG	2	Prepare metadata for all locally held GIS layers.	9/30/03	FGDC compliant metadata.	Butterfield

Objective	2	Task:	3	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 19 of 36

IDFG	3	Maintain and update the StreamNet hydrography, including additions and 	Ongoing	Updated hydrography in LLID 	Butterfield

modifications to the LLID stream and lake layers. Submit all changes to 	format.

PSMFC for inclusion into the StreamNet database.

IDFG	4	Coordinate with PSMFC to assure all data submissions are in StreamNet 	Ongoing	Effective communication and 	Brown

data exchange format.	coordination between

IDFG/StreamNet and PSMFC

regarding data deliverables.

IDFG	5	Conduct a review of IDFG redd count trends. We have identified that 	9/30/03	Newly defined redd count trends.	Murdock, Brown

some historic redd counts have changed significantly in location, length or	 New data set submitted for

method, yet remain in the same StreamNet trend. We will evaluate each 	inclusion into StreamNet.

existing trend and create new trends where necessary. When completed,

the updated data will be prepared for and updated in StreamNet.

MFWP	1	MFWP Staff will assist staff as needed.	Ongoing	Quality checked and accurate 	all staff

exchanged data

MFWP	2	Maintain, update and enhance MFWP GIS data layers, provide these data 	Ongoing	Up-to-date data layers; 	all staff

as distributed files, on the web or as part of map requests.  Integrate the 	responsive to creation of new

use of GIS into management decision making processes.(Most of this work	data layers

is conducted outside the StreamNet contract with MFWP dollars).

ODFW	1	Work with regional staff as necessary to assure seamless loading of data 	Ongoing	Errors and problems related to 	All staff

into the regional database.	data exchange resolved

Region	1	Update and append data as submitted by StreamNet participants.  Isolate 	Ongoing	Maintained StreamNet database 	Kinney

erroneous or duplicative data and work with source agencies to correct 	with data submission logs up to

problems.  Produce downloadable versions of StreamNet databases.   	date.

Maintain logs of data submissions and major database changes.

Region	2	Whenever new tabular data with a spatial component are submitted to the 	Ongoing	Data with sound spatial 	Butcher

project (e.g., fish distribution, hatchery facilities, etc.), create regional GIS	referencing available on the

layer(s) from this information where possible.  Verify correct format, accuracy	StreamNet web site

and logical consistency of spatial data sets and attributes through coordination

with state GIS contacts and then load data to the regional database in

coordination with the database manager.  Post mappable layer(s) for the online

query system and as downloadable layer(s) for StreamNet GIS users.

Region	3	Maintain a library of StreamNet GIS layers for internal use and as 	Ongoing	GIS data library and metadata	Butcher

downloadable data on the web site with complete documentation (metadata).	available on the SN website

Region	4	Obtain and refine layers such as ESUs, ecoregions, or elevations, and 	Opportun-	GIS layers and cross- reference	Butcher

create cross tables for use by the query system.	istic	tables support the web query system

Objective	2	Task:	3	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 20 of 36

Region	5	If possible, update the Hatchery Releases database with data from the 	Ongoing	StreamNet hatchery release data	Kinney

Regional Mark Information Center or directly from state agencies where 	as current as possible.

information is available.  Data must be in either StreamNet data exchange

format or a modified PSC data exchange format prior to rolling CWT

release records into single records by tag code.  Reconcile known

redundancies in the hatchery release table resulting from acquisition of

data from multiple sources.

Region	6	Assist the database manager with the spatial component of data and its 	Ongoing,	Sound spatial component of the 	Butcher

implementation online, as needed.	as needed	StreamNet database

Region	7	Assist data contributing agencies in development of data, including 	Ongoing	Assistance to data providers	Butcher, Banach,

formatting, coding, data entry, error checking, and submitting to the 	 Kinney

regional database.

Region	8	Examine the StreamNet database for errors and report any found to the 	Ongoing	The list of database errors 	Kinney, Banach

appropriate entity for correction.	encountered by users is current

and leads to corrections.

Region	9	For the reaches not yet converted, update georeferencing for the 	Ongoing	Improved georeferencing for 	Butcher

Protected Areas and Smolt Density Model data from river reach numbers 	Protected Areas and Smolt

to LLIDs, where possible.  All obvious locations have been converted.  	Density Model data.

The remainder are the ones with ambiguous or unclear location

descriptions.

WDFW	1	Work with regional staff as necessary to assure seamless loading of data 	Ongoing	Cooperation, feedback, 	Sikora,

into the regional database and improve the data submission process.	re-submittals of data or extra 	Woodard,

documentation as warranted	Hudson

WDFW	2	Provide metadata for tabular and spatial data according to any guidelines 	Ongoing	Metadata, as warranted	Sikora, Hudson,

adopted by the Steering Committee.	Woodard,

Objective	2	Data management and delivery

Task	4	Data exchange standards

Establish and maintain data exchange standards to ensure consistent content and format of data that originate from multiple data sources.

Monitor adopted and proposed data exchange formats for data categories described under Objective 1. This task will provide coordination and

technical assistance regarding interpretation of database structures and codes.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Participate in DEF review and development issues to maintain workable 	Ongoing	Maintenance of useful and 	Forrest

exchange standards.	consistent data exchange

standards.

Objective	2	Task:	4	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 21 of 36

FWS	1	Review and comment on DEF issues brought to the Steering Committee	Ongoing	Contribution to Steering 	Pastor

Committee review of DEF

IDFG	1	Provide lead development of a DEF for juvenile data.	9/30/03	New data exchange format for 	Butterfield

juvenile data.

IDFG	2	Participate in the development or modification of other data exchange 	Ongoing	New or updated data exchange 	Butterfield

formats.	formats.

IDFG	3	Participate in the development for a protocol for developing or 	Ongoing	New protocol for developing or 	Butterfield

modifying data exchange formats	modifying data exchange formats.

MFWP	1	MFWP StreamNet will participate in the design, development and 	Ongoing	Reviewed DEF's	Hess-Herbert,

maintenance of standard codes and data exchange formats. This will occur	other staff

through involvement on the Steering Committee and technical work

groups.

ODFW	1	Monitor adopted and proposed data exchange formats and provide 	Ongoing	DEFs monitored and 	All Staff

comments, feedback, and/or recommended changes as necessary.	commented on as needed.

ODFW	2	Develop and submit a draft DEF for carcass placement efforts.  Due date 	2/15/03	Carcass Placement DEF 	Hurn

presumes completion of the formal DEF developent process, and may be 	proposed

delayed if the process is delayed.

Region	1	Assist with the design and implementation of data exchange standards as 	Ongoing	Sound formats for spatial 	Butcher

they relate to the spatial aspect of data in the StreamNet database.	referencing of data

Region	2	Maintain and update the StreamNet Data Exchange Format as necessary 	As needed	Updated Data Exchange Format	Banach

to incorporate additions and modifications agreed to by the Steering

Committee.  Record accepted revisions in the DEF document.  At least

one update of the DEF document will be made during the year.

Region	3	Complete the white paper begun in FY02 that examines the implications 	5/2/03	White paper on DEF 	Banach

of a major simplification of the StreamNet Data Exchange Format.  A 	simplification

simplified DEF, using much flatter tables, could greatly ease data submittal

for StreamNet participants and potentially speed data flow to the

regional database.  It may also permit much easier data capture from

people outside of the StreamNet project.  However, potential

complications of such an approach could include data integrity problems,

unacceptable workload shifting, and a variety of other issues.  Explore

these issues and create a report on the potential benefits and detriments of

a simplified DEF.

Objective	2	Task:	4	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 22 of 36

Region	4	Assist with development of XML schema based data exchange options for	6/1/03	Report to Steering Committee 	Kinney, Wilke

both incoming and outgoing data.  Develop a written recommendation on	recommending how to utilize

how to utilize XML to maximize exchange of data for consideration by 	XML.

the StreamNet Steering Committee for future action.

WDFW	1	Engage in data exchange standards and format (DEF) discussions.  Initiate 	Ongoing	DEF and data standards 	Sikora,

discussions as warranted when WDFW's data cannot be accurately 	feedback.	Woodard,

converted and provide an adequate status report to the StreamNet 	Hudson

Regional staff when it's time to let them lead the continuing discussion.

Objective	2	Data management and delivery

Task	5	StreamNet Internet site

Continue to maintain and enhance the existing client-server system to provide access to StreamNet data products through the Internet at both the regional

and cooperating project levels.  The StreamNet home page will continue to be utilized as the project's primary data delivery vehicle.  Priority will be

given to incorporating data developed through Objective 1 and providing access to reference materials secured through Objective 3.  GIS systems will be

used to promote data sharing, data transfer, communication, and to pilot efforts that improve efficiency in data migration to the StreamNet database.

Appropriate training on the use of the system will be provided through a combination of on-line help and in-person training sessions.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

MFWP	1	Review the StreamNet web site as requested and provide comments	Ongoing	Comments and suggestions	Hess-Herbert

ODFW	1	Manage and maintain Oregon's web-based data integration, 	Ongoing	Oregon's web-based systems are 	Herber, Bowers,

communication, and transfer systems sites and their links to StreamNet.	maintained, updated, & 	Brodeur

improved, Oregon data and

reports are posted, and links to

SN are maintained

ODFW	2	Monitor and provide feedback on existing and new StreamNet Internet 	Ongoing	StreamNet site is monitored and	All staff

features.	 feedback is provided to

StreamNet

Region	1	Maintain the GIS Data, Map, and PNW Reach File Internet pages.	Ongoing	Up-to-date GIS and 	Butcher

hydrography information

available on line

Region	2	Maintain, update, and improve the Internet mapping component to the 	Ongoing	Functional Internet mapping 	Butcher

StreamNet web site to allow users to access StreamNet data through 	application

interactive map interfaces.  Improvements might include such items as

adding DRGs or aerial photos to the IMS applications, and showing trend

locations in the web query system.

Objective	2	Task:	5	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 23 of 36

Region	3	Guide development and enhancement of the StreamNet web query system 	Ongoing	Improved web query system	Banach, Schmidt

from the perspective of data users.  Review changes to the web query

system to ensure they are implemented appropriately and do not create

unforeseen problems.

Region	4	Maintain and enhance the look and usability of the current web-based 	Ongoing	Functional and enhanced query 	Wilke

query system.  Incorporate 5th and 6th field HUC GIS coverages into the		Capability

web query system and Internet mapping applications.

Region	5	Convert the core query system to an open ColdFusion environment	3/1/03	Faster, more open and easily 	Wilke

modifiable system

Region	6	Deploy new query system components and data categories that are 	Ongoing	Enhanced functionality and new	Wilke

approved by the Steering Committee	data categories available

Region	7	Maintain logs of web query history and error events.  Track and report 	Ongoing	Logs and reports of StreamNet 	Wilke

Internet site usage by month and investigate web query system errors 	website and query system usage;

encountered.	decreased error rate

Region	8	Maintain and upgrade StreamNet web server and software.	Ongoing	Web server up 99.5+% of time.	Wilke

WDFW	1	As time permits, review new products and features of the StreamNet 	Ongoing	Feedback to the Regional 	Sikora

Internet site.  Provide feedback on content, suitability, navigability and 	StreamNet staff

data currency issues, especially issues related to providing static or

dynamic map capabilities.

Objective	2	Data management and delivery

Task	6	Tool development and maintenance

Provide programming services to project participants to support efficient data entry and transfer.  Tools may be developed at the regional or

agency levels.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Develop and test data handling applications to ease transfer of tribal data 	9/30/03	Prototype data transfer 	Forrest

sets to the StreamNet system.	applications.

MFWP	1	Maintain and enhance the edit/entry interface for fisheries survey data 	As needed	Modifications as requested.	Carson

distributed to individuals with a MFWP Collector's permit, including

federal land management agencies.

MFWP	2	Maintain U of M system for genetics analysis input, Future Fisheries for 	Ongoing	Usable interfaces	Carson, Hutten

restoration project data entry, and other interfaces upon request if they

relate to StreamNet workplan.

Objective	2	Task:	6	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 24 of 36

ODFW	1	Develop and maintain tools as needed to aid and support Oregon's data 	9/15/03	Corporate system initiated with 	Herber

management and delivery. Efforts this year will focus on the initial 	the Trend and barrier/dam

development of a corporate information system targeting Oregon's trend 	Interfaces  functional

and barrier/dam interfaces.

Region	1	On an as-needed basis, update or develop tools to assist with data entry 	Ongoing,	New tools to streamline data 	Wilke

and data management.  Assist StreamNet data compilation agencies with 	as needed	acquisition and improve data

trouble-shooting, modification, or development of data input interfaces.  	searching and reporting.

Tools might include input interfaces, error checking routines, geographic

locators, etc.

WDFW	1	Review and give feedback on StreamNet's tools.  Also build internal tabular	Ongoing	Internal tools and instructions, 	Brown, Hudson,

and GIS tools and procedures to efficiently manipulate data. Share 	feedback for StreamNet or 	Sikora

experiences with such tools and the tools themselves with StreamNet 	external tools

participants upon request.

Objective	2	Data management and delivery

Task	7	Respond to data / information requests

Receive and respond to requests for data and information, source materials, and custom products.  Response to requests will be honored within

the limits of available resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.  Other

priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural resource management activities.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Respond to data requests as they are received.	Ongoing	A log of data requests received 	Forrest

and their disposition

IDFG	1	Respond to requests for data and information, source materials, custom 	Ongoing	Data and other products 	Butterfield

products and technical assistance.  Response to requests will be honored 	delivered to "customers".

within the limits of available resources.  Priority will be given to requests

having direct relevance to the Fish and Wildlife Program, including

Subbasin Planning, Monitoring and Evaluation, CBFWA, the Council,

BPA and other FWP projects.  Other priorities will include

implementation of the Endangered Species Act, other federal and state

regulations, such as NEPA, and natural resource management agencies.

All requests will be logged.

MFWP	1	Receive and respond to requests for data, source materials, and custom 	Ongoing	Completed requests	all staff

products.  Respond to requests within the limits of available resources,

with priority given to information requests having direct relevance to the

F&WP.

Objective	2	Task:	7	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 25 of 36

ODFW	1	Provide responses to data / information requests	Ongoing	Requests are cataloged and 	All staff

fulfilled within existing

resources

Region	1	Respond to requests to the StreamNet project from F&WP participants 	Ongoing	Assistance provided	Banach, Butcher

for data, maps, GIS products or general assistance.  Provide assistance,

including custom map work where feasible.  Direct users to other resources

if requests exceed project capabilities.

Region	2	Respond within one day whenever possible to users who request 	Ongoing	Satisfied requests	Banach, Butcher

information or assistance.  Requests may be for help in navigating the

StreamNet web site to find desired information, help in learning to use the

on-line data query system, help in finding information not contained in

StreamNet, assistance finding GIS layers, providing unique or customized

data, or a variety of other types of requests.

WDFW	1	Generate maps, data reports, and electronic copies of data sets as 	Ongoing	Requested data provided (if it 	Varies by data set

requested.  Provide PRIORITY data support for subbasin assessments and 	already exists)

other new elements of the NWPPC Fish & Wildlife Program, within

existing resources.

Objective	3	Library and reference services

Provide professional library services to the Columbia Basin's fish and wildlife decision-makers, planners,

managers, and researchers by acquiring and cataloging StreamNet source documents and other related

material; and by providing open and efficient access to these materials

Objective	3	Library and reference services

Task	1	Collection development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document data sources,

Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies, interested parties, and

other libraries.  Project participants will submit reference documents for all data to be included in the collection.    (Note:  The consensus

seems to be to have reference submission here, and NOT include it under Data Development.)

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Coordinate source material submissions for data compiled by participants.	9/30/03	Updated catalog of materials	Oftedahl

Objective	3	Task:	1	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 26 of 36

CRITFC	2	Develop a collection of materials related to the Columbia Basin, including 	9/30/03	Updated, expanded collection of	Oftedahl

reports from other Fish and Wildlife Program projects, other agency 	materials.

documents as they relate to the Basin, and other published and unpublished

materials as requested by clients.

CRITFC	3	Maintain and develop a collection of journals related to fisheries and 	Ongoing	Current collection of journals 	Liberty

aquatic sciences as well as other related scientific topics.	available to library users

CRITFC	4	Format the library reference table of StreamNet documents for inclusion 	Monthly	Updated reference table	Oftedahl,

in the StreamNet database.  New updates will be sent to the regional

database monthly after that.

IDFG	1	Provide copies of documents and reports referenced in data submissions.	Ongoing	Reference documents included in	Butterfield

StreamNet Library collection

MFWP	1	Update the StreamNet library with references and publications from the 	date to be 	CD of new data to the 	Carson

Fisheries Division Library on an annual basis.	determined	StreamNet library

MFWP	2	Collect and catalog supporting references to document the sources of the 	12/31/02	Updated references submitted to	Carson

distribution information and other data types developed under Objective 1	 StreamNet Library

and to connect the data to references.  Submit updated references to the

StreamNet Library

ODFW	1	Provide originals/copies of all documents and reports referenced in the 	Ongoing	Literature provided (or made 	Hurn

compilation of new StreamNet data holdings, but not already housed in 	accessible) to the StreamNet

the StreamNet Library.	Library.

Region	1	Enhance the StreamNet data reference system by repairing or establishing 	Ongoing	Reduced confusion and enhanced	Kinney

procedures for updating and reconciling data-related references between 	accessibility to data references

the StreamNet database at PSMFC and the StreamNet Library database

housed at CRITFC.

WDFW	1	Engage in discussions to finalize procedures to submit spatial data 	Ongoing	References, feedback	Varies by dataset

references.  Continue to collect documents used as source materials for

any data in Objective 1. Documents will be assigned reference numbers and

forwarded to the StreamNet library as per established StreamNet

guidelines.

Objective	3	Task:	1	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 27 of 36

Objective	3	Library and reference services

Task	2	Provide access to collection

Provide user access to the materials described in Task 3.1 by providing facilities for storage of paper and electronic copies of documents, an

online catalog of all documents in collections, and staff to answer location questions and respond to requests.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Provide and maintain an appropriate facility for the storage and public use	9/30/03	Library open to public	Oftedahl

of the StreamNet Library collections.

CRITFC	2	Catalog and organize the materials for ease of use by clients and staff.	9/30/03	Current catalog of materials	Oftedahl

CRITFC	3	Provide access to the catalog of materials via the Internet and update the 	Monthly	Updated website and catalog	Oftedahl

online catalog on at least a monthly basis.

CRITFC	4	Develop and execute a plan to place electronic documents in the catalog 	9/30/03	Access to electronic documents	Nock

and on the library website.

CRITFC	5	Develop and keep a schedule of open times and reference desk staff hours.	9/30/03	Staff available to patrons	Nock

Objective	3	Library and reference services

Task	3	Library services

Manage the StreamNet Library and provide library services to the StreamNet user community, Fish and Wildlife Program, and the general

public.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Provide information and reference services to library clients	Ongoing	Information provided as 	Nock

requested

CRITFC	2	Provide information about services and hours to library clients via print 	Ongoing	Updated website and brochure	Oftedahl

and Internet

CRITFC	3	Provide interlibrary borrowing services for library patrons to access 	Ongoing	Information or materials 	Nock

materials not yet owned by the StreamNet Library.	provided to patron

CRITFC	4	Provide access to hardcopy and electronic files of draft and final 	Ongoing	Collection is current	Oftedahl, Nock

documents related to subbasin planning and the NPPC amendment

process.

CRITFC	5	Identify changes and new features that will improve delivery library 	Ongoing	Recommendations to improve 	Oftedahl, Nock,

Services	delivery of services	Liberty

Objective	3	Task:	3	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 28 of 36

Objective	3	Library and reference services

Task	4	Inter-library coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other collections that will

enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Provide interlibrary lending services for other libraries to access the 	9/30/03	Material circulation	Nock

library's unique collection

CRITFC	2	Maintenance of memberships in appropriate library and subject-related 	9/30/03	Presentations, reports, 	Oftedahl

associations.  Ex. IAMSLIC, NRIC, OFWIM, etc.	professional development

CRITFC	3	Provide consultations for groups and other agencies on library 	9/30/03	Services as requested, detailed in 	Oftedahl

organization and services.	Reports

CRITFC	4	Coordinate with other StreamNet libraries, library clients and other 	9/30/03	Improved services	Oftedahl

libraries to improve service to clients and limit duplication of effort.

CRITFC	5	Work with subbasin planning groups and TRTs to identify modifications 	9/30/03	Recommendations to Steering 	Oftedahl, Nock

and new uses to make information related to these processes easier to retrieve	committee

Objective	4	Services to the Fish and Wildlife Program

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife

Program projects

Objective	4	Services to the Fish and Wildlife Program

Task	1	Data and services to support the Fish and Wildlife Program (Base project level only)

Provide data management assistance to the Fish and Wildlife Program, as requested.  Services may include custom development of data,

provision of data from the StreamNet database to support FWP activities (such as planning, monitoring and evaluation, etc.), and general

advice and technical assistance with database management, data delivery, and GIS.  Under base funding, requests under this objective will have

to be balanced against other ongoing activities.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

IDFG	1	Participate in Subbasin Planning work by providing data and information 	As 	Assistance to subbasin planning 	Butterfield

management advice as requested, based on our available time and funds.	requested	efforts

MFWP	1	Work with Montana's CBFWA representative involved with subbasin 	Ongoing	Services as requested	Hess-Herbert

planning and provide data, map products and assistance as needed.  Upload

Sub-basin Planning website information when requested by contractor

Objective	4	Task:	1	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 29 of 36

ODFW	1	Provide tabular and/or spatial technical assistance and data services to Fish	Ongoing	Technical assistance and data 	Herber, Bowers

and Wildlife Program participants, as requested	services provided upon request

Region	1	As requested, generate customized maps and information for subbasin 	On request	Maps and data provided to 	Butcher, Banach

planners  or monitoring programs from StreamNet data or other data 	planners

provided by the planners, as long as this work can be accomplished within

existing resources.

Region	2	Assist subbasin planners and others with the use of the StreamNet database	On request	Data flow to subbasin planners, 	Banach, Butcher

system, including GIS data and the spatial component of the StreamNet 	monitoring programs, etc.

database.

Region	3	Participate in regional discussions of Monitoring and Evaluation to 	On request	Contribution of StreamNet data 	Schmidt

coordinate the use of StreamNet data in support of M&E efforts.	and services to M&E activities

WDFW	1	Participate in Subbasin Planning work by providing data and information 	Ongoing	Standardized data, advice	O'Connor

management advice as requested, based on our available time and funds.	(Woodard)

Objective	4	Services to the Fish and Wildlife Program

Task	2	Archive function for regional data sets, as requested

Work with regional entities to aid in the capture and distribution of data generated through Fish and Wildlife Program activities and to help

determine the most appropriate means of storing and disseminating them.  Where data do not fit in existing StreamNet data sets, develop

archive functions to, at a minimum, make data available 'as is', regardless of their current form.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Work with ESA recovery planning and NWPPC subbasin planning efforts 	Ongoing	Strategies to store data and 	Roger

to ensure data and technical literature are captured and made regionally 	literature in a permanent form,

accessible.	regionally accessible over time.

MFWP	1	Be available to Montana entities as a source of information and assistance	As needed	Data sets identified and obtained	Hess-Herbert,

for capturing F&WP-related data, as needed.	Carson

ODFW	1	Support and participate in state-level and regional data management 	Ongoing	Participate in regional data 	Cooney

initiatives	management initiative to

improve data management in

within Oregon and the region.

Region	1	Maintain an archive or data warehouse capability on the StreamNet web 	As 	Data sets available on the 	Banach

site to house and distribute data in their native formats for other projects 	requested	StreamNet web site.

under the FWP.  This service will be for projects lacking the capability of

posting their own data and for data that do not fit the established Data

Exchange Format.

Objective	4	Task:	2	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 30 of 36

Region	2	Participate in regional discussions on Subbasin Planning to identify data 	Ongoing, 	Plans for acquiring data sets 	Schmidt

that may become available through the planning process.  As data are 	opportun-	produced by Subbasin Planning,

identified, begin development of data standards and formats, and processes	istic	and draft data standards

to effectively acquire the data without duplication of effort.

Objective	4	Services to the Fish and Wildlife Program

Task	3	Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas data set, b) archive the official version as a historic record, c)

in consultation with the Council, respond to requests for information concerning Protected Areas, and d) modernize georeferencing and make

data available through online mapping.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

Region	1	Maintain the Protected Areas database within the StreamNet database.	Ongoing	Protected Areas data available 	Kinney

in StreamNet query system

Region	2	As time allows, work to resolve the remaining ambiguous location of 	Ongoing	Improved locational coding for 	Butcher

Protected Areas to the LLID system.	currently unresolved locations

Objective	5	Project management and coordination

Provide effective leadership that ensures the production of high quality information products targeted at critical

applications and the development of these products in a timely, cost-effective manner.

Objective	5	Project management and coordination

Task	1	Manage project activities

Administer all aspects of the project at the regional and cooperator levels, including oversight of budget, personnel (including training and

staff development), work statement preparation and implementation, coordination among participating agencies, active participation in

steering committee work, and project reporting.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Provide guidance to project activities	Ongoing	Attend and participate in 	Roger, Oftedahl

Steering Committee meetings

and activities

CRITFC	2	Provide project management and staff supervision, including budgeting, 	Ongoing	Reports prepared on time and 	Roger

reporting, etc.	activities conducted within

budget.

Objective	5	Task:	1	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 31 of 36

FWS	1	Represent FWS in Steering Committee meetings.  Produce quarterly 	Ongoing	Project administration 	Pastor

reports w/in 30 days of quarter end.  Produce FWS component of FY2001

final report.  Create FWS StreamNet budget & statement of work for

FY2003.  Contribute FWS portion of Project Renewal documents.

IDFG	1	Administer all aspects of the project at the regional and cooperator levels,	Ongoing	Work statements, budgets and 	Butterfield

including oversight of budget, personnel and training, professional 	other work described in progress

organizations, work statement preparation and implementation, 	 reports.

coordination among participating agencies, active participation in

steering committee work, and project reporting.

MFWP	1	Provide supervision of Montana StreamNet staff and project. Produce 	Ongoing	reports, productive staff, 	Hess-Herbert

quarterly reports within 1 month after the end of each quarter.  Produce 	appropriate input

final report within 2 months of the end of the contract period.

Participate in Steering Committee meetings. Collaborate on developing a

final detailed Statement of Work for FY03 and other documents, as

requested.

ODFW	1	Administer all aspects of the project for Oregon, including budget over-	Ongoing	Successful project 	Cooney

sight, personnel, work statement preparation, staff work plan preparation,	administration

project implementation and coordination, reporting, and participation with

the Steering Committee and technical issue working groups.

Region	1	Project Administration:  Perform ongoing administration of the 	Ongoing	Functional project	Schmidt

StreamNet project, to include budget development and tracking, contract

monitoring, personnel functions, inventory control, etc.

Region	2	Reporting:  Submit quarterly progress reports to BPA within one month 	Quarterly	Reports	Schmidt

of the end of each quarter and submit an annual report within two months

of the end of the fiscal year.

Region	3	Maintain effective relationship with the StreamNet Steering Committee.  	Ongoing	Effective guidance and 	Schmidt

Organize and conduct quarterly Steering Committee meetings to facilitate 	coordination with Steering

project oversight and setting direction/goals.  Coordinate regional project 	Committee

activities with Steering Committee involvement and direction.

Region	4	Enhance productivity of the Regional team through staff training, 	9/30/03	Enhanced productivity 	Schmidt

In advanced ArcIMS, software upgrades, etc.

WDFW	1	The WDFW StreamNet state coordinator will participate in all Steering 	Ongoing	Steering Committee 	O'Connor

Committee and StreamNet Project management activities, including 	participation, quarterly and 	(Sikora)

meetings and follow-up work assignments (progress reports, Statements of	annual reports, budgets, SOW

Work, budgets).

Objective	5	Task:	1	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 32 of 36

WDFW	2	The state coordinator and the state data manager will jointly manage all 	Ongoing	Effective project management	O'Connor,

aspects of StreamNet in WDFW, including budget, personnel, work 	Sikora

scheduling, and product delivery.

Objective	5	Project management and coordination

Task	2	Participate in Fish and Wildlife Program development activities

Work with regional entities to assist in the area of data management as requested to support development of Fish and Wildlife Program

projects and programs.  Organize, facilitate, and/or participate in appropriate coordination meetings with BPA, CBFWA, the Council, ESA

officials, ISAB/ISRP, and/or staff and management of participating organizations to identify ways StreamNet can effectively contribute to

the Fish and Wildlife Program (FWP) and facilitate  capture and dissemination of data.  Participate in advisory groups, task forces, and other

groups whose purpose is enhancing the effectiveness of the Fish and Wildlife Program relative to its data development activities.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Participate in various NWPPC planning and management work groups to 	Ongoing	Reports to Steering Committee 	Roger

improve and coordinate regional information management programs.	on regional information

management needs and

opportunities.

MFWP	1	Provide input, advice, recommendations, review, as needed and requested	Ongoing,	Requested services	Hess-Herbert

as needed

ODFW	1	Work with regional entities to assist in the area of data management as 	Ongoing	Participate as need	Cooney

requested to support development of Fish and Wildlife Program projects

and programs.  Organize, facilitate, and/or participate in appropriate

coordination meetings with BPA, CBFWA, the Council, ESA officials,

ISAB/ISRP, and/or staff and management of participating organizations to

identify ways StreamNet can effectively contribute to the Fish and

Wildlife Program (FWP) and facilitate  capture and dissemination of data.

Participate in advisory groups, task forces, and other groups whose

purpose is enhancing the effectiveness of the Fish and Wildlife Program

and its data development activities.

Region	1	Work with regional entities to contribute data management expertise 	On request	Input and assistance to Fish and 	Schmidt

toward development of activities within the scope of the Fish and Wildlife	Wildlife Program

Program.  Serve as a data management resource to the FWP.

WDFW	1	Assist in any pertinent coordination efforts.	Ongoing	Participation and assistance	O'Connor

Objective	5	Task:	2	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 33 of 36

Objective	5	Project management and coordination

Task	3	Coordinate with other related activities

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities and agencies beyond the

Council's Fish and Wildlife Program to identify means for collaborative data collection, storage, and dissemination.  Collaborative data

activities will include tribal fishery programs within the Columbia Basin, federal land managers’ fishery programs, state fish and wildlife

agencies, and, with respect to water use and stream development, state water resource management and environmental quality agencies.

Collaboration with coast-wide and private data collection/compilation efforts will be pursued when this supports overall project goals.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Participate in various regional inter-agency planning and management 	Ongoing	Reports to Steering Committee 	Roger

work groups to improve and coordinate regional information management	on regional information

programs.	management needs and

opportunities.

IDFG	1	On an opportunistic basis, coordinate with other state, federal, or tribal 	Ongoing	Results described in progress 	Butterfield

agencies to enhance the collection and management of data related to 	reports.

management of natural resources.

MFWP	1	Maintain communication between state and regional entities	Ongoing	Communication	Hess-Herbert

ODFW	1	Establish / maintain working relationships with data collection projects 	Ongoing	Coordinate as needed.	Cooney

within and outside ODFW to promote efficient and beneficial data

sharing.

Region	1	Coordinate with agencies and organizations involved with habitat 	Opportun-	Coordinated efforts and 	Banach

restoration work in the Columbia Basin regarding data needs, standards and	istic	databases among regional data

formats, storage and delivery.  Work toward achieving regional 	managing entities.

consistency in restoration project data.

Region	2	Coordinate with regional entities on habitat data needs and availability.  	Opportun-	Beginnings of coordinated 	Banach

Begin developing an approach toward capturing high priority data types.  	istic	stream habitat database

Development of habitat data may require additional resources.

Region	3	Participate with regional entities in the development of effective regional	Opportun-	Contribution to regional data 	Schmidt

data management programs and approaches, such as through SAIC or  	istic	management efforts

RPA 198.  Provide input based on years of StreamNet experience with

management of data sets on a regional basis, along with insights into

challenges, obstacles and costs.  Support effective regional data

management and delivery at reasonable cost with avoidance of

unnecessary duplication of effort.  Support and encourage regional data

needs assessments.

Objective	5	Task:	3	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 34 of 36

Region	4	In order to broaden the scope and utility of the StreamNet database, 	Ongoing	Project proposals	Schmidt

develop appropriate proposals for data development activities that would

compliment the main StreamNet data holdings.  Ensure proposed work is

not currently conducted by other entities.  (Examples may include

traditional StreamNet data types outside of the Columbia River basin,

macroinvertebrates, water temperature, and habitat restoration.)  Conduct

of such work will be dependent on availability of additional resources.

Once awarded, efforts will conform to the approved contract.  Such work

will be coordinated with this work plan so that activities under this task do

not impede accomplishment of the remainder of the work plan.  This

task is necessitated by the fact that project staff have time available that

is not covered by the BPA contract.

WDFW	1	Assist in any pertinent coordination efforts.	Ongoing	Collaboration and assistance	O'Connor

Objective	5	Project management and coordination

Task	4	Prepare and present public and professional information related to the StreamNet Project.

As needed, produce public information materials and participate in various meetings and forums (public or professional) to explain the

project's capabilities and purpose and to generate support and additional data sources.  Activities may include brochures, demonstrations,

posters and talks to public, policy or professional groups and organizations.

Project	Job	Planned work elements                                                                                 	Date Due    	Deliverable                                  	Lead

CRITFC	1	Prepare and present demonstrations and descriptions of the library 	Ongoing	Reports on activities to the 	Oftedahl

services available through StreamNet.	Steering Committee

MFWP	1	Seek opportunity to provide information on the StreamNet project in 	Ongoing	Well-organized and appropriate 	All staff

public and professional settings.	information provided

ODFW	1	Produce public informational documents on StreamNet data activities for 	Ongoing	Develop, author, and/or present 	Cooney

natural resource oriented publications, give oral  presentations to relevant 	at least 3 StreamNet related

user groups, and participate in various meetings and forums.	informational pieces.

Region	1	Prepare and deliver presentations to scientific and professional meetings 	Opportun-	Presentations	Staff

to demonstrate project capabilities and accomplishments and to solicit 	istic

additional data and involvement or coordination with the project..

Expected results would be enhanced visibility for the project, increased

participation and data flow from agencies, improved coordination, and

avoided duplication of effort.

Objective	5	Task:	4	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 35 of 36

Region	2	Develop materials to support the project.  Improve public materials such 	As needed.	Materials for distribution	Schmidt

as the StreamNet brochure, data inventories, etc. as needed.  Maintain and

update explanatory materials such as the Query System User Guide and

documents that explain data categories and structures.  Prepare and deliver

StreamNet E-Newsletter at least twice as information becomes available.

WDFW	1	Participate as opportunities arise to highlight StreamNet programs & 	Ongoing	Participation, information 	O'Connor

data. Report key contacts and results to Regional Project Manager to 	materials, reports	(Sikora)

keep Manager apprised on opportunities pursued in Washington state.

Objective	5	Task:	4	StreamNet Base Level Statement of Work, Fiscal Year 2003	Page 36 of 36