|  | StreamNet Project BPA Project No.: 198810804 FY 2004 Work Statement October 1, 2003 through September 30, 2004 |
| --- | --- |

Bruce Schmidt

Pacific States Marine Fisheries Commission

Cooperators:

Phil Roger, Columbia River Intertribal Fish Commission

Bart Butterfield, Idaho Department of Fish and Game

Janet Hess-Herbert, Montana Fish Wildlife and Parks

Cedric Cooney, Oregon Department of Fish and Wildlife

Steve Pastor, U.S. Fish and Wildlife Service

Dick O'Connor, Washington Department of Fish and Wildlife

October 1, 2003

Table of Contents	Pg.

Introduction..........................................................................................	2

Objective 1.  Data Development and Update.....................................	4

Objective 2.  Data Management and Delivery...................................	15

Objective 3.  Library / Reference Services.........................................	22

Objective 4.  Services to Fish and Wildlife Program Activities........	25

Objective 5.  Project Management / Coordination............................	29

Introduction

StreamNet is a cooperative, multi-agency data compilation and data management project authorized by the Northwest Power Planning Council’s Fish and Wildlife Program (FWP).  It is funded primarily by the Bonneville Power Administration as part of its program to protect, mitigate, and enhance fish and wildlife resources affected by the development and operation of hydroelectric facilities on the Columbia River and tributaries through the Northwest Power and Conservation Council's Fish and Wildlife Program.  Other funding has been obtained in the past from agencies including the Environmental Protection Agency and the National Marine Fisheries Service.  The Pacific States Marine Fisheries Commission administers the project.

Three fourths of the project consists of sub-projects within the state fish and wildlife agencies, Columbia River Intertribal Fish Commission and US Fish and Wildlife Service to develop databases within the respective agencies and facilitate data transfer regionally.  In addition to administratively housing the StreamNet sub-projects, these cooperating agencies also contribute in kind support.  The kind and amount of support varies between agencies.  All agencies provide at least some salary support for their StreamNet Project Leader (from one or two months to full time).  Several provide use of servers or other computer equipment and services that are not covered by charges for indirect costs.  All contribute time by biologists and in some cases data entry staff to provide data to the project.  MFWP provides $65,000 worth of in-state travel, office space, computers and office supplies.

Introduction			StreamNet Statement of Work, Fiscal Year 2004	Page 2 of 31

The StreamNet Project compiles, manages and distributes information related to fish resources in the Columbia River basin, with additional information available for the rest of the Pacific Northwest.  The state, tribal and federal fish and wildlife agencies collect and utilize data related to the region’s fish and wildlife resources to meet their own mandates.  A subset of these data, primarily the annually collected types of information that are routinely used to monitor trends within fisheries and populations and provide management information, are compiled by StreamNet into regionally standardized formats and publicly distributed.  In this manner, data common to fisheries management but collected and stored in multiple formats by the individual agencies are standardized and made uniformly available basin wide.  StreamNet also ties all data to the regional 1:100,000 scale routed hydrography (GIS stream network) so that different kinds of data can be compared on a geographic basis and mapped.  The project utilizes the Internet as its primary means of data distribution, but also provides custom data services to FWP participants.  The StreamNet web site provides access to information in a queriable database and also provides maps, individual data sets not contained in the queriable database, and library references.  All data in the StreamNet database are referenced to source documents that are housed in the StreamNet Library.

This document is the FY2004 Work Statement for the base components of the StreamNet Project.  Not all tasks identified in the Work Statement apply to all participating agencies.  Each participating agency contributes work to a subset of the project tasks, with their responsibilities detailed individually for each task.  The intent of this format is to provide clarity concerning the total activities addressing each project task and the role of each project participant.  This combined Statement of Work covers Federal Fiscal Year 2004, from October 1, 2003 through September 30, 2004.

Work priorities for FY 2004 include updating existing long term data sets, managing the data and infrastructure necessary to maintain and deliver data, maintaining the StreamNet Library, providing data services to regional entities associated with the Fish and Wildlife Program, and project administration.  Updating and managing the core data sets in the StreamNet database is a primary portion of the base StreamNet project.  Since some of this maintenance has become more routine through utilization of improved technology, a small amount of effort can now be applied to some development of data types not currently contained in the database and to managing data related to subbasin planning efforts.  These efforts are contained in this work statement.  However, since the adopted budget contained support only for the base project, it was not possible to expand the project to include data development activities for many of the data types desired by regional entities that are outside the core data sets.  Such work was proposed in the FY-03-05 Project Proposal as part of a request for regional input on which new data were of the highest regional priority and therefore should be priorities for new work by the project.  Largely due to the budget crisis in FY-03, no response to that request was received, and none of that new work was funded.  The StreamNet Project remains ready to work with regional entities to locate, obtain, standardize, georeference and distribute new data types that are needed for regional recovery and monitoring programs.  Such work will be undertaken if requested by the appropriate entities and support is provided, or if regional guidance is received on changing priorities.  This Statement of Work will be revised is such changes are requested.

Introduction			StreamNet Statement of Work, Fiscal Year 2004	Page 3 of 31

Objective	1	Data acquisition and development

Support the need for region wide fisheries data for research, monitoring, modeling, and management through acquisition and regional standardization of new information and updates to previous information for priority fishery data types.  Data types may be addressed by all data providing agencies, or for specific data types by a single cooperating agency on behalf of the entire project.  This Objective addresses both anadromous and resident fish species, although priorities may differ.  The tasks under this objective are identified as high or low priority under the constraints imposed under base level funding.  Work on the low priority types will largely be limited in scope or effort unless new funding is approved.

Objective	1	Data acquisition and development

Task	1	Anadromous distribution and life history (habitat use) at the 1:100,000 scale

Document the occurrence, distribution and life history characteristics of anadromous fish species.  Project participants made major updates last fiscal year utilizing the new Data Exchange Format (DEF).  Maintenance of this data set will continue.  This is a high priority data set.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

IDFG	1	Update 100K anadromous fish distributions based on input obtained 	6/1/04	Generalized fish distribution 	Brown

from subbasin assessment work and NOAA Fisheries critical habitat 	data exchanged.

designation.

ODFW	1	Update, maintain, correct and exchange anadromous fish distribution 	Ongoing	Errors corrected and newly 	Bowers

and documentation information.	discovered and changed

distribution (based on

documented sightings)

exchanged

WDFW	1	The StreamNet database currently has all WDFW anadromous 	Ongoing	Corrections as warranted	O'Connor, Sikora

distribution data collected at 100K resolution.  Submit corrections if

warranted.

WDFW	2	If the data exchange format issues are resolved to accommodate 	Impossible to 	Data submission	O'Connor, Sikora

WDFW's 24K distribution data collections, convert and exchange 	predict at this

WDFW's most current data.  	time

Objective:	1	Task:	1	StreamNet Statement of Work, Fiscal Year 2004	Page 4 of 31

Objective	1	Data acquisition and development

Task	2	Resident fish distribution and life history (habitat use)

Document the occurrence, distribution and life history characteristics of resident fish species.  Existing resident fish distribution will be

maintained, and project participants will begin expanding data for additional species.  This is high priority for Montana and Idaho, and new

data will be developed by the other states as time allows.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

IDFG	1	Update  100K resident fish distributions using new IDFG data surveys 	6/1/04	Generalized fish distribution 	Brown

and sources, including westslope cutthroat, Yellowstone cutthroat, 	data exchanged.

interior Columbia-basin redband, and bull trout.

MFWP	1	Complete Distribution and Use Types data sets from data collected from 	12/01/03, 9/01/04	Exchanged distribution and use	Carson, Hutten

biologists, documents and reports during 2001-2002 using LLID stream 	 type data

routes and Montana's lakes coverage and watercode system. Exchange

with StreamNet.  Complete distribution and use type data sets for 2002-

2003.  Update entire state, including missed data from Western Montana

in FY03.  Focus on target species during the year if opportunity arises.

Exchange the data to the regional database in the approved DEF format.

MFWP	2	Visit MFWP, other state and federal fisheries biologists in 2004 to 	05/01/04	Data collected entered into	Carson, Hutten

collect 2002-2003 fish distribution and supporting survey data and 	MFISH

references.   Input all this information into the MFISH tables.  To aid in

visits, provide maps and other support documents to biologists.

ODFW	1	As time and funding permits update, maintain, correct and exchange 	Ongoing	Exchanged distribution data in 	Bowers

resident fish distribution and documentation information.	DEF format.

WDFW	1	Via distribution proofing parties, organize the effort to update WDFW 	06/30/04	Complete and standardized 	O'Connor, Sikora

westslope cutthroat distribution data and compile that data in concert 	WDFW internal files

with the existing federal data that was compiled in 2002.

WDFW	2	Convert and exchange the westslope cutthroat distribution data.	09/30/04 (if Job 1	Data submission, if possible	O'Connor, Sikora

ETA is correct)

WDFW	3	As time and funding permit, scope data availability and work to compile, 	Ongoing, 	Quarterly progress report, data 	O'Connor, Sikora

convert and exchange distribution data for other priority resident 	quarterly	submission if possible

species (including coastal cutthroat and rainbow trout).

Objective:	1	Task:	2	StreamNet Statement of Work, Fiscal Year 2004	Page 5 of 31

Objective	1	Data acquisition and development

Task	3	Adult abundance in the wild

Develop and maintain (update) information on adult abundance for native fish species, resident and anadromous, including escapement, redd counts, peak spawner counts, trap counts, dam and weir counts, and resident fish populations (where calculated by other agencies).  This is a high priority data type.  Also included in this data category are data gathered during spawning ground surveys regarding straying of hatchery fish onto spawning areas, i.e., marked/unmarked ratio.  These are lower priority under base funding.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Update mainstem Columbia and Snake River dam counts through 2003 	3/31/04	Updated dam count data sets 	Forrest

and provide updated data to the StreamNet database.	exchanged

CRITFC	2	Update available tribal spawning ground survey data.	6/30/04	Updated available spawning 	Forrest

ground data sets

IDFG	1	Complete the compilation of the 2003 field season redd count data from 	4/1/04	Redd count data exchanged.	Brown

IDFG.  Prepare the data for inclusion into StreamNet and submit.

MFWP	1	Collect all 2003 stream and lake fish survey data during field office visits;	05/01/04	none; data collected will be 	Carson, Hutten

data may be one time visits, index streams and/or results from gill nets 	entered into MFISH

in lakes and reservoirs.

MFWP	2	Input 2003 data into MFISH, including trend, count and references.  	09/01/04	Data input into MFISH 	Carson, Hutten

Through the DEF Process, we will explore the creation of a DEF for 	database structure

Montana's stream survey data.  If DEF is not developed, Montana will

look into submitting these data as a supplemental dataset to the

StreamNet website.

ODFW	1	Update existing anadromous, resident, and non-game abundance and 	4/15/04, 9/15/04	All Columbia Basin trends, 	Hurn

index trends through 2002. Opportunistically collect new trend 	where new information is

information, including marked-to-unmarked ratio data (relative to dam, 	available, are updated with

weir, spawning ground, etc. counts) and hatchery-fraction data.	available information

WDFW	1	Update and enhance the existing natural spawner database (escapement 	06/30/04	Data submission (2003 	Woodard

estimates and/or detailed counts) for available species (including a 	anadromous data)	(Groesbeck)

focus on steelhead data AND any dam or weir counts that might not

already be captured in our on-going Adult Abundance collection).

Objective:	1	Task:	3	StreamNet Statement of Work, Fiscal Year 2004	Page 6 of 31

Objective	1	Data acquisition and development

Task	4	Hatchery releases

Develop and maintain (update) information on the release of hatchery reared fish.  Emphasis this year will be on developing release data before release information is rolled up into PSC location codes.  Release data for resident species under base funding will be developed only where the data are readily available (primarily Montana).  Efforts will be made to complete cross references between PSC release codes and LLID stream location identifiers.  This is a high priority data set.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

FWS	1	Data received from National Fish Hatcheries will be processed and 	9/30/04	hatchery release database file	Pastor

added sent to the Regional Mark Information System via the USFWS

Lacey Office.

IDFG	1	Work with IDFG Fisheries staff to incorporate IDFG hatchery release 	9/30/04	Hatchery release data 	Murdock

data into StreamNet.	exchanged.

MFWP	1	Exchange Montana's hatchery release data after development of a 	12/01/03	Exchanged hatchery release 	Hutten

resident DEF and/or modifications to the existing anadromous hatchery 	data.

release DEF.  Number of years and number of waters will need to be

determined.

ODFW	1	Compile and submit anadromous hatchery releases through 2002, and 	7/30/04	Unrolled release data 	Herber

2003 where available.	exchanged with StreamNet

Region	1	Assist contributing projects with cross referencing PSC codes with 	On request	Assistance provided, resulting 	Butcher

LLID codes, as needed or requested.	in georeferenced PSC Codes

WDFW	1	For anadromous species, finish researching, compiling, converting 	12/15/03	Data submission (1995-Current 	Sikora

existing WDFW anadromous release data as detailed, "unrolled" 	anadromous data)

records.  Submit the data (and yearly updates) directly to the StreamNet

database (instead of via RMIS).

WDFW	2	For anadromous species, WDFW and WDFW StreamNet staff work 	Impossible to 	Accurate and efficient data 	Cox, Sikora

jointly to create a more efficient and predictable means to compile the 	predict at this

unrolled releases.	time

WDFW	3	WDFW resident stocking data is fractured in several collections by 	Ongoing, 	Quarterly progress report, data 	Sikora

year.  Work at researching, compiling, standardizing and converting data	quarterly	submission if possible

for any years we have finalized at a given time, until all collections are

submitted.  (Progress with this data set relies heavily upon initial

improvements to our Lakes spatial layer).

Objective:	1	Task:	4	StreamNet Statement of Work, Fiscal Year 2004	Page 7 of 31

Objective	1	Data acquisition and development

Task	5	Hatchery returns

Develop and maintain (update) information on the return, disposition and straying (e.g., from other hatcheries) of adult fish returning to hatcheries, including information on coded wire tags.  This is an anadromous related task only.  Priority will be placed on updating total return and egg take data through 2002.  Development of disposition data is lower priority and would require additional resources.  This is a high priority data set.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

FWS	1	Data received from National Fish Hatcheries will be processed and 	9/30/04	Hatchery Return database files	Pastor

added to the new hatchery return file in the DEF, after a new program is

written and debugged.

IDFG	1	Complete compilation of the 2003 field season hatchery return data from 	4/1/04	Hatchery return data 	Brown

IDFG. Prepare the data for inclusion into StreamNet and submit

IDFG	2	Convert existing hatchery return data to new DEF.	12/30/03	Existing hatchery return data 	Murdock

exchanged in new DEF.

ODFW	1	Compile data on returns to ODFW hatchery facilities (updated through 	6/30/04	Updated return data exchanged	Herber

2002 returns where possible).	 with StreamNet

WDFW	1	Update and enhance the existing hatchery return database for available 	11/30/03	Data submission (2002 	Woodard

species per the newest DEF.	anadromous data)

WDFW	2	WDFW and WDFW StreamNet staff work jointly to create a more 	Impossible to 	Accurate and efficient data 	Cox, Woodard

efficient means to analyze and simplify the hatchery return data flow 	predict at this

from the internal WDFW database. 	time

Objective	1	Data acquisition and development

Task	6	Dams and Fish Passage Facilities

Develop and maintain information on dam facilities.  Update information as necessary.  This is a high priority data set.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

IDFG	1	Update dam information as necessary.	Ongoing	Dam data exchanged.	Brown

MFWP	1	Continue to update Montana's spatial coverage and associated tabular 	3/31/04	Updated dams spatial and 	Hutten

file of dams.  Exchange with StreamNet.	tabular data in DEF.

ODFW	1	Maintain and update, as needed, based on errors found in the Oregon 	Ongoing	Corrected dam and fish passage	Bowers, Brodeur

dam and fish passage facilities information.	facility information exchanged

WDFW	1	Update the dam database, adding records and improving field entries as 	07/30/04 if 	Data submission if warranted	Sikora

warranted.	warranted

Objective:	1	Task:	6	StreamNet Statement of Work, Fiscal Year 2004	Page 8 of 31

Objective	1	Data acquisition and development

Task	7	Hatchery facilities

Develop and maintain information on anadromous and resident hatchery facilities, including information on location, design, management and authorization.  Update information as necessary.  This is a high priority data set.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

FWS	1	The hatchery facility database file will be updated as needed.	9/30/04	hatchery facility database file	Pastor

IDFG	1	Update hatchery facility data as necessary.	Ongoing	Hatchery facilities data 	Brown

exchanged.

MFWP	1	Update the StreamNet hatchery database with Montana's public and 	05/01/04	Updated database in exchange 	Hutten

private facilities.  Exchange with StreamNet upon completion.	format

ODFW	1	Maintain and update, as needed, based on errors found in the Oregon 	Ongoing	Corrected hatchery facilities 	Bowers, Brodeur

hatchery facilities information.	information exchanged

WDFW	1	Update the hatchery database, adding records and improving field 	02/28/04	Data submission	Sikora

entries as warranted, including record updates for related tables (i.e.

HatcheryXProduction data).

Objective	1	Data acquisition and development

Task	8	Harvest

Develop and maintain (update) information on sport and commercial harvest.  Higher priority is assigned to anadromous species.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Complete and update ocean and Columbia River catch data through 2003	9/30/04	Updated harvest data Exchanged	Roger

IDFG	1	Work with IDFG Fisheries staff to incorporate IDFG harvest data into 	9/30/04	Harvest data exchanged.	Murdock

StreamNet.

MFWP	1	Explore the possibility of exchanging Montana's limited creel survey 	06/01/04	Exchanged data.	Carson

data using the current Harvest DEF.  Exchange if data is compatible

and/or desired by Steering Committee

ODFW	1	Compile and exchange Oregon sport harvest data through 2001.	4/15/04, 9/15/04	All Columbia Basin sport 	Hurn

harvest trends where new

information is available are

updated with available

information

Objective:	1	Task:	8	StreamNet Statement of Work, Fiscal Year 2004	Page 9 of 31

WDFW	1	Although we should only be in maintenance mode for this data set, 	Ongoing, 	Quarterly progress report, data 	Sikora

WDFW re-organized their data collection process several times since 	quarterly	submission if possible

our last StreamNet update (and it's still in flux) so it poses a large

workload.  As such, we need a large allotment of time before renewing

this effort and this year we're devoting any discretionary time to barriers.

As funding and time permits, compile freshwater harvest for key

Columbia Basin salmonid stocks for both anadromous and resident data,

using existing WDFW data sets (i.e. Angler Fish Database) and other

sources.  Standardize the data (to stock if possible), convert and submit

it to the StreamNet database.

Objective	1	Data acquisition and development

Task	9	Hydrography

Maintain a regionally consistent routed hydrography layer at the 1:100,000 scale.  This LLID based hydrography is the basis for georeferencing and displaying locations for all other data in the StreamNet database, and as such is an essential data set.  Data will be updated as necessary.  Exploratory work will be initiated in preparation for the eventual, inevitable move to the 1:24,000 scale hydrography being developed by other entities.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

IDFG	1	Maintain and update, as necessary, the 1:100,000 scale hydrography 	Ongoing	Hydrography data exchanged.	Butterfield

files for Idaho.  Submit all changes to the StreamNet database at the

Regional office.

IDFG	2	Complete lakes GIS layer for Idaho and incorporate into StreamNet.	4/1/04	Lake GIS data exchanged.	Butterfield

MFWP	1	Using the NHD, complete updating the routes using the updated NHD 	10/01/03	Updated hydrography data 	Carson

layer; quality check the cross-reference between the LLID system and 	exchanged

MFWP's watercode system (a system still used to index fishing

pressure, hatchery plans and numerous other databases).

MFWP	2	Error check and edit Montana's lakes layer which was created using 1:24 	12/01/03	Updated lakes layer for 	Carson

000 and 1:100 000 base hydrography.  Provide to StreamNet for use with 	Montana exchanged

Hatchery Release Data.

MFWP	3	Using ArcGIS, create new stream annotation layers at 3 scales; 	05/01/04	Updated annotation layer	Lindstrom

generalized, HUC level and Stream Level.

ODFW	1	Maintain and update, as necessary, the 1:100,000 scale hydrography 	Ongoing	Functional and current Oregon 	Bowers

files for Oregon.  Submit all changes to the StreamNet database at the 	100K hydrography, data

Regional office.	Exchanged

Objective:	1	Task:	9	StreamNet Statement of Work, Fiscal Year 2004	Page 10 of 31

WDFW	1	Update, as necessary, the Washington 1:100,000 scale Stream, Lake, and 	Ongoing	Functional and current 	Hudson, Sikora

Marine Area hydrography files.  Submit all spatial and tabular changes to	Washington 100K Stream

the StreamNet database at the Regional office for inclusion in the PNW 	hydrography

regional hydrolayer.

Objective	1	Data acquisition and development

Task	10	Habitat restoration / improvement projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations within the Columbia Basin, and compile and maintain them in standardized, consistent formats.  Preliminary work has been completed on this data type, but regional priority has not been assigned to developing these data.  Work continues on improving the data structure and DEF, primarily through work being done by a related project in California.  This currently remains a low priority data type under current base funding, but is ready should a higher priority be assigned by regional entities.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

MFWP	1	Continue to collect, centralize and maintain all stream restoration 	3/31/04, 9/30/04	Updated data exchange	Hutten

projects data for Montana using the "Future Fisheries Interface" which

StreamNet staff maintains and the Fisheries Division inputs data.

Exchange data to the Region twice during the year.

MFWP	2	Update location of all restoration projects through a review with regional	12/01/03	Updates in database of locations	Lindstrom

MFWP fisheries biologists.  Provide hard copy maps of locations in

data base and store updated coordinates in database.

MFWP	3	If the opportunity arises, participate in any regional actives related to 	Ongoing	Participation	Hess- Herbert

restoration projects including the Pacific Coast Salmon Recovery Fund.

ODFW	1	Maintain and update, as needed, based on errors found in existing 	Ongoing	Exchange corrected tabular 	Brodeur

Oregon tabular restoration data.  Maintenance only.	restoration data

ODFW	2	Input a small set of historic restoration project records as a test to scope	12/31/03	Small number of historic 	Wegner

the level of effort needed to input available historic information.	restoration project records

exchanged in current DEF.

WDFW	1	If funding and time permits, convert  habitat restoration project data 	Ongoing, 	Quarterly progress report, data 	Sikora (Blatz)

stored in Washington's IAC's (Interactive Committee for Outdoor 	quarterly	submission if possible

Recreation) PRISM database and submit to StreamNet.  NOTE - We

anticipate a pilot effort (under other funding) to compile other source

habitat restoration data in StreamNet's newest format.

Objective:	1	Task:	10	StreamNet Statement of Work, Fiscal Year 2004	Page 11 of 31

Objective	1	Data acquisition and development

Task	11	Barriers

Develop and maintain data sets for barriers to fish migration.  This category is still being organized.  Existing data on adult barriers will be maintained and updated as practical.  Other sources of data will be explored.  Work on juvenile barriers and culverts may require revisions to the DEF.  The primary emphasis is on anadromous species except in non-anadromous areas.  This is a low priority data set under current base funding, and will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

IDFG	1	Continue to compile barrier records.	Ongoing	Barrier data exchanged.	Brown

MFWP	1	Complete update to barrier location, species affected and other fields on 	05/01/04	Exchanged barrier data.	Hutten

stream barriers in Montana once the data collected during the

Westslope Cutthroat Assessment Process conducted in 2002 is

reviewed by MFWP biologists.  Information will be collected on all

species regardless of life history.  Exchange Barriers data with the

StreamNet database.

ODFW	1	Update and maintain Oregon's Barrier data and minimal Fish Barrier data 	Ongoing	Exchange new barrier location 	Bowers,

development based on new barrier information.	information (with minimal fish 	Brodeur

barrier information)

WDFW	1	Scope any existing Washington state barriers data for a pilot data 	9/30/04	Data submission	Sikora

submission this FY.  Data sources will at least include the SSHIAP and

TAPPS databases.

Objective	1	Data acquisition and development

Task	12	Juvenile data (abundance and outmigration)

Develop and maintain information on smolt production (as determined from smolt traps), juvenile abundance (as determined through snorkel, electrofishing, and other surveys), and smolt density model estimates.  Primary emphasis will be on maintaining the existing smolt density model data and development of a DEF for these data.  The rest of the work for this data category is still under development and will require additional resources to accomplish.  This is a low priority data set under current base funding, and will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

ODFW	1	Compile juvenile abundance data as it is identified and becomes 	9/15/04	Exchange available age data.	Hurn

WDFW	1	As funding and time permits, keep informed about other WDFW agency	Ongoing, 	Quarterly progress report, data 	Sikora, O'Connor

staff efforts to organize the juvenile data and scope existing juvenile 	quarterly	submission if possible

data to plan future conversion and submission efforts.

Objective:	1	Task:	12	StreamNet Statement of Work, Fiscal Year 2004	Page 12 of 31

Objective	1	Data acquisition and development

Task	13	Age

Develop and maintain information on age/sex composition of returning adults, primarily for anadromous species.  Emphasis on this data

type will increase once the draft DEF is tested and finalized.  This is a low priority under current base funding.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Update CRITFC age data on sockeye and Bonneville Dam sampling 	9/30/04	Updated age data 	Roger

FWS	1	The Age table will be updated using the Snage program after processing	9/30/04	Age table updated and 	Pastor

is completed within the CRiS database.	exchanged

IDFG	1	Complete the compilation of the 2003 field season age data using 	4/1/04	Age composition data 	Brown

hatchery returns data from IDFG.	exchanged.

ODFW	1	Compile age composition data as it is identified and becomes available.	6/30/04	Available age data exchanged	Hurn

WDFW	1	As warranted, update Age data links with other "count" data records 	11/30/03 and 	Data submission with hatchery 	Woodard

(i.e. hatchery returns and adult abundance).	06/30/04	returns and adult abundance 	(Groesbeck)

tables

Objective	1	Data acquisition and development

Task	14	Production factors and run reconstruction

Develop and maintain information on survival, production factors, spawner / recruit estimates, and run reconstruction.  This is a low priority data type under current base funding, but the existing spawner / recruit estimate data will be maintained.  Current effort will focus on what aspects of this kind of data are most needed.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Coordinate with ESA recovery planning and NWPPC subbasin planning	9/30/04	Available productivity data 	Roger

efforts to capture available anadromous fish and bull trout productivity

data for eventual DEF testing and inclusion in StreamNet.

ODFW	1	Participate and/or contribute to the maintenance of existing data related 	As needed	Contribute to the maintenance 	Hurn

to production factors and run reconstruction.	of existing data

WDFW	1	Scope the availability of stock based catches used in the PSC treaty 	Impossible to 	Quarterly progress report, data 	O'Connor

process which are crucial for run reconstruction.	predict at this 	submission if possible

time

Objective:	1	Task:	14	StreamNet Statement of Work, Fiscal Year 2004	Page 13 of 31

Objective	1	Data acquisition and development

Task	15	Diversion Screening

Explore the availability of data on diversion screening.  Capture data on screens as time and other priorities allow.  The DEF will need to be finalized before much can be done with this data type.  This is a low priority data set under current base level funding.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

MFWP	2	Work with MFWP Habitat Bureau to review diversion screening data 	06/01/04	Exchanged data to StreamNet, if	Pearson

collected as a result of FRIMA activities in Montana during 2003.  	 available

Exchange if there are any data and if it is an appropriate format

ODFW	1	Compile Oregon fish screening and diversion data. Data will be posted 	4/15/04	Make screening/diversion 	Brodeur

on the NRIMP site and linked to StreamNet as an 'as is' submission until 	information available.

a DEF is adopted.

ODFW	2	Capture GPS coordinates for water diversions and fish screens in the 	12/31/03	Accurate coordinates for fish 	Wegner

Willamette subbasin.	screens and diversions

WDFW	1	As funding and time permits, review existing Washington diversion 	Ongoing, 	Quarterly progress report, data 	Sikora

screening data, identify additions and corrections needed and plan for 	quarterly	submission if possible

future exchanges.  Possible data sources include Yakima Screen Shop,

SSHIAP, TAPPS, HPA databases.

Objective	1	Data acquisition and development

Task	16	Other data sets

On an opportunistic basis, develop other types of data as available or as requested by FWP participants.  This relates to data relevant to StreamNet objectives which would be developed by StreamNet cooperators.  Actual acquisition, standardization, georeferencing and distribution of these data will be dependent on available time and funding.  These data may be included in the DEF in the future, or may be obtained and distributed as independent data sets in 'as is' condition.  This is a low priority under current base funding.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

IDFG	1	On an opportunistic basis, develop other types of data.	As Requested	New data sets exchanged or 	Butterfield

posted as independent data sets.

MFWP	1	Provide updated genetic results information on Montana's species of 	06/01/04	Data exchanged, as possible	Carson

concern.  Explore providing data on Whirling Disease results for

Montana's streams and rivers; creel data if format is not appropriate for

harvest DEF; and fishing pressure data on Montana's lakes and streams.

ODFW	1	We will work with ODFW and other agency staff to facilitate either the 	Ongoing	Potentially various 	Cooney

incorporation of their data into StreamNet or independently posting their	independent data sets made

data on the StreamNet web site.	available as opportunities arise

Objective:	1	Task:	16	StreamNet Statement of Work, Fiscal Year 2004	Page 14 of 31

Region	1	Advise and assist data developers with other data sets (those being 	On request	Assistance or advice to data 	Butcher, Banach

compiled by StreamNet cooperators but not currently in the StreamNet 	developers

DEF or the queryable database).  Low priority, and within current

resources only.

Region	2	Acquire data sets from other (non-StreamNet) entities where the data 	Ongoing, 	Knowledge of available data 	Banach

would be useful in relation to data available in the StreamNet database 	opportunistic	sets, and acquired data sets

and for regional planning and management needs.  Initial efforts may be 	posted on the StreamNet web

only exploratory in nature, and will only be pursued within existing 	site in original format

resources and as data become available.

WDFW	1	On an opportunistic basis, develop other types of data, as time allows	Opportunistic, 	Other data sets developed, as 	O'Connor

as requested	limited time allows

Objective	2	Data management and delivery

Provide high quality data management services, with specific emphasis on the creation of regionally consistent data sets and the timely delivery of data to users in formats that meet their policy, planning, monitoring, and management needs.

Objective	2	Data management and delivery

Task	1	System Administration

Manage and maintain the computer systems (hardware and software) necessary for supporting the tabular and GIS data systems at the regional and cooperating agency levels, including system backup.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	Manage, maintain and enhance the computer systems (hardware and 	Ongoing	Functional hardware and  	Forrest, Pastor,

Cooperators		software) necessary for supporting the tabular and GIS data systems,		software infrastructure	Murdock, Hess-

including system administration, backup and recovery, hardware and			Herbert, Herber /

software upgrades, and security.			Bowers, Sikora /

Woodard / Hudson

Region	1	Manage, maintain and enhance the existing tabular database systems, 	Ongoing	Functional, updated tabular 	Kinney

including hardware, software, tools, database structure, QA/QC 	database system

activities, and system administration, backup and security.

Region	2	Maintain and update, as necessary, the hardware and software, 	Ongoing	Functional, updated GIS 	Butcher

including ArcView and other tools, extensions and projects, that

constitute the regional Geographic Information System.  Provide system

administration, backup and recovery, and security.

Objective:	2	Task:	1	StreamNet Statement of Work, Fiscal Year 2004	Page 15 of 31

Region	3	Maintain and upgrade the StreamNet web server and software, including	Ongoing	Web server up and operational 	Wilke

programming, tool development, system security, etc.	99.5+% of the time

Region	4	Assist with development of XML schema based options for both 	Ongoing, as 	Increased use of XML in data 	Wilke, Kinney

incoming and outgoing data.  Continue exploration of how XML can 	time allows	acquisition and delivery.

enhance data exchange and develop data use agreement to control

subsequent use of StreamNet data by other websites.

Objective	2	Data management and delivery

Task	2	Application and Interface Development

Develop computer applications and interfaces that facilitate the entry, management and dissemination of tabular and GIS data at the regional and cooperating agency levels.  This will include development of new applications and tools as well as maintenance or modification of existing applications.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Develop data handling applications to ease transfer of tribal data to 	9/30/04	Prototype data transfer 	Forrest

StreamNet	application

IDFG	1	Develop and/or maintain computerized databases, applications and 	Ongoing	Computer databases, 	Murdock

interfaces that facilitate the entry, compilation, management and 	applications, and interfaces

dissemination of tabular and GIS data.	used to compile and manage

StreamNet compatible data at

IDFG/StreamNet.

MFWP	1	Develop and/or maintain computerized databases, applications and 	Ongoing	User interfaces modified and/or	Hess- Herbert

interfaces that facilitate the entry, compilation, management and 	 created as necessary.

dissemination of tabular and GIS data.

ODFW	1	Develop and/or maintain computerized databases, applications and 	Ongoing	Functioning applications and 	Herber, Bowers

interfaces that facilitate the entry, compilation, management and 	interfaces for ODFW-

dissemination of tabular and GIS data.	NRIMP/StreamNet

Region	1	Develop and/or maintain computerized databases, applications and 	Ongoing, as 	Functional tools	Wilke

interfaces that facilitate the entry, compilation, management and 	needed

dissemination of tabular and GIS data..  Assist cooperating agencies

with tool development, as requested.  Tools may include input

interfaces, error checking, geographic locators, etc.

Region	2	Maintain and improve the LLID/NHD hydrography conversion tool.  	Ongoing	Improved NHD/LLID 	Butcher

Immediate need is to complete error trapping routines and polish the 	Conversion Application

final application.

Objective:	2	Task:	2	StreamNet Statement of Work, Fiscal Year 2004	Page 16 of 31

Region	3	Create an Online Event Mapper to allow users to create event tables 	4/01/04	Online Event Mapper	Butcher

based on 1:100K Hydrography over the Internet

WDFW	1	Develop and/or maintain computerized databases, applications and 	Ongoing	Efficient processes to compile 	Hudson, Brown,

interfaces that facilitate the entry, compilation, management and 	and convert data	Sikora

dissemination of tabular and GIS data.

Objective	2	Data management and delivery

Task	3	Data (content) Management

Manage data at the regional and cooperating agency levels to assure timely and accurate data flow from source to final distribution.  Activities include exchange of data to PSMFC, data loading, updating data, quality assurance procedures, metadata development, etc.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	Manage data at the agency level (including data loading, data updating 	Ongoing	Accurate, up to date, documented	Forrest, Pastor,

Cooperators		and quality assurance), develop and maintain FGDC compliant metadata		data, maintained in StreamNet	Brown, Hess-

for GIS data, work toward developing metadata for tabular data, and		Compatible format, exchanged	Herbert, Cooney,

exchange data to PSMFC according to deadlines specified in this work		as appropriate.	Sikora

statement.

ODFW	2	Continue development of a corporate information system.	Ongoing	Functional interfaces as part of 	Herber

a corporate system.

ODFW	3	Coordinate and work with internal ODFW staff to improve the agency 	Ongoing	Consultation and assistance to 	All staff

data collection efforts to allow more efficient compiling into internal 	ODFW staff

intermediate ODFW-NRIMP/ StreamNet databases and/or StreamNet

databases.

Region	1	Assist data contributing agencies in development of data, including 	Ongoing, as 	Assistance to data providers	Butcher, Banach,

formatting, coding, data entry, error checking, and submitting to the 	needed	Kinney

regional database.

Region	2	Examine the StreamNet database for errors and report any found to the 	Ongoing	List of database errors reported	Kinney, Banach

appropriate entity for correction.  Continue to improve error-checking 	to originating agency for

capabilities.	correction.  Users encounter

fewer errors.

Region	3	Update and append data as submitted by StreamNet participants.  	Ongoing	Maintained StreamNet 	Kinney

Isolate erroneous or duplicative data and work with source agencies to 	database with data submission

correct problems.  Maintain logs of data submissions and major 	logs up to date

database changes.  Produce downloadable versions of the StreamNet

databases to keep in synch with the updated regional databases.

Objective:	2	Task:	3	StreamNet Statement of Work, Fiscal Year 2004	Page 17 of 31

Region	4	Work with RMIS and the StreamNet partners to develop a means of 	9/30/04	Progress toward geographically	Kinney, Banach

georeferencing hatchery release data.   Since it is not currently possible 	 accurate release records

to georeference the RMIS hatchery release data to the 100K hydrography

and the data can't be updated without such georeferencing, work with

StreamNet data compilers to provide release data in StreamNet data

exchange formats to be developed.  Until that time, send data users to the

RMIS site for current release information.

Region	5	Help the StreamNet Librarian to optimally format an export of the library 	On-going, 	Exchanges between the Library 	Kinney

reference database of StreamNet documents for routine inclusion in the 	monthly	and the StreamNet tabular

StreamNet database for use by the web query system.	databases should occur monthly.

Region	6	Whenever new tabular data with a spatial component are submitted to the	Ongoing	Spatial Data available to the 	Butcher

Region (e.g., fish distribution, hatchery facilities, etc.), create regional	public

GIS layer(s) from this information where possible.  Verify correct format,

accuracy and logical consistency of spatial data sets and attributes through

coordination with state GIS contacts and then load data to the regional

database in coordination with the database manager.  Post mappable layer(s)

to the online query system, the ArcIMS interactive mapping system, and

as downloadable layer(s) for StreamNet GIS users.

Region	7	Maintain a library of StreamNet GIS layers for internal use and as down-	Ongoing	GIS data available through the 	Butcher

loadable data on the web site with complete documentation (metadata).	StreamNet web site are current

Region	8	Obtain and refine layers such as ESUs, ecoregions, or elevations, and 	Opportunistic	Improved GIS	Butcher

create cross tables for use by the query system.

Region	9	Assist the database manager with the spatial component of data and its 	As needed	Improved spatial location of 	Butcher

implementation online	features

Region	10	Maintain and update, as necessary, the 1:100,000 scale hydrography 	Ongoing	Up to date 1:100K hydrography	Butcher

files for the states and the PNW region.  Submit all changes to the

StreamNet database at the Regional office.

Region	11	Integrate the functioning of the GIS system with the StreamNet fisheries 	Ongoing	Improved Query System	Butcher

and habitat database in support of the query system.  Maintain up-to-

date cross tables used via the StreamNet web interface to select

information by geographic area.

Region	12	Maintain the Protected Areas database.  Provide access to the Protected	Ongoing	Protected Areas data remain 	Kinney, Butcher

Areas data through the online queryable database and through the interactive	publicly available.  The 	Note:  THIS IS A

map application.  Work to resolve the remaining location issues where	remaining location issues are 	         DUPLICATE

protected areas did not translate well to the 1:100,000 hydrography.	resolved.			       of 4.5.R.1

Objective:	2	Task:	3	StreamNet Statement of Work, Fiscal Year 2004	Page 18 of 31

Objective	2	Data management and delivery

Task	4	Data exchange standards

Establish and maintain data exchange standards to ensure consistent content and format of data that originate from multiple data sources.  Monitor adopted and proposed data exchange formats for data categories described under Objective 1. This task will provide coordination and technical assistance regarding interpretation of database structures and codes.  The formal process for creating new and revising old DEFs may require significant amounts of time, potentially more than a year, for complex data categories

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	Work cooperatively through the Steering Committee, following the DEF 	Ongoing	Updated and new DEFs	Project leaders

Cooperators		Process document, to revise existing and develop new DEFs to assure		submitted to the Steering

regional data consistency and allow for inclusion of new data types.		Committee

IDFG	2	IDFG/StreamNet will take the lead on developing DEFs for two new data 	12/31/03	Development of new DEFs is 	Butterfield

categories:  Juvenile Fish Abundance and Run Reconstruction.	initiated, then quarterly reports

of progress

MFWP	2	Co-develop a draft resident release DEF, in cooperation with Leslie 	12/31/03	Development of new DEF is 	Hess- Herbert

Sikora, WA StreamNet	initiated, then quarterly reports

of progress

ODFW	2	Review the Barrier DEF for juvenile fish passage and recommend an 	4/30/04	Recommendation to Steering 	Bowers

approach to the Steering Committee.	Committee on how to handle

juvenile fish barriers

ODFW	3	Initiate the process to develop a new DEF for fish screen data	3/31/04	Development of new DEF is 	Brodeur

initiated, then quarterly reports

of progress

ODFW	4	Investigate the potential for developing a Life-stage Timing DEF	6/30/04	Preliminary recommendation to 	Cooney

Steering Committee on

approach to a Life-stage Timing

DEF

Region	1	Work cooperatively through the Steering Committee, following the DEF 	Ongoing, as 	Data Exchange Format is 	Banach

Process document, to revise existing and develop new DEFs to assure 	needed	maintained and updated as new

regional data consistency and allow for inclusion of new data types.  	data types are added

The regional Biologist will serve as the primary coordinator of the DEF

process and is responsible for updating and publishing the official DEF

document.

Objective:	2	Task:	4	StreamNet Statement of Work, Fiscal Year 2004	Page 19 of 31

Region	2	Investigate the use of the "TypeID" field in StreamNet time series data 	3/31/04	Improved description of time 	Banach, Schmidt

in relation to other fields.  Propose fixes if appropriate, and adopt 	series data in the StreamNet

through the DEF modification process.	database.

Region	3	Initiate work on a new DEF for Fish Sightings data.  Review the 	2/28/04	Development of new DEF is 	Banach

approach being taken in California and in coordination with the 	initiated, then quarterly reports

cooperating projects, adapt for use in the Columbia Basin.	of progress

WDFW	2	Co-develop a draft resident release DEF, in cooperation with Janet 	12/31/03	Development of new DEF is 	Sikora

Hess-Herbert, MT StreamNet	initiated, then quarterly reports

of progress

Objective	2	Data management and delivery

Task	5	StreamNet Internet sites

Continue to maintain and enhance the StreamNet Internet sites.  Provide access to StreamNet data products through the Internet at both the regional and cooperating project levels.  The StreamNet home page (www.streamnet.org) will continue to be utilized as the project's primary data delivery vehicle.  Priority will be given to incorporating data developed through Objective 1 and providing access to reference materials secured through Objective 3.  The site will also be used to archive data sets developed by FWP participants for data that do not fit within the StreamNet DEF, including the means to index and search the archive.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	Provide ongoing review of the StreamNet website through routine use of	Ongoing	StreamNet web site is monitored, 	Roger, Butterfield,

Cooperators		the site, providing feedback to StreamNet staff at PSMFC on any		feedback is provided to PSMFC,	Hess-Herbert, Pastor,

problems, errors or needed improvements		and improvements implemented	Cooney, O’Connor

CRITFC	2	Maintain, and enhance as needed, the web pages used to provide public	Ongoing	Functional Library website	Oftedahl

access to the StreamNet Library collections and services, including

hardware and software maintenance, web page development, and

system security.

CRITFC	3	Work with PSMFC staff to upgrade formats for displaying library 	12/31/03	Improved output from literature	Oftedahl

catalog search results to facilitate development of bibliographies and to 	 searches, from the perspective

assist patrons locating needed literature	of users

ODFW	2	Manage and maintain Oregon's web-based data integration, 	Ongoing	Oregon's web-based systems 	Bowers, Brodeur,

communication, and data transfer systems and their links to StreamNet.	are maintained, updated, & 	Herber

improved, Oregon data and

reports are posted, and links to

SN are maintained

Objective:	2	Task:	5	StreamNet Statement of Work, Fiscal Year 2004	Page 20 of 31

Region	1	Guide development and enhancement of the StreamNet web query 	Ongoing	Improved web query system	Banach, Schmidt

system from the perspective of data users.  Review changes to the web

query system to ensure they are implemented appropriately and do not

create unforeseen problems.

Region	2	Maintain and enhance the functionality, look and usability of the 	Ongoing	Functional and enhanced query	Wilke

StreamNet web-based query system.	capability

Region	3	Conduct a thorough review of the web query system.  Identify and 	6/30/04	Web query system with 	Staff

address errors and omissions in data delivery.  Improve help files.	improved usability and

improved data delivery.

Region	4	Review and rearrange the links pages on the StreamNet web site.	3/31/04.	Improved links pages.	Banach

Region	5	Maintain the GIS Data, Map, and PNW Reach File Internet pages.	Ongoing	GIS Data available to users 	Butcher

over the Internet

Region	6	Maintain, update as necessary, and improve the Internet mapping 	Ongoing	Internet Mapper maintained 	Butcher

component to the StreamNet web site to allow users to access 	and available

StreamNet data through interactive map interfaces.  Improvements might

include such items as adding DRGs or aerial photos to the IMS

applications, and showing trend locations in the web query system.

Region	7	Incorporate 5th and 6th field HUC GIS coverages into the web-based 	Improved Query system	Butcher

data query system and Internet mapping applications so data can be

provided by HUC 5 and/or 6, as data become available at those scales.

Region	8	Deploy new query system components and data categories that are 	Ongoing, as 	Enhanced functionality and 	Wilke

approved by the Steering Committee	needed	new data categories available

Region	9	Maintain logs of web query history and error events.  Track and report 	Ongoing	Logs and reports of StreamNet 	Wilke

Internet site usage by month and investigate web query system errors 	website and query system

encountered.	usage; decreased error rate

Region	10	Work with the StreamNet Librarian to improve user access to data 	Ongoing	Improved function of the 	Kinney

references through the web data query system.	StreamNet website in providing

reference documentation to users

Objective:	2	Task:	5	StreamNet Statement of Work, Fiscal Year 2004	Page 21 of 31

Objective	2	Data management and delivery

Task	6	Respond to data / information requests

Receive and respond to requests for data and information, source materials, and custom products at the regional and cooperating agency levels.  Response to requests will be honored within the limits of available resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.  Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural resource management activities.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	Respond to requests for data, maps, technical assistance, source 	Ongoing	Requests satisfied, details 	Project Leaders

States	materials, or custom data products at the agency level, within the 	reported quarterly

capabilities provided by base funding.  Requests will be logged and

reported.

Region	1	Respond within one business day to requests for data, information or 	Ongoing	Requests satisfied, responses.	Staff appropriate

help.  Log and report responses to all requests received.		logged and reported quarterly	to request

Region	2	Finalize a standard user request tracking database structure so that all 	2/28/04	More consistent user request 	Banach

StreamNet partner agencies can use the same format for reporting 	reporting for the StreamNet

responses to requests for data and other information or help.	project's quarterly and annual

reports.

Objective	3	Library and reference services

Provide professional library services to the Columbia Basin's fish and wildlife decision-makers, planners, managers, and researchers by acquiring and cataloging StreamNet source documents and other related material; and by providing open and efficient access to these materials.  Provide a repository for the source documents for the data contained in the StreamNet database.

Objective	3	Library and reference services

Task	1	Collection development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document data sources, Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies, interested parties, and other libraries.  Project participants will submit reference documents for all data contained in the StreamNet database.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	Obtain reference documents for all data developed under Objective 1 	Ongoing	Documents delivered to 	Project Leaders

Cooperators	and submit them to the StreamNet Library for inclusion in the collection 	StreamNet library.

and catalog.

Objective:	3	Task:	1	StreamNet Statement of Work, Fiscal Year 2004	Page 22 of 31

CRITFC	2	Coordinate source material submissions for data compiled by StreamNet 	Ongoing	Updated, expanded collection 	Oftedahl

participants under Objective 1	of materials

CRITFC	3	Develop a collection of materials related to the Columbia Basin, 	Ongoing	Updated, expanded collection 	Oftedahl

including reports from other Fish & Wildlife Program projects, other 	of materials

agency documents as they relate to the Basin, and other published and

unpublished materials as requested by clients.

CRITFC	4	Maintain and develop a collection of journals related to fisheries and 	Ongoing	Updated, expanded collection 	Oftedahl

aquatic sciences as well as other related scientific topics.	of material

ODFW	2	Initiate organization of ODFW Library documents and update the library	Ongoing	ODFW Library contents 	ODFW Library Tech

bibliography with new titles as they are identified.	shelved and the bibliography

updated.

Objective	3	Library and reference services

Task	2	Provide access to collection

Provide user access to the materials described in Task 3.1 by providing facilities for storage of paper and electronic copies of documents, an online catalog of all documents in the collection, and staff to answer location questions and respond to requests.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Provide and maintain an appropriate facility for the storage and public 	Ongoing	Library open to public 8 to 5 on	Oftedahl

use of the StreamNet Library collections.	 workdays

CRITFC	2	Catalog and organize the materials for ease of use by clients and staff	Ongoing	Current catalog of materials	Oftedahl

CRITFC	3	Provide access to the catalog of materials via the Internet and update 	Monthly	Updated website and catalog	Oftedahl

the online catalog on at least a monthly basis.

CRITFC	4	Develop and execute a plan to place electronic documents in the catalog 	9/30/04	Access to electronic 	Hannon

and on the library website.

CRITFC	5	Develop and keep a schedule of open times and reference desk staff 	Ongoing	Staff available to patrons at all 	Hannon

times during the work day

Objective:	3	Task:	2	StreamNet Statement of Work, Fiscal Year 2004	Page 23 of 31

Objective	3	Library and reference services

Task	3	Library services

Manage the StreamNet Library and provide library services to the StreamNet user community, the Council's Fish and Wildlife Program, and the general public.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Provide information and reference services to library clients	Ongoing	Information provided as 	Hannon

Requested

CRITFC	2	Publish information about services and hours to library clients via print 	Ongoing	Updated website and brochure	Oftedahl

and Internet

CRITFC	3	Provide interlibrary borrowing services for library patrons to access 	Ongoing	Interlibrary loan functions 	Hannon

materials not yet owned by the StreamNet Library.	available to patrons

CRITFC	4	Provide access to hardcopy and electronic files of draft and final 	Ongoing	Collection is current	Oftedahl, Hannon

documents related to subbasin planning and the NWPCC amendment

process.

CRITFC	5	Identify changes and new features that will improve delivery of library 	Ongoing	Recommendations to improve 	Oftedahl, Hannon,

services	delivery of services	Liberty

Objective	3	Library and reference services

Task	4	Inter-library coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other collections that will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Provide interlibrary lending services for other libraries to access the 	Ongoing	Material circulation	Hannon

StreamNet Library's unique collection.

CRITFC	2	Maintain memberships in appropriate library and subject-related 	Ongoing	Presentations, reports, 	Oftedahl

associations. Ex. IAMSLIC, NRIC, OFWIM, etc.	professional development

CRITFC	3	Provide consultations for groups and other agencies on library 	On request	Services as requested, detailed 	Oftedahl, Hannon

organization and services	in reports

CRITFC	4	Coordinate with other StreamNet libraries, library clients and other 	Ongoing	Improved services	Oftedahl

libraries to improve service to clients and limit duplication of effort

CRITFC	5	Work with subbasin planning groups and TRTs to identify 	Ongoing	Services to Subbasin Planning 	Oftedahl, Hannon

modifications to Library services and new uses of the Library to make 	efforts

information related to these processes easier to retrieve.

Objective:	3	Task:	4	StreamNet Statement of Work, Fiscal Year 2004	Page 24 of 31

Objective	4	Services to the Fish and Wildlife Program

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife Program projects.

Objective	4	Services to the Fish and Wildlife Program

Task	1	Data and Data Services to Support the Fish and Wildlife Program

Provide data management assistance to the Fish and Wildlife Program, as requested.  Services may include custom development of data, provision of data from the StreamNet database to support FWP activities (such as planning, monitoring and evaluation, etc.), and general advice and technical assistance with database management, data delivery, and GIS.  Work under this task will have to be based on time available, particularly for larger requests.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	At the agency level, support Fish and Wildlife Program activities, such 	Ongoing	Technical assistance and data	Project Leaders

States		as R, M & E, subbasin assessment, etc., by providing data and maps of		services provided on request

existing StreamNet data and technical information management advice or

assistance as requested, within available time and budget under base

level funding.

CRITFC	1	Participate in various NWPCC planning and management work groups 	Ongoing	Participation in groups	Roger

to improve and coordinate regional information management programs,

such as serving as leader of the technical work group for Oregon's

Subbasin Planning effort.

Region	1	At the regional level, support Fish and Wildlife Program activities, such 	As requested	Data provided to Subbasin 	Banach

as R, M & E, subbasin assessment, etc., by providing data and maps of 	Planners

existing StreamNet data and technical information management advice or

assistance as requested, within available time and budget under base

level funding.

Region	2	Participate in and assist regional Monitoring and Evaluation efforts to 	On request	Participation in R,M&E 	Schmidt

provide relevant StreamNet data, and to initiate work to obtain new data 	activities to scope data needs,

types necessary for R,M&E.  Since no specific requests or funding have	provide existing data, and

been received for this, work may be limited to scoping and advising.  	advise on data management

Development of new data types to serve R,M&E will be initiated only as 	and developing new data types

current time and funding permit, or as current work priorities are

reprioritized by regional processes.

Objective:	4	Task:	1	StreamNet Statement of Work, Fiscal Year 2004	Page 25 of 31

Objective	4	Services to the Fish and Wildlife Program

Task	2	Participate in Fish and Wildlife Program Development Activities

Participate in planning, development and/or coordination meetings with regional entities to provide assistance in the area of data management, as requested, to support development of Fish and Wildlife Program projects and programs.  Provide input on ways StreamNet can effectively contribute to the programs and general advice about data management.  Participate in advisory groups, task forces, and other groups whose purpose is to enhance the effectiveness of the Fish and Wildlife Program relative to its data development activities.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Participate in groups to develop strategies for ESA recovery planning 	Ongoing	Strategies to store data & 	Roger

efforts to ensure data and technical literature are captured and made 	literature in a permanent form

regionally accessible. This will be done "as possible"' under base level 	that is regionally accessible

funding.	over time.

All	1	At the agency level, work with regional entities to contribute data 	Opportunistic	Participation in development of 	Project Leaders

States	management expertise toward development of activities within the scope	FWP programs, as requested

of the Fish and Wildlife Program.  Serve as a data management resource

to the FWP.

Region	1	At regional level, work with regional entities to contribute data management	Opportunistic	Participation in development of 	Schmidt

expertise toward development of activities within the scope of the Fish and	FWP programs, as requested

Wildlife Program.  Serve as a data management resource to the FWP.

Region	2	Continue participation on the Program Team for the Council's project to 	Ongoing	Provide input to development 	Schmidt

develop a Columbia Basin Cooperative Information System to convey 	of a CBCIS

recommendations based on experience in the development of a regional

approach to data dissemination.

Region	3	Continue participation in the Federal/State/Tribal Partnership for 	Ongoing	Provide input to developing a 	Schmidt

watershed data coordination (the group being led by Steve Lanigan).  	regional approach to obtaining

Participate in other R, M & E groups, including the Action Agencies and	and managing watershed data

CBFWA, to provide support and data management expertise.

Region	4	Participate with CBFWA, the Council and others to assist development 	Ongoing	Contribution toward creating a 	Schmidt

of a regional scope data management oversight group or function.	regional scope data

management group

Objective:	4	Task:	2	StreamNet Statement of Work, Fiscal Year 2004	Page 26 of 31

Objective	4	Services to the Fish and Wildlife Program

Task	3	Support to Subbasin Planning

At the regional and cooperating agency levels, work with subbasin planners to provide needed information from the StreamNet database and to capture data developed as part of the subbasin planning process.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

CRITFC	1	Participate in subbasin planning efforts, such as serving as leader of the 	Ongoing	Organization and capture of 	Roger

technical work group for Oregon's Subbasin Planning effort.	subbasin technical planning

information

IDFG	1	At the state or local level, and within existing resources, work with 	Ongoing	Quarterly reports on support 	Butterfield

subbasin planners to provide needed information from the StreamNet 	provided.

database and to capture data developed as part of the subbasin

planning process.  In particular, IDFG/StreamNet is providing lead

technical, logistical, and administrative support to subbasin

assessments for the Salmon, Weiser/Boise/Payette, Middle Snake, and

Upper Snake subbasins.

MFWP	1	At the state or local level, and within existing resources, work with 	As requested	Assistance to subbasin 	Hess- Herbert

subbasin planners to provide needed information from the StreamNet 	planners, as requested

database and to capture data developed as part of the subbasin

planning process.

ODFW	1	At the state or local level, and within existing resources, work with 	As needed	Requested data provided and 	Hurn

subbasin planners to provide needed information from the StreamNet 	newly developed data

database and to capture data developed as part of the subbasin 	captured, as resources allow.

planning process.  Work with the Oregon technical work group.

Region	1	At the regional level, and within existing resources, work with subbasin 	Ongoing, as 	Begin capturing data being 	Schmidt

planning groups to provide needed information from the StreamNet 	possible	developed under Subbasin

database and to capture data developed as part of the subbasin 	Planning

planning process and make it publicly available.

WDFW	1	At the state or local level, and within existing resources, work with 	As requested 	Data and assistance provided 	O'Connor, Woodard,

subbasin planners to provide needed information from the StreamNet 	and possible	to the Subbasin Planning effort	Sikora

database and to capture data developed as part of the subbasin

planning process.

Objective:	4	Task:	3	StreamNet Statement of Work, Fiscal Year 2004	Page 27 of 31

Objective	4	Services to the Fish and Wildlife Program

Task	4	Archive and deliver independent data sets, as requested

Work with participants to aid in the capture and distribution of data generated through Fish and Wildlife Program activities and to help determine the most appropriate means of storing and disseminating them.  Where data do not fit in existing StreamNet data sets, post data in the archive as independent data sets in their native formats.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	Work with FWP supported projects in the states and tribes to assist them	Opportunistic	FWP project data made 	Project Leaders

Cooperators	with making their data widely available, and if requested, assist them with	available through StreamNet

submission of their data sets to StreamNet for archiving and dissemination

as part of the formal DEF or as Independent Data Sets.

Region	1	Provide a location within the StreamNet web site to disseminate 	12/31/03	Searchable data sets page 	Schmidt, Wilke

Independent Data Sets obtained from FWP funded projects and others 	based on Cold Fusion.

engaged in fish and wildlife research and management in the Columbia

Basin.  Work with BPA, the Council, and individual projects to inform

them of the availability of this site to post data sets.  Improve the current

Independent Data Sets page to a dynamic, searchable system.

Region	2	Coordinate with BPA and BPA contractors and the StreamNet 	12/31/03	Mechanisms for easy 	Wilke, Banach

cooperators to capture data sets, reports, and other electronic materials 	submission of data sets to

for inclusion in the StreamNet Independent Data Sets page.  Finalize 	StreamNet, and easy

metadata needs.  Create a tool to help data submitters to easily provide 	incorporation of these data sets

needed information	on the StreamNet web site.

Objective	4	Services to the Fish and Wildlife Program

Task	5	Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas dataset, b) archive the official version as a historic record, c) in consultation with the Council, respond to requests for information concerning Protected Areas, and d) modernize georeferencing and make these data available through online mapping.  If the Council so directs, work with subbasin planners to record any desired changes to the protected status of individual streams.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

Region	1	Maintain the Protected Areas database, and as time allows, work to resolve 	Ongoing	Protected Areas data remain	Kinney, Butcher

the remaining unresolved location issues that resulted from conversion of 		available publicly

the data from the 1:250,000 scale to the 1:100,000 regional hydrography.

Objective:	4	Task:	5	StreamNet Statement of Work, Fiscal Year 2004	Page 28 of 31

Objective	5	Project management and coordination

Provide effective leadership that ensures the production of high quality information products targeted at critical applications and the development of these products in a timely, cost-effective manner.

Objective	5	Project management and coordination

Task	1	Manage Project Activities

Administer all aspects of the StreamNet project at the regional and cooperating agency levels, including oversight of budget, personnel (including training and staff development), work statement preparation and implementation, coordination among participating agencies, active participation in steering committee work, and project reporting.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	Project oversight and guidance.  Participate cooperatively in the 	Ongoing	Project guidance provided	Project Leaders

StreamNet Steering Committee to guide the direction of the project,

coordinate within respective agencies, and resolve policy and technical

issues for the project

All, except	2	Supervision.  Supervise project staff at the cooperator level to provide 	Ongoing	Staff supervision provided	Project Leaders

FWS	guidance and staff development.

All	3	Budget.  Manage expenditures to accomplish the jobs in the Statement 	Ongoing	Project accomplished within 	Project Leaders

of Work within the approved budget.	budget

All	4	Develop the annual project proposal and budget within submission 	7/15/04	Draft project proposal and 	Project Leaders

deadlines.	budget submitted to PSMFC

All	5	Report accomplishment of the work outlined in the annual Statement of 	20 days after 	Draft quarterly report submitted	Project Leaders

Cooperators	Work through quarterly progress reports submitted to PSMFC within 20 	end of quarter	to PSMFC

days of the end of each quarter and to BPA within 30 days of the end of

the quarter.

All	6	Submit the draft FY-03 annual progress report for the sub project to 	11/20/03	Draft annual report submitted 	Project Leaders

Cooperators	PSMFC within 50 days of the end of the fiscal year.	to PSMFC

Region	5	Report accomplishment of the work outlined in the annual Statement of 	10/31/03, 	Quarterly report submitted on 	Schmidt

Work through quarterly progress reports submitted to BPA within 30 	1/31/04, 4/30/04, 	time

days of the end of each quarter.	7/31/04

Region	6	Submit the Annual Progress Report to BPA within 60 days of the end 	11/30/03	Annual Report submitted to  	Schmidt

of the fiscal year. 	BPA on time

Objective:	5	Task:	1	StreamNet Statement of Work, Fiscal Year 2004	Page 29 of 31

Region	7	Move the Regional StreamNet office and all computing equipment from 	11/30/03	Services maintained to the 	Schmidt, staff

Gladstone, Oregon to a new PSMFC office.  Attempt to minimize down 	extent possible and down time

time for the StreamNet website and other data services	of web query system minimized.

Objective	5	Project management and coordination

Task	2	Coordinate with Related Activities Beyond the FWP

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities and agencies beyond the Council's Fish and Wildlife Program to identify means for collaborative data collection, storage, and dissemination.  Collaborative data activities will include tribal fishery programs within the Columbia Basin, federal land managers’ fishery programs, state fish and wildlife agencies, and, with respect to water use and stream development, state water resource management and environmental quality agencies. Collaboration with coast-wide and private data collection/compilation efforts will be pursued when this supports overall project goals.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All 	1	On an opportunistic basis, coordinate with other state, federal, or tribal 	Opportunistic 	Coordination, activities 	Project Leaders

Cooperators	agencies and various local inter agency planning and management 		reported in quarterly and

work groups beyond the FWP to enhance the collection and management	annual progress reports.

of data related to management of fish and wildlife resources.

Region	1	On an opportunistic basis, coordinate with other state, federal, or tribal 	Opportunistic 	Participation and advice to 	Schmidt

agencies and various regional inter agency planning and management		organizations not involved with

work groups beyond the FWP to enhance the collection and management	the Council's FWP

of data related to management of fish and wildlife resources.

Objective	5	Project management and coordination

Task	3	Professional and Public Involvement

As needed, produce public information materials and participate in various meetings and forums (public or professional) to explain the project's capabilities and purpose and to generate support and additional data sources.  Activities may include brochures, issue papers, demonstrations, posters and talks to public, policy or professional groups and organizations.

Project	Job	Planned work elements                                                                           	Date Due   	Deliverable                                	Lead

All	1	As requested, prepare and deliver presentations to public, scientific and 	Ongoing	StreamNet related informational	Project Leaders

Cooperators	professional meetings to demonstrate project capabilities, services and 	pieces and presentations

accomplishments and to solicit additional data and involvement or 	delivered, activities reported in

coordination with the project.	quarterly reports

Region	1	Publish at least two editions of the StreamNet Newsletter during the 	12/31/03 and 	Two StreamNet Newsletters.  	Banach

fiscal year, providing readers with information about StreamNet 	7/1/04	Informed StreamNet user

activities, available data, data updates, new data services, etc.	community.

Objective:	5	Task:	3	StreamNet Statement of Work, Fiscal Year 2004	Page 30 of 31

Region	2	Prepare and deliver presentations to scientific and professional meetings	Opportunistic	Presentations given	Schmidt

to demonstrate project capabilities and accomplishments, and to solicit

additional data and coordination with the project.

Region	3	Develop / distribute materials to support the project.  Improve public	As needed	Explanatory materials produced	Schmidt

materials (e.g., the StreamNet brochure, data inventories, etc.).   Maintain

and update explanatory materials such as the Query System User Guide

and documents explaining data categories and structures, as necessary.

Objective:	5	Task:	3	StreamNet Statement of Work, Fiscal Year 2004	Page 31 of 31