StreamNet Quarterly Progress Report

(October - December 1998)

Submitted to:

Bonneville Power Administration

Submitted by:

Pacific States Marine Fisheries Commission

| Contents |  |
| --- | --- |
| I. | Columbia River Inter-Tribal Fish Commission |
| II. | Idaho Department of Fish and Game |
| III. | Montana Department of Fish, Wildlife & Parks |
| IV. | Oregon Department of Fish and Wildlife |
| V. | Pacific States Marine Fisheries Commission |
| VI. | Shoshone-Bannock Tribes |
| VII. | U.S. Fish and Wildlife Service |
| VIII. | Washington Department of Fish and Wildlife |

I.  Columbia River Inter-Tribal Fish Commission

PERIOD HIGHLIGHTS

Cataloging

Limited numbers of documents were cataloged this quarter due to the loss of Krista Schauer, Library Technician in August and Gretta Siegel, Managing Librarian in mid-October.  We were able to catalog 182 pieces, including StreamNet documents.

Services

Continued to provide reference, online search, and interlibrary loan services.

Reference requests

Approximately 40; Requesters included:

CRITFC

NMFS

Several independent writers

Members of the public

USFWS

Bureau of Indian Affairs

H. Radtke (consultant)

CRiSP

Pacific Biological Station / Department of Fisheries and Oceans (Canada)

Michael Black, Consulting (CA)

PSU graduate students

Marylhurst students

BioAnalysts (consulting group from Boise)

Stratus Consulting (CO)

PSMFC

Interlibrary loan requests

150 items borrowed, 10 items lent (Several to federal agencies, including National Agriculture Library and Environmental Protection Agency)

Circulation

Approximately 100 books and technical reports.

Photocopier usage

2573 copies made by CRITFC, NMFS, NPPC, and PSU students.

Meetings

Library staff only attended pertinent CRITFC meetings this quarter due to staff shortages.

Administrative and Miscellaneous

Wrote quarterly report for StreamNet project.

Signed on as a Lender with OCLC Interlibrary Loan, taking effect January 1, 1999.

Provided input for Library Technician and Librarian job descriptions.

Successfully completed hiring process for Library Technician.  David Liberty, Umatilla Tribe, was hired for the position and began work in mid-November 1998.  Began limited training for managing the periodical collection as well as familiarization with the books and technical reports collection.

II.  Idaho Department of Fish and Game

PERIOD HIGHLIGHTS

Ongoing development of interface for entering stream and lake survey data. System will be used to compile Department data for StreamNet.

Entered and edited juvenile and adult anadromous/resident data.

Coordinated information systems strategies with Fisheries Bureau.

Completed first review of new Idaho portion of region 1:100,000 scale hydrography and submitted changes to regional GIS Manager.

Continued development of AML program to programmatically route unrouted, unnamed streams in hydrography.

Implemented Reference and Collecting Permit interface in Fisheries Bureau.

Trained Fisheries Bureau staff to enter data into Reference and Collecting Permit interface.

Fisheries staff entered data into Reference and Collecting Permit interface.

Completed matching lake polygons to IDFG catalog numbers.

Continued data entry and error checking historical fish stocking data.

Hosted StreamNet Steering Committee Meeting.

Completed initial database development of Instream Flow database on SR3 project.

PLANS FOR NEXT QUARTER

Continue development of stream and lake survey interface.

Complete second review of new hydrography.

Submit all changes to hydrography to regional GIS Manager.

Rebuild hydrographic network connections in regional hydrography layer

Continue entry of stream survey forms into SSS.

Attend StreamNet Steering Committee Meeting

Continue development of hatcheries, dams, and barriers databases.

Complete data entry in historical fish stocking database.

Continue error-checking historical fish stocking data.

Process 1998 anadromous fish update data.

Begin data entry into SR3 Instream Flow database.

Start 1998 Spawning Ground Report.

DATA REQUESTS

| END_DATE | USER_ORG | USER_REP | SUPPLIER | DATA_TYPE |
| --- | --- | --- | --- | --- |
| 10/6/98 | NRCS | Dave Hoover | Butterfield | fish dist data |
| 10/6/98 | Alden Research | Freq Winchell | Butterfield | bull tr. And redband dis |
| 10/6/98 | BioAnalysts, Inc. | Mark Miller | Butterfield | bull tr and redband dist |
| 10/6/98 |  | Vicki Hill | Butterfield | IRIS recreation data |
| 11/8/98 | IDFG | Steve Yundt | Butterfield | WSC dist map |
| 11/16/98 | DEQ | Tom Herron | Klaus | upper Salmon hydro, fish |
| 11/17/98 | AG office | via Will Reid | Hartpence | BT, WSC, RB maps |
| 11/16/98 | IDFG | Mike Larkin | Hartpence | Brook Trout dist maps |
| 12/16/98 | Strata Consulting | Amy Beaulieu | Butterfield | Resident fish dist data |
| 11/4/98 | IDFG | Will Reid | Hartpence | bull trout distribution |
| 11/10/98 | IDFG | Mike Larkin | Hartpence | maps of barriers and div |
| 11/16/98 | IDFG-CDC | Stephanie Mitche | Hartpence | presence of WSC, STHD by |
| 11/30/98 | IDFG - Nampa Res. | Paul Bunn | Hartpence | 6th field HU coverage |
| 12/21/98 | Idaho Rivers United | Scott Bosse | Hartpence | distrib of BTR and Cutth |
| 12/23/98 |  | Bob Griswold | Hartpence | graphics of streams |
| 12/22/98 |  | Carol | Hartpence | presence of BTR and WSC |

III.  Montana Department of Fish, Wildlife & Parks

Period Highlights

# Data Development

Completed update of tabular and spatial Fish Electrophoretic Sampling Data; will provide map products and reports to state and federal fisheries biologists and managers this spring. Began discussions with staff of the Wild Trout and Salmon Genetics Lab at the University of Montana concerning reporting the data to us.  Will create a reporting/data entry prototype in Access for their use.

Received all additional information to review FWP Stream Fisheries Ratings; began design of ArcView project to review ratings and rewrote the assessment guidelines outlining the procedures used to rate each stream for their recreational value and their species and habitat value.

Sent out maps, tabular lists, and instructions to state and federal fisheries biologists for the annual updating and editing of MRIS Bull trout data; made follow-up phone calls and received all edited products back except R-1.

Collected information from state, federal, and private hatcheries for the StreamNet hatchery database.

Reviewed several other states standard Stream Survey forms and developed a prototype for Montana.  Standard stream survey form would allow for many fields in MRIS to be filled in.

Continued to coordinate and make progress toward the conversion from RRN to LLID; received some data from the USFS and continue to try to include them in the process; certain forests have proceeded in assigning LLIDs only on the forest, not the entire hydrologic unit and others did not name the streams that they assigned LLIDs to.  Part of process has including quality checking the 1:100 K hydrography.

Worked on data exchange format for resident fish; process has including redesigning structure for MRIS as we move these data from short_rrn to LLID.

Received outplanting data from Bob McFarland, FWP ISU Coordinator in Bozeman.  Will provide to StreamNet when data exchange format has been finalized.

Prepared maps of westslope distribution data.

Data Management and Delivery

The Fisheries Division has initiated a Native Species Management Plan.  Had initial meetings at the Fisheries Division meeting in December; Janet has volunteered to chair the Identification of Native Species Management Areas; fish distribution data from MRIS and GIS will be used extensively in the initial determination of these areas.

Began work on creating a new Montana Rivers Information System database with a spatial component for entering and retrieving data.  Met with NRIS staff Duane Anderson and began the first steps of the process which involved a new MRIS structure in Access, “streamizing” the data prior to LLID, checking the data for referential integrity and cleaning up according and designing a Web-Based reporting program through NRIS.

Created strategy for providing Internet access to the Stream Fisheries Rating Program results and its supporting fisheries data on the Internet.

Modified FWP Restoration edit/entry program in Access and began entering records into the database.

Responded to 95 requests for GIS data products (request log on file).

# Library/Reference Services

Continued to have documents from the Fisheries Division Library inputted into a library cataloging system.  2500 records have been entered to date.  Work will continue next quarter.

# Project Management and Coordination

Created and gave a Power Point presentations for the Fisheries Division meeting in Great Falls; included an update on StreamNet activities and all other information services we are providing.

Attended Steering Committee Meeting in October in Boise.

Hired Kim Lindstrom temporarily to help with hydrography conversion and GIS requests.

MRIS Report

Continued scoping MRIS to web task.  Evaluated MRIS 100k river reach number to StreamNet 100k reach number matches in Western Montana and found significant discrepancies.  Identified problem reaches and prepared files for FWP (Jeff Hutten) to work with to correct problems.  Met with Janet Decker-Hess and converted Dbase version of MRIS into Microsoft Access.

Other MRIS related requests served by NRIS during the period:

| Date Received | Date Sent | NARRATIVE | Company/Organization | SectorName |
| --- | --- | --- | --- | --- |
| 10/3/98 | 10/5/98 | MRIS reports on Wildcat Creek, Cottonwood Creek, and Sweetgrass Creek, all of which are tributaries to Yellowstone River. Wants to look at stream evaluation and see what MRIS reports look like. Called again on 10-13-98 and asked questions about report. |  | Private Non Profit |
| 10/14/98 | 10/14/98 | Latest climate info for Trout Creek, MT. | Department of Environmental Quality | State |
| 10/1/98 | 10/5/98 | MRIS reports for 10030101 on Prickly Pear Creek. Following reaches: 040000, 0470000, 0510000, 0520000, 0540000, 0560000, 0560100, 0560200, 0560213, 0560224, 0560300. | State of Montana | County/Local |
| 10/8/98 | 10/13/98 | Ownership, topography, streams, roads for the Absaroka-Beartooth mt as a whole and 7 of its basins clipped with the same info. | Montana Fish, Wildlife, and Parks | State |
| 10/14/98 | 10/16/98 | Water quality and uses of Trumbull Creek in the Miller Creek area (probably Flathead drainage.) | Whitefish High School | Academic |
| 10/27/98 | 10/27/98 | MRIS stream covers for MT and the dewatered database file. To be used to aid and assist in the federal adjudication of water rights for the forest service. |  | Unknown |
| 10/29/98 | 10/30/98 | Needed correction to Peoples Creek map and addition of creek names. | Fort Belknap Reservation | Federal |
| 11/23/98 | 11/23/98 | Requested help on how to locate information source on 303d streams in Montana on the Internet. | WCEI | Private Non Profit |
| 11/16/98 | 11/18/98 | Resource materials for Mineral County Watershed including a map of the county showing creeks, and historic averages of water flows. | Mineral County Watershed Council | County/Local |
| 11/2/98 | 11/9/98 | Information on 1 mile of the Clearwater River near Seeley Lake: discharge or stream flow data, upstream regulations (dams, water rights), water quality info, aquatic life, recreation uses and management considerations. | Five Valleys Land Trust | Private Non Profit |
| 11/9/98 | 11/9/98 | EPA reach number for Carpenter Creek in HUC 10030105 (T14NR8E). | Montana Bureau of Mines and Geology | State |
| 11/24/98 | 11/24/98 | Fisheries report for reach #2120000 on Spring Creek for HUC 10030101. | State of Montana | County/Local |
| 11/30/98 | 11/30/98 | In house request for 12 copies each of the following: Conservation District Map, SWSI 9/98 map, Well Distribution map, MRIS report. (For DEQ meeting with heads of the departments.) | Montana State Library | Private Non Profit |
| 11/30/98 | 12/1/98 | Any information on N. Meadow Creek. To be used in land use planning in a collaborative effort between Mad Valley Ranch Lands Association Group and him (a hired person). | MONTANA NATURE CONSERVANCY | Private Non Profit |
| 12/1/98 | 12/4/98 | Info on the Hell Creek Formation; what areas does it cover? |  | Unknown |
| 12/12/98 | 12/14/98 | Copy of following: Pfankuch, D.J. 1975. Stream reach inventory and channel stability evaluation. US Department of Agriculture, Forest Service, Region 1, Missoula, MT. | Universidade Estadual de Campinas | Academic |
| 12/6/98 | 12/8/98 | Info on Upper Rock Creek, between Sluice Gulch and Antelope Creek. Specifically, discharge info, water withdrawals, water rights, damps, biota, conservation and management of the wetland region. | Five Valleys Land Trust | Private Non Profit |
| 12/6/98 | 12/7/98 | Info on Liverpool creek just north of Lincoln. Specifically, discharge, water manipulation, biota, management of area. | Five Valleys Land Trust | Private Non Profit |
| 12/30/98 | 1/5/98 | MRIS report requests: Lump Gulch, Jackson Creek, Warm Springs Creek. | State of Montana | County/Local |
| 12/12/98 | 12/14/98 | Requested hard copy of following: Pfankuch, D. J. 1975. Stream reach inventory and channel stability evaluation. US Department of Agriculture Forest Service, Region 1, Missoula, MT. | Universidade Estadual de Campinas | Academic |
| 12/16/98 | 12/17/98 | Would like stream flow data (from a previous request) sent to him on floppy in .xls format (Excel). | Montana State University | Academic |
| 12/1/98 | 12/11/98 | Map with prickly pear info including watershed, county, streams, hwy, towns, and ownership, mines. | Lewis and Clark Conservation District | County/Local |

IV.  Oregon Department of Fish and Wildlife

Period Highlights

Completely updated the anadromous species distribution maps for the Rogue basin. This included providing verifiable data documentation where it was available and accessible. (Bowers, Brodeur, Cooney, Forsberg, Sounhein; Task 1.1a).

Converted 1998 Coastal Salmonid Inventory Project data into StreamNet compatible format and incorporated into Rogue basin distribution update in order to rectify differences. (Bowers, Task 1.1a).

Continued efforts to develop Oregon's Barrier Database.  To this point, 1,014 Oregon barriers have been reviewed, verified, and referenced. Some barriers discovered during the 1996 Salmon Inventory Project: Random Summer Reconnaissance Surveys were also incorporated into our Barriers Database.  These data will be converted into the new Barrier Exchange format when the format is finalized. (Brodeur, Sounhein; Task 1.1a and 1.2a).

Began reviewing and updating the Hatchery Facilities and Hatchery Production data tables. (Forsberg; Tasks 1.1e,1.2d, and 1.4b).

Submitted modifications to the StreamNet Juvenile Abundance and Mitigation exchange formats, and a provided comments on a number of other exchange formats. (Brodeur, Cooney, Forsberg, Sounhein; Task 2.3).

Updated & rectified discrepancies in the stream route coding system in the Oregon portion of the PNW 100K Hydrography. (Bowers, Forsberg; Task 2.6).

A total of 7 data, 69 document, 4 map/GIS related, and 5 other requests were answered during this quarter.  (All staff; Task 2.7).

Created a project poster presentation to be displayed at the October 1998 ODFW Commission meeting. This poster will be periodically updated and used for future meeting. (Forsberg; Task 5.3).

Hired Jon Bowers to fill our GIS Analysts position. (Cooney; Task 5.1).

One or more staff members participated in 12 essential project coordination meetings. Bowers, Brodeur, Cooney, Forsberg, Hill, Sounhein; Task 5.1).

Compiled and submitted 1998 Annual/Quarterly Report information for Oregon. (Cooney; Task 5.1).

Plans for Next Quarter

Complete hiring process for ODFW StreamNet Database Manager. (Cooney).

Continue updating the anadromous species distribution throughout Oregon using the 1:100K Hydrography and provide data documentation for distribution in the Willamette basin. (Bowers, Brodeur, Cooney, Forsberg, Sounhein, Data Manager).

Enhance our Barriers Database with new information and link this database with our anadromous species distribution information. (Bowers, Brodeur, Sounhein).

Modify and improve electronic Library request data entry system and continue to catalog pending and completed Library requests. (Data Manager, Cooney, Bourne).

Provide updated adult abundance estimates and indices for anadromous species with available 1997 and 1998 data. (Sounhein).

Continue to answer information requests as received. (All).

Data Request/Response Log

| DATE | REQUESTER | ORGANIZATION | REQUEST | Who Responded |
| --- | --- | --- | --- | --- |
| 10/01/98 | Georgia | BioAnalysts Inc, Boise | 2 docs | Bourne |
| 10/01/98 | Laura Conroy | NW Economics Assoc. | doc | Bourne |
| 10/01/98 | Lenora Oftedall | CRITFC SN Library | doc | Bourne |
| 10/01/98 | Matthew Luxon | Institute Env. Toxicology & Chemistry, Bellingham, WA | 6 docs | Bourne |
| 10/01/98 | Steve Cramer | SP Cramer Assoc. | 2 docs | Bourne |
| 10/02/98 | John Hawksworth | Wash Co Soil & Conservation | 2 docs | Bourne |
| 10/06/98 | Greg Lomnicky | Pacific Habitat Service | 2 docs | Bourne |
| 10/06/98 | Nikki Moore | BLM Medford | doc | Bourne |
| 10/12/98 | Briana Sounhein | ODFW@Corvallis | doc | Bourne |
| 10/12/98 | Darren Cobeck | OR Wheat Growers League, Pendleton | doc | Bourne |
| 10/12/98 | Paul Reimers | ODFW | Barriers in the Coos-Coquille District | Brodeur |
| 10/13/98 | Dick Ewing | Bio Tech | doc | Bourne |
| 10/13/98 | Emily Smith | PSU student | 5 docs | Bourne |
| 10/14/98 | E. J. Williams | North Wales, U.K. | 6 docs | Bourne |
| 10/14/98 | Kelly Hazen | BLM- Burns, GIS | Export file of Wildlife Management Units | Forsberg |
| 10/15/98 | Steve Kuchas | Portland Water Bureau | Salmonid distribution map info. | Forsberg |
| 10/15/98 | Troy Christenson | Eastern WA Univ. Library | 17 docs | Bourne |
| 10/16/98 | Bryan Flaig/Jennifer Vick | Stillwater Sciences, Berkeley, CA | 8 docs | Bourne/NWPPC |
| 10/16/98 | Gretchen Oosterhout | Division Matrix, Canby | Doc | Bourne |
| 10/20/98 | Joseph Taylor | Dept. of History, Iowa St Univ. | 5 doc, 1 picture | Bourne |
| 10/21/98 | Michael Wing | Forest Engineering Dept., OSU | CSRI CORE maps | Forsberg |
| 10/22/98 | Burke Strobel | USFS Estacada | 2 docs | Bourne |
| 10/22/98 | Lloyd Golden | public | Doc | Bourne |
| 10/23/98 | Asa Kestrup | ? Agency, Montreal, Canada | 5 docs | Bourne |
| 10/26/98 | Barb Taylor/Dave Heintzman | PGE Hydro Project | 2 docs | Bourne |
| 10/26/98 | Neal Young | MHCC, Biology Dept | Doc | Bourne |
| 10/27/98 | Michael Wing | OSU Forest Engineering | Converted CSRI CORE tables to coverages, exported, and zipped them to ftp. He wanted more than maps. | Forsberg |
| 10/28/98 | Robert Marquette | private | 9 docs | Bourne |
| 10/30/98 | Becky Crockett | Montgomery & Watson Cons. | 5 docs | Bourne |
| 10/30/98 | Todd Moses | Watershed Application | Doc | Bourne |
| 10/30/98 | Travis Collier | MHCC student | 2 docs | Bourne |
| 11/02/98 | Briana Sounhein | ODFW@Corvallis | 2 docs | Bourne |
| 11/03/98 | Ted Williams | SP Cramer Assoc. | Doc | Bourne |
| 11/03/98 | Ted Williams | SP Cramer Assoc. | Doc | Bourne |
| 11/05/98 | Debra Sparber | OR State Library | Doc | Bourne |
| 11/05/98 | Gordon Haas | Ministry of Fisheries, Canada | 6 docs | Bourne |
| 11/06/98 | Keith Braun | ODFW - Tillamook | Review salmonid age/life stage table | Cooney |
| 11/06/98 | Ted Williams | SP Cramer & Assoc. | Doc | Bourne |
| 11/07/98 | Joseph Taylor | Dept History, Iowa St Univ. | Picture | Bourne |
| 11/10/98 | Judi Chein | Willamette Univ. Library | Doc | Bourne |
| 11/10/98 | Kathryn ? | R 2 Resources | Doc | Bourne |
| 11/10/98 | Susan Brodeur | ODFW@Corvallis | 2 docs | Bourne |
| 11/12/98 | Ted Williams | SP Cramer & Assoc. | 4 docs | Bourne |
| 11/12/98 | Ted Williams | SP Cramer & Assoc. | 9 docs | Bourne |
| 11/13/98 | Molly McClure | PSU, State of the Envir. Report Dept Public Admin | 2 docs | Bourne/to Lance |
| 11/16/98 | Callie Ronning | Montana St Univ. student | Info | Bourne |
| 11/16/98 | Janet Webster | OSU Guin Library | Doc | Bourne |
| 11/18/98 | Lenora Oftedahl | CRITFC SN Library | 2 docs | Bourne |
| 11/19/98 | Ann Richards | Southern OR Univ. Library | Doc | Bourne |
| 11/19/98 | Jay Beckstead | public | Doc | Bourne |
| 11/19/98 | Trish Webb | Foster, Wheeler Envir Corp Library | 2 docs | Bourne |
| 11/20/98 | Jay Beckstead | public | 2 docs | Bourne |
| 11/20/98 | Molly McClure | PSU, State of the Envir Report Dept Public Admin | Doc | Bourne |
| 11/23/98 | Gary Susac | ODFW | Winter Steelhead: Mid-Willamette | Sounhein |
| 11/23/98 | Jay Beckstead | public | 21 docs | Bourne |
| 11/23/98 | Mark Miller | BioAnalysts | bib copy | Bourne |
| 11/23/98 | Molly McDonald | CH2MHill for ODOT | Fish and Wildlife resources in Polk Co for ODOT improvement project environmental assessment | Forsberg |
| 11/23/98 | Nick Iadanca | NMFS, Portland | doc | Bourne |
| 11/23/98 | Sean Meegan | BEAK | 2 doc | Bourne |
| 11/24/98 | Georgia | BioAnalysts | bib copy | Bourne |
| 11/24/98 | Robert Busch | private, B.C. Canada | 2 docs | Bourne |
| 11/30/98 | Becky Fried | ODFW-Corvallis | Projection file from PSMFC to Oregon Lambert | Forsberg |
| 11/30/98 | Diane Mitchell | WA State Library, Olympia | 4 docs | Bourne |
| 11/30/98 | Kevin Kitchart | Williams Creek Watershed Council | ORIS web location | Forsberg |
| 11/30/98 | Lenora Oftedahl | CRITFC SN Library | Doc | Bourne |
| 11/30/98 | Ron Yokum | private | 2 docs | Bourne |
| 12/02/98 | Bill Pearcy | OSU Oceanography student | Doc | Bourne |
| 12/02/98 | Briana Sounhein | ODFW@Corvallis | bib zip | Bourne |
| 12/02/98 | Jurgen Westrheim | Can Fish & Oceans | tour, 9 docs | Bourne |
| 12/02/98 | Mary Hanson | ODFW | Maps of STS in L. Deschutes & Trout Cr. & CHS for L. Deschutes. for review of report on Lower Deschutes | Forsberg |
| 12/07/98 | Briana Sounhein | ODFW@Corvallis | 2 docs | Bourne |
| 12/08/98 | Bruce Jackson | ODFW-Engineering | Wanted copy of ORIS for Fishways info | Forsberg |
| 12/09/98 | Molly McClure | State of the Envir Report PSU | Doc | Bourne |
| 12/10/98 | Karen Pratt | Pratt Consulting | Doc | Bourne |
| 12/10/98 | Molly McCluer | State of Environment Project, PSU | Sent 4-disk copy of ORIS and manual for their project review. | Forsberg |
| 12/11/98 | Briana Sounhein | ODFW@Corvallis | 2 docs | Bourne |
| 12/11/98 | Kay Quigley | OSU student | Doc | Bourne |
| 12/11/98 | Randy Smith | ODFW | Coos & Coquille Winter Steelhead maps with Public Land Survey boundaries | Bowers |
| 12/11/98 | Briana Sounhein | ODFW@Corvallis | Doc | Bourne |
| 12/14/98 | Gary Susac | ODFW | Winter Steelhead: Rogue creel data | Sounhein |
| 12/14/98 | Steve Cramer | SP Cramer | 4 docs | Bourne |
| 12/15/98 | Steve Evans | Agra Earth & Environment | Doc | Bourne |
| 12/16/98 | Jay Beckstead | private | 3 docs | Bourne |
| 12/21/98 | Patty Michak | Fishpro | Doc | Bourne |
| 12/21/98 | Peggy O’Neal | PSU | 6 docs | Bourne |
| 12/28/98 | Janet Webster | OSU Guin Library | 5 docs | Bourne |
| 12/29/98 | Lenora Oftedahl | CRITFC SN Library | 2 docs | Bourne |
| 12/29/98 | Susan Gilmont | OSU Guin Library | disk of Progress Reports | Bourne |
| 12/30/98 | Janet Webster | OSU Guin Library | 2 docs | Bourne |
| 12/30/98 | Kent Mayer | PSU student | doc | Bourne |
| 12/31/98 | Paul Reimers | ODFW | Barriers in 4 HUCs | Brodeur |

StreamNet GIS Data Downloads off the ODFW FTP Server

(Tabulated by Brent O. Forsberg 1/6/99)

| GIS Coverages | Number of Files Downloaded | Number of Different Users Downloading Files |
| --- | --- | --- |
| Fall Chinook | 211 | 16 |
| Spring Chinook | 219 | 12 |
| Chum | 44 | 8 |
| Coho | 279 | 19 |
| Winter Steelhead | 179 | 11 |
| Summer Steelhead | 173 | 10 |
| Bull Trout | 21 | 17 |
| Oregon Rivers Information System | 518 | 89 |
| Routed Streams | 157 | 19 |
| Coastal Salmon Plan Core Areas | 27 | 5 |
| Postscript maps | 80 | 6 |
| Misc. other coverages | 81 | 28 |

V.  Pacific States Marine Fisheries Commission

PERIOD HIGHLIGHTS

Data Development

Reviewed the status of all data development tasks with project participants.

Prepared a proposal for development of an online version of the Fish and Wildlife Program Annual Implementation Work Plan.

Prepared a Columbia Basin-wide ecoprovince and subbasin delineation proposal for use by the Fish and Wildlife Program's Framework and M&E initiatives.

Data Management

Incorporated major data updates from WDFW.

Incorporated new anadromous distribution coverages including use types for Idaho, Washington, and Oregon.

Incorporated new Oregon hatchery release data.

Revised the StreamNet data holdings document.

Initiated a major revision of the StreamNet data exchange format document.

Error checked and revised the 100K river reach system for Idaho, Oregon, and Washington.  Coordinated enhancement activities within the states.

Completed review and revision of the 1:100,000-scale PNW hydrography.

Maintained contact with regional river reach system users including the USFS, BLM, and states, in order to ensure compatibility of efforts.

Maintained contact with the national NHD team.

Maintained and revised the StreamNet 100K web site feature.

Library/Reference System

Assisted CRITFC in the hiring of a new librarian and library technician by reviewing resumes and participating in interviews.

Data Delivery

Introduced the updated version of the StreamNet online query system, including mapping and tabular reporting capabilities.  Incorporated an online data holdings feature.

Maintained and enhanced test versions of the data query and reference system.

Enhanced the education portion of the StreamNet home page by adding links to environmental education sites.

Maintained and revised the project management section to the home page, principally by posting new project documents as these were produced.

Monitored use of the StreamNet web site.

Responded to all web site “feedback” comments within 24 hours of receipt.

Revised a list of StreamNet home page enhancement ideas and identified priorities for future home page improvements.

Project Management

Prepared sub-contracts for seven participating agencies.

Prepared a project "quick" plan that summarized the more detailed work statement.

Prepared a project implementation and data development plan that identified

Attended and gave presentations at two Multi-species Framework workshops.

Attended and made a presentation at the Resident Fish Caucus meeting.

Attended and made a presentation at a CRITFC-sponsored watershed conference.

Held coordination meetings with NWPPC and CBFWA staff.

Scheduled and facilitated the October Steering Committee meeting.

Maintained contact with project coordinators via telephone and email on at least a weekly basis.

Reviewed sub-contractor invoices and prepared BPA invoices.

Prepared the FY 2000 project proposal including background, proposed tasks, and proposed budget.

PLANS FOR NEXT QUARTER

Data Development

Continue to coordinate data development by participating agencies, including mid-year review of status.

Data Management

Incorporate new data as received from participating agencies.  Significant additions are anticipated from ODFW, IDFG, and WDFW.

Consult with BPA, NWPPC, and CBFWA regarding an online version of the FY2000 Annual Implementation Work Plan.  Prepare an online product based on these discussions.

Complete version 99.1 of the data exchange format document.

Library

Provide direction to library staff regarding library use policies and other appropriate issues.

Cooperate with library staff in updating source references.

Data Delivery

Continue to enhance the online data query system as per the existing enhancement plan.

Enhance the utility and visual appeal of the StreamNet Internet query system by revising the help system, revising text, and inserting appropriate graphic images.

Respond to requests for data and data services as needed.

Project Management

Hold coordination meetings with CRITFC, IDFG, ODFW, and WDFW.  Contact other participants via telephone.

Prepare for and conduct a January steering committee meeting.

Continue to monitor project progress, including overseeing work of subcontractors.

Continue to monitor Fish and Wildlife Program-related activities and reports in order to identify links with these activities.

Prepare and conduct briefings on the project to applicable CBFWA managers' caucuses.

Prepare work priority lists for a) data manager, b) programmer, and c) data technician.

VI.  Shoshone-Bannock Tribes

PERIOD HIGHLIGHTS

Attended quarterly Steering Committee meeting.

Reviewed project products.

PLANS FOR NEXT QUARTER

Attend quarterly Steering Committee meeting.

Review project products.

Monitor applications/issues for StreamNet in the Fish and Wildlife Program as identified in the CBFWA project evaluation process.

VII.  U.S. Fish and Wildlife Service

Period Highlights

Attended the Steering Committee meeting.

Plans for Next Quarter

Continue translating return information to the exchange format.

VIII.  Washington Department of Fish and Wildlife

Period Highlights

General

WDFW participated in the StreamNet Steering Committee meeting in Boise to review the direction of work and relationship to contributing funding sources for the upcoming fiscal year. Staff also participated in a number of conference calls to discuss compiling and integrating resident fish data in priority categories.

Database Development

Tabular

Key developments this quarter include 1997 data updates initiated for several adult abundance categories, compilation of 1998 statewide hatchery returns data for conversion and eventual exchange, compilation of statewide sport and commercial harvest data, and provision (finally!) of historical 1981-1994 steelhead release data.

Spatial

Staff worked with Ken Williams of Region 2 to identify, enter data, and produce maps indicating lake and stream presence of westslope cutthroat trout in selected Eastern Washington basins in response to a proposed USFWS regional listing for this species. We also made other updates to the salmonid distribution and use data, began integration and review of a statewide hatchery facilities layer, began to move old resident fish distribution data into the spatial data library, and started cleanup work on the lakes information tables.

Systems Development

Tabular

The SaSI98 stock status and reporting system development was completed for Windows 95/98, except for user documentation and help files. Existing SaSI data were restructured to fit the new model, which is flexible enough to meet current extended needs that weren’t evident in 1992. Exchange formats for all data categories were reviewed in conjunction with other regional StreamNet staff, with special attention paid to the usefulness of current versions of certain  formats for capturing resident fish data.

Spatial

The “StreamNet” menu-based data release and mapping system was updated to allow dBASE format exports, bull trout and cutthroat trout distribution data maps, and prototype lakes data access. SaSI stock-related presence data was integrated with our standard species-based “distribution/use” data and reviews of the “fit” are on-going. A program generating simple township-based presence reports for all priority fish species in Washington was also added to this system. Digitizing routines that support spatial data entry onto streams layers were updated to provide data entry and subsequent mapping into lakes on a trial basis, to support the westslope cutthroat urgent need.

Data Request/Response Log

WDFW StreamNet staff record both spatial data and tabular data requests in a similar format. The cooperation of Habitat Management Program staff was instrumental to both compilation and standardization of information concerning spatial data requests, or "data releases". Over 150 data requests that use some of the StreamNet-developed spatial layers (hydro, barriers, facilities, or fish distribution/use) were filled by these staff during this reporting period, but are not listed here. More specific requests for StreamNet data products and services are handled directly by the StreamNet staff listed at the beginning of this report.

The table on the following pages (Appendix A) summarizes the people who made these more specific requests, the type of information they needed, and the date the information was delivered by StreamNet staff during this project reporting period.

| Requestor | Organization | Data Requested | Date Delivered |
| --- | --- | --- | --- |
| Dick O'Connor | St.Michael School | General Fish and Wildlife maps | 10/05/1998 |
| Tom Owens | WDFW | HUC map 17110011-Coho | 10/05/1998 |
| Bill Zook | WDFW | 10 Statewide Resident Fish maps | 10/10/1998 |
| Tom Johnson | WDFW | WRIA 15 for all species | 10/13/1998 |
| Tom Owens | WDFW | HUC 17100103 PHS | 10/14/1998 |
| Don Haring | WA Conservation Commission | WRIA 13-all species | 10/15/1998 |
| Ken Williams | WDFW | Westslope Cutthroat For E. Washington; several maps | 10/15/1998 |
| Steve Meyer | WA Conservation Commission | Streams with Critical or Depressed SaSI stocks by county | 10/26/1998 |
| Robert Kope | NMFS | Columbia River Chum Data | 10/27/1998 |
| Maggie Bell-McKinnon | DOE | Lakes with salmon/anadromous fish in them | 10/30/1998 |
| Robert Woodard | WDFW | Complete copy of Oldrel.db (Historical Hatchery Releases database) | 11/04/1998 |
| Don Haring | WA Conservation Commission | 8 user defined steelhead maps of assorted WRIA's | 11/09/1998 |
| Olaf Langness | WDFW | Historical hatchery returns for Lower Columbia Hatcheries. | 11/09/1998 |
| Jenny Lang | Nature Conservancy | ESA-state maps poster, Bull trout statewide map | 11/10/1998 |
| Virginia Neff | WDFW | WRIA 32,33 | 11/10/1998 |
| Ken Williams | WDFW, Region 2 | Statewide Historical Hatchery Cutthroat Releases | 11/19/1998 |
| Wolf Dammers | WDFW | Cedar Creek trap counts and Gorley Creek Trap Counts. | 11/19/1998 |
| Roger Ramsdell | DNR | Washington state hatcheries: name, owner, TRS | 11/24/1998 |
| Sara Breslow | UW PNW Coastal Ecosystems Reg. Office | StreamNet Online basic navigation, results interp. | 12/04/1998 |