StreamNet

BPA Project Number 198810804

## Fiscal Year 2001

### Fourth Quarter Progress Report

#### Bruce Schmidt

Pacific States Marine Fisheries Commission

Cooperators:

Phil Roger, Columbia River Intertribal Fish Commission

Bart Butterfield, Idaho Department of Fish and Game

Janet Hess-Herbert, Montana Game, Fish and Parks

Cedric Cooney, Oregon Department of Fish and Wildlife

Steve Pastor, U.S. Fish and Wildlife Service

Dick O’Connor, Washington Department of Fish and Wildlife

Table of Contents

Introduction………………………………………………………………………………..	Page   2

Objective 1.  Data Development…………………………………………………………..	Page   3

Task 1.1.  Anadromous Fish…………………………………………………….……….	Page   3

Task 1.2.  Resident Fish and Other Aquatic Species…………………………..………..	Page 13

Task 1.3.  Habitat…………………………………………………………..……………	Page 19

Task 1.4.  Facilities……………………………………………………..……………….	Page 20

Task 1.5.  Habitat Restoration / Improvement Projects……………..…………………..	Page 25

Task 1.6.  Sub-basin Planning…………………………………..……………………….	Page 26

Objective 2.  Data Management and Delivery…………………………………….……….	Page 30

Objective 3.  Library……………………………………………………………………….	Page 46

Objective 4.  Services to Fish and Wildlife Program Activities…………………………...	Page 50

Objective 5.  Project Management / Coordination…………………………………………	Page 55

# Introduction

This report presents accomplishments of the StreamNet project for the Fourth Quarter of Fiscal Year 2001.  The report is organized to clearly link accomplishments by the project participants to the Tasks and responsibilities detailed in the FY2001 Statement of Work.  It is organized by Task for all project participants rather than by individual project participant.  Job statements from the Statement of Work are presented on the left of this report for each participant, with work accomplishments for those jobs presented on the right.  Since not all work elements are addressed each quarter, and project participants often work on different jobs at different times, some jobs do not show activity in the Fourth Quarter.  Those jobs with no activity are not listed in this report.

Project participants contributing to the StreamNet project were Columbia River Intertribal Fisheries Commission (CRITFC), US Fish and Wildlife Service (FWS), Idaho Department of Fish and Game (IDFG), Montana Fish, Wildlife and Parks (MFWP), Oregon Department of Fish and Wildlife (ODFW), Pacific States Marine Fisheries Commission 	(Region), and Washington Department of Fish and Wildlife (WDFW).  The Shoshone-Bannock Tribes (SBT) have been a participant for a number of years, but they are currently fazing out their participation in the project due to other workloads, and were not active this quarter.

Introduction				Fiscal Year 2001 Fourth Quarter Report	Page 2 of 63

Objective	1	Data Development

Increase the knowledge base concerning the region’s fish and wildlife resources through the acquisition of new information

that responds to emerging needs as well as the updating and enhancement of production and survival trends and other existing

information.

Objective	1	Data Development

Task	1	Anadromous Fish

Acquire data sets related to salmon, steelhead and, where data are readily available, other anadromous fish populations from

the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized,

consistent formats for the following categories:

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.a	Distribution, Life History (use type), and Barriers

Document the occurrence, distribution and habitat use of anadromous species, related barriers to migration, and life history

Characteristics

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

ODFW	1	Update, maintain, correct and exchange barrier information.	1)  We initiated an effort to incorporate culvert information into the Barrier

database.  T o do this, a data entry form was created and linked from

main form to show additional information on culverts not currently

captured in the database.

2)  Staff requested, acquired and processed culvert data from

Clackamas and Multnomah counties. Also acquired culvert data from

Hood River County.

3)  We added several new hatchery facility-related barriers found in a

report developed by ODFW pathology staff, and new information

associated with hatchery facilities already in the barrier table.

ODFW	2	Update, maintain, correct and exchange anadromous fish 	1)  We worked to compile disparate sources of documentation data

distribution information (DistUse and DistPresence tables).	(DistPres table) to supplement what had previously been entered into

the Documentation database. From this, a table was generated that

included all records for the Willamette, Rogue and Mid-coast collection

efforts (6,668 records).

2)  We transitioned management of fish distribution event data from Info

format to MS Access. We created a Design Master and Replicate copies

to facilitate distributed management.

Objective	1	Task	1.a	Fiscal Year 2001 Fourth Quarter Report	Page 3 of 63

ODFW	4	Design and develop a database to capture carcass placement 	Duplicate Task - information is provided under Objective 1, Task 5.b -

data.	Work Component 2.

ODFW	5	Update (and modify if needed) the Fish Presence Survey 	1)  We continued to enter data into the Fish Presence Survey Database

database which helps populate the DistPresence table.	that is designed to capture Oregon’s upper fish distribution and culvert

information collected by ODF/ODFW surveyors.  To date, 5,542 records

have been entered.

2)  We began modifying the design and structure of the Database to

facilitate more efficient data entry by users.

3)  PS data was processed into GIS coverages.

4)  We prepared a district level summary of data entered thus far, and

sent the reports to ODFW district staff with a request to submit additional

data that had not yet been provided to us.

ODFW	6	Update (and modify if needed) the Incidental Fish Observation 	1)  We continued to enter forms as they came in - currently, 32 of the 116

database, which captures incidental species observations not 	records in the database are for Col. Basin streams. New information

routinely reported in agency documents, which helps populate 	will not be processed and submitted to StreamNet due to budget cuts.

the DistPresence table.	2)  We work was initiated and completed to derive LLID or coordinate

points for all IFO forms that are missing this information.

ODFW	7	Identify appropriate documents/references for anadromous fish 	Ongoing.

distribution data in order to populate the DistPresence table.

ODFW	8	Update, maintain, correct and exchange photographic 	We acquired existing electronic images of Oregon hatcheries that were

information (MapCat and related tables).	located on the agency network in Portland. Added 122 hatchery

photographs to the MapCat Database and linked them hatchery facilities

in the Barrier Database. The photos and updated MapCat database were

submitted to Regional StreamNet.

ODFW	9	Populate the genetic origin and production origin fields in 	This Task was dropped due to budget cuts. Standards and definitions

StreamNet distribution exchange format for all anadromous fish 	need to be developed in order for this work to occur. As part of our 24K

distribution data in the Columbia basin.	Fish Habitat Distribution Development Project, definitions were drafted

but they still need to be reviewed and adopted by ODFW and StreamNet.

They are currently being used on a provisional basis.

Region	3	Assist StreamNet partners with acquisition, development, 	Over the past year, several attempts have been made to create a data

formatting and submission of data.	structure for integrating fish distribution information at the regional level.

This quarter, PSMFC personnel led a new attempt to compile the ODFW,

WDFW, IDFG, and MFWP data.  This effort took off from significant

progress made by MFWP during this quarter. Further progress was

made.  Significant problems have repeatedly occurred in the attempt,

Objective	1	Task	1.a	Fiscal Year 2001 Fourth Quarter Report	Page 4 of 63

due to the fact that it is not just data structures which vary between

agencies.  Rather, the concepts behind what data are stored are

somewhat different between the states, making the effort to merge

the data focus largely on creating carefully-worded descriptions which

are inclusive but also clearly define the meanings. For example, two

states record where fish are thought to exist, and two states record

where appropriate and accessible fish habitat exists.  The final resolution

of this problem will depend on creation of precise language acceptable

to all the states, and an agreement on the level of detail needed to make

the data valuable.  Work on this will continue into next fiscal year.

WDFW	1	Review barriers in the anadromous fish distribution layer, based 	Hudson and O'Connor assisted in updating smelt presence data for

on SSHIAP information and indicators in the Stream Catalog. 	the Lower Columbia River on an emergency basis to support EIS

Update and exchange the data with the regional database.	assessment for the Army Corps of Engineers dredging project.

New programs were written, maps were developed, new data

were collected and entered, and new, publication-ready maps

were generated.

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.b	Adult Abundance

Escapement, redd counts, trap counts, dam counts, hatchery returns

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

IDFG	1	Compile 2000-field season redd count data and 2000 field 	1)  We completed compilation and entry of the year 2000 redd count data

season hatchery return data and submit to the regional 	into the FIS.

database.	2)  We completed correct assignment of IDFG transects to 100K hydro

(LLID) for the years 1989-1992 and 1996-2000.

ODFW	1	Update existing abundance and index trends (escapement, redd 	1)  We continued updating trends from the Columbia Basin and Coastal

counts, trap counts, peak/other spawning counts, etc.) for 	HUCs as information became available.

anadromous species through 1999 and modify as needed to 	2)  A total of 968 trends were either updated or created during this period.

adhere to the 2000.2 Data Exchange Format.  Four data 	Of the 968, 367 were Adult Return - Estimates of Spawning Population,

submissions are planned.	584 were Adult Return-Peak/Other Spawning Counts, 9 were Adult

Return - Redd Counts, and 8 were Adult Return - Dam/Weir counts.

3)  We submitted updated data to StreamNet at the end of September,

including updated hatchery return data.

4)  We completed updating the Stratified Randomly Sampled surveys for

coho and chinook with 1999 data.

Objective	1	Task	1.b	Fiscal Year 2001 Fourth Quarter Report	Page 5 of 63

4)  We worked on updating Trends with only a MethodID to having a

SampMethodID and CalcMethodID in the Fish Abundance database.

- We updated Marmot Dam and Pelton Dam trends.

ODFW	2	Compile data on returns to ODFW hatchery facilities (updated for	6)  We completed the Hatchery Return data effort by compiling almost

1997, 1998,  and part of 1999 returns).	all the HMIS data into our abundance database.  The data was

delivered to Regional StreamNet in late September including 320

trends, with 4,424 detail records for those trends.

Region	1	Assist StreamNet partners with acquisition, development, 	We loaded 58 new anadromous Trends and updated 910 Trends for

formatting and submission of data.	ODFW in Oregon.

WDFW	1	Update and exchange hatchery returns through 1999 in 	1)  Woodard downloaded 1995-2000 hatchery returns data from the

StreamNet data exchange format.	WDFW hatcheries division.  Upon review of the data it was noted that

a field not previously filled was now being filled with data

(Shipped/Planted).  A review of the WDFW StreamNet hatchery returns

database also revealed that a new rollup of data would be required in

order to correctly account for fish returning to WDFW hatchery facilities.

This showed that we inaccurately reported the data in previous submittals

to StreamNet because the WDFW Hatchery Division does not correct

their database.  Instead they merely correct their printed reports.

2)  Woodard met with Kyle Adicks several times to discuss how to

properly roll up existing data in the WDFW hatchery division database

to fit the StreamNet DEF.  After further review Woodard decided to

abandon old procedures for rolling up WDFW hatchery division data and

start all over with a new format.  This draconian measure was taken as an

ever-evolving WDFW hatchery division database changes too much from

year to year to rely on previous years’ roll-up tools and documentation.

3)  Woodard rolled up the 1995-2000 hatchery returns data, added the

new Shipped/Planted field to his WDFW StreamNet hatchery returns

database and checked for accounting errors.  He created a master table

to convert hatchery division alpha location and stock codes to DEF

numeric coding schemes.  Woodard also created a master species table

to coordinate species, run, and subrun numeric codes per StreamNet's

DEF with WDFW hatchery division's alpha species and run codes.

4)  Woodard added the rolled up 1995-2000 hatchery return data to his

StreamNet Returns database and is preparing for a data exchange. Yet

we still must discuss and decide how to convey the data in the current

StreamNet DEF so it makes sense compared to the WDFW Hatchery

Division reports since there is no current easy way to report the number

that was shipped\planted. At this early date, the best option seems to be

to add the shipped\plant count to the comment field and include that

count in the Total field.

Objective	1	Task	1.b	Fiscal Year 2001 Fourth Quarter Report	Page 6 of 63

5)  After the exchange, we will intensify our work with the Hatchery

Division to improve their Form 5 database and procedures.  Also after the

exchange in FY2002, Sikora must update the id-logs to reflect the status

after both the FY2002 and Dec2000 returns data was exchanged.

6)  Also see Objective 1 Task 4b Work Component 1 for inconsistent

entries in the Form 5 database's facility and trap fields.

WDFW	2	Update and exchange natural spawner data (returns and/or 	1)  On their budget code, Lensegrav assisted the WDFW's Wild Stock

redd counts) through 1999 for available species (CR, PS)	Unit with five days of field work on a chinook mark\recapture study of the

Green River to assess adult returns that get above the fisheries.

2)  Smith worked on tying up loose ends and looking for missing data for

the escapement database.  Smith worked on the TrendStat and HistStat,

and sent her final classifications over to Bruce Sanford, to get a response

as to whether it is correct or changes need to be made.  Smith also asked

him about a couple of trends regarding the Hoh River.

3)  Smith collected data from Ron Roler for Upriver Brights, typed

up a memo and entered the escapement data for the Hanford Reach

area.  Travis Nelson was contacted about the missing chum data for the

Puget Sound and a complete list of chum data was sent and entered.

Smith also revisited already entered Puget Sound redd count data to

verify the numbers.

4)  Smith looked over the 60K trends from Pacific States Marine Fishery

Commission and compared them to already existing WDFW trends.  We

already have WDFW trends for each 60K trend that she assessed so we

will direct StreamNet to delete the 60K escapement trends upon the next

exchange.

5)  Smith tried to track down missing data from some Eastern Washington

rivers.  Smith talked with Olaf Langness and he provided her with some

information, and also gave her a couple of names to contact for more

information, Tom Cooney and Kris Petersen.  Smith emailed Tom

Cooney, but has yet to hear back from him.  Kris Petersen was also

Emailed.  She responded by giving Smith another name of someone who

would probably be able to send her what she is looking for, Andrew

Murdoch.  Andrew Murdoch promised data by the end of July or early

August, as he would be in Alaska.

6)  Andrew Murdoch emailed Smith some data in August for east side

rivers and gave Smith a list a people to contact for additional information.

Andrew also mentioned that he was mailing Smith some spawning

ground data.  Smith received a couple of reports containing Mid-Columbia

data from Andrew Murdoch through the mail.  Smith read through these

reports and pulled out a lot of data that she had been looking for to fill

Mid-Columbia data gaps.  Smith also acquired from Lisa Harlan,

Objective	1	Task	1.b	Fiscal Year 2001 Fourth Quarter Report	Page 7 of 63

Vancouver Region 5 Bio, some data she had collected for some of the

Wenatchee area rivers.  Smith also acquired from Bob Woodard a 2000

report done on the Entiat River, that contained some data that Smith

was looking for, as well as an escapement book with general summary

reports from 1952-1979.

7)  Smith also worked on a few data requests.  Brian Edie's (WDFW)

request contained information for spring chinook, chum, summer and

winter steelhead for years 1997 to current, from Bonneville Dam

downstream.  Ron Roler's request included fall chinook data for Grays,

Elochoman, and Cowlitz rivers and chum escapement on the Grays

River System.

8)  For the next escapement data exchange, Sikora will use Smith's

current snapshot rather than the older snapshot she was working with

earlier this FY before priorities shifted to hatchery facility and bull trout

distribution data.

(Also see  Objective 2 Task 1 Work Component 1 for Brown's work

creating a consolidated survey data collection system.)

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.c	Juvenile Data

Sample records, abundance indices (as available)

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

IDFG	1	Finalize the incorporation of the IDFG General Parr Monitoring 	We helped IDFG staff error check and summarize juvenile salmonid

(juvenile) data into StreamNet.	trapping and tagging data for 2001.

ODFW	1	Prepare and submit recommended modifications of the draft 	This Task was dropped due to budget cuts.

Juvenile abundance portion of the DEF.

ODFW	2	Update Oregon's 10 existing juvenile abundance records to 	Juvenile data have been catalogued and saved for a future effort. No

approved DEF standards.	work has been accomplished to create Trend data with this information.

ODFW staff are awaiting a format change to the juvenile abundance

record requirements and interface form design.

Objective	1	Task	1.c	Fiscal Year 2001 Fourth Quarter Report	Page 8 of 63

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.d	Harvest

In-river, terminal, and other harvest, as available

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

ODFW	1	Provide remaining 1997 & statewide 1998 tributary sport harvest	No work was performed on this task during this quarter.  We are awaiting

from angler harvest cards.	additional update of harvest card database from the Portland

headquarters.

WDFW	1	Update and exchange salmon harvest data through 1999, 	1)  Early Aug, Lensegrav enhanced WDFW’s marine area code table

beginning with Columbia River commercial, sport and treaty 	(wamarcs5.db) with separate commercial catch & sport catch area fields

harvest.	to capture the different area naming protocols, entered area designations

for questionable records and documented his enhancements.

2)  Smith built tables for a report on sport mark recoveries for the

tributaries of the Columbia River, 1999 and 2000.  The final table was

delivered to Susan Markey in FY2002 (end of October) and will help in

future years to update Columbia River harvest data for StreamNet.

(Also See  Objective 2 Task 3 Work Component 4)

WDFW	2	Update and exchange steelhead harvest through 1998.	N/A – We didn't add this back after budget cut.

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.e	Hatchery Production

Releases and disposition

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

FWS	1	Compile FWS hatchery release data, w/ added CWT information	Additional release information was added to sr80s.dbf.

FWS	2	Transform data to format 032	The initial transformation of 2001 release data was performed.

IDFG	1	Compile 2000-field season hatchery returns data.	We began verification and  correction of historic hatchery return data.

Objective	1	Task	1.e	Fiscal Year 2001 Fourth Quarter Report	Page 9 of 63

ODFW	1	Develop the ability to remotely access the Portland mainframe 	1)  Our new Database Manager began familiarizing himself with the

hatchery database and download hatchery return data 	Insyte software by working through all examples in the user's manual

consistent with the StreamNet contract.	and producing several test reports.  He learned the syntax for the Insyte

query language and produced reports from the HMIS system for import

into Access. He then worked on retrieving and formatting hatchery data

from the Insyte system and familiarized himself with running test reports

and saving files to the Unisys system. He downloaded large amounts of

raw data to insure the information was there that StreamNet needed in

the Trend database.

2)  We began work on an application to automate the process of

gathering and translating the raw data from the HMIS system into

StreamNet format.  Currently the program can process individual records,

but will soon have the ability to automatically process all the information

and output the results to Jet database tables.  Downloaded all the raw

data needed to populate the HatchRetData table and started to process

the data to get the calculated information required by the DEF.

3)  We completed the Hatchery Data Compiler program. This program

takes the raw data from the HMIS system and compiles it into usable

HatcheryRel data.  Also working on the manual to enable other users

to complete the process.

ODFW	2	Compile egg-take data into StreamNet format and submit to 	1)  Completed work on the Hatchery Data Compiler, an application that

PSMFC.	automates the collection of data from the HMIS system and transforms it

for input into the StreamNet database. It also allows users to graphically

select queries rather than enter commands into the telnet session (which

requires the user to remember the correct syntax).

2)  Because the DEF requirements have not been finalized, no disposition

data were exchanged during this quarter, but we are prepared to obtain

the data in the agreed upon format once the format is finalized.

WDFW	1	Update and exchange juvenile release data to PSMFC through 	Cox submitted release data updates to PSMFC including all the available

2000.	2001 data at that time.  His last submittal during this period was on

Aug 22, 2001.

WDFW	2	Explore providing "unrolled" release data directly to StreamNet.	To send the data described in the first component directly to StreamNet

in their format instead of the RMIS format, we continued to identify some

of the proper LLID or HatchID codes that would be needed for this effort.

In the first and second quarter of FY2002, WDFW will focus on converting

all relevant release data fields and exchanging the data directly to

StreamNet. In May 2001, Kinney reminded WDFW that the system he left

does all error checks and PSC code conversion to WDFW's Hatchery

Division release data BEFORE the rollups to one record per CWT.

Objective	1	Task	1.e	Fiscal Year 2001 Fourth Quarter Report	Page 10 of 63

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.f	Natural Production

Survival, production factors, spawner recruit

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

ODFW	1	Compile hatchery-wild fractions in OR portions of the Columbia 	No data were delivered for inclusion in the database.  Considerable

basin for spring chinook and fall chinook.	progress was made in compiling data for inclusion in the database.  We

expect to provide data early in next contract period.

ODFW	2	Compile spawner-recruit data (updated for spring chinook 	This Task was dropped due to budget cuts.

surveys in 1998 and 1999, and available time series for fall

chinook and coho returns)

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.g	Age

Age/sex composition for returning adults

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

FWS	1	Update age and sex data through 2000	Pastor investigated alternate methods of assigning ASNID.

IDFG	1	Compile 2000-field season age and sex composition data.	We began verification and correction of age/sex data in conjunction with

hatchery returns (work component 1.1e.1).

ODFW	1	Compile age frequency data (updated for natural spring chinook 	This task was dropped due to budget cuts.

in 1998, available time series for natural steelhead in OR portion

of Columbia basin).

WDFW	1	Provide age/sex data associated with exchanged CRB natural 	See  Objective 2 Task 1 Work Component 1

returns data.

Objective	1	Task	1.g	Fiscal Year 2001 Fourth Quarter Report	Page 11 of 63

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.h	Genetics

Areas where genetics data exists and the sources of these data

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Develop, with SC input, standardized database format and DEF 	Developed draft DEFs for a genetic database and a sample application

for existing regional genetic data	using CRITFC data. We plan to demonstrate this application to

geneticists at a conference in October. Final recommendations for

StreamNet management of genetic data will be made following this

conference.

CRITFC	2	Provide allozyme and genetic data developed by CRITFC in 	A small test application was developed using CRITFC data. The

standard format	approach taken will be discussed with a coast-wide fish genetics working

group during the first quarter of FY02. Full CRITFC data will be provided

through StreamNet, if appropriate, after a DEF is agreed to by the

Steering Committee in FY02.

WDFW	1	Participate in decisions regarding genetic data	There were no decisions requiring Steering Committee action during

FY2001.

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.i	Populations

Population delineation, as determined by others

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

ODFW	1	Produce a cross-reference table of ODFW designated Gene 	This Task was dropped due to budget cuts.

Conservation Groups (GCG) by subbasin.

WDFW	1	Compile and exchange updated Washington SaSI stock status 	O'Connor chose to postpone work on updating the statewide SaSI GIS

data for anadromous fish using newly developed 2000.1 Data 	layer until a new SaSI biologist/data manager could be recruited and

Exchange Format (see Task 2.3).	brought up to speed. Significant SaSI database changes have been made

to existing stocks, and dozens of new stocks have been added since

1992,so the amount of work required to update the GIS layer is

substantial. However, agency budget constraints required that position

to be kept vacant through September 2001. The new recruit is expected

to be ready to work with StreamNet GIS staff late in the year, so an

updated SaSI GIS layer will not be ready before February 2002.

Objective	1	Task	1.i	Fiscal Year 2001 Fourth Quarter Report	Page 12 of 63

Objective	1	Data Development	Task   1   Anadromous Fish

Task	1.j	Historic Range

As available at the watershed-level.  Compilation at the reach level is an option if these data are available

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

ODFW	1	Work with the Steering Committee to define the term "historic" in 	During this quarter, the "historic" discussion blossomed into a larger

the DEF.	discussion on the overall compatibility of our distribution data. This portion

of the discussion was tabled until the larger, more general compatibility

issues are resolved.

Objective	1	Data Development

Task	2	Resident Fish and Other Aquatic Species

Acquire data sets related to resident fish species, and where specifically identified other aquatic species, from the multiple

agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent

formats for the following categories:

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.a	Distribution and Life History

Document species occurrence and distribution and life history characteristics

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

IDFG	1	Add additional distribution information from references, collecting	Fisheries staff continued data entry into reference and collecting

permits and stream and lake surveys for resident fish.	permit modules.

MFWP	2	Provide distribution data in DEF to StreamNet when completed.	Ongoing.

MFWP	3	Determine a schedule for updating data in the future and at what	Ongoing

frequency data needs to be collected from field biologists, also

addressing species of special concern.

MFWP	4	Collect and catalog supporting references to document 	Ongoing

distribution and connect distribution to reference.

MFWP	5	Explore the development of a standard field survey form to be 	Ongoing

used by state and federal biologists to record occurrence

information.

Objective	1	Task	2.a	Fiscal Year 2001 Fourth Quarter Report	Page 13 of 63

MFWP	6	Continue to work with regional StreamNet staff and SC to 	The DEF is still being reviewed.

develop/modify/add to a resident fish data exchange format if

not completed in FY2000.

ODFW	1	Update, maintain, correct and exchange resident fish distribution	1)  We created cutthroat template maps for the Hood basin using the

information (DistUse and DistPresence tables).	most recent Fish Presence Survey database, existing documentation

data,existing Hood cutthroat data, and the DRG Mapper AMLs, and

provided the maps the 24K Project for compilation of Hood River cutthroat

distribution data.

2  We incorporated changes to the Lahontan Cutthroat event data that

had been pending.

Region	1	Compile distribution updates (tabular events) as they arrive.  	1)  As in the third quarter, all StreamNet partners continued conversations

Create and maintain distribution GIS coverages from these event	on how to integrate at the regional level the fish distribution and habitat

tables and distribute these via the StreamNet web site.	use tables maintained by each state.  The state databases contain similar

data, but the concepts of the data stored are slightly different and the data

are stored in dissimilar fashions.  No resolution was reached this quarter

on how to accomplish the integration.

2)  QAed, and compiled resident fish distribution information from MFWP

for 18 new species in Western Montana.  Added this distribution data to

the StreamNet database and online query system.  Created GIS files and

documentation (metadata) from this information and posted these to the

StreamNet site for download.

3)  Reviewed updated distribution information for Lahontan cutthroat trout

from ODFW.  Updated the StreamNet database, online query system,

downloadable GIS files, and documentation (metadata) with this new

information.

WDFW	1	Update and exchange statewide updated bull char distribution 	1)  Hudson notified Sikora, Burns, O'Connor of King County's Fish

data at 100K resolution (see Task 2.3).	Distribution layer and either noted differences with WDFW's layer or

suggested it should be compared.  The resident fish component

(cutthroat, kokanee) is much stronger than the current WDFW data

offering. Sikora has yet to review this issue.

2)  Hudson and Burns performed a series of Bull Trout data layer

updates as the last of a series of corrections and new sightings came in

from field offices. The data were dumped to perform QC on the data entry

and the code assignments following each major update. A final dump will

precede exchange of this layer later in the year.

Objective	1	Task	2.a	Fiscal Year 2001 Fourth Quarter Report	Page 14 of 63

3)  Hudson and Burns corrected the spatial Bull Trout layer code

assignment issues and they re-dumped the tabular file on 9/6/2001.

Sikora re-scoped the data, verified the code corrections were in place

and itemized the remaining issues.  All relevant staff met again to discuss

when more than one record was unexpectedly created and we learned it

was a product of the process when a stream bordered or bisected more

than one HUC .  Sikora also started researching David Graves'

EventCompare tool to see if the tool can find other issues or be used

instead of independent on-the-fly queries.

4)  Sikora demonstrated WDFW's internal hatchery facility interface for

Burns to provoke discussion of the different experiences and false

assumptions and consider possibilities for the distribution update process.

Until the StreamNet exchange format is defined, Burns continues (into

FY2002) to update the layer with new or corrected information as it is

submitted by the biologists.

5)  See Objective 3 Task 1 Work Component 1 for contacts database

reference work related to this data.

(Also see Objective 2, Task 3, Work Component 1 for O'Connor's

on-going involvement in the distribution format discussions.)

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.b	Adult Abundance

Escapement, redd counts, trap counts, dam counts

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

IDFG	1	Coordinate with IDFG personnel to determine the feasibility of 	Fisheries staff continued data entry into reference and collecting

incorporating resident adult abundance.	permit modules. We captured abundance data where it was available.

MFWP	1	Enter 2000-2001 stream fisheries survey data collected for 	Ongoing

population trends; genetics and escapement, redd counts, trap

count and other counts during visits to biologists.

MFWP	2	Collect reference for each survey.	Ongoing

MFWP	3	Provide data in data exchange format to regional StreamNet 	Data not ready to exchange.

staff.

Objective	1	Task	2.b	Fiscal Year 2001 Fourth Quarter Report	Page 15 of 63

ODFW	1	Update existing abundance and indices trends (escapement, 	1)  We looked for resident data projects on the BPA project web-site, and

redd counts, trap counts, peak/other spawning counts, etc.) for 	then contacted numerous ODFW project leaders to acquire resident fish

resident species through 1999 and modify as needed to adhere 	data for projects funded by BPA. We called Neil Ward at CBFWA for an

to the 2000.2 data exchange standards.  Four data submissions 	explanation on project postings and for more information on where to find

planned.	BPA data.  We called biologists listed on the BPA project web-site in

order to acquire more resident species counts in the Columbia Basin.

2)  We acquired a copy of the ODFW Collections Permit Database in an

effort to locate other projects collecting resident fish data.

3)  We searched Oregon's 4-d Database to identify projects targeting

resident species as well as those targeting anadromous species.

4)  We contacted biologists involved with resident data collection to

request their abundance data.

5)  We acquired Bull Trout data from ODFW's Native Trout Project.  We

Created 285 Resident trends that were submitted in the September Data

Submission.  Of the 285 trends, 267 were Adult Return - Estimates of

Spawning Population, 3 were Adult Return-Harvest - Freshwater/Estuary

counts, 10 were Adult Return - Redd Counts, and 5 were Adult Return -

Dam/Weir counts.

Region	1	Assist StreamNet partners with acquisition, development, 	1)  Regional and WDFW staff discussed whether submission to the

formatting and submission of data.	regional database of single-record time series was warranted.   We

decided that it is, as single records of some types of data, such as fish

stocking, can be extremely important information.

2)  Several changes needed in the trend data input interface that were

identified January 23 were implemented.

3)  We loaded 285 new Adult Return Trends for Oregon resident species.

WDFW	1	Explore opportunities to compile, convert, and exchange	N/A – we didn't add this back after budget cut.

portions of the Yakima Basin juvenile and adult abundance

data from Ken Ham.

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.c	Angler Use

Fishing pressure, creel census

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

MFWP	1	Add FWP 1999 angler survey data collected by MFWP mail 	Completed.

survey to MRIS.

ODFW	1	Evaluate available creel data for appropriateness and fit into the 	This Task was dropped due to budget cuts.

StreamNet format.

Objective	1	Task	2.c	Fiscal Year 2001 Fourth Quarter Report	Page 16 of 63

WDFW	1	Explore conversion of Angler Fish Database harvest information 	WDFW budget restrictions eliminated a full-time database manager for

from the Columbia Basin into either "harvest" or a new "census" 	cold water species, and the warm water data manager isn't scheduled

format for exchange.	to be recruited until November 2001. Without this support, WDFW

StreamNet staff do not have the expertise to explore such conversion. We

will recommend that staff working on the JSAP Project consider adding

this to their work statement.

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.d	Hatchery Production

Hatchery production (releases and outplants) for salmonids

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

ODFW	1	Acquire trout release data from 1997 through 2000 (by species, 	This Task was dropped due to budget cuts.

location, and facility) and compile into SN exchange format.

WDFW	1	Complete conversion and exchange resident fish stocking data 	As of April 10, 2001, Lensegrav answered all game fish release

from 1930-1981, once location coding has been standardized 	data requests.  Further release work was suspended until Lake

and verified.	work can be re-initiated and resolved  in late FY2002.

WDFW	2	Add stocking data from 1981-2000.	See Objective 1 Task 2.d Work Component 1.

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.e	Genetics

Areas where genetics data exists and the sources of these data

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

MFWP	1	Update genetic spatial and tabular databases that contain the 	Updated databases with results received during the quarter.

results of genetic analysis of populations of Montana's species

of special concern

MFWP	2	Update fish distribution table when new samples affect fields.	Ongoing.

MFWP	4	Work with University of Montana Genetics Lab staff to develop a	Ongoing

more efficient method of data entry/delivery.

Objective	1	Task	2.e	Fiscal Year 2001 Fourth Quarter Report	Page 17 of 63

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.f	Population

Population delineation, as determined by others

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

WDFW	1	Compile and exchange Washington SaSI stock status data for 	See Objective 1 Task 1.i.

resident fish using newly developed exchange format (see Task

2.3).

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.g	Historic Range

As available at the watershed-level

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

MFWP	1	Complete the review of the historic distribution of Montana's 	Ongoing

native species developed by The Nature Conservancy.

Objective	1	Data Development	Task   2   Resident Fish and Other Aquatic Species

Task	2.h	Status

Population stability index

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

MFWP	2	If DEF adopted, submit bull trout, arctic grayling and westslope 	Completed

and Yellowstone cutthroat trout data.

Objective	1	Task	2.h	Fiscal Year 2001 Fourth Quarter Report	Page 18 of 63

Objective	1	Data Development

Task	3	Habitat

Acquire data sets related to fish habitat from the multiple agencies, tribes and organizations within the Columbia Basin and

compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   3   Habitat

Task	3.a	Stream / Watershed Habitat

Incorporate applicable stream and watershed level habitat and stream survey data, as these become available

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

IDFG	1	Incorporate the IDFG General Parr Monitoring habitat data into 	We began verification of LLID location for general parr monitoring sites,

StreamNet.	and began identification of additional GPM sites.

MFWP	1	Develop a statewide stream survey form based on information 	Ongoing

provided by Montana state and federal fisheries biologists in

FY2000.

MFWP	2	Work with regional StreamNet staff on data exchange format, if 	Ongoing

sufficient interest and/or data.

WDFW	1	Transfer and exchange spatial layers of SSHIAP habitat 	Hudson completed 24K hydro layer cleanup and routing for the

characteristics and segmentation (based on gradient, 	Lower Columbia River basins (WRIAs 24-30) and generated

confinement, and substrate).	segments for all streams based on Cosentino's routines. Other

WRIAs will be addressed next fiscal year.

Objective	1	Data Development	Task   3   Habitat

Task	3.b	Water Quality

Incorporate existing Clean Water Act 303(d) data and other water quality data as applicable

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

All	No work was done on this task this quarter.

Objective	1	Task	3.b	Fiscal Year 2001 Fourth Quarter Report	Page 19 of 63

Objective	1	Data Development	Task   3   Habitat

Task	3.c	Miscellaneous Habitat Data

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

ODFW	1	Update key stream management area designations for OR 	This Task was dropped due to budget cuts.

including FEMAT key watersheds, AFS aquatic diversity areas,

ODFW coho source river reaches, ODSL essential salmon

habitat and Priority Areas.

ODFW	2	Track the progress of ODFW aquatic habitat prioritization model 	The Project Leader communicated with the Aquatic Habitat Prioritization

and provide a URL for StreamNet to link to model results when 	Model project leader. The effort is not yet to a point where information can

they are available.	be distributed publicly, but it is being reviewed internally.

WDFW	1	Explore Cosentino's model to assess habitat suitability for 	Model development took too long to allow for comparative analysis and

anadromous and resident fish by comparing predictions to 	development of a paper describing the results. First uses of Cosentino's

actual. Write paper on techniques and findings.	program took place during this quarter for Lower Columbia River WRIAs,

and the initial results (in terms of modeled segment assignments and

breaks) look quite good. The decision was made (on this qualitative

basis)to continue use of Cosentino's model/program to generate

segments for streams in other Columbia Basin WRIAs as time permits

(next fiscal year).

Objective	1	Data Development

Task	4	Facilities

Acquire data sets related to fishery-related facilities and structures from the multiple agencies, tribes and organizations within

the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   4   Facilities

Task	4.a	Dams and Fish Passage Facilities

Enhance the existing StreamNet dams data set by updating relevant data from the Pacific Northwest Hydropower Database and

Analysis System (NWHS) and the National Inventory of Dams

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

MFWP	1	Combine the StreamNet dams dataset with dams named in the 	The spatial data layer is near completion. Processing for data exchange

GNIS and the National Inventory of Dams, and exchange 	has begun.

Montana's data.

Objective	1	Task	4.a	Fiscal Year 2001 Fourth Quarter Report	Page 20 of 63

ODFW	1	Update, maintain, correct and exchange dam information (as	We added a "Flag24k" field to the Dam and Barrier tables and forms to

part of the Barrier database).	indicate dams and barriers located on 24K streams.  We also checked

on and deleted two mysterious DamIDs (53201-02; they were

accidental creations).

WDFW	1	Review, update, and exchange any new Washington state 	No work was conducted this FY.  Per request, dam work is prioritized

dams information.	for the first and second quarter of FY2002.

Objective	1	Data Development	Task   4   Facilities

Task	4.b	Hatchery Facilities

Update and maintain a dataset on anadromous and resident hatchery facilities containing information on location, design,

management and authorization

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

FWS	1	Update hatchery facility records as needed	No corrections were submitted this quarter.

MFWP	1	Provide update of these data if changes have occurred in 	Spatial data and related ACCESS database are complete and currently

Montana's facilities.	at MFWP Hatchery Bureau for final review.

ODFW	1	Locate at least one public domain photo of each hatchery in 	We acquired existing electronic images of Oregon hatcheries that were

Oregon and provide to PSMFC.	located on the agency network in Portland. We wrote the hatchery

photos to a CD and provided it to Regional StreamNet.

ODFW	2	Review and update Oregon hatchery facilities data and submit to	We continued to contact hatchery facilities trying to get updated

PSMFC.	information.

Region	3	Assist StreamNet partners with acquisition, development, 	It was agreed during the last DEF modification for hatchery facilities that

formatting and submission of data.	only permanent and "semi-permanent" hatchery facilities would be

included in the list of facilities.  This was done in order to avoid collecting

information for the large list of temporary weirs and other structures used

for collecting adult fishes or releasing juveniles.  However, while working

to develop hatchery returns data this quarter, ODFW encountered the

problem of needing to code hatchery returns to temporary structures.

After discussing several possible solutions to the problem, it was

determined that the best course of action would be to add these

temporary facilities to the Hatchery table so that the database structure

and function would be preserved.  The problem this presents is that the

temporary facilities will be included in the list of hatchery facilities

available to query at www.streamnet.org.  However, until the list of

temporary facilities becomes large, this should not present a problem.

Objective	1	Task	4.b	Fiscal Year 2001 Fourth Quarter Report	Page 21 of 63

WDFW	1	Provide standard geo-spatial coordinates (Longitude-Latitude) 	1)  For our 5/2000 exchange, we did not confirm all our GIS site points.

for each facility.	As we continued our hatchery facility work, we were reminded that the

initial location coding was based on the technology we had at the time

and current technology lets us see issues that were not clear in earlier

determinations.  Although we could see the points in our GIS interface,

we could not easily see the stream name (or LLID) that was closest to

the site point.  For the 5/2000 exchange, we assigned LLIDs based on

our internal Location field description.  Now EventMapper and Hudson’s

GIS interface lets us read the LLID and name of the stream closest to

the point.  It showed some of our Location field and LLIDs are nowhere

near the point.  This meant either the point was wrong OR the Location

description was wrong.  For some cases, there wasn't reason to question

the point because it was clear we just assigned the wrong LLID or the

Location description obviously was just vague when it could have been

specific.  For other cases, the point was suspect, especially when the

PSC code description jived with the Location description, so we tried to

verify the point before we changed the Location field entry and LLID

assignment.  The text below describes the work as succinctly as possible

so it doesn't follow the chronological order of the work.

2)  Sikora reviewed 1\2 the issues Lensegrav found per his initial work in

the third quarter while determining BegFts for each hatchery.  Sikora

prompted Hudson to automate WDFW's interface so compilers could

immediately correct WDFW's layer attribute information or refresh the

attributes determined by the GIS system. Hudson completed the

automation & Sikora verified his system worked properly.  Lensegrav

updated our documentation of Hudson’s changes.

3)  Lensegrav updated the address, manager and telephone fields per a

9/2001 re-issue of the WDFW Hatchery Division phone book. Yet a day

after he updated our file, we were informed that the phone book had a

few errors and a revised document would be re-issued.  To date, a new

version hasn't arrived yet.

4)  Despite an earlier intent to capture Graves' exact site-long and site-lat

for Bruce Watson's Yakima area sites on WDFW's layer, Sikora just

digitized these points because Graves' points were based on river miles

that are imprecise when applied to the sophistication of our hydrolayer.

When the complete hatchery file is exchanged, Graves and Watson will

see how we treated all fields for these records.  If any changes are

warranted they can be made before the next hatchery facility exchange

that probably will be sent with our anadromous release exchange.

Objective	1	Task	4.b	Fiscal Year 2001 Fourth Quarter Report	Page 22 of 63

5)  Woodard asked Sikora for PSC codes and StreamNet HatchIDs for

4-5 hatchery "facilities" to accommodate hatchery returns data. Sikora

researched the Hatchery Division Adult Report (Form 5) and Form 3

databases to learn more about these errant facility descriptions.  She

learned a few new sites and new ways to describe existing facilities. The

Form 5 database carries a facility and a trap site field with the intent that

the facility field only describes the hatchery responsible for the

paperwork.  Yet the entry for these two fields is very inconsistent and to

decipher the data you must understand the process for a given facility

and a given year.

6)  Sikora finalized the review of the issues Lensegrav found in his first

attempt to assign BegFTs and organized our next effort to confirm more

existing site points before we fixed the GIS layer for all the issues and

then finished the BegFT assignments.  Sikora and Lensegrav coordinated

each effort as they both moved or added more facility sites, corrected

OutflowTypeID assignments and updated all attribute information so the

GIS system matched the tabular management file.  For future reference,

Sikora taught Lensegrav how to use Hudson's automation to update the

attributes.

7)  Lensegrav refreshed EventMapper with our current snapshot of

hatchery locations and the 10/2001 streamsllid.dbf file that is a backdrop

for EventMapper.  He finished assigning BegFTs, relying on the older

streamsllid.dbf file for streams that bordered or bisected more than one

HUC because the newer file would only snap the distance from the

border of each HUC.

8)  Per Sikora’s request, StreamNet reserved more HatchID codes for

WDFW.  Lensegrav updated our internal HatchID-Log table that tracks

the availability or use of these codes and Sikora continued the on-going

updates.

9)  Even though we resolved most of what we need at this time, we still

need better confirmation of some sites and many description fields (i.e.,

owner, water supply etc).  To minimize our effort and maximize the

broadcast of our request for help, Sikora started thinking on how we can

use the WDFW intranet and Internet.  Lensegrav noted the WDFW

intranet already carries a test site of spatial maps posted by Don Saul of

WDFW.  In FY2002 we must continue this web research and coordinate

updates to the existing site.

Objective	1	Task	4.b	Fiscal Year 2001 Fourth Quarter Report	Page 23 of 63

WDFW	2	Compile similar coordinates for fish releases that occur away 	Sikora started some of this work when she digitized a few of

from these facilities, in order to develop a spatial layer of fish 	Bruce Watson's acclimation\release ponds in the Yakima area

release sites (including streams, lakes, and marine areas).	described under Objective 1 Task 4b Work Component 1. Extension of

this work to cover all Washington Columbia Basin facilities will

require access to equipment and staff time beyond what is

available in the current budget.

WDFW	3	Complete, convert, and exchange tabular and spatial data tables 	See Objective 1 Task 4.b Work Component 1

of Washington state hatchery facilities, including federal and

tribal stations.

Objective	1	Data Development	Task   4   Facilities

Task	4.c	Diversion/screening

Develop a data set for water diversions and screening

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

ODFW	1	Develop a database structure and compile Oregon's fish 	1)   Due to budget cuts, no DEF was developed or submitted to

screening data and submit a draft data exchange format to	StreamNet - See note in revised Oregon SOW 7/17/2001. We

Steering Committee for review and adoption.	completed the revisions and additions to the FishScreen Database

User's Guide, and completed the form and report revisions. Network

and non-network versions of the database were developed and

distributed to their respective locations for corporate use in late July.

2)  We provided a training session to Fish Screening and Passage staff

on how to use the database on August 1, and a training session on

database synchronization in early September.

3)  We continued to provide physical and technical support for the

FishScreen Database through the remainder of the quarter as issues

arose.

ODFW	2	Identify fish screening data that is appropriate for the StreamNet 	This Task was dropped due to budget cuts.

site and submit test records once an exchange format has been

adopted.

Objective	1	Task	4.c	Fiscal Year 2001 Fourth Quarter Report	Page 24 of 63

Objective	1	Data Development

Task	5	Habitat Restoration/Improvement Projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations

within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   5   Habitat Restoration/Improvement Projects

Task	5.a	Fish and Wildlife Program Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects related to the Fish and

Wildlife Program

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

MFWP	1	Data will be updated for FWP Projects during FY-01; the spatial 	Smaller report of dataset was delivered to MRIS web development team.

data layer of project location will be updated.

WDFW	1	Follow-up from FY2000 habitat restoration project compilation 	1)  O'Connor drafted several versions of a budget and work plan to finish

and/or expand our initial habitat restoration work using new money from

EPA.  Sikora reviewed O'Connor's plans and scoped the more detailed

work requirements, learning that the current PRISM data conversion must

be corrected to reflect BegFT and EndFTs based on PRISM's longitude

latitude data instead of the sporadic RM data.

2)  The latest plan is to exchange the initial PRISM data that Lensegrav

compiled for WRIA 5 (Stillaguamish basin), portray it spatially using

ArcView and create a visual means to compare the restoration data with

the Washington State Conservation Commission's (WSCC) Habitat

Limiting factors (LFA) and/or SaSi data.  Lensegrav started an ArcView

project for this effort.  This tool will allow managers to assess whether

the restoration work is conducted in the areas of greatest need.

Lensegrav received positive feedback from George Pess of NMFS about

the proposal and contacts for more information.  Everyone thinks the

proposal is a good idea, yet we must find the proper funding source since

EPS's contract specifications do not encompass the nature of this work.

O'Connor contacted Bruce Crawford of IAC to initiate interest in the

proposal and improving IAC's PRISM database.

3)  Based on his initial knowledge of IAC's PRISM data, Lensegrav

drafted a document of proposed improvements to StreamNet's Habitat

Restoration format.  Sikora reviewed and directed revisions for this effort.

This proposal won't be submitted to StreamNet until we learn more.

Lensegrav also updated our Habitat Restoration documentation to reflect

recent findings and researched materials for O'Connor to consider for his

upcoming presentation at the November meeting of the Organization

of Fish and Wildlife Information Managers (OFWIM).

Objective	1	Task	5.a	Fiscal Year 2001 Fourth Quarter Report	Page 25 of 63

Objective	1	Data Development	Task   5   Habitat Restoration/Improvement Projects

Task	5.b	Other Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects other than related to

the Fish and Wildlife Program

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

MFWP	1	Update Montana's Fish and Wildlife habitat restoration projects 	Smaller report of dataset was delivered to MRIS web development team.

into StreamNet's Restoration and Mitigation database and submit

in data exchange format.

ODFW	1	Assist PSMFC with the creation and development of the map 	Restoration project summary efforts from California were shown to

presentation of Oregon GWEB restoration data.	Bobbi Riggers & Kelly Moore of OWEB as examples of what can be

done in Oregon.

ODFW	2	Design and develop a database to capture carcass placement 	Three meetings were held during the quarter to evaluate the Carcass

data for Columbia Basin activities.	Placement Database.  The Carcass Placement Database was redesigned

to run more efficiently using suggestions from the meetings and the

knowledge of the new database manager, including a total redesign of

the Placement Location form and increasing error trapping.  A beta test

version and users manual were delivered to the project manager on July

31 and August 3, respectively. The final version of the database was

finalized and 12 replicated copies, along with the final instruction manual

were delivered to the project manager and biologists in the field in early

September.

Objective	1	Data Development

Task	6	Sub-basin Planning

Develop consistent data sets and information that are particularly suitable and useful for regional sub-basin planning and make

them readily available for planners

Objective	1	Task	6	Fiscal Year 2001 Fourth Quarter Report	Page 26 of 63

Objective	1	Data Development	Task   6   Sub-basin Planning

Task	6.a	Provide data for Sub-basin Planning

Organize and distribute the available fish, wildlife and habitat data in a standardized format for use in Sub-basin Planning or other

regional planning efforts

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Develop tools and applications to make regional watershed 	Efforts on this Task have been minimal awaiting NWPPC and state

assessment and other planning information available to	agreement on an approach to subbasin planning.  Discussions with

subbasin planners	Oregon agencies and local subbasin planning groups have determined

that it is feasible to use OWEB watershed inventory data as input to the

Ecosystem Diagnosis and Treatment model to assess watershed and fish

status.  We anticipate implementing this strategy with subbasin planners

in FY02.

IDFG	1	Coordinate with sub-basin planning efforts to supply data.	We began developing data and map products for subbasin summaries

for the Upper Snake Headwaters, Closed Basins, Upper Middle Snake,

and Boise-Payette-Weiser.

ODFW	2	Provide consultation services and assistance to ODFW data 	Efforts this quarter centered on reviewing budget sheets to ensure our

managers to assist them in meeting Subbasin Planning needs.	activities were charged to the correct funding source.

Region	2	Provide available tabular data described under Tasks 1.1	1)  Due to the unexpectedly extensive work load encountered in

through 1.5 to entities conducting sub-basin planning.	summarizing all StreamNet data by subbasin, a separate contract was

obtained from NWPPC to provide data to the subbasin planning effort.

This contract covered work by staff that were not covered by the

StreamNet contract and would have been working on other work under

other contracts.  This work involved the following general elements:

a)  We obtained the GIS coverage of the new subbasin boundaries from

BPA.  We modified this coverage as necessary for our use to correct

inconsistencies resulting from differences in GIS layer scale.  That is,

subbasin boundaries were adjusted to ensure that streams and lakes fell

within the correct subbasins.

b)  Several errors unrelated to layer scale were encountered in the BPA

subbasin GIS coverage.  We corrected these errors as found.

c)  Using GIS, a cross table of lakes and streams versus subbasin was

created.

d)  The cross table was used to query the StreamNet database by

subbasin for each data type.  The various data types were grouped

according to subbasin, and a spreadsheet of data was created for each

subbasin.

Objective	1	Task	6.a	Fiscal Year 2001 Fourth Quarter Report	Page 27 of 63

e)  Maps of species distribution, dam locations, hatchery locations, and

streams listed under section 303(d) of the Clean Water Act were created

for each subbasin.

f)  GIS layers of species distributions, dam locations, etc. were created

for each subbasin.

g)  The spreadsheets, maps, and GIS layers were posted to the

StreamNet web site.  A series of web pages were created to provide

easier access to the files.

h)  The files for each subbasin were copied onto CD and the maps were

printed for each subbasin.

2)  The data summaries on CD and the maps developed in job 1 above

were delivered to the initial meeting of each province. During this quarter,

the data CD and maps were delivered to subbasin summary writers at the

initial meetings of the Columbia Cascade, Lower Columbia and Columbia

Estuary provinces.

Region	3	Provide StreamNet GIS coverages or other data (on request) to 	1)  Approximately 350 maps of fish distribution, hatchery locations, and

the entities conducting sub-basin planning.  Assist subbasin 	dam locations were created for use by the subbasin planners. These

planners with use of this data as needed.	maps, in addition to being made available on the StreamNet ftp site and

indexed via a series of web pages, were added to the StreamNet

database and made available via the on-line query system.

2)  The project provided a set of custom maps and GIS data for a request

from the Malheur subbasin report writer.  This request included finding

and formatting necessary GIS data, designing custom maps to illustrate

this information in the subbasin report, and deriving spatial data for the

report through GIS processes.

WDFW	1	Continue to participate in discussions concerning data needs to 	There were no FY2001 meetings with RAAC or other Council staff

support sub-basin assessment coordinated by the Regional 	regarding sub-basin assessment data needs.

Assessment Advisory Committee or other processes adopted

by the amended Fish & Wildlife Program. Modify data plan and

priorities as needed to be responsive.

WDFW	2	Coordinate data compilation from other WDFW Units as needed 	Woodard coordinated data compilation with Vancouver Region 5

to respond to the above needs, using StreamNet data exchange 	biologists for use in the sub-basin write-ups due in mid October. Chum

experience.	and Chinook data for tributaries below Bonneville Dam were delivered to

Ron Roler along with past write-ups on these tributaries.  Ongoing

consultation of historical data on these tributaries continues and data is

delivered or manipulated as needed.

WDFW	3	Provide consultation services for WDFW wildlife and habitat	No requests for this assistance were received in FY2001.

data managers to assist them in meeting the above needs.

Objective	1	Task	6.a	Fiscal Year 2001 Fourth Quarter Report	Page 28 of 63

Objective	1	Data Development	Task   6   Sub-basin Planning

Task	6.b	Capture information from Sub-basin Planning

Acquire information developed during subbasin planning to update anadromous fish, resident fish, and wildlife data sets

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1  Develop applications and procedures to update watershed 	Regional discussions have produced a final draft of subbasin assessment

assessment data during subbasin planning	guidelines. We held a one-day workshop with ODFW, NWPPC, NMFS,

and City of Portland staffs and other NGO representatives to discuss

integrating OWEB and EDT tools into a single subbasin assessment

methodology.  We presented our results to the NWPPC in September.

Actual progress on this Task has been minimal, however, awaiting

NWPPC and state agreement on an approach to subbasin planning. The

NWPPC created a budget "placeholder" for subbasin planning in FY02 at

their September 2001 meeting. We anticipate progress on this Task in

FY02.

ODFW	1	Evaluate Subbasin Summaries and other Subbasin Planning 	This Task was dropped due to budget cuts.

related documents related to Oregon, identify data which are

not contained in StreamNet and adjust staff work plans to

capture new data if appropriate and applicable.

WDFW	1	Provide data compilation, conversion, and analytical services in 	No requests for these services were received during this quarter.

support of the subbasin assessment process, the NMFS Viable

Salmon Populations model, and related NWPPC needs.

Objective	2	Task	6.b	Fiscal Year 2001 Fourth Quarter Report	Page 29 of 63

Objective	2	Data Management and Delivery

Provide high quality data management services, with specific emphasis on the creation of regionally consistent data sets and

the timely delivery of data to users in formats that meets their policy, planning, and management needs

Objective	2	Data Management and Delivery

Task	1.	Database Management

Maintain functional database programs at the state and regional levels to make consistent data sets for anadromous fish,

resident fish and to a lesser extent wildlife available through the StreamNet online database system.  At both the regional and

state levels, provide database management and administration necessary for accomplishing StreamNet Objectives, to include: 1)

maintaining regional and state-level StreamNet data sets, 2) processing exchange data into the regional database, 3)

transporting data to the SQL environment, 4) enhancing StreamNet database structures and capabilities, and 5) providing

programming services to project participants to allow for efficient data entry and transfer.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

IDFG	1	After beta testing, implement Fish Information System in IDFG 	1)  We tested and implemented Redd Count and Hatchery Return data

StreamNet and IDFG Fishery Bureau	entry screens to the IDFG Fisheries Information System (FIS).

2)  We migrated historic hatchery return data into the new FIS data

structure.

3)  We implemented a methodology to validate and correct problems in

the hatchery returns and redd count data in the FIS. These errors

included inconsistent RRNs, inability to georeference locations based on

percent of reach, misidentified StreamNet reference numbers, and

assignment of redd counts to an inappropriate trend based on location,

species or time.

4)  We prepared a tool for the analysis and assignment of IDFG redd

count transects to StreamNet trends. A tool to graphically display a

time-series of trends and compare changes in the trends over time was

included.

5)  We started to develop a methodology, data structure and interface for

assignment of multi-stream trends (super trends).

6)  We began development of administrative routines in the FIS to

translate data into StreamNet Data Exchange Format.

7)  We began development of hatchery facilities data entry and

maintenance interfaces.

8)  Monitoring and administration of the joint IDFG/BLM fish data entry

project was accomplished.

9)  We provided administrative and technical support to IDFG related to

the Reference and Collection Permit modules of the FIS.

Objective	2	Task	1.	Fiscal Year 2001 Fourth Quarter Report	Page 30 of 63

10)  We implemented data transfer methodology using Internet e-mail and

XML data structures to send field data to headquarters.  Administrative

routines to automatically process data transfer and update the FIS

database were included.

11)  We continued development of data presentation and analysis tools

for access to the FIS database.

12)  We began planning for migration of historic Idaho Supplementation

Studies data into the FIS, and expansion to all Idaho cooperators.

IDFG	2	Continue development and improvements to Fish Information 	See work component 1.

System.

MFWP 	3	Update existing data sets as described in Task 1 and provide 	Ongoing

data to the regional StreamNet office in DEF.  Provide data as

sub-sets are updated rather than waiting for entire data to be

complete.

ODFW	1	Provide state-level StreamNet database management / 	1)  We started the process of creating DLLs to encapsulate many of our

administration / development.  Enhance StreamNet and ODFW 	commonly used database functions.  This effort is to simplify and better

database structures, interfaces, tools, and capabilities as 	manage the updating of data tables common to many of our databases.

needed.	This approach will also prepare us for future use of IIS [Internet] and SQL

Server services.  This is strictly an alpha testing stage.

2)  We created a small utility to map the fields from an Access database.

The utility populates an Excel spreadsheet with the field name, type, and

description of selected tables.

ODFW	2	Develop custom GIS products and database structures that help 	1)  We filled a request for a single routed western Oregon streams			improve data management and transfer with ODFW staff.	coverage.

2)  We filled a request for distribution and barrier data from NMFS and

also a consultant working on the Willamette Technical Recovery Team.

Region	1	Maintain and manage the StreamNet database so information / 	We performed optimization of the database server and software that were

data are available internally to project participants and externally 	purchased in the third quarter continued.

via Internet.

Region	2	Add data submitted to the StreamNet regional office into the SN 	Routine database maintenance and data cleaning characterized the work

database within ~30 days of receipt from the project partners.	done this quarter.

Objective	2	Task	1.	Fiscal Year 2001 Fourth Quarter Report	Page 31 of 63

Region	3	Assist data-providing agencies with error checking of data sets.	1)  While preparing a presentation for the OFWIM meeting in November

(see Objective 5, Task 4.b), several coding errors were found in the

database related to georeferencing, methodologies, and data

categorization.  These errors were catalogued and brought to the

attention of appropriate personnel so that they may be corrected.

2)  Error checking and coding assistance were performed on Habitat

Restoration data that were received from Montana FWP.

3)  The source of some photographs in the database were

investigated to assure that they are cited correctly.  Photos from

copyrighted sources were identified and cited correctly.

Region	4	Coordinate database compilation between agencies, helping to 	To assist with updates of ocean and inland harvest data, regional

ensure that data submitted are usable, scientifically sound, and 	personnel assisted CRITFC personnel with understanding the new

consistent.	georeferencing conventions in use by StreamNet.

Region	8	Develop metadata for all spatial data sets posted to the SN	1)  We created metadata for Montana resident fish distribution layers

GIS web page.	(18 layers).

2)  We updated metadata for the PNW Reach File (hydrography) and

the Oregon Lahontan cutthroat layer to reflect new information.

Region	11	Based on direction from the Steering Committee, develop 	A new Web server to host the StreamNet web site was investigated

recommendations on the means to move the StreamNet 	and purchased during this quarter that will run newer software such as

database into an SDE-compatible format to provide enhanced 	the latest version of the Internet mapping program ArcIMS, permitting

interactive mapping and to develop necessary structures to 	the StreamNet staff to develop interactive Internet mapping applications.

serve data through SDE.	These applications will take advantage of SDE for speeding access

to the data in the database.

Region	13	Ensure georeferencing of data is accurate and complete.	We reviewed and corrected, where necessary, georeferencing for

stream and supercode referencing information in the database.

WDFW	1	Washington state data maintenance and exchange support 	1)  Brown researched WDFW's Stream and Lakes Fish Database

services, including updated exchange format system, support 	functionality for O'Connor to assess how and when we can use this

for MS Access 97, and support for new data categories and 	resource for StreamNet collections.  Brown created a Paradox tool

fields.	(named dms2dd.fsl) to convert longitude and latitude entries in

Degrees, Minutes and Seconds to Decimal Degrees.

2)  Brown built a prototype tool to address the need for the managers

of three similar-yet-not-identical natural spawner datasets to work

separately while undergoing data integration.  Throughout the quarter,

Brown continued to meet with O'Connor and other WDFW managers to

enhance and finalize this product.

Objective	2	Task	1.	Fiscal Year 2001 Fourth Quarter Report	Page 32 of 63

3)  Per Sikora's request, Kinney gave her more feedback on how he'd

like her to use queries or SQL to convey necessary changes when she

exchanges data.  Based on Kinney's feedback, Sikora also researched

ODBC databases and concluded using SQL queries will serve both

Kinney and Sikora's immediate needs.

4)  Lensegrav documented Age table format issues by analyzing the

StreamNet's existing 8/1/2001 USFWS age records and hatchery returns

links as one first step in exchanging WDFW's age data in a standard form

OR launching discussions about format issues.  Before we advertise

these issues Sikora must assess the remainder of the work that needs to

be done.  Meanwhile Lensegrav further refined his comments by studying

the life-cycle issues.

5)  Per Kinney and a data user's request, Sikora confirmed that missing

trends had not been lost and were legitimately accounted for elsewhere.

Sikora and O'Connor explained the compiler's need to have the flexibility

to change trend numbers and users needed to re-run the logic of their

query to insure they received any new trends.

6)  Hudson reworked some of his data release and mapping programs

after WDFW changed internal locations for GIS datasets and libraries.

Township-based mapping routines for the Priority Habitats and Species

(PHS) reports were improved considerably.

WDFW	2	Update existing data sets as described in Task 1 and provide 	1)  Kinney updated the Access database and posted the current snapshot

data to the regional StreamNet office in Data Exchange Format 	of all StreamNet data (Aug2001 SN mdb) and Sikora immediately started

(DEF).  Provide data as subsets are updated, rather than	using it to check the presentation of data WDFW has sent since the last

waiting for entire data to be complete.	update.

2)  Again, the EndFTs included in StreamNet's Aug2001 Access

database seem to include the measures submitted in WDFW's Oct. 2000

returns submission and not the Dec. 2000 submission.  As of Aug 18, the

true status still need to be resolved.  Kinney is seeing one thing on his

end and Sikora is seeing another on hers.

Objective	2	Task	1.	Fiscal Year 2001 Fourth Quarter Report	Page 33 of 63

Objective	2	Data Management and Delivery

Task	2.	Data Plan

Update and maintain a project data plan that identifies 1) current data holdings at the regional level, 2) data items to be

incorporated in the current contract period and in future years, and 3) expectations for data development and delivery from

participating organizations within the current contract period

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Provide input to the data plan to keep it responsive to subbasin 	We kept Steering Committee apprised of regional discussions, issues and

planning and Framework needs and schedules.	developments concerning subbasin planning. It now appears that

subbasin planning will actually begin the next fiscal year. Data priorities

and schedules were discussed at Steering Committee meetings. They

will be described in the FY02 work statement.

ODFW	1	Work jointly with other participants to modify elements of data 	We investigated rumors of new issues being raised about the fin-clipping

plan or priorities based on needs arising out of sub-basin 	data we submitted to StreamNet. The rumors were unsubstantiated.

planning or other processes that drive Basin data needs

through the amended Fish &Wildlife Program.

WDFW	1	Work jointly with other participants to modify elements of data 	No requests for this assistance were received in FY2001.

plan or priorities based on needs arising out of subbasin

assessments or other processes stemming from the amended

Fish & Wildlife Program.

Objective	2	Data Management and Delivery

Task	3.	Data Exchange Standards

Establish and maintain data exchange standards that ensure consistent format and content of data that originated from the

multiple agencies and data sources in the basin.  Included will be proposed and adopted data exchange formats, metadata and

location look-up tables for specific data items as described under Objective 1.  At the regional level, this Task will provide

technical assistance regarding standard codes and exchange formats for Fish and Wildlife Program and ESA- related projects,

and for applicable tribal data compilation activities.  At the state level, this Task will provide similar technical assistance for state

agency data activities applicable to StreamNet.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Participate in the design, development and maintenance of 	We reviewed DEF issues as they were presented to the Steering

standard codes and data exchange formats. This will occur 	Committee. We evaluated the Harvest DEF issues and determined they

through involvement on the Steering Committee and technical 	should be updated. A report will be sent to the Steering Committee after

work groups.	reviewing PSC, PFMC, ODFW, and WDFW harvest data collection and

reporting protocols, but this will run into the next fiscal year.

Objective	2	Task	3.	Fiscal Year 2001 Fourth Quarter Report	Page 34 of 63

IDFG	1	Participate in the design, development and maintenance of 	We provided review and input to the fish distribution data exchange

standard codes and data exchange formats. This will occur 	format, especially the fish distribution data format.

through involvement on the Steering Committee and technical

work groups. There is no set schedule for this Task, because it

is highly dependent on issues facing the Steering Committee.

Potential new data exchange standards may include juvenile

abundance, genetics, stream habitat, stream temperature and

resident fish releases.

MFWP	1	MFWP StreamNet will participate in the design, development	Still under review.

and maintenance of standard codes and data exchange formats

through involvement on the Steering Committee and technical

work groups.

ODFW	1	Participate in the design, development and maintenance of 	We submitted several requests to Regional StreamNet for new species

standard codes and data exchange formats. This will occur 	codes, and incited a debate over the need for non-fish species codes.

through involvement on the Steering Committee and technical

work groups. There is no set schedule for this Task, because it

is highly dependent on issues facing the Steering Committee.

Potential new data exchange standards may include juvenile

abundance, genetics, stream habitat, stream temperature and

resident fish releases.

WDFW	1	Compile and review the specific criteria used by participating 	O'Connor helped lead discussion at the August Steering Committee

agencies in describing fish distribution, use, or extent 	meetings to iron out the last concerns about the proposed new approach

information, in order to find and adopt common standards	to both fish surveys (sightings data) and generalized fish distribution data

among data providers.	(presence and use). While progress was made, some points that

remained unclear to representatives from other states delayed

acceptance of the new concepts until the next meeting (FY2002, probably

October). Washington data will be ready to exchange once the new

approach is finalized, as long as progress continues and doesn't back-

track in an unexpected direction.

WDFW	2	Analyze Hatchery Returns exchange format and explore 	1)  After considering the other agencies' conflicting responses on

whether a second table (covering Spawning and Disposition 	WDFW's initial hatchery returns format proposal, O'Connor drafted a new

data fields) is needed to more accurately meet the needs of the 	proposal.  Internally, Sikora reviewed the proposal and O'Connor and

Artificial Production Committee.	Sikora clarified more expectations in how separate fields and the two

tables would relate to each other.  Woodard also reviewed the proposal

and met with O'Connor and Sikora to discuss the issues with WDFW's

data.  The discussion revealed that capturing some fields would sacrifice

others.

Objective	2	Task	3.	Fiscal Year 2001 Fourth Quarter Report	Page 35 of 63

2)  O'Connor scheduled contacts with the IDFG, USFWS, and ODFW

representatives to learn their feelings on the necessity of each disposition

field. Initial responses were very helpful, but scheduling difficulties

prevented working with the IDFG representative until at least October.

As a result, the new hatchery returns DEF proposal will not be circulated

for final approval until November 2001 at the earliest.

WDFW	3	Finalize and distribute for adoption an exchange format for	Work on an exchange format has been postponed until WDFW can

State Risk status (stock status) to provide information on	update our SaSI database, both tabular and spatial components.

sensitive salmonid stocks.	See Objective 1 Task 1.i.

WDFW	4	Move toward complete adoption of LLIDs as the standard	1)  In late July Lensegrav prepared a list of potentially flawed stream

stream referencing code by reviewing and completing the	names or routing in WDFW's GIS hydro layer for Hudson to review and

RRN-to-LLID conversion, addressing supercode issues, and	correct as warranted.  Lensegrav also established contact with the GNIS

assuring that LLIDs are assigned to all locations where	manager (Jennifer Runyon) to resolve questions about the confusing

StreamNet data exist.	Plumbago Cr. area.

2)  Sikora gave StreamNet the appropriate location codes to legalize the

LocType 5 code assignments for the Washington release and harvest

data compiled by PSFMC.  Many of these codes were based on

O'Connor's digitized points for select marine areas.

3)  After receipt of the work proposed in the FY2001 Carryover Proposal,

Sikora also researched the scope of addressing the existing LocType

98 or 99 trends.

WDFW	5	Provide metadata for tabular and spatial datasets according to 	To alleviate concerns that the metaform.doc sent with all exchanges

guidelines adopted by the Steering Committee.	should not be mistaken as formal metadata, Sikora posed new potential

names and Kinney described his preferred naming convention and how

it addressed his needs.

WDFW	6	Construct a new data compilation and conversion system to 	See Objective 2 Task 1 Work Component 1 for details.

provide data in MS Access according to the most recently

adopted exchange format version. Begin exchanging data in MS

Access form by winter, 2001.

Objective	2	Task	3.	Fiscal Year 2001 Fourth Quarter Report	Page 36 of 63

Objective	2	Data Management and Delivery

Task	4.	GIS Data System

Establish and implement procedures for coordination of StreamNet-related spatial data activities among participating

organizations, to include regular meetings and or other communication links among participating GIS specialists. Designate and

maintain metadata format for spatial data to be used by StreamNet participants. Prepare map products in hardcopy and/or

electronic format for use in Program-related aquatic resource policy, planning, and management.  Provide for distribution of

spatial data in GIS and tabular format and as GIS products.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

IDFG	1	Maintain and enhance a geographic information system (GIS) 	1)  We enhanced the Fish Tools ArcView application to project UTM

related to regional and state-level StreamNet goals and 	coordinates to ITM (the standard projection in use by Idaho state

Objectives.	agencies, including IDFG).

2)  We loaded the Fish Tools ArcView application onto laptop computers

for use by IDFG biologists in the field.

IDFG	2	Prepare data and map products from StreamNet data on request	We started making maps for subbasin summaries (see work component

1.6a.1)

ODFW	2	Maintain and enhance a geographic information system (GIS) 	Ongoing maintenance continued.  We upgraded both Desktop ArcGIS

related to regional StreamNet goals and Objectives (general 	and Workstation ArcInfo from version 8.02 to 8.1 and installed ArcGIS

maintenance, metadata development and maintenance, planning 	patch.

and coordination activities, etc.).

ODFW	3	Prepare spatial data and map products in hardcopy and/or 	We filled request for Willamette Basin maps of Winter Steelhead and

electronic format for use in Program-related aquatic resource 	Spring Chinook distribution in PDF format for policy discussion purposes.

policy, planning, and management.

Region	1	Maintain and enhance a geographic information system (GIS) 	We continued maintaining the StreamNet GIS system.

related to regional StreamNet goals and Objectives.

Region	2	Prepare GIS data and map products from StreamNet data.	We prepared GIS data and map products from StreamNet data, as

needed.  We received and responded to 35 requests from the public

and prepared GIS data, maps, and other products.  Requests were from

a variety of sources including private citizens, environmental consulting

firms, government agencies, educators, and students.  We prepared more

detailed map products for requests from the NWPPC and associates for

use in reports, etc. This included a continued project to develop maps

that illustrate the number and proportion of adipose clipped fish that were

released from hatcheries in the Columbia Basin in year 2000, and a

request from council staff to determine a complete list of mail zip code

districts by NWPPC subbasin.

Objective	2	Task	4.	Fiscal Year 2001 Fourth Quarter Report	Page 37 of 63

Region	3	Integrate the functioning of the GIS system with the StreamNet 	1)  We completed the task to determine tributary flow information for all

fisheries and habitat database, in support of the query system.  	streams in our database, establishing a complete stream flow network at

Create cross tables and queriable maps used via the StreamNet 	the 1:100,000 scale.

web interface.	2)  We added 323 new maps to the map catalog.  This involved

determining all relevant information needed for each map to enable their

selection by the query system and formatting the maps into web-ready

images.

Region	4	Direct users to other GIS resources when requests exceed	We directed users to other GIS resources when requests exceeded

StreamNet capability	StreamNet capability.

WDFW	1	Create approved reference documents for all exchanged	Burns began to compile metadata for the WDFW Bull Trout presence/use

spatial data sets. (See also Task 2.3, work component 5)	spatial data layer, starting with a PSMFC example involving a region wide

coho layer. Hudson assisted on the parts of the metadata document that

required technical GIS expertise.

Objective	2	Data Management and Delivery

Task	5	StreamNet Internet Site

Continue to maintain and enhance the existing client-server system to provide access to StreamNet data products through the

Internet.  The StreamNet home page will continue to be recognized as the project's primary data delivery vehicle.  Priority will be

given to incorporating data developed through Objective 1 and providing access to reference materials secured through

Objective 3.  Appropriate training on the use of the system will be provided through a combination of on-line help and in-person

training sessions.

Objective	2	Data Management and Delivery	Task   5   StreamNet Internet Site

Task	5.a	Maintain the StreamNet Client Server system

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

Region	1	Maintain, upgrade as needed, and administer the StreamNet	A new Web server to host the StreamNet web site was investigated and

web servers.	purchased during this quarter, but not yet reconfigured or installed on the

PSMFC network.   In addition to faster processing, the new server will run

newer software that was not possible to run on the old server, such as

ColdFusion Server and the latest version of the Internet mapping program

ArcIMS.  These tools will eventually permit the StreamNet staff to revamp

and enhance the web query system with new programmed capabilities

such as returning  XML output and allowing users to overlay various data

categories on a single map.  The new server will go online in January,

2002.

Objective	2	Task	5.a	Fiscal Year 2001 Fourth Quarter Report	Page 38 of 63

Objective	2	Data Management and Delivery	Task   5   StreamNet Internet Site

Task	5.b	Enhance and improve the StreamNet website

Maintain and enhance components of the StreamNet home page and incorporate new features that complement existing

Components

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Work with subbasin planners to identify modifications and new 	Work continued on developing web pages, but this is lower on the list due

uses which will make the website more useful to them	to lack of funding and staff time to accomplish Objectives.

CRITFC	2	Identify changes and new features which will improve delivery 	We continued to work with improvements made throughout the year.

of Library services	We identified the need for more electronic copies of documents,

especially those with fewer than 5 pages.

CRITFC	3	Work with regional staff to implement changes identified above.	1)  We continued working with Karen McGill on website coordination.

2)  We purchased HomeSite software to ease transitions.

ODFW	1	Recommend and/or take part in review of new products and 	We continued with modifications to various forms, code modules, etc.

features.  Provide feedback on content, suitability, navigability 	as part of the 24k Project Data Capture Tool development process. We

and data currency issues.	Conceptualized a beta testing and a training approach. We initiated

testing with real data compiled for the Clackamas basin.  We worked

toward building "Event Mapper" type of functionality. We worked with

issues related to the management of barrier and dam identifiers. We

updated the User Guide to reflect the most recent changes to the

DCT.  We loaded everything onto a laptop for training purposes and

conducted a 2-day training session on how to install and use the DCT

with 24K staff. After initial field use and testing, we finalized version 1.1

and summarized changes that were made from version 1.0 to version 1.1.

ODFW	2	Provide a link from the StreamNet website to available Columbia 	We completed and submitted informational text describing the link from

River fisheries information (including Columbia River Compact 	the StreamNet website to the CRM website that updates Columbia River

Action Notices, In-Season Updates, and Joint Columbia River 	fisheries and stock status information.  This text would be included with

Management Staff Reports and possibly in-season catch 	the link on the StreamNet Home Page to let users know what information

estimates) along with informational text to describe each link.	is on this website.

Region	2	Continue to review the StreamNet website for clarity, 	1)  After a number of months in preparation, the StreamNet website was

organization and ease of use.  Recommend and implement 	reorganized and given a new format.  The completely revamped site was

changes to maximize utility for people accessing the site to 	made functional at the end of the quarter.  Emphasis in the new site was

obtain information.  Changes will include updating, replacing,	placed on improved organization and ease of use for people seeking

and retirement of existing web pages, and archiving of all	information.  All of the new pages were reviewed for content, accuracy

existing pages.	and function of live links.  Review of the site was requested of Steering

Committee members prior to making the new site available.

Objective	2	Task	5.b	Fiscal Year 2001 Fourth Quarter Report	Page 39 of 63

2)  In FY 2000, it was brought to our attention by a WDFW biologist that

several of the images on our web site may be copyrighted, and that the

attribution to BPA that we provided was incorrect.  During this quarter we

obtained the book mentioned and confirmed that the several images are

not public domain and were being attributed incorrectly to BPA.  We

therefore removed the images from the StreamNet web site.  In addition,

we contacted several people who had asked for permission to use

those images and informed them that the images were copyrighted.

Region	3	Plan to enhance the website content by adding additional kinds 	1)  During the quarter, Regional personnel organized several independent

of information that will support the Fish and Wildlife Program.  	water temperature data sets and provided links to them from the

Develop concept for increasing information by coordinating with 	StreamNet web site.  These data sets had been available from StreamNet

regional data users	but were not advertised.  Making these data sets available is the first step

toward an infrastructure for making available independent data sets via

the StreamNet web site.

2)  We begin compiling a list of all BPA-funded projects that generate

resident fish data, per a request from the NW Power Planning Council.

During the next fiscal year we will contact project sponsors to determine

what resident fish data they may be generating, in what format the data

are stored, and means to obtain and make the data available.

3)  A location for 'Independent Data Sets' was added to the On-line data

page as a location to deliver these kinds of data.

Region	7	Develop an on-line mapping application which may be used	We created a basic ArcIMS application with the assistance of a

over the Internet by the public to view StreamNet data "layers" 	contractor, Alsea Geospatial.  The application allows the display

through interactive maps.  This application will allow users to 	and query of StreamNet data through a map interface over the

view and query StreamNet data spatially, generate reports and 	internet to users without GIS software/expertise.  We found that

tabular or GIS data based on spatial queries, and create their 	our existing hardware was not adequate to serve this application

own custom maps.	efficiently so have decided to delay further development and

implementation of internet mapping applications until a new web

server with greater speed and capacity is available and running

(est. November 2001).

WDFW	1	Take part in review of new products and features. Provide 	No formal feedback was provided this quarter. The "new look" Web site

feedback on content, suitability, navigability and data currency 	was announced ready for final review in late September, but staff review

issues, especially issues related to providing static or dynamic 	was not completed during this time period.

map capabilities.

Objective	2	Task	5.b	Fiscal Year 2001 Fourth Quarter Report	Page 40 of 63

Objective	2	Data Management and Delivery

Task	6.	1:100,000-scale Hydrography

Maintain the 1:100,000-scale PNW hydrography for purposes of attaching StreamNet data.  Coordinate with efforts to prepare a

National Hydrographic Dataset (NHD). Develop a standardized method for incorporating lake hydrography and attribute

information.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

IDFG	1	Maintain the Idaho portion of the 1:100,000-scale PNW 	The ‘Distribution Fish Tools’ ArcView application was distributed to a few

hydrography for purposes of attaching StreamNet data.	IDFG biologists to allow them to tag streams that need routing and

incorporate them into the Fish Information System and StreamNet.

MFWP	1	Support the efforts of the NHD and convert Montana 	Ongoing

hydrography to NHD upon receipt.

MFWP	2	Enhance layer with LLID and stream level routing.	Completed

MFWP	3	Coordinate with NRIS in the QA/QC of the NHD for Montana 	Synchronization of the lakes layer with MRIS lakes database is ongoing.

including the development of a lakes layer (funding provided

by the BOR for lakes).

ODFW	1	Continue to maintain the Oregon portion of the 1:100,000-scale 	We worked with Regional StreamNet staff to confirm some necessary

PNW hydrography for purposes of attaching StreamNet data	changes to the 100k hydrography in the Silver Creek and Malheur

and for use in ODFW information management systems. Submit	basins.

all modified PNW hydrography to PSMFC for inclusion in the

regional PNW hydrography data.

ODFW	2	Participate in technical and policy discussions concerning 	We continued to address issues surrounding inconsistencies between

efforts and activities that relate to or impact the PNW 	the states in StreamNet's distribution data.

hydrography (NHD, OR/WA state framework physical data

model, clearinghouse issues, data dictionary development, etc.)

ODFW	3	Provide technical advice on hydrology routing and other issues 	We provided technical support to ODFW staff working with the routed

including those related to working with higher resolution 	hydrography.

hydrography.

Region	1	Continue to maintain the regional 1:100,000-scale PNW 	1)  Routine maintenance and management of the hydrography

hydrography.							continued.

Objective	2	Task	6.	Fiscal Year 2001 Fourth Quarter Report	Page 41 of 63

2)  For each LLID in the 1:100,000 scale hydrography, StreamNet lists the

water body into which the stream flows.  Several errors were found in this

list during the quarter, which resulted in circular references.  These

problems were corrected by regional staff. Also this quarter, regional staff

began identifying why a fairly large number of LLIDs have no downstream

link listed.  Work began on these LLIDs to identify the stream, ocean, or

lake that they flow into; a specific code was added for streams that run

subsurface before entering another water body.

3)  We participated as a contributor to the Hydro Framework Review

process to develop a national hydrography standard format.  We

commented on the initial proposal to do this.

Region	3	Update and serve a regional web version of the 1:100,000-scale	We performed a complete update of all 1:100,000 scale PNW

PNW hydrographic set from the StreamNet website.	Hydrography files to the StreamNet web site.  This incorporated

recent significant revisions to the hydrography data in Idaho and

Montana, and a series of smaller changes in Oregon.  We updated

online hydrography documentation to reflect recent changes and

added an online edit log to allow users to view changes that have

been made to the hydrography.

Region	7	Develop a complete cross-reference application between all 	We completed a draft version of a cross reference application for

streams in the PNW Reach Files and the NHD (National 	transferring data between the PNW LLID-based stream referencing

Hydrography Dataset)  for Washington, Oregon, and Idaho to 	system and the NHD reach-based referencing system and related GIS

allow collection and distribution of stream-based data in both 	files. Work this quarter consisted of completing the last 30% of the rebuild

LLID and NHD formats.	of LLID routes onto the NHD linework.  A database application was then

programmed to use this cross reference to convert data between the two

systems.  Finally, complete help documentation and metadata were

written for the project and a web site was designed to serve these

products to the public.  This was an EPA funded project.  The GIS

Specialist worked on this half-time during Quarter 4.  This was possible

because the StreamNet contract does not cover a full year for the GIS

Specialist.

WDFW	1	Complete Steering Committee discussion about lake attributes 	Other participants are not ready to standardize lake attributes at this

useful to share in a regional database; determine support for a 	time.

new data format.

WDFW	2	Compile, standardize, and exchange point, line, and polygon 	Further lakes work was delayed until hatchery facilities and hatchery

information for lakes stocked with fish that appear at 100K (or 	returns data could be finalized and exchanged, based on StreamNet

higher) resolution.	Project-wide priorities set in the May 31-June 1 meeting.

Objective	2	Task	6.	Fiscal Year 2001 Fourth Quarter Report	Page 42 of 63

WDFW	3	Participate in technical and policy discussions concerning 	Hudson performed preliminary assessment of the NHD for the Pacific

adoption of the NHD 100K framework for the Northwest.	Northwest with respect to transfer of our LLID-based hydro system to a

Review Washington state NHD datasets if funding is available.	system supporting the NHD model. Initial findings are very encouraging,

and Hudson notified David Graves (PSMFC) that he will support

conversion of WDFW's hydro to an NHD model when NHD 24K linework

is ready for Washington state. 100K linework may be converted if delivery

problems arise in the state's Hydro Framework project.

WDFW	4	Maintain Washington 100K HUCs by performing error fixes, 	Hudson revisited cleaning and routing of 24K stream linework in WRIAs

addressing cross-border and cross-HUC incompatibilities, and 	24-30 (lower Columbia River) by using the newly-available 10-meter

related duties.	Digital Elevation Model (DEM) data as a back layer. This procedure

seems to facilitate decisions for determining routes and connecting

hanging streams, and may be a useful technique to apply to the 100K

hydrography before conversion to NHD.

WDFW	5	Provide technical advice on hydrology routing and other issues 	Hudson reviewed and wrote a brief assessment of the Bureau of Land

related to working with higher resolution hydrography as 	Management (BLM) criteria for densifying or simplifying hydro linework,

needed.	which they applied to the 24K hydrography on BLM lands.

Objective	2	Data Management and Delivery

Task	7.	Data Requests

Receive and respond to requests for data, source materials, and custom products.  Response to requests will be honored

within the limits of available resources, with priority given to information requests having direct relevance to the Fish and

Wildlife Program.  Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural

resource management activities.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	See Tasks 1.1h, 1.6, and Objective 3	We answered requests for materials and information (see Objective 3).

IDFG	1	Continue to respond to requests for information from StreamNet 	1)  We entered previous data request information into a new Data

database, including requests for fishery information that comes 	Request tracking database.

into the Idaho Conservation Data Center (Natural Heritage 	2)  We completed 26 requests for location specific fish species lists

Program), other IDFG programs and personnel, and outside 	and other data requests.

agencies and consultants.

ODFW	1	As requested, consistent with other deliverables in this contract,	A total of 6 data, 32 document, 5 map, and 20 'other' requests were

receive and respond to requests for data, source materials, 	answered during this quarter. A detailed list by requester and request

technical training, and custom products.	type can be made available upon request.  Also, 3,168 data downloads

were made from the ODFW FTP site during this quarter.

Objective	2	Task	7.	Fiscal Year 2001 Fourth Quarter Report	Page 43 of 63

Region	1	Respond within one day whenever possible to all user	As in the third quarter, we responded to 62 requests from users during

requests received via email, phone, or other medium.  Typical	this quarter.  Assistance was given to users from NWPPC, USFWS,

requests received include help using the query system,	NMFS, NMFS Northwest Fisheries Science Center, the USFS San Dimas

complex data requests not easily done with the query system,	research laboratory, USGS-BRD's Cook Lab, EPA, ODFW, CRITFC,

and requests for GIS coverages and maps.	Yakama Nation, the interagency PTAGIS and RecFIN systems housed

at PSMFC, several universities in the US and Canada, Clackamas

County Oregon, Chelan County PUD, several watershed councils, Gulf

States Marine Fisheries Commission, nonprofit organizations, private

consultants, conservation groups, and the general public.  User request

topics were varied and included help with the on-line query system, map

requests, advice on initiating a GIS program, general fisheries and fish

biology questions, error reports, help finding data, reports of dead internet

links on the StreamNet web site, and suggestions for new Internet links.

Fairly extensive help was given to several users of the water temperature

database that was compiled by PSMFC and is now housed on the

StreamNet web site.  One user was searching for the original reference

for the NWPPC's list of protected stream reaches.

Region	2	Fill requests for data not available via the web in an expeditious 	The project updated the data in the compilation of adipose fin clipping

manner, with highest priority for people working for the NPPC's 	data that was provided to the NW Power Planning Council. The CBFWA

Fish and Wildlife Program.  Requests from outside the Fish and 	Anadromous Fish Committee prepared a response to the Council request

Wildlife Program or participating agencies will be addressed on 	for additional information, and StreamNet put together updated maps and

an 'as possible' basis.	data.  These materials were prepared for presentation at the October

Council meeting.

WDFW	1	Generate maps, data reports, and electronic copies of datasets 	1)  Sikora provided WDFW release data citations to Chris Thomas.

as requested.	2)  Hudson performed extensive work on his menu system for accessing

spatial data from the WDFW fish and hydro datasets.  Base layer choices

with improvements include WRIA, WDFW district, and Public Land

Sector.  Place names, stream names (24K), and user-defined areas were

all added as options.  Bull trout mappers have the choice of mapping an

entire WRIA or just the part of the WRIA where data exist (helpful for

large WRIAs with extremely localized fish data). Release options now

include event tables or line layers, and an option to generate an 8.5 by

11 size user-customizable map is now under construction.

3)  The newly-completed statewide "Bull Trout 2001" layer generated a

significant number of data requests, particularly for digital copies of the

data (Arc export files of layers; event tables in INFO, Excel or MS

Access).

Objective	2	Task	7.	Fiscal Year 2001 Fourth Quarter Report	Page 44 of 63

4)  O'Connor and one of his PSC-funded staff (Brodie Cox) spent

significant time responding to a request from NWPPC staffers concerning

numbers of marked fish released from Washington Columbia Basin

hatcheries in 2000. Lessons learned during this exercise include the

importance of clear and precise communication of needs, the futility of

expecting new data items to be automatically incorporated into

under funded state data systems, and the importance of involving

associated CBFWA representatives in a review cycle prior to submitting

the results of such a large-scale data compilation to Power Planning

Council staff.

5)  Important data requests are reported under the task number pertinent

to each dataset when requests reveal data issues or inspire different

compiling approaches. Upon request, the details for each data request is

also available from a detailed tracking file (internally stored on WDFW’s

server at S:\Fish\Groups\BDS\Streamnt\Requests\Datareq.db).

WDFW	2	Provide PRIORITY data support for subbasin assessments and 	No requests for this assistance were received during the fourth

other new elements of the NWPPC Fish & Wildlife Program.	quarter of FY2001.

Objective	2	Task	7.	Fiscal Year 2001 Fourth Quarter Report	Page 45 of 63

Objective	3	Library / Reference Services

Provide a full service regional library for fish (and to some degree wildlife) literature (published and gray), including

documentation of all data in the StreamNet database.

Objective	3	Library / Reference Services

Task	1.	Collection Development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document

data source materials, Fish and Wildlife Program activities and reports, and other gray literature for access by regional

scientists, agencies, interested parties, and other libraries.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Coordinate source material submissions for data compiled under 	We received submissions from Project members.  These will be

Objective 1. Develop standards for document submissions	cataloged in the First Quarter of FY2002.

CRITFC	2	Collect and catalog documents prepared by contractors 	Library staff continued to catalog BPA contractor documents.  Several

(including final products published by BPA and draft documents 	gaps were identified and filled in with copies received from BPA.  Other

suitable for public release) under the Fish and Wildlife Program. 	gaps are being left open in hard copy as the Publications Dept. identified

Work with Publications distribution for better publication 	those titles as electronic only.  If we want hard copy, we will have to print

notification and deposit system.	out the documents from PDF files on the Web.  A couple of these

documents are over 100 pages.

CRITFC	3	Collect and catalog documents from the Council's Fish and 	We continued cataloging ephemeral (gray & black) literature.

Wildlife Program-related collection.

CRITFC	4	Collect and catalog additional books, journals, agency reports, 	Over 529 records were added to the online catalog.  At least 110 of these

gray literature, research reports, and documents that are 	are periodical/newsletter titles that we did not previously have cataloged.

applicable to management of the region's aquatic resources.	Over 690 records were updated/upgraded from minimal level cataloging.

ODFW	1	Provide originals/copies of all documents and reports	Referencing of new data holdings continued.  We prepared a StreamNet

referenced in the compilation of new StreamNet data holdings,	Library submission of new references used to update trends and create

but not already housed in the StreamNet Library.	new trends in accordance with the DEF protocol. Of the references to be

submitted 12 were new and 5 were updates of existing materials. This

will be ready for submission in early October.

ODFW	2	Update the set of historic (pre-1975) Oregon Fish Commission 	This task was dropped due to budget cuts and the fact that the

and Game Commission reports and provide to the StreamNet 	StreamNet Library is running out of physical space to hold new materials

library as available.	not linked to StreamNet trends.

Objective	3	Task	1.	Fiscal Year 2001 Fourth Quarter Report	Page 46 of 63

ODFW	3	Update library bibliography of ODFW, Fish Commission, and 	We continued to perform numerous maintenance, update and correction

Game Commission reports with historic and current publications 	activities to the InMagic bibliography, however the bibliography is not yet

and make the bibliography available for reference via StreamNet 	ready for online access because the database manager (who will develop

and ODFW websites.	this capability) continues to focus on higher priority tasks that went

undone prior to his hiring.

WDFW	1	WDFW StreamNet will continue to collect documents used as 	Burns continued to update her contacts database for spatial distribution

source materials for data in Objectives 1 and 2. Documents will 	data references.

be assigned reference numbers and forwarded to the

StreamNet library as per established SN guidelines.

Objective	3	Library / Reference Services

Task	2.	Provide Access to Collection

Provide user access to the materials described in Task 3.1 by providing facilities for storage of paper and electronic copies of

documents, an online catalog of all documents in collections, and staff to answer location questions and respond to requests.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Maintain an appropriate facility for the storage and public use of 	Negotiations with Ashforth Pacific and the Commission continue for the

the physical collection.	Library growth.  Key areas of needed space are client seating, map

reference and more shelving for the growing collection.

CRITFC	2	Catalog, organize and maintain the collection for appropriate 	We have been shifting materials for necessary space in a few

on-site use.	areas.  Backlog materials are being cataloged for inclusion in the

regular collection.  StreamNet materials continue to be integrated

and records combined to limit confusion when searching for

materials.

CRITFC	3	Provide access to the StreamNet Library Catalog.	In-house computer terminals and electronic media were maintained.  We

continue to develop web access to the catalog.  We began working on

the ability to add images to the online records.  Began working on the ability to add images to the online records.

CRITFC	4	Develop a schedule for regular updates of the reference table.	We began working on separate database for the StreamNet reference

documents.  Import and export functions need to be fine-tuned for easier

information sharing between the Access/SQL and InMagic databases.

ODFW	1	Enhance, maintain, and update ODFW Library software and 	1)  No effort was made this quarter regarding the library software because

procedures to ensure adequate tracking of information requests,	the Database Manager continues to focus on higher priority tasks that

key word searches, and easy comparison to the StreamNet 	went undone prior to his hiring.

Library holdings.	2)  In an effort to refurbish the space that has been provided to the library,

we did a preliminary web search for library improvement grants and

talked to Tim Kopf, the Information and Education Coordinator for the

Benton Co. Conservation District about funding sources. Several grant

requests will be mailed in the coming months on behalf of the library.

Objective	3	Task	2.	Fiscal Year 2001 Fourth Quarter Report	Page 47 of 63

Objective	3	Library / Reference Services

Task	3.	Improve Electronic Access

Enhance the online capabilities of the StreamNet Library, including catalog access via the internet and an electronic archive of

key Columbia Basin documents.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Manage and maintain the Library catalog server	We moved the server behind a firewall for security purposes, and

continued to work with Regional staff for synchronicity.

Objective	3	Library / Reference Services

Task	4.	Library Services

Manage the StreamNet Library and provide library services to the StreamNet user community and the general public.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	2	Assist users to locate information by providing reference, 	We filled over 150 requests for clients.   These requests included the

referral, and computer based search services.	following types:

Locating materials for Administrative records.

Developing bibliographies for summer chinook and steelhead.

Developing bibliographies for the Lower Columbia and Willamette

subbasins and their tributaries.

CRITFC	3	Provide document delivery services, including inter-library 	We lent 30 items to other libraries.  These included libraries in

lending and borrowing.	Mexico, California, and the National Agriculture Library.

ODFW	1	Respond to requests for ODFW documents and other source 	We provided 335 hardcopy documents and 8 electronic documents to

materials.	37 individual users during the quarter.

Objective	3	Library / Reference Services

Task	5.	Inter-library Coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other

collections that will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	3	Coordinate with users, agencies, and regional libraries to 	We completed the addition of holdings records to online union list on

improve services and avoid unnecessary duplication.  Perform	OCLC.  This will enable other libraries to know at a glance exactly

a needs assessment for the Library.	what we have in our periodical literature.

CRITFC	4	Facilitate communications between subject related library 	The Librarian was accepted as a presenter at the OFWIM meeting in

service providers. Coordinate concurrent Library Needs 		November 2001.

workshop with Data Needs workshop (Task 4.7).

Objective	3	Task	5.	Fiscal Year 2001 Fourth Quarter Report	Page 48 of 63

CRITFC	5	Maintain presence in related Library groups (i.e. IAMSLIC, NRIC) 	1)  The StreamNet Librarian joined OFWIM.

to provide access to knowledge on Best Management Practices 	2)  The library renewed membership in NRIC.

for libraries and current awareness of subject-related materials.	3)  The Librarian attended the annual NRIC conference.

ODFW	1	Coordinate with the Oregon State Library system to enhance 	1)  We distributed flyers to users in remote areas describing how they can

access to published periodicals, journals, and other documents 	sign up for electronic access to the State Library to direct requests for

for StreamNet users.	published articles.

2)  We signed 10 users up for access to the State Library during

in-person visits to the ODFW Library.

Objective	3	Task	5.	Fiscal Year 2001 Fourth Quarter Report	Page 49 of 63

Objective	4	Services to Fish and Wildlife Program Activities

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife Program projects

Objective	4	Services to Fish and Wildlife

Task	1	Monitoring and Evaluation

Assist in the development of products that contribute to the monitoring and evaluating (M&E) of Fish and Wildlife Program

effectiveness.  Specific area of involvement will include:

Objective	4	Services to Fish and Wildlife 	Task   1   Monitoring and Evaluation

Task	1.a	M&E Participation

Participate in Program-related monitoring and evaluation work groups

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Assist basin wide efforts to develop an R/M/E plan consistent 	We conducted a one-day workshop with ODFW, NWPPC, NMFS, tribal,

with the regional Framework	City of Portland staffs to explore the feasibility of coordinating OWEB

and EDT subbasin assessment methods. This appeared feasible after the

first workshop and follow-up meetings were scheduled to address specific

issues. When the methods are coordinated, we will attempt to extend

the OWEB habitat monitoring approach to fish and wildlife populations

during the subbasin planning process.

IDFG	1	Participate in discussions concerning data needs to support 	We participated in discussions at Steering Committee meetings.

processes adopted by the amended Fish & Wildlife Program for

Monitoring and Evaluation.

Objective	4	Services to Fish and Wildlife 	Task   1   Monitoring and Evaluation

Task	1.b	Evaluation

Periodically re-evaluate the StreamNet data plan to ensure consistency with M&E needs

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Keep Steering Committee apprised of regional R/M/E plans and 	Presentations are made regularly to the Steering Committee when

needs	new information or action occurs at the regional level.

Objective	4	Task	1.b	Fiscal Year 2001 Fourth Quarter Report	Page 50 of 63

Objective	4	Services to Fish and Wildlife 	Task   1   Monitoring and Evaluation

Task	1.c	M & E Reporting

Prepare reports and data products that illustrate key M&E topics

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Assist Steering Committee to identify useful M&E products	No activity this quarter. Emphasis was placed on updating key data

that StreamNet can produce at regular intervals	sets.

ODFW	1	No work planned but we are willing to adjust work plans to 	This Task was dropped due to budget cuts.

address amended Fish and Wildlife Program needs.

Objective	4	Services to Fish and Wildlife

Task	2.	Watershed Projects

Provide data and data services to Fish and Wildlife Program-sponsored watershed planning and assessment projects

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Assist subbasin planners to develop monitoring and evaluation 	Subbasin planning activities have yet to begin. No activity this

activities for watershed projects that will integrate smoothly with	quarter.

StreamNet databases (cost sharing)

Objective	4	Services to Fish and Wildlife

Task	3.	Stock Assessment Projects

Provide technical assistance to the Upper Columbia Basin and Upper Snake River Basin resident fish stock assessment projects,

including a) identification of regionally consistent data exchange standards and b) Internet access to project data and other

information. Specific actions will be defined in consultation with stock assessment project managers

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

ODFW	1	Provide assistance as needed.	This Task was dropped due to budget cuts.

WDFW	1	Provide spatial, tabular data standardization and exchange 	JSAP consultation need was limited this fiscal year due to turnover in

consultation and assistance to participants in the BPA-funded 	project leadership at Kalispel Tribe and a subsequent delay in scheduling

Joint Stock Assessment Project (JSAP).	steering committee meetings.  O'Connor provided copies of data records

from the WDFW Stream Lake and Fish Database (SLFD) pertinent to the

Blocked Area of NE Washington to Jim Lemieux, project data manager.

O'Connor also obtained copies of contemporary sampling data formats

and location coding protocols from the WDFW JSAP staff to review for

conversion to StreamNet exchange format in 2002.

Objective	4	Task	3.	Fiscal Year 2001 Fourth Quarter Report	Page 51 of 63

Objective	4	Services to Fish and Wildlife

Task	4.	Service to Other Fish and Wildlife Program Projects and Activities

In consultation with CBFWA, the Council, and BPA StreamNet will provide technical assistance and data services to select

Program projects

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Collaborate with CBFWA, NPPC, and other fish and wildlife 	We discussed possible StreamNet services with NWPPC and NMFS

programs in the Columbia Basin to identify and provide technical 	staffs.  Although specific services are not yet fully defined, NWPPC staff

and other services to the Fish and Wildlife Program	are expecting StreamNet to provide fishery information to the subbasin

assessment process and provide other as yet undefined services to

subbasin planners.  I feel the project has particular strengths in the areas

of 1) providing existing information, 2) providing data management tools

and assistance to planners, and 3) capturing new information developed

during the new round of subbasin planning.

IDFG	1	Provide technical and other services to other FWP projects 	We worked with Idaho Supplementation Studies project to implement the

occurring in IDFG. 	Juvenile Trapping and Redd Count modules of the Fish Information

System.  IDFG biologists used these applications to enter data and

submit to our database. See work component 2.1.1 for details.

ODFW	1	Provide technical assistance and data services to F&W Program 	No other technical assistance was requested this quarter.

projects as needed and adjust work plan priorities accordingly.

ODFW	2	Produce pre- and post-season harvest and stock status reports 	1)  We continued progress on the Status Report on Columbia River Fish

for Columbia River fish runs and fisheries and make reports 	Runs and Fisheries, 1938-2000.

available via either via the StreamNet site directly or via the 	2)  We continued progress on the 2000 Lower Columbia River and Buoy

ODFW Columbia River Management site with a link from 	10 Recreational Fisheries report.

StreamNet.	3)  We completed 1 Joint Staff Report, 10, 10 Columbia River Fact

Sheets, and 16 Columbia River Action Notices.

4)  All reports, Fact Sheets, and Action Notices completed during this

report period were posted on the ODFW/CRM website.

ODFW	3	Draft a summary of real-time data services that can be provided 	We completed and submitted a document describing the new format for

as well as a description of how these services differ from 	our website to better incorporate real-time data for use by fishery

current data services provided in the Basin.	managers throughout the region.  The document describes what will be

included in the website.  The website will be expanded to include

additional data of interest to regional fishery managers that is not

included on the current ODFW/CRM website.

Objective	4	Task	4.	Fiscal Year 2001 Fourth Quarter Report	Page 52 of 63

Region	1	Work with Fish and Wildlife Program projects throughout the 	1)  BPA is interested in capturing the information generated by the fish

basin to assist with providing information needed by the projects	and wildlife projects it funds.  The Regional Fisheries Biologist discussed

and acquiring and distributing information generated by the 	with BPA personnel the utility, strengths, and weaknesses of GIS and

projects.	GPS in determining the locations of work sites, so that data may

eventually be captured in StreamNet or other regional databases.

2)  Work continued on developing data on the mass adipose marking of

hatchery salmon and steelhead to meet a data request from the Power

Planning Council.  Errors in the preliminary data were identified and

corrected.  A presentation of the updated adipose clipping data was

prepared for delivery at the October Power Planning Council meeting.

WDFW	1	No work planned; available as needed and as prioritized.	No requests for services were received during FY2001.

Objective	4	Services to Fish and Wildlife

Task	5.	Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas dataset, b) archive the official version as a

historic record, and c) in consultation with the Council, respond to requests for information concerning Protected Areas

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

Region	1	Maintain the existing Protected Areas database.	The Protected Areas data continued to be available on the

StreamNet website.  A plan was developed to tie these data to the

hydrography through assignment of LLID stream identifiers.  The

work will be done during Q1 of FY 2002.

Objective	4	Services to Fish and Wildlife

Task	6	Basin Data Needs

StreamNet will provide information and assistance to regional reviews of data management projects and data management

needs conducted by the PPC, ISRP, ISAB and other regional entities

Objective	4	Services to Fish and Wildlife 	Task   6   Basin Data Needs

Task	6.a	Data Management Needs

Work with regional entities to develop an analysis of regional data management needs, challenges and capabilities

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Participate on Council advisory committees to identify data	The RAAC EDT validation projects administration was approved by the

needs and data gaps	NWPPC.  Actual contracts and work may be in place by the end of this

quarter.  We will work with both RAAC and the Steering Committee to

capture relevant information into the StreamNet system.

Objective	4	Task	6.a	Fiscal Year 2001 Fourth Quarter Report	Page 53 of 63

ODFW	1	Assist as needed with identifying data needs of the amended 	We provided project direction, support, and supervision for the Viable

Fish and Wildlife Program	Salmon Population data compilation effort. Also initiated efforts to secure

additional funding for the VSP data compilation and database

development effort.

WDFW	1	Participate in regional discussions of data needs and data 	1)  O'Connor reviewed and provided both written and verbal comments

management strategies in support of the newly amended Fish 	on the SAIC work plan proposal to both CBFWA and NWPPC staff in

and Wildlife Program.	Washington.  SAIC proposes a Basin-wide review of information

management systems and information needs through a series of user

interviews and an examination of existing systems.

2)  O'Connor reviewed approved Columbia Plateau-North projects for

data needs and impacts on existing WDFW staff that StreamNet can

help address.

Objective	4	Services to Fish and Wildlife 	Task   6   Basin Data Needs

Task	6.b	Data Needs Workshop

Promote organization of a regional 'data needs workshop' to establish regional data / information needs and priorities and to

develop recommendations for roles and responsibilities for acquiring and providing the needed data / information

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

All			No work was done on this task this quarter.

Objective	4	Task	6.b	Fiscal Year 2001 Fourth Quarter Report	Page 54 of 63

Objective	5	Project Management / Coordination

Provide effective leadership that ensures the production of high quality products targeted at critical applications and the

development of these products in a timely, cost-effective manner.

Objective	5	Project Management / Coordination

Task	1.	Manage Project Activities

Administer all aspects of the project at the regional and sub-contractor levels, including oversight of budget, personnel, work

statement preparation and implementation, coordination among participating agencies, active participation in steering

committee work, and project reporting

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Provide normal supervision of StreamNet Library staff and the 	1)  Normal supervision of staff was provided as required.

CRITFC database Programmer.	2)  A new work plan and budget information were discussed with the

Steering Committee and provided to the project manager.

3)  Staff performance evaluations were completed by the end of the

quarter.  COLA raises were implemented on September 1 as directed

by our Commission and Executive Director. Budget adjustments were

made as necessary.

- The FY01 contract was closed out.

CRITFC	2	Produce quarterly reports within 1 month after the end of each 	All quarterly reports were completed.

quarter

CRITFC	4	Participate in Steering Committee meetings	One Steering Committee meeting was attended this quarter.

CRITFC	5	Collaborate on developing a final detailed Statement of Work	Provided detailed budget and work statement for FY02 as per

for the current contract and for the coming year	Steering Committee discussions and NWPPC policies.

FWS	1	Represent FWS in Steering Committee meetings	Pastor attended the August Steering Committee Meeting.

FWS	2	Produce quarterly reports w/in 30 days of quarter end	Third quarter activity report was submitted.

IDFG	1	Participate in Steering Committee activities. Manage all aspects 	1)  The Project Leader conducted all parts of StreamNet management for

of StreamNet in IDFG, including budget, personnel, and work 	IDFG, including progress reports, budget management, work

management. Products will include:  Annual IDFG StreamNet 	management, and supervision.

work statement; Quarterly and annual reports of progress; and, 	2)  The Project Leader participated in Steering Committee activities.

Objective	5	Task	1.	Fiscal Year 2001 Fourth Quarter Report	Page 55 of 63

ODFW	1	Administer all aspects of the project for Oregon, including 	1)  The Project Leader attended the August StreamNet Steering

budget oversight, personnel, staff work plans, project 	Committee meeting in Gladstone.

implementation and coordination, Steering Committee and 	2)  We submitted a revised request-to-hire, position description, and

technical issues meeting attendance.	physical factors paperwork for our vacant GIS Analyst position.

The position was announced on September 17.

ODFW	2	Participate/attend appropriate training and conferences in order 	One staff member took a free Sigma Plot computer class at OSU and one

to enhance technical skills which are relevant to StreamNet's 	staff member cross-trained on the Chinook research and monitoring

mission.	project in the Nehalem basin.

ODFW	3	Produce and provide a Statement of Work, budget proposal, 	1)  We submitted the 2001-1, and 2001-2 Oregon StreamNet quarterly

quarterly reports, and annual report for Oregon.	reports to Regional StreamNet.

2)  We submitted the FY 2000 Inventory Report and Annual Report.

3)  We developed and submitted a FY-2002 budget proposal for Oregon.

4)  We developed and submitted a justification for this year's Oregon

StreamNet cost overrun.

5)  We submitted a list of products and needs that could be addressed

using StreamNet carryover funds that recently became available.

6)  Staff submissions were incorporated into the third quarter Report.

7)  We developed and submitted the CRM budget for FY 2002

8)  We revised the CRM work plan for FY2002

9)  The CRM 2001-3rd Quarter Report was completed.

Region	1	Provide oversight for the StreamNet Program	Normal program administration continued during the quarter. Specific

accomplishments included fiscal year end budget adjustments,

prioritization of work Objectives for next year, and finalization of the

FY 2002 work statement

Region	2	Supervise StreamNet regional staff.  Provide training 	1)  During this quarter a StreamNet programmer was recruited.  Greg

opportunities for project staff to further their technical 	Wilke was hired and began duties on September 17.  Training of Greg

development and capabilities.	continued through the end of the quarter in order for him to learn the web

query system he will be responsible for, and associated information.  In

addition to information related directly to his programming responsibilities,

Greg was given an overview of fisheries management, fisheries

management in the Columbia River basin, types of fisheries data,

fisheries data storage and management in general, the role of StreamNet

in regional fisheries management, and his role within StreamNet.  This

background understanding will be very useful as he learns the

requirements of his position in order to best provide the services needed.

2)  A learning experience was provided for the non-biological

regional staff in field data collection methods by participation with

ODFW staff in spawning ground surveys.

Objective	5	Task	1.	Fiscal Year 2001 Fourth Quarter Report	Page 56 of 63

Region	3	Develop program budgets and manage / monitor expenditures	Year end budget tracking was conducted.  The Program Manager worked

with BPA regarding year end expenditures.

Region	6	Coordinate with regional management agencies / entities and 	StreamNet coordinated with the state, tribal and federal agencies involved

data using entities to determine information and data service 	in stocking in the Columbia Basin to obtain data on adipose clipping of

needs and to assure rapid response to reasonable data and 	hatchery salmon to meet a request for information from the NWPPC.

information needs.

Region	7	Produce quarterly reports within 1 month after the end of each 	The report database was improved to speed production of quarterly

quarter	reports.  Significant progress was made, but the second and third quarter

reports did not get formally released until the first quarter of FY2002.

Region	8	Produce final report within 2 months of the end of the contract 	The annual report was delayed in FY 2001 due to competing work

period	priorities.  The report database was improved during the fourth

quarter and the FY 2000 annual report was completed during the

quarter.  The improved report database should improve the speed

with which reports are completed in the future.

Region	9	Manage and serve the StreamNet Steering Committee through:  	The regional office hosted the summer Steering Committee meeting in

Organizing and conducting committee meetings at least 	Gladstone on August 7 and 8.  Among the issues addressed were initial

quarterly; Calling additional meetings as needed to address 	demonstration of what ArcIMS interactive internet mapping can do, and

timely issues; and, Actively consulting with Steering Committee 	review of the FY 2000 Annual Report.  Based on lessons learned in

on program activities	organizing the FY 2000 Annual Report, a new approach to defining and

organizing work activities for the FY 2002 Work Statement were

discussed and adopted.

Region	10	Prepare a project proposal and Statement of Work for FY2002.	The organization and prioritization of tasks for the FY 2002 Statement

of Work were modified as part of the summer Steering Committee

meeting.  The Objectives were changed to separate the development of

specific data sets into two tiers:  top priority and other priority, and these

became Objectives One and Two, respectively.  Distinctions between

separate Objectives for anadromous species and resident species were

dropped, with these details to be handled within the individual jobs under

each Objective and Task.  All sub-Tasks were eliminated to provide a

more succinct and understandable organization.  Some sub-Tasks were

combined, while others became individual Tasks.  A new template was

written to facilitate entry of each project's work elements into a database

developed in the new format.  And, a new report format was written so

that the work statement can be easily printed.  Most project had submitted

their budgets and work components by the end of the quarter, but the

finished work statement was not submitted to BPA formally until October.

Objective	5	Task	1.	Fiscal Year 2001 Fourth Quarter Report	Page 57 of 63

WDFW	1	The WDFW StreamNet state coordinator will participate in all 	1)  Sikora reviewed Schmidt's initial draft Annual Report for FY2000 and

Steering Committee and StreamNet Project management 	provided extensive feedback.  O'Connor attended the August 7-8

activities. The state coordinator and the state data manager will 	Steering Committee in Gladstone to complete fish distribution/use data

jointly manage all aspects of StreamNet in WDFW, including 	discussions, resolve more budget issues (including unspent FY2001

budget, personnel, work scheduling, and product delivery. 	funds) and make plans for the upcoming Rolling Review.  Following the

meeting, O'Connor and Sikora reviewed and commented on the FY2001

Carryover proposal and O'Connor finalized a proposal to spend extra

EPA monies.  For the FY2002 proposal, Sikora also projected potential

wage increases for Smith and Lensegrav in FY2002.

2)  O'Connor created a brief paper, "Strategy for the Upcoming Program

Review", based on notes taken during the August meeting. As part of that

Strategy, O'Connor and Sikora generated and circulated a "starter" list of

White Paper topics appropriate for assignment to StreamNet staff.

3)  O'Connor performed the usual staff and project management tasks

during this period, including managing the FY2001 budget to near-zero

balance, submitting the annual equipment inventory report, participating

in the annual personnel evaluation for the Project Manager, and

generating work plans and budgets for proposed extensions to StreamNet

contract work, including one for EPA funds and one for FY2000

Carry-over funds.

4)  Early July, Sikora drafted a work plan for Hudson's StreamNet

priorities.  O'Connor, Hudson and Sikora met in July and again in August

to discuss potential issues and throughout the quarter continued

coordinating priorities and work.  Sikora worked with Woodard to revise

his monthly or tri-monthly reporting style, relating a cohesive story of

Smith and Woodard's work and ignoring the Objective, Task and Work

Component numbers.  Lensegrav updated the Access database with

Smith, Woodard and his own third quarter work and Sikora synthesized

the descriptions of their work with her own.

5)  This year performance evaluations included several extra forms.  On

July 31, Sikora attended Woodard's performance evaluation of Smith and

conducted Woodard's evaluation.  Sikora then met with Kinney to discuss

StreamNet issues.  O'Connor evaluated Sikora on Aug 21 and Brown on

Aug 24 with Sikora in attendance.  Later in August, O'Connor evaluated

Burns and Hudson, and submitted all required paperwork to WDFW.

Planning issues were discussed in all the meetings. O'Connor also

worked with Sikora and WDFW Personnel on finalizing the outcomes of a

re-allocation petition for her position.

6)  Smith began an on-line statistics class to improve her escapement

data work and Sikora researched how she could file for class

reimbursement.  Lensegrav attended a ESRI GIS open house to preview

new GIS software and assess relevance to future GIS work.

Objective	5	Task	1.	Fiscal Year 2001 Fourth Quarter Report	Page 58 of 63

7)  Throughout the FY, all staff kept current with their FY2001 activity

reports and Lensegrav built a report to show all quarter activities (first -

fourth) together to maximize space efficiency. Sikora thoroughly reviewed

Schmidt's draft document of the first quarter report, noting the draft was

merely an export of our Q1 Access database entries so future quarterly

document reviews will not be necessary.  The WDFW Third Quarter

Progress Report was finalized and submitted to PSMFC.  Sikora and

O'Connor prepared the WDFW StreamNet FY2002 Statement of Work

(SOW) and gave Schmidt feedback on corrections needed or issues of

accommodating work.  Extensive SOW comments were forwarded in

early June (immediately after the late May Steering Committee meeting)

and in August (following the early August meeting), mostly addressing the

significant revamping proposed by Schmidt and the Steering Committee.

8)  All WDFW staff increased their virus detection routines and a

WDFW systems manager tailored the PC's to minimize the likelihood

a virus would attack or spread (i.e. by removing Microsoft Outlook).

Objective	5	Project Management / Coordination

Task	2.	Participate in Fish and Wildlife Program Development Activities

Organize, facilitate, and/or participate in appropriate coordination meetings with BPA, CBFWA, the Council, ESA officials,

ISAB/ISRP, and/or staff and management of participating organizations aimed at identifying ways that StreamNet might more

effectively contribute to the Fish and Wildlife Program (FWP). Participate in advisory groups, Task forces, and other groups

whose purpose is enhancing the effectiveness of the Fish and Wildlife Program and its data development activities.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Participate in appropriate coordination meetings with BPA, 	Discussions regarding StreamNet role under the Fish and Wildlife

CBFWA, the Council, ESA officials, ISAB/ISRP, and/or staff and 	program continued with NWPPC staff and contractors and with the

management of participating organizations aimed at identifying 	RAAC group. NWPPC staff is much more receptive to a significant

ways that StreamNet might more effectively contribute to the 	role for StreamNet in subbasin planning efforts. Specific have yet

Fish and Wildlife Program.	to be completely specified, and discussions will continue.

CRITFC	2	Where appropriate, participate in advisory groups, Task forces, 	The Council released final draft guidelines for subbasin assessments and

and other groups whose purpose is enhancing the 	subbasin planning. These provide significant opportunities for defining a

effectiveness of the Fish and Wildlife Program and its data 	StreamNet role. CRITFC and ODFW staff developed a work statement

development activities, with particular emphasis on subbasin 	and budget to implement subbasin planning in Oregon, defining specific

planning and R/M/E issues.	roles for StreamNet to 1) provide information to subbasin groups, 2)

assist subbasin groups with a variety of data management services,

and 3) capture new information, including the EDT data sets, developed

in this round of subbasin planning.

Objective	5	Task	2.	Fiscal Year 2001 Fourth Quarter Report	Page 59 of 63

ODFW	1	Participate in activities aimed at identifying ways that StreamNet 	We assisted in drafting a  letter requesting data from ODFW folks.

might more effectively contribute to the Fish and Wildlife 	Attended the July 11 WLC Technical Recovery Team meeting in

Program, including participation in Fish and Wildlife Program 	Portland at the Bonneville Power Administration office.

advisory groups and applicable regional policy, planning, and 	Provided input and support to the VSP database development

management forums.	effort.

Region	1	Participate in appropriate coordination meetings with BPA, 	The Program Manager participated in several Anadromous Fish

CBFWA, the Council, ESA officials, ISAB / ISRP, and/or staff	Committee meetings.  The data developed with state and federal agency

and management of participating organizations aimed at	input on adipose clipping were reviewed through the AFC to assure

identifying ways that StreamNet might most effectively	accuracy.  Input for presentation to the Power Planning Council regarding

contribute data / information and support to the FWP. 	the adipose clipping data request was solicited through AFC and

incorporated in the presentations to the Council.

WDFW	1	No specific work planned; available as needed for coordination 	See related work under Tasks 1.6, 2.2, 2.7, 4.2a, 4.7a.

Objective	5	Project Management / Coordination

Task	3.	Coordinate with Other Related Activities

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities to identify

means for collaborative data collection, storage, and dissemination. Collaborative data activities will target tribal fishery

programs within the Columbia Basin, federal land managers’ fishery programs, state fish and wildlife agencies, and, with

respect to water use and stream development, state water resource management agencies. Collaboration with coast-wide and

private data collection/compilation efforts will be pursued when this supports overall project goals. Areas of particular

emphasis are 1) participation in Fish and Wildlife Program monitoring and evaluation activities, and 2) exploring opportunities for

integration of StreamNet data exchange formats into Fish and Wildlife Program contract terms and conditions.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Seek closer cooperation, coordination, and consistency of 	No activity occurred this quarter.  It is most likely that coordination of

information management practices and standards between 	information management across programs (e.g. the Power Act,

salmon restoration programs in the Columbia Basin (e.g. 	Forest Service, and LSRCP) will surface during subbasin planning

Mid-Columbia PUDs, LSRCP) by participating on appropriate 	which will be most active during the next two fiscal years.

work groups.

ODFW	1	Establish / maintain working relationships with data collection 	1)  The project leader attended a meeting at OWEB to discuss the

projects within and outside ODFW to promote efficient and 	creation of an OWEB - Oregon Plan Information Manager position.

beneficial data sharing.	2)  The project leader attended the N. & S. Willamette Watershed District

meeting where data collection activities in the basin were presented and

discussed.

Objective	5	Task	3.	Fiscal Year 2001 Fourth Quarter Report	Page 60 of 63

Region	1	Coordinate the efforts of the StreamNet project with other data 	1)  StreamNet and Xerces Society personnel developed a project

compilation projects occurring in the region.  Address issues of 	proposal for creation of a regional aquatic macroinvertebrate database.

data gaps, duplication of effort, data set integration, 	This project, if funding can be obtained, will add macroinvertebrate data

georeferencing standardization, scientific rigor, management 	to StreamNet and produce a region-wide program of data reporting.

needs, etc.	This system would ease flow of required data to EPA and would allow

aquatic managers and researchers to quickly and easily obtain data of

interest in a standard format.  Several possible sources of funding for this

proposal were identified, and a greater effort to locate funds will be

undertaken in FY2002.

2)  StreamNet personnel provided advice to personnel from California

Department of Fish and Game with their efforts to produce a standard

hydrography layer with LLIDs for the state of California.

3)  Because much of StreamNet's hatchery release data are obtained

from the coded wire tag database, the Regional Fisheries Biologist

discussed georeferencing of hatchery releases with the CWT program

manager.  It was learned that many of the locations are not well defined

in the CWT database due to the data submitted to them.  Options for

eventually correcting this problem were discussed.

WDFW	1	Maintain working contact with Washington Hydro Framework 	Hudson attended two state Hydro Framework meetings and a meeting

partners and USGS Regional Ecosystem Office staff to promote 	of the SWIM-TAC Hydro Action Team to advise on testing of hydro

effective sharing of hydrology base layers and attached fish 	check-in and check-out procedures. These groups work to coordinate

and habitat data.	hydro layer work among the state and federal agencies of Washington

and Oregon.  As current subject material is quite technical, Hudson is

attending these meetings in place of O'Connor.

Objective	5	Project Management / Coordination

Task	4	Prepare Public Information Materials.

As needed, produce public information materials including updated versions of the project brochure, computer demonstration

materials, and/or other appropriate materials

Objective	5	Project Management / Coordination	Task   4   Prepare Public Information Materials.

Task	4.a	Prepare Public Information Materials

As needed, produce public information materials including updated versions of the project brochure, computer demonstration

materials, and/or other appropriate materials

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	Produce and update a Library brochure and Access guide listing	Brochure was distributed at a Tribal Water Quality Conference at

services, hours and cost recovery fees.	Kah-Nee-Ta Resort.

Objective	5	Task	4.a	Fiscal Year 2001 Fourth Quarter Report	Page 61 of 63

ODFW	1	Write informational articles on StreamNet data activities for 	1)  We prepared and gave a presentations on the ODFW Fish Screening

natural resource oriented publications and give oral 	and Passage Program Database to the Fish Screening and Passage

presentations to relevant user groups.	Task Force.  A representative from NMFS indicated that they'd be

interested in using the database to capture like data in Washington.

2)  We wrote a rough draft of an article on the Incidental Fish Observation

database for ODFW's internal bimonthly publication, "Inside Tracks".

3)  We worked with Fish Screening and Passage staff to draft a short

article on our database development efforts for them.

4)  We developed Willamette basin fish distribution maps and finalized the

Sport Fish Restoration report and submitted it to ODFW Fish Division.

5)  We drafted an article on Spreadsheet vs. Database utilities for

biologists, to be posted on the web sometime in the future.  We also

drafted another "Inside Tracks" article about who NRIMP is and how

we are involved in StreamNet.

Region	2	Create improved web page help files to assist users in 	During the quarter we considered how to help users better understand

understanding and making better use of StreamNet information.	the contents of the StreamNet on-line database, the work done by

StreamNet, and the products and serviced provided by StreamNet.  A

series of white papers was suggested that would explain these various

aspects of the StreamNet project.  Several white papers were suggested,

and one was developed as a potential template.  This template white

paper was a description of the habitat restoration projects database held

by StreamNet.  If feasible, we plan in the future to create a white paper

for each of our data types, in order for users to better understand the data

available to them.

Objective	5	Project Management / Coordination	Task   4   Prepare Public Information Materials.

Task	4.b	Participate in informational meetings/conferences

Participate in appropriate state, regional, and national educational and professional conferences, including, where applicable,

giving presentations, preparing poster session materials, and contributing to conference proceedings.

Project	Work Element	Accomplishments, Fourth Quarter, FY2001

CRITFC	1	See Task 3.5	An abstract was accepted for presentation of a paper at the NRIC

conference in October.

IDFG	2	Serve as chairman and organizer for the 2001 ArcInfo User's 	The Project Leader organized all aspects of the 2001 Northwest GIS User

Group Conference scheduled for October 2001.	Group Conference, including facility planning, program development,

catering, scheduling, registration and advertising.

Objective	5	Task	4.a	Fiscal Year 2001 Fourth Quarter Report	Page 62 of 63

ODFW	1	Participate in appropriate meetings & conferences as 	1)  Staff attended a presentation/demonstration by Shaun McKinney on

opportunities arise to highlight StreamNet programs & data	the USFS Natural Resources Information System - Water Module. No

commitment was made on behalf of StreamNet to exchange information

at this time, but OWEB's Restoration Tracking Project and ODFW's

Aquatic Inventory Project have agreed to give some of their data to

Shaun so he can integrate it into his system as a demonstration of NRIS's

utility.

2)  We attended a meeting in Hood River to discuss and develop a

process for prioritizing culvert replacements.

Region	2	Represent StreamNet in relevant state, regional and national 	During the quarter topics were developed for presentations at the

meetings and conferences.	November 2001 meeting of the Organization of Fish and Wildlife

Information Managers, which will be held in Portland, OR.  The Regional

Fisheries Biologist will present an analysis of the quality of data for

fisheries management decisions that exist in the StreamNet system; the

Program Manager will give two presentations, one on strategies for

developing data at a regional level from independent projects and

another on obstacles to establishing standardized field sampling

methodologies.  Drafts of these preparation were completed this quarter.

WDFW	1	Participate as opportunities arise to highlight StreamNet 	O'Connor agreed to give a presentation on Habitat Restoration Project

programs & data	data standards and issues (based on StreamNet Project experience) at

the annual meeting of the Organization of Fish and Wildlife Information

Managers (OFWIM) in November 2001.

Objective	5	Task	4.b	Fiscal Year 2001 Fourth Quarter Report	Page 63 of 63