|  | StreamNet Project BPA Project No. 198810804 Fiscal Year 2005 Fourth Quarter Progress Report July 1, 2005 through September 30, 2005 |
| --- | --- |

###### Bruce Schmidt

###### Pacific States Marine Fisheries Commission

###### Cooperators

Phil Roger, Columbia River Intertribal Fish Commission

Bart Butterfield, Idaho Department of Fish and Game

Janet Hess-Herbert, Montana Fish Wildlife and Parks

Cedric Cooney, Oregon Department of Fish and Wildlife

Steve Pastor, U.  S.  Fish and Wildlife Service

Dick O'Connor, Washington Department of Fish and Wildlife

##### November 17, 2005

|  | Table of Contents | Pg. |
| --- | --- | --- |
| Introduction........................................................................................ | 2 |
| Work Element 159. | Submit/Acquire Data.................................... | 9 |
| Work Element 160. | Create/Manage/Maintain Database............ | 25 |
| Work Element 161. | Disseminate Raw & Summary Data............ | 35 |
| Work Element 98. | Other (Library Services).............................. | 41 |
| Work Element 118. | Coordination.................................................. | 44 |
| Work Element 99. | Outreach and Education.............................. | 49 |
| Work Element 119. | Manage and Administer Projects................ | 51 |
| Work Element 141. | Produce Status Report.................................. | 53 |
| Work Element 132. | Produce Annual Report................................ | 53 |
| Work Element 115. | Produce Inventory or Assessment............... | 54 |
| Supplemental Information: Work Outside the SOW..................... | 54 |

Introduction

StreamNet is a cooperative, multi-agency data compilation and data management project authorized by the Northwest Power and Conservation Council’s Fish and Wildlife Program (FWP), funded primarily by the Bonneville Power Administration.  The project is administered by the Pacific States Marine Fisheries Commission (PSMFC).  Three fourths of the project consists of sub-projects within the state fish and wildlife agencies, Columbia River Intertribal Fish Commission and the US Fish and Wildlife Service to acquire, georeference and standardize fish related data; develop databases within the respective agencies; facilitate data transfer regionally; and maintain a library of data references and fish and wildlife related reports and publications.  The remaining fourth consists of the regional staff at PSMFC to manage the regional database, disseminate regionally standardized data, provide regional data services and administer the project.  Information about the project, fish related data and past reports and other project documents are available at the project website at www.streamnet.org.

This report describes the work accomplished by the StreamNet Project during the fourth quarter of fiscal year 2005 (FY-05).  The work reported is tied to the specific jobs contained in the FY-05 Statement of Work, which is available at http://www.streamnet.org/about-sn/project_management.html.  Work priorities for FY-05 include updating existing long term data sets, conducting a thorough Quality Assessment review of data, managing infrastructure necessary to maintain and deliver data, maintaining the StreamNet Library, providing data services to regional entities associated with the Fish and Wildlife Program, and project administration.  Not all project participants address every milestone every quarter, so only the milestones worked on this quarter are included in this report.

Introduction			StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 2 of 56

Activities in the Fourth Quarter of FY-05 included routine development, maintenance, updating and posting of various data sets; QA reviews of data; administration of the computer systems (hardware and software) necessary for project operations; data dissemination; coordination with related projects and regional entities; and operation of the StreamNet Library, in addition to routine administrative activities to continue project function.  Key highlights of project activities are summarized below, with details provided under the individual Milestones.

Submit/Acquire Data

StreamNet’s participating agencies continued acquisition, updating, georeferencing and standardization of standard data sets during the quarter.  In addition, based on this year’s objective of conducting a thorough quality review of all StreamNet data, significant time was spent in reviewing and correcting data sets.  Highlights of activities included:

Work on the hydrography:  Regional StreamNet (PSMFC) performed major work on the hydrography GIS layers that will be used into the future.  IDFG made over 300 hydrography modifications, which will be incorporated into the Idaho and StreamNet hydrography layers in the near future.  ODFW and WDFW participated in the multi-agency Hydro Framework/NHD effort.  In addition, WDFW completed a mixed-scale hydrography layer for Washington state, which included much error correction of the GNIS (geographic names) database.

Idaho StreamNet (IDFG) completed compiling 2004 field season hatchery return and age composition data.  Submission is waiting for completion of a QA/QC review of existing trend data and completion of migration to new hatchery return and age composition Data Exchange Formats (DEF).  Significant progress was made developing distribution information for non-game species.

Montana StreamNet (MFWP) exchanged distribution, sightings, resident hatchery releases and all other data types with updated data to StreamNet.  Data were sent for development of a draft Sightings DEF.  The contacts to state agencies to receive 2004 data were completed and contacts to federal agencies continued this quarter.  Dams and the hatchery facilities databases were also updated.

Oregon StreamNet (ODFW) progressed on most project deliverables slated for attention during the quarter.  Most data submissions previously delayed by staff vacancies or database changes needed to accommodate the latest DEF were made this quarter.  However, the hatchery release data submission continues to be held up while DEF issues are resolved.  Updated and corrected hatchery return trends submissions are anticipated when the DEF is finalized.  The focus on QA/QC of existing data continues to pay dividends.  Existing data records are being corrected and/or made consistent across the years of data availability, and QA/QC protocol documents are being improved and refined as error-checking strategies are added or improved, and employed.  All abundance trends, as well as information related to fish passage at various in-stream impediments in Oregon, are seeing improvement.  Progress continued toward establishing an agreed upon approach to address 24K hydrography development and the generation of linear event data for the Basin’s 24K scale fish distribution.  Significant progress was made in developing distribution information for non-game species.

Introduction			StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 3 of 56

Washington StreamNet (WDFW) completed development of the mixed-scale hydrography layer for Washington state, including a complex system of linework and attribute management programs.  Upon completion (September), three reference basins were sent to the StreamNet GIS Manager for review and comment.  These basins provided examples of the Washington/Oregon Columbia River border, the Idaho/Washington border, and the Washington/Oregon border in NE Oregon.  The Fish GIS Manager also began to transfer generalized fish distribution data for salmon, steelhead and bull trout to the new Washington mixed-scale hydrography layer, based on the new WDFW internal fish distribution data format.

A series of pending WDFW data exchanges all came together this quarter.  4,300 hatchery returns records were resubmitted in the new data exchange format, following a review of issues identified in last quarter's initial submission.  This exchange included all historical data through the 2003 return year.  In addition, 12,265 culvert records were submitted in the new barriers data exchange format.  A preliminary conversion of the fishway and dam records to the new exchange format is underway.  Finally, 4,847 data entries in the Age Table were reviewed and updated with new fields prior to submission in the newly-updated data exchange format.

FWS submitted the vast majority of Hatchery Return data for National Fish Hatcheries to the new Hatchery Returns DEF.  "Historic" data not previously available through StreamNet was added.  A program to convert data to the new Hatchery Returns DEF was partially completed.  A change in the DEF part way through the current year was responsible for this work not being fully completed.

## Create/Manage/Maintain Database

All project members performed ongoing systems administration (hardware and software maintenance and management), maintained various data management tools and interfaces, maintained data and database systems, and contributed to ongoing review and development of Data Exchange Formats (DEF).  A few key highlights by the individual project members includes:

Regional StreamNet at PSMFC received a large number of data submissions from the project partners during the quarter.  These data were validated through routine QA procedures and loaded into the regional database (see details on p. 30).

The Columbia River Inter-tribal Fish Commission StreamNet project (CRITFC) improved QA/QC procedures, which led to faster cataloging of material, improved accuracy of information, and improved security of the Library databases.  In response to tightened budgets, they began converting the Library catalog to open-source software, thus eliminating software license costs.

IDFG completed initial user interface and database design for the new Spawning Ground Survey using .Net.  A coordination effort with IDFG fishery biologists began fine-tuning the application.  Work continued on redesign of the IDFG StreamNet database.  This included creating a single master hydrography database and formatting to match the new hatchery returns and age composition DEFs.  Existing StreamNet data were migrated into the new database, but still require a review and edits.  Smolt trapping data from 1990 to 2004 were captured from existing spreadsheets and consolidated into a central database.  Web-based reports were developed for querying and reviewing the data.  Revisions are being made in coordination with IDFG fishery biologists before posting to the web.

Introduction			StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 4 of 56

The review of IDFG's redd count trends for Chinook, sockeye and steelhead was completed, and Idaho converted redd count records from whole-stream trends into reach-specific trends, thus providing more detailed information.  Because of splitting whole stream trends into individual transect based trends, the number of IDFG redd count trends increased from 113 to 779.  These included for the first time non-index trends.  The new trends were cross-referenced with the old trends in order to facilitate migration of the redd count data.

MFWP sent sightings and hatchery release data to regional staff for use in developing the draft DEF.

ODFW expended a significant amount of time this quarter ensuring the data quality of existing StreamNet Trend information, and made major strides toward modernizing data management and dissemination capabilities through the use of SQL Server and ArcIMS software packages.  A draft general purpose ODFW Internet Map Server (IMS) web site was developed and released for beta testing this quarter.  ODFW also began designing an agency geo-database to store agency spatial data sets, as well as other common base data.  Other work related to data and database management infrastructure improvements, including tool, website, and database development.  Work on the corporate information system continued, with progress on a number of disparate Windows-based components being made.

The WDFW Fish GIS Manager overhauled the internal spatial data format for the files that feed StreamNet's generalized fish distribution data from WDFW.  Separate events for the same species-run and location that were once stored on separate records (distribution, use types) are now assimilated into a single record based on a use hierarchy.  This organization mirrors the approach used to support the WDFW ArcIMS application "SalmonScape" and will greatly ease data conversion to the StreamNet exchange format.

Disseminate Raw & Summary Data

Data dissemination via the StreamNet web page continued throughout the quarter.  The Internet is the project’s primary means of data dissemination, and StreamNet members continued website maintenance and management.  In addition, all project partners responded to direct requests for data and information.  Staff in the seven StreamNet agencies responded to 254 requests for information or assistance during the quarter.  Roughly half of these requests were for library materials.  Private consultants and state government employees made the most requests.  Federal agencies, tribal agencies, and the general public also were significant users of StreamNet services.  Of the 254 requests 228 were fully satisfied, 8 were only partially satisfied, for 12 we could only refer the user to other sources, and for 6 we could not help at all.  Our inability to help stemmed from the questions posed being inappropriate for the kind of information in our project.

Introduction			StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 5 of 56

PSMFC expended significant effort on website look and feel improvements, easier navigation, and improved features.  This was a significant overhaul, and these improvements will be available on the production StreamNet web site in the first quarter of FY-06.  The large amount of new fish data added to the database during this quarter was made available to users via the online web query system, as downloadable ASCII tables and as Access databases.  The Northwest Critical Habitat Mapper was revised to reflect the final rule published in August.   The Southwest region Critical Habitat Mapper was taken off-line, with users now directed to our partner project, CalFish, to view the final rule designations for California.

IDFG filled 48 requests for data during the fourth quarter.  There were 21 requests from private companies, 18 from state agencies, 6 from federal agencies, 1 from a non-governmental organization, and 2 from a university.  The data types requested were:  barriers-6, distribution/presence (species lists)- 27, GIS layers-9, harvest-1, redd counts-3, references-1, and general technical assistance-1.

MFWP filled 13 requests for map products or data from the Fisheries Division.  There were no requests from the public.  The FWP electronic fisheries library was enhanced by adding the Repository ID to collector's permits.  High resolution color aerial photographs and a layer containing updated plat maps of the Flathead and Kootenai River watersheds (the main river corridors are top priority) were provided for use by a 3-way MOA (MFWP-BPA-CSKT [Confederated Salish and Kootenai Tribes]) for land acquisitions and conservation easements to protect critical fisheries habitat in the two watersheds for BPA mitigation staff in northwest Montana.  The maps will be used to define criteria for parcel selection in order to identify 10 properties to review and rank based on the criteria.

ODFW performed routine maintenance of its web sites and responded to 26 direct information requests.  A draft Work Request Form / GIS Dataset Development Request Appendix was developed to facilitate responding to spatial data-related requests.

WDFW responded to 18 major data requests directly during the fourth quarter, including 11 for GIS data and 7 for tabular data or general information.  The most frequent data types this quarter were harvest, population numbers, and GIS data (standard maps, EDT stream reach priorities and generalized fish distribution layers).  Details can be found in the WDFW Q4 StreamNet Data Requests database records (at PSMFC).  In addition, fish and hydrography GIS layers built and maintained by StreamNet staff were used by WDFW's Priority Habitats and Species group to respond to over 350 data requests, involving 1,080 maps and 70 digital datasets.

## Library Services

The StreamNet Library at CRITFC continued to provide responsive services for a large and growing user base.  Library staff responded to 127 requests for direct services plus walk-in visitors and regular web service users.  QA/QC procedures were improved, leading to faster cataloging of material, improved accuracy of information, and improved security of the Library databases.  In response to tightened budgets, the library began converting the library catalog to open-source software, thus eliminating software license costs.

Introduction			StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 6 of 56

Organization of the ODFW Library and updates to the bibliography continued, with nearly 9,500 bibliography records in the database so far.  Organization activities will not continue through the first quarter of FY-06 due to budget limitations.

### Coordination

StreamNet members at all levels coordinated with and provided data services to a wide variety of entities in support of data management programs.  StreamNet staff continued participation in regional efforts such as PNAMP, NED, CSMEP, creation of a standard regional GIS hydrography, and capture of information generated during subbasin planning.

PSMFC staff spent significant time in assisting other data development efforts in the region or in exploring potential collaborations.  These included on-going participation in NED and PNAMP, reviews of a "protocol builder" being developed by BOR, testing of a new web site for PTAGIS, meeting with the PNW mussels work group to discuss data sharing and archive capabilities, and meeting with the PNW Water Quality Data Exchange to discuss real-time interaction between that system and StreamNet.

The CRITFC Project Leader was very active in support of related regional and NPCC program activities.  Specifically, he served as an ex-officio member of the ISAB, served on the steering committees of the PNAMP and NED, and served as co-chair of the NED Subbasin Data Workgroup.  In addition, the Librarian participated in the development of the NED white paper on marketing, education and outreach.  She also worked with the NED web portal development team.

MFWP regional staff met with various USGS and state representatives concerning the future of regional hydro.  Steve Carson provided input and follow-up discussion.  Discussion on this topic is slated for the October 2005 Steering Committee meeting.

IDFG completed the CSMEP data inventories for the upper Salmon and Middle Fork Salmon basins.

ODFW continued support for the CSMEP effort, including participation in regularly scheduled meetings/calls, and routine maintenance and updating of the CSMEP web application.  Currently there are 1,450 records in the CSMEP web application, 174 of which were added this quarter.  Oregon StreamNet staff participated in the NED/PNAMP Data Management Meetings on August 3rd and September 7th.  A great deal of collaboration and support took place this quarter with the Oregon Plan Monitoring Team, resulting in three data management-related funding proposals being submitted for consideration by the Monitoring Team.  Contributions to Recovery Planning efforts were also significant this quarter based on a shift in agency priorities.  Coordination continued with the ODFW Marine Resources Program (MRP) by maintaining and updating the online harvest status tracking system for the 2005 marine sport season.  A lower level of support to the Oregon Plan Assessment continued via data compilation of Oregon Watershed Council datasets, data management, and database and web site development.  Staff continued to support the Comprehensive Wildlife Conservation Strategy throughout the quarter, contributing GIS and analytical support to the successful completion of the draft

Introduction			StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 7 of 56

strategy.  Staff members helped initiate the development of a GIS Coordination Group in ODFW to make progress in the area of agency collaboration in order to obtain the full value, understanding, and support of GIS at ODFW.

The WDFW StreamNet Project manager met with other WDFW and CRITFC staff in Vancouver on 8/9/2005 to discuss CRITFC involvement in a project to compile and store Washington EDT spatial data for the Columbia River Basin in a repository that would hold all Basin EDT data.  In addition, the agency sent four representatives to a 9/15/2005 meeting between StreamNet participants and the Pacific Northwest Hydrography Framework Working Group to discuss issues with the coming NHD hydrography linework and format standards, including migration from the regional 100K-based layer to the higher-resolution (24K) NHD product.  WDFW is committed to pursuing an approach that benefits StreamNet data exchange and dissemination.

## Manage and Administer Projects

All project members performed routine administrative duties, including supervision, budget management, development of the FY-06 SOW and budget, completion of the Third Quarter Report, and program guidance through participation in the StreamNet Steering Committee.  In addition, ODFW filled two long vacant positions.

Specific details of work accomplished by the StreamNet Project in the fourth quarter of fiscal year 2005 are presented below.  Individual milestones that did not receive any work during the quarter have been skipped.

Introduction			StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 8 of 56

Work Element:	159	Submit/Acquire Data

Work Element:	159	Submit/Acquire Data

Work Element Title:	1	Develop anadromous fish distribution data

Document the occurrence, distribution and life history characteristics of anadromous fish species.  Efforts will be made to utilize the current mixed scale hydrography for these data, with intent to migrate to 24K when a regionally consistent 24K routed hydrography becomes available.  Maintenance of this high priority data set will continue.  The state StreamNet sub-projects will maintain the existing data on anadromous fish distribution and habitat use in their respective states.  New distribution information will be incorporated as they become available.  Updated distribution data will be conveyed ("exchanged") to the regional StreamNet database at PSMFC, where they will be incorporated into the database.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

2	ODFW development of 	ODFW, on an Ongoing and opportunistic basis, will 	Routine maintenance was performed on Oregon's anadromous fish

anadromous fish 	update, maintain, correct and exchange anadromous	distribution and documentation information during the quarter.

distribution data, 	fish distribution and documentation information

progress reported 	with the regional StreamNet database in the DEF 	The Data Technician converted lamprey observation location data

quarterly	tied to the current hydgrography scale.	from degrees-minutes-seconds to decimal degrees, and unrolled native

non-game fish observations into individual species-specific data

records, creating new lamprey observation records from previously un-usable records.  This work will also facilitate compilation of native non-game fish information being planned for FY-2006.

Efforts were made to jump start the cross state distribution reconciliation pilot started during the third quarter with Washington StreamNet staff, but it looks like this process will not restart before early October.

3	WDFW development of 	WDFW, on an Ongoing and opportunistic basis, will	The Fish GIS Manager began to transfer generalized fish distribution

anadromous fish 	update, maintain, correct and exchange 	data for salmon, steelhead and bull trout to the new Washington

distribution data, 	anadromous fish distribution and documentation 	mixed-scale hydrography layer, based on the new WDFW internal

progress reported 	information with the regional StreamNet database 	fish distribution data format.  A test basin of new hydrography and

quarterly	in the DEF tied to the current hydgrography scale.	fish distribution data will be submitted to the StreamNet GIS Manager

in late October for review and approval.

WE No.:	159	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 9 of 56

Work Element:	159	Submit/Acquire Data

Work Element Title:	2	Develop resident fish distribution data (top priority for MFWP, lower priority for others)

Document the occurrence, distribution and life history characteristics of resident fish species, at the most current available hydrography scale.  Existing resident fish distribution will be maintained, and project participants will begin expanding data for additional species.  This is high priority for Montana, and new data will be developed by the other states as time allows.  Updated distribution data will be exchanged to the regional StreamNet database at PSMFC, where they will be incorporated into the database.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

2	MFWP first exchange of	MFWP will complete Distribution and Use Types 	A decision was made earlier in the year to exchange these data only one

resident fish distribution	data sets from data collected from biologists, 		time during the year.  These data were exchanged to the regional

data, first quarter	documents and reports during 2002-2003 using 	StreamNet database this quarter.

LLID stream routes and Montana's lakes coverage

and water code system and exchange them in the

DEF with regional StreamNet.  They will complete

distribution and use type data sets for 2003-2004

and update the entire state.  The focus will be on

target species during the year if opportunity arises.

Exchange the data to the regional database in the

approved DEF format.  Two exchanges are planned,

with the first due 12/01/04.

3	MFWP second exchange	MFWP will complete Distribution and Use Types 	These data were exchanged to the regional StreamNet database this

of resident fish 	data sets from data collected from biologists, 		quarter.

distribution data, fourth 	documents and reports during 2002-2003 using

quarter	LLID stream routes and Montana's lakes coverage

and water code system and exchange them in the

DEF with regional StreamNet.  They will complete

distribution and use type data sets for 2003-2004

and update the entire state.  The focus will be on

target species during the year if opportunity arises.

Exchange the data to the regional database in the

approved DEF format.  Second exchange is due

9/01/05.

4	MFWP collect 2003-4 	MFWP will visit MFWP and other state and federal 	The contacts to state agencies are complete.  Contacts to federal

resident fish distribution 	fisheries biologists to collect 2003-2004 resident 	agencies continued in this quarter.

data from biologists, 	fish distribution data and supporting survey data and

progress reported 	references and enter them into MFISH .

quarterly

WE No.:	159	Title No.:	2	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 10 of 56

5	MFWP develop fish 	MFWP, in an ongoing effort,  will work with FWP 	No action was taken this quarter; we are waiting for review of the

distribution field 	Fisheries Division to assist in the development of 	survey from the Fisheries Division staff.

collection survey 	fisheries field collection survey standards.

standards, progress

reported quarterly

6	MFWP review habitat 	MFWP, on an exploratory, ongoing basis, will 	No action this quarter.

fields to identify core 	review commonly used habitat fields collected on

data sets, progress 	streams by agency biologists to see if there is a core

reported quarterly	set related to fish distribution data.

7	ODFW development of 	ODFW, on an ongoing basis as time and funding 	Routine maintenance was performed on Oregon's resident fish

resident fish distribution 	permits, will update, maintain, correct and exchange	distribution and documentation information during the quarter.

and documentation 	resident fish distribution and documentation

information, report 	information in the DEF tied to the current 	The GIS Analyst incorporated draft Redband distribution data into the

quarterly	hydgrography scale..	Distribution database and synchronized it with the Master copy.

The Data Technician converted resident native non-game observation

location data from degrees-minutes-seconds to decimal degrees, and

unrolled existing native non-game observations into individual

species-specific data records, creating new, previously un-usable

observation records.  This work will also facilitate compilation of

native non-game fish information being planned for FY-2006.

10	WDFW exchange of 	WDFW will incorporate any Washington bull trout 	Last quarter, ODFW and WDFW's effort to resolve cross-border

resident bull trout 	distribution data updates resulting from the regional 	distribution conflicts stalled until WDFW could investigate the proof

distribution data, 	5-year bull trout status review into internal files by 	behind their existing distribution descriptions in the Walla Walla

progress reported 	11/30/04 and will exchange to regional StreamNet 	basin.  The Location Data Manager started linking existing bull trout

quarterly	by 3/31/05.	distribution data with the relevant supporting data.  When the linking

is complete ODFW and WDFW will continue their discussions

(likely in the first quarter of FY-06).

Follow-up to resolve purported bull trout spawning activity in certain

areas continued, related to the five-year status review.  Updates are

being posted to the WDFW internal layer, which will be transferred to

the new Washington mixed-scale hydrography layer starting in

October, and the new layer will be subsequently submitted to regional

StreamNet to replace the existing Washington bull trout data.

WE No.:	159	Title No.:	2	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 11 of 56

Work Element:	159	Submit/Acquire Data

Work Element Title:	3	Develop data for adult abundance in the wild

Develop and maintain (update) information on adult abundance for native fish species, resident and anadromous, including escapement, redd counts, peak spawner counts, trap counts, dam and weir counts, and resident fish populations (where calculated by other agencies).  This is a high priority data type.  Also included in this data category are data gathered during spawning ground surveys regarding straying of hatchery fish onto spawning areas, i.e., marked/unmarked ratio.  These are lower priority under base funding.  Updated data will be exchanged with the regional StreamNet database at PSMFC at least once per year.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

2	CRITFC update adult 	CRITFC will update available tribal spawning ground	No additional work was performed this quarter.

abundance (spawning 	survey data and exchange them with regional

survey) data, progress 	StreamNet.

reported quarterly

3	IDFG develop adult 	IDFG will compile the 2004 field season spawner 	Work began to compile the 2005 field season IDFG redd count data.

abundance (redd count) 	survey data from IDFG and submit them in the DEF

data, progress reported 	 to regional StreamNet.

Quarterly

5	MFWP obtain adult 	MFWP will obtain all 2004 stream and lake fish 	This task was completed this quarter.

abundance (fish survey) 	survey data during scheduled field office visits; data

data, progress reported 	may be one time visits, index streams and/or results

quarterly	from gill nets in lakes and reservoirs.  Data will be

provided to regional StreamNet in the DEF if it is

developed or as independent data sets if not.

6	MFWP exchange adult 	MFWP will input 2003 adult abundance data into 	Data were provided to regional staff as an independent data set.   Data

abundance in the wild 	MFISH, including trend, count and references, and 	were sent to the Regional Fish Biologist for the development of a draft

data, progress reported 	exchange them with regional StreamNet in the 	Sightings DEF.

quarterly	DEF, if it is developed or as an independent data set

if not.

7	ODFW development of 	ODFW will maintain existing anadromous, resident, 	Routine maintenance was performed on Oregon's abundance and index

adult abundance in the 	and non-game abundance and index trends.  Any 	trend information during the quarter, including requesting information

wild data, progress 	updates will be the result of QA/QC efforts and 	from data providers in order to perform trend corrections, and to

reported quarterly	easily incorporated trend data, and will be provided 	update StreamNet trends.

in two exchanges, the first by April 4, 2005.

WE No.:	159	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 12 of 56

A trend submission was made to StreamNet on July 19th.  The submission consisted of 672 updated trends (containing 2,696 data records), including 232 new trends.  As a result of our comprehensive QA/QC efforts, 808 EscData records and 32 EscData Comments were tagged for deletion, as they were replaced with corrected information.  The majority of these corrections were associated with beginning and/or ending dates, not the counts themselves.  The 672 trends were broken out into the following data types: Adult Return Dam/Weir counts (26), Adult Return-Estimates of Spawning Population (57), Adult Return-Redd counts (178), Adult Return-Peak/Other Spawning Counts (409), and Harvest-Freshwater/Estuary (2).

8	ODFW development of 	ODFW will maintain existing anadromous, resident, 	Routine maintenance was performed on Oregon's abundance and index

adult abundance in the 	and non-game abundance and index trends.  Any 	trend information during the quarter, including requesting information

wild data, second 	updates will be the result of QA/QC efforts and 	from data providers in order to perform trend corrections, and to

exchange, reported 	easily incorporated trend data, and will be provided 	update StreamNet trends.

quarterly	in two exchanges, the second by 9/15/05.

Trends were updated based on Steering Committee direction, and necessary corrections that came to light during the July data submission were made.  The updated and corrected data were submitted to the Region in early August.  The submission included 19 trends (containing 66 data records), broken out into the following data types: Adult Return-Estimates of Spawning Population (1), Adult Return-Redd counts (8), Adult Return-Peak/Other Spawning Counts (10).  Work was also started on a stack of corrections for trends that are no longer updated.

9	WDFW development of 	WDFW will update and enhance the existing natural	To finalize some old lingering responsibilities, the Location Data

adult abundance in the 	spawner database (escapement estimates and/or 	Manager prepared existing steelhead Trend and EscData table records

wild data, progress 	detailed counts) for available species, and will 	per the current DEF.  The current DEF expects both CountValue and

reported quarterly	exchange the data in the DEF.	Count/Mile data to be reflected on the same record instead of on

separate records and trends.  This effort revealed some interesting

complexities about data used in two source publications.  The data will

be submitted after she confirms any other records from the same

publications.

The WDFW Project Manager requested and reviewed Washington EscData on file at the regional StreamNet office to verify eastern Washington datasets that have already been provided by the Yakama Nation through CRITFC, to assist in work planning for eastern Washington next fiscal year.

WE No.:	159	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 13 of 56

There were 30 records added to the Escapement data set in the fourth quarter.  We double checked all 2004 data entered into the Escapement data set and changed the table format to meet DEF requirements before sending the data set to be exchanged.  We also received feedback as to what changes needed to make for next Escapement data set exchange.  The Stream Survey data set is continually being populated with historic and current data to meet the needs of both StreamNet and Washington Department of Fish and Wildlife.  There were 1,618 records added in the fourth quarter to the Stream Survey data set.  A couple of issues occurred with the Stream Survey data set that are currently being resolved.

Work Element:	159	Submit/Acquire Data

Work Element Title:	4	Develop hatchery release data

The hatchery release data category is currently undergoing revision by the StreamNet project.  Release data have in the past been obtained from the Regional Mark Information System (RMIS).  However, a significant number of release records in RMIS is aggregated into Pacific Salmon Commission codes, which combine ("roll up") multiple locations and release dates so the data can not be assigned a specific release location.  StreamNet is in the process of obtaining hatchery release information based on individual release locations and times.  During this year, we will initiate a new system of obtaining release data directly from the management agencies and make them available regionally as soon as possible, although some individual release locations may not be available this year.  Release data for resident species under base funding will be developed only where the data are readily available (primarily Montana).  Efforts will be made to complete cross references between PSC release codes and LLID stream

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	FWS development of 	FWS, on an ongoing basis, will acquire and process 	The Project Leader performed the final processing of 2005 fish release

hatchery release data, 	hatchery release information from national fish 	information, moving it into the format for RMIS submission.  That

progress reported 	hatcheries in the region, update the CRiS SR80s file,	information was uploaded to RMIS at the end of September.

quarterly	and exchange the data in DEF with regional

StreamNet.

2	IDFG development of 	IDFG, on an ongoing basis, will work with IDFG 	IDFG StreamNet met with IDFG Fisheries personnel to begin

hatchery release data, 	Fisheries staff to identify hatchery release locations	development of a common hatchery data management system.

progress reported 	and incorporate hatchery release data into

quarterly	StreamNet.  Hatchery release locations and data will

be exchanged to regional StreamNet.

3	MFWP development of 	MFWP will exchange Montana's hatchery release 	Data were provided to regional staff as an independent data set for the

hatchery release data, 	data after development of a resident DEF and/or 	last 10 years.  Regional staff are looking at these data as they

progress reported 	modifications to the existing anadromous hatchery 	consider a resident fish hatchery release DEF.

quarterly	release DEF.  The number of years and number of

waters included will need to be determined.

WE No.:	159	Title No.:	4	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 14 of 56

4	ODFW development of 	ODFW will compile and submit anadromous 	Data compilation and submission was delayed by work on the new

hatchery release data, 	hatchery releases through 2003, and 2004 where 	DEF.  Work on the DEF will continue, with the hope of submitting

progress reported 	available, in an unrolled format if possible.	data during the first quarter of FY-06.

quarterly

Work Element:	159	Submit/Acquire Data

Work Element Title:	5	Develop hatchery return data

Develop and maintain (update) information on the return, disposition and straying (e.g., from other hatcheries) of adult fish returning to hatcheries, including information on coded wire tags.  This is an anadromous related task only.  Priority will be placed on updating total return and egg take data through 2003.  Development of disposition data is lower priority and would require additional resources.   Updated data will be exchanged with the regional StreamNet database at PSMFC at least annually.  This is a high priority data set.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	FWS development 	FWS will complete work on the new program to 	Because of an emphasis on updating information that had already

(conversion) of hatchery	convert information from the FWS CRiS format to 	been transformed to the new DEF, code producing records for the

return data, progress 	the new StreamNet hatchery returns format.  	HatchRetDetail table was not completed this fiscal year.  This item

reported quarterly	Deliverable will be a dBASE program to convert to 	will be completed in FY-06.

the new data structure.

2	IDFG development of 	IDFG will compile the 2004 field season hatchery 	IDFG StreamNet compiled 2004 hatchery return data.  Submittal is

hatchery return data, 	return data from IDFG and submit in DEF to 	waiting for completion of a quality review of trends.

progress reported 	regional StreamNet.

quarterly

3	ODFW development of 	ODFW will compile data on returns to ODFW 	Compilation of Oregon hatchery return data was completed this

hatchery return data, 	hatchery facilities (updated through 2003 returns 	quarter, and data were submitted in the new format to the Region on

progress reported 	where possible) and exchange in DEF to regional 	July 19th, amounting to 154 hatchery return trends containing 1,481

quarterly	StreamNet.	annual data records.  Oregon hatchery return data are now current

through 2004.

4	WDFW development of 	WDFW will complete the conversion of old DEF 	A total of 4,300 records were resubmitted in the new data exchange

hatchery return (old) 	hatchery returns data to the new DEF for all species	format, following a review of issues identified in last quarter's initial

data, first quarter	and sites, and exchange to regional StreamNet 	submission.  This exchange included all historical data through the

when complete.	2003 return year.  However, some trends were withheld due to

accounting problems that will be resolved later.  Washington

Department of Fish and Wildlife hatchery return data requires

ongoing review and correction due to a past lack of adequate internal

QA/QC practices.

WE No.:	159	Title No.:	5	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 15 of 56

Work Element:	159	Submit/Acquire Data

Work Element Title:	6	Develop dam and fish passage facility data (mid-priority)

Data on dam and fish passage facilities will be maintained and updated as necessary and possible by each of the state StreamNet sub-projects.  Updated data will be exchanged with the regional StreamNet database at PSMFC.  This is a key data set, but mid priority for update under base level funding.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

2	MFWP development of 	MFWP will update dam facilities data, in the DEF, 	The database was updated in the 4th quarter.

dam and fish passage 	as necessary or possible.

facility data, progress

reported quarterly

3	ODFW development of 	ODFW, on an ongoing basis, will maintain existing 	Routine maintenance was performed on Oregon's existing dam and fish

dam and fish passage 	dam and fish passage facilities information.  Any 	passage facilities information during the quarter.  Effort this year is

facility data, progress 	updates will be the result of QA/QC efforts and 	focused on improving the quality of existing information rather than

reported quarterly	easily incorporated dam and fish passage data.	updating or adding to the existing data.  For details on this quarter's

QA/QC efforts, see Work Element 160, Title 3; Milestones 5 and 6.

Work Element:	159	Submit/Acquire Data

Work Element Title:	7	Develop hatchery facility data (key dataset, update once per year)

Develop and maintain information on anadromous and resident hatchery facilities, including information on location, design,  management and authorization.  Information will be updated as necessary and exchanged to the regional database at PSMFC.  This is a high priority data set.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	FWS development of 	FWS will collect and add any revised information on	Personnel changes are imminent at several hatcheries, and will be

hatchery facility data, 	National Fish Hatcheries to the CRiS sr80s file.	reflected in next year's data submission.

progress reported

quarterly

3	MFWP development of 	MFWP will update the StreamNet hatchery database	The database was updated in the 4th quarter.

hatchery facility data, 	with Montana's public and private facilities.

progress reported

quarterly

4	ODFW development of 	ODFW, on an ongoing basis, will maintain and 	Routine database maintenance was performed this quarter.

hatchery facility data, 	update hatchery facility information, as needed,

progress reported 	based on errors found in the Oregon hatchery

quarterly	facilities information, including facility location

information.

WE No.:	159	Title No.:	7	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 16 of 56

5	WDFW development of 	WDFW will update the hatchery database, adding 	A few new Hatchery table records were submitted to support the

hatchery facility data, 	records and improving field entries as warranted, 	hatchery return data submission.  During that effort, we unexpectedly

progress reported 	including record updates for related tables (i.e.  	found a source to populate the Hatchery table's AuthorizationID data

quarterly	HatcheryXProduction data), and will exchange data.	and plan to submit it when the pending Hatchery DEF proposal is

adopted.

Work Element:	159	Submit/Acquire Data

Work Element Title:	8	Develop harvest data

StreamNet has traditionally posted harvest data from in-river sport fisheries.  This will continue in FY-06, but we will also explore the availability of ocean / commercial harvest data as estimated by others and determine whether these data can be realistically obtained and standardized for regional distribution.  Higher priority is assigned to anadromous species.  Updated data will be exchanged to the regional StreamNet database at PSMFC.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC development of	CRITFC will update available ocean and mainstem 	Harvest data maintained on other web sites were identified and links

harvest data, progress 	Columbia River harvest numbers through 2004, as 	were provided for listing on the StreamNet website.

reported quarterly	possible (dependent on other agencies), and

exchange with regional StreamNet.

2	IDFG development of 	IDFG will compile and exchange the 1997- 2004 	IDFG StreamNet obtained Idaho harvest data, but progress has been

harvest data, progress 	freshwater harvest data from IDFG.	stalled because of work on quality review of redd count trends.

reported quarterly

4	ODFW status review of 	ODFW will maintain existing harvest trends.  Any 	Routine maintenance was performed on Oregon's existing harvest

harvest data, second 	updates will be the result of QA/QC efforts, and 	information during the quarter.  Effort this year was focused on

phase, reported quarterly	easily incorporated trend data.  Any updated sport 	improving the quality of existing information rather than updating or

harvest trends will be exchanged in two phases, the 	adding to the existing data.  For details on this quarter's QA/QC

second by 09/15/05.	efforts, see WE 160; WE Title No 3; MS No 5.  Corrected harvest

trends were submitted during the quarter.  For details on the harvest

data submission, see WE 159; WE Title No 3; MS No 8.

WE No.:	159	Title No.:	8	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 17 of 56

Work Element:	159	Submit/Acquire Data

Work Element Title:	9	Develop hydrography data

Maintain the regionally consistent routed hydrography layer at the 1:100,000 (100K) scale for which StreamNet is the official keeper.  This LLID based hydrography has been the basis for georeferencing and displaying locations for all other data in the StreamNet database, and as such is an essential data set.  In FY-06 we will continue to maintain these data, but emphasis will shift to development and use of a mixed scale hydrography (100K plus 24K streams that have attached fish data) as an intermediate step toward the eventual conversion to 24K when a regionally consistent routed 24K hydrography becomes available from other entities

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	IDFG maintenance of 	IDFG, on an ongoing basis, will maintain and 	IDFG StreamNet made over 300 modifications to the PNW

hydrography for Idaho, 	update, as necessary, the 1:100,000 scale 	hydrography.  The changes will be submitted as soon as IDFG

progress reported 	hydrography files for Idaho.	incorporates them internally.

Quarterly

2	MFWP maintenance of 	MFWP, on an as needed basis, will continue to 	No action was taken this quarter.  NRIS will convene a MT hydro

hydrography for 	update the routes using the updated NHD layer, 	meeting in the next quarter.

Montana, progress 	including lakes; quality check the cross-reference

reported quarterly	between the LLID system and MFWP's water code

system, and will pursue any needs developed by the

Steering Committee for a 1:24 K product.

3	ODFW maintenance of 	ODFW, on an ongoing basis, will maintain and 	Routine maintenance was performed on Oregon's 1:100,000 scale

hydrography 	update, as necessary, the 1:100,000 scale 	hydrography information during the quarter.  The GIS Analyst

development for 	hydrography files for Oregon.	followed up on stream route issues related to Oregon’s trend data

Oregon, progress 	submission this quarter, and suggested updates/changes to the

reported quarterly	StreamNet hydrography data.

4	ODFW development of 	ODFW, on an ongoing basis, will assist regional 	The GIS Analyst focused significant attention on Framework/ NHD

hydrography for Oregon,	staff with the development of a hybrid 100k and 	hydrography data development, including participating in StreamNet

progress reported 	24k hydrography layer that will enable display of all	Steering Committee discussions related to the inevitable conversion to

quarterly	distribution data in a linear format.	the NHD model and the quickening pace at which the Framework

hydrography data from WA and OR will be converted to this model, and sharing ideas about the challenges and trade-offs of potentially adopting the NHD hydrography data model to serve as the regional streams data template.  He also worked with Regional StreamNet staff to summarize StreamNet's objectives and requirements related to a regional hydrography dataset in preparation for the joint Framework /StreamNet hydrography meeting held in mid-September.  He attended the meeting, where Rick Jordan from the Forest Service demonstrated their efforts at building the Framework data into the NHD model.  Next steps include demonstration of the tools for creating, editing and maintaining event data on the NHD route system and working toward a decision point on the regional hydrography product for StreamNet.

WE No.:	159	Title No.:	9	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 18 of 56

5	WDFW development of 	WDFW will build and submit a "hybrid" layer 	The Fish GIS Manager completed development of the mixed-scale

hydrography for 	containing 24K representation of all 100K 	hydrography layer for Washington state, including a complex system

Washington, first quarter	Washington streams plus only 24K streams 	of linework and attribute management programs.  Late in the

containing StreamNet data.	development, an intense, statewide review of stream names was

undertaken when errors (omission, spelling) were found in the Geographic Names Information System (GNIS) database which had been the basis for the stream names in our GIS layer.  USGS maps were used to verify GNIS-supplied names.  Upon completion (September), three reference basins were sent to the StreamNet GIS Manager for review and comment.  These basins provided examples of the Washington/Oregon Columbia River border, the Idaho/Washington border, and the Washington/Oregon border in NE Oregon.

Our first pass to add the Washington Stream Catalog codes to the hydrography as an attribute at the arc level is almost complete for the Non-Columbia river streams.  The Location Data Manager created routines to verify any attribute assignments that were missed and a plan to tackle the omissions.  She also tested one Columbia River drainage to assess the feasibility of making this a statewide effort.  The Columbia River will require a different process but it is feasible.  Stream Catalog codes are used to a lesser extent for sampling location identification in eastern Washington.

Work Element:	159	Submit/Acquire Data

Work Element Title:	10	Develop data to track habitat restoration / improvement projects

Preliminary work has been completed on developing data related to habitat restoration and improvement projects, but regional priority has not been assigned to StreamNet for developing these data.  Even though we have developed an improved DEF for these data, this now is a low priority data type under current base funding.  We are ready should a higher priority be assigned by regional entities.  We believe that there is not yet a comprehensive compilation of all of this kind of data in the region, and we suggest that a project be tasked with obtaining this information from the many sources of such data, including OWEB, WSRFB, US Forest Service, BLM, tribes, and the PCSRF database, updating it annually, and providing it in a regionally standardized format.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC development of	CRITFC will provide tribal PCSRF project 	Projects approved through 2004 are available in a shapefile and

habitat projects tracking	information.	associated databases.  The project approval process for 2005 began

data, progress reported 	during the fourth quarter and will continue into the first quarter of

quarterly	FY-06.  These projects will be added to the database in the next fiscal

year.

WE No.:	159	Title No.:	10	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 19 of 56

2	MFWP development and	MFWP will continue to collect, centralize and 	Data editing is ongoing.  The data exchange originally planned for the

exchange of habitat 	maintain all stream restoration projects data for 	second quarter was actually performed in this quarter.

projects tracking data, 	Montana using the "Future Fisheries Interface" and

first data exchange 	exchange the data to regional StreamNet in two

second quarter	exchanges, the first by 03/31/05.

3	MFWP development and	MFWP will continue to collect, centralize and 	Work continued on this ongoing task.  Data were exchanged in this

exchange of habitat 	maintain all stream restoration projects data for 	quarter.

projects tracking data, 	Montana using the "Future Fisheries Interface" and

first data exchange 	exchange the data to regional StreamNet in two

fourth quarter	exchanges, the second by 09/30/05.

4	MFWP participation 	MFWP, on an ongoing basis if the opportunity 	No opportunities to capture project information occurred this quarter.

with habitat projects 	arises, will participate in any regional activities

tracking data, progress 	related to restoration projects.

reported quarterly

6	WDFW development of 	WDFW will complete conversion and exchange of 	The Olympia data compiler began compiling and exchanging habitat

habitat projects tracking 	Washington habitat restoration project information	restoration project data, in late September.  A work plan was drafted

data, progress reported 	extracted from IAC's PRISM system and 	to orient the compiler to the LIP, PRISM, and PCSRF sources for

quarterly	2000-2002 NWIFC PCSRF data, but only if a final 	these data in Washington state, and copies of relevant past work were

DEF exists for this data category.  They will also 	provided for his study.

scope out additional content from WDFW's LIP

initiative and other sources as time permits.

Exchange of data to regional StreamNet will occur

60 days after a 24K hydrography layer is available

(WE 159, Title 9, Milestone 5).

Work Element:	159	Submit/Acquire Data

Work Element Title:	11	Develop fish barrier data

Develop and maintain data sets for barriers to fish migration.  This category is still being organized.  Existing data on adult barriers will be maintained and updated as practical and exchanged with the regional database at PSMFC.  Other sources of barrier data will be explored.  Work on juvenile barriers and culverts will require revisions to the DEF.  The primary emphasis is on anadromous species except in non-anadromous areas.  This is a low priority data set under current base funding, and will be addressed as time

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

2	MFWP development of 	MFWP will maintain barrier location, species 	These data were updated in the 4th quarter.

fish barrier data, progress	affected and other fields on stream barriers in

reported quarterly	Montana.  Information will be collected on all

species regardless of life history.  Data will be

exchanged to regional StreamNet.

WE No.:	159	Title No.:	11	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 20 of 56

3	ODFW status review of 	ODFW, on an ongoing basis, will update and 	New .pdf barrier maps were created with embedded fonts so that users

fish barrier data 	maintain Oregon's Barrier data and minimal Fish 	without GIS related fonts would not experience difficulties interpreting

development	Barrier data development based on new barrier 	the map symbols.  Previous versions of these maps were replaced on

information, including information from 	the ftp site and several users were informed of the update.

non-ODFW sources.

5	WDFW development of 	WDFW will scope existing Washington state 	The Olympia data compiler reviewed and evaluated LLIDs in

fish barrier data, progress	barriers datasets for a pilot data submission this FY.  	conjunction with the QA/QC process with the Location Data

reported quarterly	Data sources will at least include the Salmon and 	Manager.  WDFW barrier locations that did not snap to LLIDs in the

Steelhead Habitat Inventory and Assessment 	QC routines were individually reviewed for the Columbia Basin and all

Project (SHIAP) and TAPPS (now renamed as the 	other areas.  The research of best strategies to tie barrier data with

Fish Passage and Diversion Screening Inventory - 	LLIDs is still on-going and we are still in process of cross-referencing

FPDSI) databases.  Barriers data will be exchanged.	fishway data.

A final selection of 12,265 culvert records for submission to the Regional StreamNet database was made.  These records were converted to the new exchange format.  The revised format for the WDFW Fish Passage and Diversion Screening Inventory database is still under review by the Information Technology Services division (ITS) and awaits final approval.  Part of this process is a QA/QC of the current database records.  Because existing errors will be corrected in this process, the conversion and submission of other WDFW barrier records will commence after ITS final approval.  A preliminary conversion of the fishway and dam records to the new exchange format is underway.

We completed data exchange format transfer documentation for the

Washington culvert barriers dataset and internal conversion process

documentation for other barriers data.

The Olympia Data Compiler identified and documented missing or

questionable data in the WDFW hydrography layer for further

evaluation by the GIS Manager.  He also continued cooperation with

WDFW Fish Passage and Diversion Screening Inventory personnel

regarding barrier conversion issues and worked with them on defining

a format for including natural barriers in their barriers database.  This

data set is being developed in close conjunction with WDFW

StreamNet staff

WE No.:	159	Title No.:	11	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 21 of 56

Work Element:	159	Submit/Acquire Data

Work Element Title:	12	Develop juvenile fish data

Develop and maintain information on smolt production (as determined from smolt traps), juvenile abundance (as determined through snorkel, electrofishing, and other surveys), and smolt density model estimates.  Primary emphasis will be on maintaining the existing smolt density model data and development of a DEF for these data.  The rest of the work for this data category is still under development and will require additional resources to accomplish.  This is a low priority data set under current base funding, and will be addressed as time and other priorities allow.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC development of	CRITFC will provide tribal juvenile abundance 	Juvenile data were provided in the third quarter.  No additional work

juvenile fish data, 	and/or outmigration data as time and availability 	was done this quarter.

progress reported 	allow.

quarterly

2	ODFW maintenance of 	ODFW, on an ongoing basis, will maintain existing 	Routine maintenance was performed on Oregon's existing juvenile

juvenile fish data, 	juvenile data records.  Any updates will be the result 	abundance information during the quarter.  Effort this year is focused

progress reported 	of QA/QC efforts and easily incorporated trend 	on improving the quality of existing information rather than updating

quarterly	data.	or adding to the existing data.  For details on this quarter's QA/QC

efforts, see Work Element 160, Title 3, Milestones 5 and 6.

3	WDFW maintenance of 	WDFW will continue maintaining and updating 	The Vancouver Data Compiler provided data assistance to a technician

juvenile fish data, 	smolt trap databases on all traps in Region 5 (lower 	who was writing the preliminary 2005 report and building tables for

progress reported 	Columbia River).	local biologists.  She also provided 2004 tables of data to Olympia

quarterly	based biological staff members.  These reports are used in order to gain

funding to continually operate these traps.

Work Element:	159	Submit/Acquire Data

Work Element Title:	13	Develop fish age data

Develop and maintain information on age/sex composition of returning adults, primarily for anadromous species.  Emphasis on this data type will increase once the draft DEF is tested and finalized.  This is a low priority under current base funding.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC development of	CRITFC will exchange CRITFC age data on sockeye	Data were updated in a previous quarter.  No additional work was done

fish age data, progress 	populations and Bonneville Dam sampling.	this quarter.

reported quarterly

2	FWS development of 	FWS will finish work on the new program to 	Minor changes in the data transformation program were made, and

fish age data, progress 	transform age information from the CRiS format to	the resultant Age data conforms to an extent that permits loading

reported quarterly	the new StreamNet format.	by StreamNet.

WE No.:	159	Title No.:	13	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 22 of 56

3	IDFG development of 	IDFG will compile and submit the 2004 field season 	IDFG StreamNet compiled 2004 age composition data.  Submittal is

fish age data, first two 	age data from IDFG.	waiting for completion of a quality review of trends.

Quarters

4	ODFW maintenance of 	ODFW, on an ongoing basis, will maintain existing 	Age data were compiled and evaluated in the most recent draft version

fish age data, progress 	age data trends.  Any updates will be the result of 	of the StreamNet DEF, which includes a new Age Data table.  There

reported quarterly	QA/QC efforts and easily incorporated trend data.	were issues that came up while using the new Age Data table and we

worked with Regional StreamNet staff to resolve them.

5	WDFW development of 	WDFW will update and exchange age data records 	The Data Manager created a new Age Table based on the new Data

fish age data, first phase 	gleaned from hatchery returns and adult abundance 	Exchange Format.  He reviewed all 4,847 data entries in the Age

in first quarter	exchanged data.  Data will be exchanged twice, with 	Table, updating those entries to accommodate new fields recently

the first exchange  by 11/30/04.	created for that table.  He submitted the Age data set to PSMFC for

exchange, and awaits confirmation and initial review of this

submission from the StreamNet Regional Data Manager.

Work Element:	159	Submit/Acquire Data

Work Element Title:	14	Develop production factor and run reconstruction data

Develop and maintain information on survival, production factors, spawner / recruit estimates, and run reconstruction.  This is a low priority data type under current base funding, but the existing spawner / recruit estimate data will be maintained.  Current effort will focus on what aspects of this kind of data are most needed.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

No work was done on this title during the quarter.

Work Element:	159	Submit/Acquire Data

Work Element Title:	15	Develop diversion screening data

Explore the availability of data on diversion screening.  Capture data on screens as time and other priorities allow.  The DEF will need to be finalized before much can be done with this data type.  This has been a low priority data set under current base level funding, although NPCC has recently expressed interest in these data..

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	MFWP development of 	MFWP, if data are available, will collect diversion 	Existing records were maintained.  No new records were added.

diversion screening data, 	screening data from the MFWP Habitat Bureau

progress reported 	collected as a result of FRIMA activities in

quarterly	Montana and exchange them.

WE No.:	159	Title No.:	15	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 23 of 56

Work Element:	159	Submit/Acquire Data

Work Element Title:	16	Develop other data sets

On an opportunistic basis, develop other types of data as available or as requested by FWP participants.  This relates to data relevant to StreamNet objectives which would be developed by StreamNet cooperators.  Development of other data by StreamNet is a low priority under current base funding.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

5	MFWP development of 	MFWP will provide updated genetic results 	Data entry continued during the quarter.

other data sets, progress 	information on Montana's species of concern by

reported quarterly	08/01/05.  They will also explore providing data on

Whirling Disease results, fishing pressure data on

Montana's lakes and streams, and other data sets if

appropriate.

7	ODFW development of	ODFW, as requested or available, will work with 	Oregon StreamNet’s Data Technician worked on getting existing

other data sets, progress 	ODFW and other agency staff to facilitate either 	independent native non-game fish distribution information into one

reported quarterly	the incorporation of their data into StreamNet or 	database, in preparation for future inclusion into StreamNet.

independently posting their data on the StreamNet

web site (opportunistically, and as time allows).	The Data Analyst reviewed Fishery Management and Evaluation Plan

documents from NOAA to identify independent data set opportunities.

9	ODFW development of	WDFW, on an opportunistic basis, will work with	WDFW compiled and submitted 2004 data tables and the final report

other data sets, progress	FWP supported projects in the state to assist them	from the Joint Stock Assessment Project for resident fish above Chief

reported quarterly	with submission of their data sets to StreamNet for archiving	Joseph Dam for posting as a StreamNet Independent dataset.

and dissemination as part of the formal DEF or as

Independent Data Sets.

Work Element:	159	Submit/Acquire Data

Work Element Title:	17	Archive and deliver Independent Data Sets

On an opportunistic basis, encourage other entities to submit their data, in native format, to StreamNet for posting on the Independent Data Sets page.  This relates primarily to data relevant to StreamNet objectives that would be developed by other agencies or projects, but could also include data developed by StreamNet cooperators outside of the DEF.  Actual acquisition, standardization, georeferencing and distribution of these data would be dependent on available time and funding, so these data will be posted in native format.  The Region will be responsible for receiving and posting Independent Data Sets.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	PSMFC development of 	The Region, on an ongoing and opportunistic basis, 	We received and posted data sets and reports for 2003 and 2004 for

independent data sets 	will coordinate with BPA and BPA contractors, 	WDFW's "Resident Fish Stock Status Above Chief Joseph and Grand

archiving and delivery, 	StreamNet cooperators, and others to capture data 	Coulee Dams" project.

progress reported 	sets, reports, and other electronic materials for

quarterly	inclusion on the StreamNet Independent Data Sets 	When a data set is sent for inclusion on the IDS web page, we must

(IDS) Internet page and post these items as IDS.	enter the information provided into a database to make it available.

WE No.:	159	Title No.:	17	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 24 of 56

Until now we had been doing this by hand, taking substantial time.  This quarter a program was written to allow a simple drag and drop operation to add the data set into the database, greatly speeding addition of data sets once obtained.

2	PSMFC develop of 	The Region will review the StreamNet Links web 	The Independent Data Sets page can deliver not only data sets archived

independent data set 	pages to identify Internet sites that provide on-line 	by StreamNet, but can also act as a search tool for data sets on other

links archiving, progress 	data and add those sites to the Independent Data 	web sites.  This quarter PSMFC staff reviewed the StreamNet Links

reported quarterly	Sets (IDS) page.	pages to locate data sets of interest that could be linked to from the

Independent Data Sets page.  Eighteen on-line data sources were

identified on the StreamNet links pages.  Of these, six were not

included on the IDS page because they were judged to be of inadequate

value, were too complex for Regional StreamNet staff to characterize,

or had ill-functioning web sites.  The remaining 12 now have metadata and a link on the StreamNet IDS page so that they may be found by users.  As part of this exercise an application was written to automate data transfer from the metadata creation tool to the database, thus saving substantial time for future independent data set submissions.

3	PSMFC develop input 	The Region, on an ongoing, opportunistic basis, will	The IDS submission tool was maintained in a functional condition.

tool to independent data 	solicit feedback on the use of the Independent Data

sets archive, progress 	sets submission tool, make changes to the tool and

reported quarterly	the IDS web page as appropriate, and assist users

with the IDS page and the IDS submission tool.

Work Element:	160	Create/Manage/Maintain Database

Work Element:	160	Create/Manage/Maintain Database

Work Element Title:	1	System administration

All StreamNet cooperators will manage and maintain the computer systems (hardware and software) necessary for supporting the tabular and GIS data systems at the regional and cooperating agency levels, including system backup.  This is a high priority work element that is essential to proper functioning of the project.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC computer 	CRITFC, on an ongoing basis, will manage, 	Backup capacity was added to the Library server and a backup was

system administration, 	maintain and enhance the computer systems 	provided to Regional staff.  These backups will occur at regular

progress reported 	(hardware and software) necessary for supporting 	intervals on an ongoing basis.

quarterly	the StreamNet Library, including system

administration, backup and recovery, hardware and 	The Librarian evaluated available open-source cataloging systems to

software upgrades, and security.	replace the commercial software presently used.  She recommended

evaluation of the Koha program for possible use by the Library.  The

Database Programmer set up a test bed for evaluating the Koha system.

WE No.:	160	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 25 of 56

2	IDFG computer system 	IDFG, on an ongoing basis, will manage, maintain 	Work to install and configure new hardware continued on a low

administration, progress 	and enhance the computer systems (hardware and 	priority basis in order to make progress on StreamNet programming

reported quarterly	software) necessary for supporting tabular and GIS 	and database management needs.

data systems, including system administration,

backup and recovery, hardware and software

upgrades, and security.

3	MFWP computer system	MFWP, on an ongoing basis, will manage, maintain 	All necessary backups were completed.  FWP staff at the Montana

administration, progress	and enhance the computer systems (hardware and 	State Library are now part of the FWP network rather than the

reported quarterly	software) necessary for supporting tabular and GIS 	Library.  The transition was smooth.

data systems, including system administration,

backup and recovery, hardware and software

upgrades, and security.

4	ODFW computer system	ODFW, on an ongoing basis, will manage, maintain 	The GIS Analyst developed a DRAFT general purpose ODFW

administration, progress	and enhance the computer systems (hardware and 	Internet Map Server (IMS) web site.  Feedback was sought from select

reported quarterly	software) necessary for supporting tabular and GIS 	users, and functionality was added based on beta test results, including

data systems, including system administration, 	more location and mapping functions and the implementation of

backup and recovery, hardware and software 	custom symbols for hatchery related features and fish passage barriers.

upgrades, and security.	The site will be used to share ODFW spatial information with agency

biologists, and to solicit additions and corrections to these data.

Eventually, the site will be release for use by all resource managers

and the general public.

Routine operating system updates and patches were installed during

the quarter on all project servers.  Staff researched and drafted 	documentation for computer purchases and submitted it to Regional

StreamNet for review and approval.

5	PSMFC computer 	The Region, on an ongoing basis, will maintain and 	Regional GIS Software was patched with the latest Service Packs and

system administration	update, as necessary, the hardware and software 	the Internet Map Server received an OS upgrade to Windows 2003

necessary to accomplish StreamNet's mission, 	Server.  The regional primary web server was upgraded with Apache

including system administration, system backup and 	and Cold Fusion security patches.  Service Pack updates were applied

recovery, and security.  Specific functions include:	to all servers with Windows operating systems.  The web query

1.  Management and maintenance of the GIS system,	system was upgraded for better stability and handling of web robot

including ArcView, ArcGIS and other tools, 	Internet traffic.  Uptime for the primary web server was near 100%

extensions and projects, that constitute the regional	for Q4.

Geographic Information System;

2.  Maintenance and upgrade of the StreamNet web

server and software, including programming, system

security, etc., with a target of the web server being

on line and operational over 99.5% of the time;

WE No.:	160	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 26 of 56

3.  On an ongoing and as time allows basis, assist

with development of XML schema based options

for both incoming and outgoing data and continued

exploration of how XML can enhance data

exchange; and,

4.  Management and maintenance of the database

servers and SQL Server software and databases;

installing updates, patches and service packs as they

become available, managing logins and permissions,

and routine backup of all StreamNet databases.

6	WDFW computer 	WDFW, on an ongoing basis, will manage, maintain	The WDFW Olympia and Vancouver offices were plagued by

system administration, 	and enhance the computer systems (hardware and 	widespread communications equipment failures this quarter.  Joint

progress reported 	software) necessary for supporting tabular and GIS 	work between our two offices was stalled from time to time, slowing

quarterly	data systems, including system administration, 	progress to some degree this quarter.  WDFW Information Systems

backup and recovery, hardware and software 	has hopefully resolved the problems.

upgrades, and security.

Work Element:	160	Create/Manage/Maintain Database

Work Element Title:	2	Application and interface development

All StreamNet cooperators will develop and maintain computer applications and interfaces that facilitate the entry, management and dissemination of tabular and GIS data at the regional and subcontracting agency levels.  This will include development of new applications and tools as well as maintenance or modification of existing applications.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC development of	CRITFC, on an ongoing basis, will develop and/or 	All databases and applications needed to provide the data described in

applications and 	maintain computerized databases, applications and 	WE 159 were maintained and updated in the fourth quarter, as

interfaces	interfaces that facilitate the entry, compilation, 	appropriate.

management and dissemination of tabular data.

2	IDFG development of 	IDFG, on an ongoing basis, will develop and/or 	The initial user interface and database design for the new Spawning

applications and 	maintain computerized databases, applications and 	Ground Survey using .Net was completed.  A coordination effort with

interfaces	interfaces that facilitate the entry, compilation, 	IDFG fishery biologists began to fine tune the application.

management and dissemination of tabular and GIS

data.	Work continued on the redesign of the IDFG StreamNet database.

This included creating a single master hydrography database and

formatting to match the new hatchery returns and age composition

data exchange formats.  Existing StreamNet data were migrated into

the new database, but still requires a review and edits.

WE No.:	160	Title No.:	2	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 27 of 56

3	IDFG develop automated	IDFG, on an ongoing basis, will work with the Idaho	Smolt trapping data from 1990 to 2004 were captured from existing

data export for Idaho 	Supplementation Studies project to increase the use	spreadsheets and consolidated into a central database.  Web-based

Supplementation Studies	of the IDFG/StreamNet Spawning Ground Survey 	reports were developed for querying and reviewing the data.  Revisions

and Juvenile Trapping programs by IDFG biologists 	are being made in coordination with IDFG fishery biologists before

to create automated export of these data to 	posting to the web.

StreamNet DEF for inclusion in the StreamNet

database.

4	MFWP development of 	MFWP, on an ongoing basis, will develop and/or 	Support to Fisheries Division staff administering the program and

applications and 	maintain computerized databases, applications and 	using the system occurred.

interfaces	interfaces that facilitate the entry, compilation,

management and dissemination of tabular and GIS

data.

5	ODFW development of 	ODFW, on an ongoing basis, will develop and/or 	We began designing an agency geo-database to store ODFW spatial

applications and 	maintain computerized databases, applications and 	datasets, as well as other common base data.  In efforts to populate

interfaces	interfaces that facilitate the entry, compilation, 	the geo-database, we acquired updated city and watershed datasets.

management and dissemination of tabular and GIS 	We also loaded the street map dataset to provide detailed street

data.	information.  Digital Elevation Model (DEM) data were processed in

preparation for loading.  A separate geo-database was also created

which will store data for streams, fish distribution, barriers,

observations and other aquatic resources.

6	ODFW development of 	ODFW, on an ongoing basis, will continue 	Development of a corporate information system continued this

corporate information 	development of a corporate information system, 	quarter with attention being given to a number of disparate

system	developing functional interfaces as part of a 	components of the system.  Efforts this quarter benefited individual

corporate system.	database systems, but collectively contributed to the development of

the corporate system.

7	PSMFC maintain and 	The Region, on an ongoing basis, will maintain and 	The LLID/NHD conversion tool is still available by request, but

improve LLID/NHD 	improve the LLID/NHD hydrography conversion 	because the NHD crosswalk table has not been kept in synch with

conversion tool	tool.  The immediate need is to complete error 	changes in the latest version of NHD, the tool has been taken

trapping routines and polish the final application.	off-line to avoid confusing end users.

8	PSMFC development of 	The Region will create an Online Event Mapper to 	It appears that the Internet based solutions to this problem are quite

online location identifier	allow users to create event tables based on 	expensive as they would require significant upgrades to StreamNet's

tool (event mapper)	1:100,000 scale hydrography over the Internet.	GIS license (from ArcIMS to ArcGIS Server).  In the meantime, the

new tools built into the desktop ArcGIS software perform many of

the functions of the  original Event Mapper tool without its

limitations.  The GIS Specialist suggests that we consider making

pooled licenses for desktop ArcGIS software available through the

Internet as a possible solution to meet our needs.

WE No.:	160	Title No.:	2	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 28 of 56

9	PSMFC development of 	The Region, on an ongoing, as needed basis, will 	Work was done on a test linking of water quality data with StreamNet

applications and 	develop and/or maintain computerized databases, 	fisheries data via an XML interface developed by Oregon DEQ.

interfaces	applications and interfaces that facilitate the entry,

compilation, management and dissemination of

tabular and GIS data.  They will assist cooperating

agencies with tool development, as requested.

Tools may include input interfaces, error checking,

geographic locators, etc.

10	WDFW development of 	WDFW, on an ongoing basis, will develop and/or 	The Location Data Manager finalized an ArcGIS model to create a

applications and 	maintain computerized databases, applications and 	merged file of the hydrography sections that are currently managed in

interfaces	interfaces that facilitate the entry, compilation, 	62 separate chunks (one per basin, or WRIA).  The merged file allows

management and dissemination of tabular and GIS 	us to run a routine once instead of 62 times.

data.

Work Element:	160	Create/Manage/Maintain Database

Work Element Title:	3	Data (content) management

The StreamNet project will manage data at the regional and subcontracting agency levels to assure timely and accurate data flow from source to final distribution.  Activities include exchange of data to PSMFC, data loading, updating data, quality assurance procedures, metadata development, etc.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC data content 	CRITFC, on an ongoing basis, will perform 	The author field in the StreamNet catalog had some discrepancies

management, QA/QC	comprehensive QA/QC on all datasets maintained 	with the author field in the references database in the overall

by CRITFC.	StreamNet database.  These have all been merged and matched so that

the author fields are now compatible with the citation display format.

2	FWS data content 	FWS will add data, check quality, transform data to 	The FY-05 data submission was accepted and posted by StreamNet

management, QA/QC	DEF, and exchange data with StreamNet.	regional staff.

3	IDFG data content 	IDFG will conduct a data quality review of all 	The review of IDFG's redd count trends for Chinook, sockeye and

management, QA/QC	exiting IDFG redd count, dam/weir counts, 	steelhead was completed.  Because of splitting whole stream trends

freshwater harvest, hatchery returns and age 	into individual transect based trends the number of IDFG redd count

composition data.  Where necessary, they will edit 	trends increased from 113 to 779.  These included for the first time

these data sets to improve their accuracy and 	non-index trends.  The new trends were cross-referenced with the old

quality.	trends in order to facilitate migration of the redd count data.

4	MFWP data content 	MFWP, on an ongoing basis, will manage data at 	This ongoing work continued throughout the quarter.

management, QA/QC	the agency level, develop and maintain FGDC

compliant metadata for GIS data, and exchange data

to PSMFC according to deadlines specified in this

work statement.

WE No.:	160	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 29 of 56

5	ODFW data content 	ODFW, on an ongoing basis, will manage 	Staff responded to questions related to data submissions, and worked

management	ODFW-NRIMP and StreamNet data, including 	with the Region to resolve data exchange and other issues of concern.

metadata development/maintenance, QA/QC

activities, and work with regional staff as necessary 	The ODFW Facilities GIS dataset was redesigned, as the coding

to assure seamless loading of data into the regional 	scheme was in dire need of normalization.  A separate table to track

database.	dataset maintenance was also created.  The GIS Analyst developed

metadata for the new ODFW Facilities dataset and refined metadata

for the Hatchery Facilities dataset.

The Data Analyst researched and responded to an issue regarding

supercodes for Spawner Recruit trends that are Oregon’s responsibility.

6	ODFW data content 	ODFW, on an ongoing basis, will perform 	Staff continued efforts to ensure the data quality of Oregon's existing

management, QA/QC	comprehensive QA/QC on all Oregon Trends, Age, 	Trend information by executing quality control queries on the trend

Harvest, Dams, and Barrier datasets.	database and fixing the resulting trend errors.  Trends having non-consecutive Escape Data Begin/End Dates were completely corrected this quarter.  This effort is resulting in a number of trend corrections, corrections to stream data being sent to Regional StreamNet, adding new trends for old data not yet in the system, and adding new information to old trends in the system.  This also includes adding new trends to the database from data that were not captured previously.

9	PSMFC tabular data 	The Region, on an ongoing basis, will manage the 	Data submissions from agency compilers to StreamNet were numerous

content management, 	content and quality of the data stored at PSMFC 	this project quarter.  The highest percentage increase of new records

QA/QC	through the following actions:	appended to StreamNet tables included: age (4,847), hatchery returns

1.  They will examine the StreamNet database for 	(5,246 main and 2,479 detail), barriers (13,412 main and 294 fish

errors and report any found to the appropriate 	specific), locations (14,285), escapement data (5101), trend series

entity for correction.  They will continue to 	(467), references (205) and dams (142).  Twenty new tables were

improve error-checking capabilities;	created, populated with habitat restoration project information from

2.  The Regional Database Manager will update and 	MFWP in Montana.  An updated database of major StreamNet tables

append data as submitted by StreamNet participants.	is available for downloading in either MS Access 97 or 2000 database

He will maintain logs of data submissions and 	format.  To obtain these data, visit

major database changes, manage logins and 	http://www.streamnet.org/online_data.html and click on the

permissions, produce downloadable versions of the 	"Download the StreamNet database" link.

StreamNet databases to keep in synch with the

updated regional databases, create views and stored 	The StreamNet Library database was imported into StreamNet's

procedures for use by the web query system and in 	Reference table and synchronized.   Work was done to debug and

the data loading process, routinely backup all 	update all document URLs for online viewing of documents that have

databases, create and revise database structures and 	been scanned at the Library.

indexes, develop and run QA/QC processes on new

and existing data tables to Isolate missing, erroneous

or duplicative data, and work with source agencies

to correct problems;

WE No.:	160	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 30 of 56

3.  The Regional Database Manager will assist the

StreamNet Librarian to export the library reference

database of StreamNet documents for routine

inclusion in the StreamNet database for use by the

web query system; and,

4.  The Region will work with the Steering

Committee to complete a document describing the

QA/QC processes followed by project cooperators.

10	PSMFC GIS data content	The Region, on an ongoing basis, will manage GIS 	Coordination efforts related to the eventual migration to a

management	data content for the StreamNet project through the 	standardized 24k hydrography continued.  PSMFC hosted a meeting

following actions:	with the PNW Hydrography Framework and StreamNet GIS

1.  Whenever new tabular data with a spatial 	Specialists to discuss the plans of State and Federal agencies to adopt

component are submitted to the Region (e.g., fish 	24k NHD as the regional standard.  The possibility of enhancing

distribution, hatchery facilities, etc.), the GIS 	NHD to better meet the needs of regional users, including StreamNet,

Specialist will create regional GIS layers from this 	was discussed.

information where possible.  He will verify correct

format, accuracy and logical consistency of spatial

data sets and attributes through coordination with

state GIS contacts and then load data to the regional

database in coordination with the database

manager.  He will post mappable layers to the

online query system, the ArcIMS interactive

mapping system, and as downloadable layers for

StreamNet GIS users;

2.  The GIS Specialist will maintain a library of

StreamNet GIS layers for internal use and as

downloadable data on the web site with complete

documentation (metadata);

3.  He will obtain and refine layers such as ESUs,

ecoregions, or elevations, and create cross tables for

use by the query system;

4.  He will assist the database manager with the

spatial component of data and its implementation

online;

5.  He will coordinate efforts by the StreamNet

partners to maintain and update, as necessary, the

1:100,000 scale hydrography files for the states and

the PNW region;

WE No.:	160	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 31 of 56

6.  He will coordinate efforts by the StreamNet

partners to create a hybrid 1:100,000 / 1:24,000

scale hydrography for the states and the PNW

region, and will implement these changes at the

Regional office; and,

7.  He will integrate the functioning of the GIS

system with the StreamNet fisheries and habitat

database in support of the query system, and will

maintain up-to-date cross tables used via the

StreamNet web interface to select information by

geographic area.

11	WDFW data content 	WDFW, on an ongoing basis, will :	We created internal cross-reference tables and submitted relevant

management, QA/QC	1.  Manage data at the agency level, conduct quality	LocMaster and related location table submissions to support the data

checks, develop and maintain FGDC compliant 	submissions made this quarter.  This included our first effort to convey

metadata for GIS data, and exchange data to PSMFC	hatchery return capture locations in addition to the location of the

according to deadlines specified in this work 	hatchery handling the fish.

statement;

2.  Provide and update/geo-reference field data as 	We created a geodatabase to store any spatial information relevant to

needed for all StreamNet data submissions.  The 	fish that are codified into some part of Washington or Regional law.

improved geo-references generally contribute to 	One table captures the downstream point used to define sport catch

multiple data categories; and,	fishing boundaries for select rivers.  Another captures the Washington

3.  Create standardized storage formats and 	and Oregon boundary line.  We expect the information in this

protocols for area biologists to use with data 	geodatabase will be used for QA/QC routines.

collected at various fish collection facilities.

A geodatabase capturing river miles from the Washington Stream

Catalog was started for river mile 0 and 1 for the bigger coastal

streams.  This information will be used to generally QC the shift

between the 100K and 24K stream mouth starting points and research

the difficulties in developing a conversion factor between the Stream

Catalog river mile index points and river mile measures based on our

24K hydrography.

The WDFW Fish GIS Manager overhauled the internal spatial data format for the files that feed StreamNet's generalized fish distribution data from WDFW.  Separate events for the same species-run and location that were once stored on separate records (distribution, use types) are now assimilated into a single record based on a hierarchy (Spawning; then Rearing; then Presence).  This organization mirrors the approach we use to support our ArcIMS application SalmonScape and will greatly ease data conversion to the StreamNet exchange format.

WE No.:	160	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 32 of 56

Work Element:	160	Create/Manage/Maintain Database

Work Element Title:	4	Data exchange standard development

The project will establish and maintain data exchange standards to ensure consistent content and format of data that originate from multiple data sources.  We will maintain adopted and develop proposed data exchange formats for data categories described under Work Element 159.  This task will provide coordination and technical assistance regarding interpretation of database structures and codes.  The formal process for creating new and revising old DEFs may require significant amounts of time, potentially more than a

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC development 	CRITFC, on an ongoing basis, will work 	Staff reviewed and evaluated proposed DEFs as they relate to data

and maintenance of data 	cooperatively through the Steering Committee, 	provided, or likely to be provided in the future, by CRITFC.

exchange standards	following the DEF Process document, to revise

existing and develop new DEFs to assure regional

data consistency and allow for inclusion of new data

types.

3	MFWP development and	MFWP, on an ongoing basis, will work cooperatively	Montana sent sightings and hatchery release data to regional staff for

maintenance of data 	through the Steering Committee, following the DEF	use in evaluating draft DEFs

exchange standards	Process document, to revise existing and develop

new DEFs to assure regional data consistency and

allow for inclusion of new data types.

4	ODFW development and	ODFW, on an ongoing basis, will monitor adopted 	Age Data DEF collaboration continued this quarter, as well as

maintenance of data 	and proposed data exchange formats and provide 	discussions related to Hatchery Release data.  As needed, specialists

exchange standards	comments, feedback, and/or recommended changes 	within ODFW were engaged to ensure compatibility with data

as necessary.  They will work cooperatively through	processes used in Oregon.

the Steering Committee, following the DEF

Process document, to revise existing and develop

new DEFs to assure regional data consistency and

allow for inclusion of new data types.  New or

modifications to existing DEFs will be submitted as

warranted.

5	PSMFC development 	The Region, on an ongoing, as needed basis, will 	We worked with the StreamNet partners to resolve a newly noticed

and maintenance of data 	work cooperatively through the Steering 	data problem.  In some cases, field workers are unable to count the

exchange standards	Committee, following the DEF Process document, 	number of fish or the number of redds due to high abundance.  This

to revise existing and develop new DEFs to assure 	presents a problem for how to capture and display this information.

regional data consistency and allow for inclusion of 	When fish are too abundant to count, field staff note the situation but

new data types.  The Regional Biologist will serve as	do not record a count or even an estimate.  Leaving this as a '0' or null

the primary coordinator of the DEF process and is 	in the database mischaracterizes the situation.  A satisfactory strategy

responsible for updating and publishing the official 	for capturing and presenting this information was agreed to.

DEF document.

WE No.:	160	Title No.:	4	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 33 of 56

A data exchange format for age data was completed this quarter.  This

will be included in the next version of the StreamNet Data Exchange

Format document, which we expect to release in the first half of

FY-06.

6	PSMFC development 	The Region will Investigate the use of the "TypeID"	After brief review, this was determined to be a low priority issue for

and maintenance of data 	field in StreamNet time series data in relation to	now.

exchange standards, 	other fields, propose fixes if appropriate, and adopt

TypeID	any changes through the DEF modification process.

7	PSMFC development 	The Region will initiate work on a new DEF for 	Work on a "Sightings" data exchange format was renewed.

and maintenance of data 	Fish Sightings data.  They will review the approach 	"Sightings" are instances where a species was observed in some

exchange standards, Fish 	being taken in California and, in coordination with 	fashion and are useful in definitively establishing occurrence at a

Sightings	the cooperating projects, adapt it for use in the 	location.  In addition to StreamNet personnel, we have asked for

Columbia Basin.	input on this from the Pacific Northwest Mussels Workgroup, because

sightings data are not restricted to fishes and this group has much

knowledge of how other organisms are handled.  We intend to be able

to store information for a variety of taxa.  This work was not

completed this quarter but is expected to be completed in the next

fiscal year.

8	WDFW development 	WDFW, on an ongoing basis, will work cooperatively	The Location Data Manager continued to periodically push for

and maintenance of data 	through the Steering Committee, following the DEF	finalization of the Hatchery DEF proposal.

exchange standards	Process document, to revise existing and develop

new DEFs to assure regional data consistency and	The Project Manager reviewed progress on Forums with open DEF

allow for inclusion of new data types.	topics on 8/1/2005.  Individual WDFW staff contributed to consensus

and closure of open topics under the Age, Count/mile, and Sample

Method forums.

Further detailed discussion of issues WDFW has with parts of the

current generalized fish distribution DEF will be postponed until

December.  This will allow the WDFW transfer of existing 24K-based

anadromous and resident fish distribution data to the mixed-scale

Washington hydrography to help identify any further issues with

representing common Washington situations using this DEF.

WE No.:	160	Title No.:	4	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 34 of 56

Work Element:	161	Disseminate Raw & Summary Data

Work Element:	161	Disseminate Raw & Summary Data

Work Element Title:	1	Develop and maintain Internet sites for data dissemination

StreamNet will continue to maintain and enhance the StreamNet Internet sites.  We will provide access to StreamNet data products through the Internet at both the regional and cooperating project levels.  The StreamNet home page (www.streamnet.org) will continue to be utilized as the project's primary data delivery vehicle.  Priority will be given to incorporating data developed through Work Element 159 and providing access to reference materials secured through Work Element 98.  The site will also be used to archive data sets developed by FWP participants for data that do not fit within the StreamNet DEF (Independent Data Sets), including

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

4	ODFW assist Internet 	ODFW, on an ongoing basis, will:	Ongoing review of the StreamNet website continued, including

site maintenance and 	Provide ongoing review of the StreamNet website 	commenting on the functionality of the Critical Habitat Mapper.

development	(StreamNet's primary data dissemination tool)

through routine use of the site, providing feedback 	Management of the Corvallis Research Lab website included posting

to StreamNet staff at PSMFC on any problems, 	nearly two dozen newly scanned ODFW Information Reports.

errors or needed improvements, and

Manage and maintain Oregon's web-based data 	For the period of April through September 2005, our web server

integration, communication, and data transfer 	provided an average of 31,801 page views per month to an average of

systems and their links to StreamNet.	3,722 unique IP addresses.   FTP downloads for the third and fourth

quarters, respectively, were:

Distinct IP addresses:  783 and 794

Total files served:  6,403 and 8,517

Bandwidth served:  2.86 GB and 5.01 GB

StreamNet related Oregon website usage is summarized in Table 1.

Table 1.  Use (page views) of the Oregon StreamNet related websites

during the third and fourth quarters, FY-2005.

| Website | April | May | June | July | Aug. | Sept. |
| --- | --- | --- | --- | --- | --- | --- |
| NRIMP (OR StreamNet) | 15,002 | 13,998 | 11,164 | 10,001 | 12,792 | 10,814 |
| CSMEP Web Application | 164 | 5,522 | 1,659 | 2,531 | 828 | 1,205 |

5	PSMFC Internet site 	The Region, on an ongoing basis, will maintain and 	The GIS related web pages and Internet map applications were

maintenance and 	improve the StreamNet Internet site (the primary 	maintained.  The Internet Map Server was given an operating system

development	means of disseminating StreamNet data), through 	upgrade and configured to enable the use of a new Map Viewer

the following actions:	developed by our partner project, CalFish.  The GIS Specialist plans

1.  Correcting errors, adding or fixing links, improving	to implement this new viewer to improve StreamNet's existing

performance, improving looks and usability, etc.;	interactive mappers in FY-06.

WE No.:	161	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 35 of 56

2.  Guide development and enhancement of the 	We worked toward replacing the existing StreamNet Search feature

StreamNet web query system from the perspective of	with a new Google based search engine using the investment made by

data users, and review changes to the web query 	PSMFC.  This should be completed in the first few weeks of FY-06.

system to ensure they are implemented appropriately

and do not create unforeseen problems;	Work toward upgrading the overall look and navigation of the

3.  Maintain the GIS Data, Map, and PNW Reach 	StreamNet web site and associated applications progressed.  The goal

File Internet pages;	is to improve web site and application navigation and give all

4.  Maintain, update as necessary, and improve the 	StreamNet associated web pages and applications a similar look and

Internet mapping component to the StreamNet web	feel.  It is anticipated that the first stage of this project will be rolled

site to allow users to access StreamNet data through	out in Q1 of FY-06.

interactive map interfaces.  Improvements might

include such items as adding DRGs or aerial photos 	PSMFC is updating their web site and StreamNet staff provided

to the IMS applications, and showing trend 	StreamNet information for use on the PSMFC site.

locations in the web query system;

5.  Research integration of 4th, 5th and 6th field	Use of the regional StreamNet website remained strong in Q4 (Table 2)

HUC boundary layers into a single region-wide

dataset and plan improvements to the web-query	Table 2.  Use of the StreamNet website in the fourth quarter, FY-05.

|  | July-05 | Aug.-05 | Sept.-05 |
| --- | --- | --- | --- |
| Main Web server |  |  |  |
| Total static page requests | 20,325 | 25,440 | 27,424 |
| Number of visits | 3,708 | 3,739 | 2,624 |
| Unique visitors | 2,328 | 2,527 | 1,737 |
| Data query page requests | 12,897 | 15,748 | 42,286* |
| Unique query sessions | 3,656 | 4,947 | 33,366* |
| Unique query sessions / hr. | 4.9 | 7.4 | 44.8* |
| Data reports viewed | 2,038 | 2,128 | 1,906 |
| FTP files downloaded | 1,094 | 729 | 853 |
| IMS Web Server |  |  |  |
| Total IMS page requests | 24,588 | 26,921 | 28,487 |
| Number of IMS visits | 840 | 973 | 1,049 |
| Unique IMS visitors | 458 | 495 | 521 |
| Mean pages / IMS visit | 29 | 28 | 27 |

system and Internet map application as this

improved base data becomes available;

6.  Deploy, as needed, new query system

components and data categories that are approved

by the Steering Committee;

7.  Maintain logs of web query history and error

events, track and report Internet site usage by

month, and investigate web query system errors

encountered; and,

8.  Maintain and enhance the functionality, look and

usability of the StreamNet web-based query system.

* One time anomalous results due to search robot hits being included in total.

6	PSMFC Internet site 	The Region will conduct a thorough review of the 	Corrections and improvements were made to data and web query

maintenance and 	web query system by 03/31/05 to identify and 	programming, including updated handling of library reference data.

development, review 	address errors and omissions in data delivery and to

query system	improve help files.	The web query system was updated to use the new hatchery returns

data format.  This new format provides more detailed data and in a more usable format than previously existed.  We now deliver (as available) the total number of fish coming to a hatchery, the capture sites for these fish, by-sex spawning information, and the final disposition of the fish bodies.

WE No.:	161	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 36 of 56

7	PSMFC Internet site 	The Region will review and rearrange the links 	The links were reviewed and those leading to useful data were added

maintenance and 	pages on the StreamNet web site.	into the Independent Data Sets page so they would be searchable.

development, rearrange 	Reorganization of the links page will take place at a convenient time

links pages	next fiscal year.

Work Element:	161	Disseminate Raw & Summary Data

Work Element Title:	2	Respond to data/information requests

Receive and respond to requests for data and information, source materials, and custom products at the regional and cooperating agency levels.  Response to requests will be honored within the limits of available resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.  Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural resource management activities.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC respond to 	CRITFC, on an ongoing basis, will respond to 	The Library responded to 127 document requests (Tables 3, 4, 5).

data/information 	requests for data, maps, technical assistance, source 	Other details are reported in WE 98, WE Title 3, MS no.1.

requests	materials, or custom data products at the agency

level, within the capabilities provided by base

funding.  Requests will be logged and reported.

3	IDFG respond to 	IDFG, on an ongoing basis, will respond to requests 	We filled 48 requests for data during the fourth quarter (Tables 3, 4, 5).

data/information 	for data, maps, technical assistance, source

requests	materials, or custom data products at the agency

level, within the capabilities provided by base

funding.  Requests will be logged and reported.

4	MFWP respond to 	MFWP, on an ongoing basis, will respond to 	We filled 13 requests during the quarter (Tables 3, 4, 5).  We enhanced

data/information 	requests for data, maps, technical assistance, source 	the FWP electronic fisheries library by adding the RepositoryID to our

requests	materials, or custom data products at the agency 	collector's permits.

level, within the capabilities provided by base

funding.  Requests will be logged and reported.

5	ODFW respond to 	ODFW, on an ongoing basis, will respond to 	The GIS Analyst developed a draft Work Request Form / GIS Dataset

data/information 	requests for data, maps, technical assistance, source 	Development Request Appendix and distributed it to other NRIMP GIS

requests	materials, or custom data products at the agency 	staff for comments.

level, within the capabilities provided by base

funding.  Requests will be logged and reported.	Staff responded to 26 information requests this quarter (Tables 3, 4, 5).

6	PSMFC respond to 	The Region, on an ongoing basis, will respond 	Regional StreamNet staff responded in a timely manner to all

data/information 	within one business day to requests for data, 	information requests received during the fourth quarter.  Information

requests	information or help, and will log and report 	requests are summarized in Tables 3, 4, and 5.

responses to all requests received.

WE No.:	161	Title No.:	2	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 37 of 56

7	PSMFC track responses 	The Region will finalize a standard user request 	Responses to all data/information requests by project partners were

to data/information 	tracking database structure so that all StreamNet 	logged in the standardized database.  Results are reported for the fourth

requests	partner agencies can use the same format for 	quarter for all partners in Tables 3, 4, and 5.

reporting responses to requests for data and other

information or help.

8	WDFW respond to 	WDFW, on an ongoing basis, will respond to 	The Olympia data compiler developed a MS Access database interface

data/information 	requests for data, maps, technical assistance, source 	for WDFW StreamNet staff to document data requests using the

requests	materials, or custom data products at the agency 	StreamNet standardized format.

level, within the capabilities provided by base

funding.  Requests will be logged and reported.	WDFW StreamNet staff responded to 18 major data requests directly

during the fourth quarter (Tables 3, 4, 5).  Details can be found in the

WDFW Q4 StreamNet Data Requests database records (at PSMFC).

In addition, fish and hydrography GIS layers built and maintained by

StreamNet staff were used by WDFW's Priority Habitats and Species

group to respond to over 350 data requests, involving 1,080 maps and

70digital datasets.

Table 3.  Summary of responses to data/information request by StreamNet members during the fourth quarter, by type of request.

| Type of request | CRITFC | IDFG | MFWP | ODFW | PSMFC | WDFW | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Data request |  | 37 | 6 | 10 | 3 | 6 | 62 |
| General fish information |  |  |  |  | 2 | 1 | 3 |
| GIS data / map |  | 9 | 7 | 4 | 8 | 11 | 39 |
| Hardware / software technical support |  | 1 |  | 2 |  |  | 3 |
| Help finding information |  |  |  |  | 3 |  | 3 |
| Help with data interpretation / analysis |  |  |  |  |  |  | 0 |
| Library / Documents | 127 | 1 |  | 5 | 1 |  | 134 |
| Other |  |  |  | 5 | 4 |  | 9 |
| Report error or problem |  |  |  |  | 1 |  | 1 |
| Total | 127 | 48 | 13 | 26 | 22 | 18 | 254 |

WE No.:	161	Title No.:	2	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 38 of 56

Table 4.  Summary of responses to data/information requests, fourth quarter, by source of request.

| Source of request | CRITFC | IDFG | MFWP | ODFW | PSMFC | WDFW | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| College / university |  | 2 |  | 2 | 1 | 1 | 6 |
| General public / other | 281 |  |  | 1 | 5 |  | 34 |
| Government, county / local |  |  |  |  |  |  | 0 |
| Government, federal | 21 | 6 |  | 3 | 3 | 2 | 35 |
| Government, state | 3 | 18 | 13 | 11 | 6 | 10 | 61 |
| Government, tribal | 32 |  |  | 2 | 2 | 2 | 38 |
| Nonprofit organization |  | 1 |  | 3 | 3 | 1 | 8 |
| Private consultant | 43 | 21 |  | 4 | 2 | 1 | 71 |
| Regional entity |  |  |  |  |  |  | 0 |
| Unknown |  |  |  |  |  | 1 | 1 |
| Watershed council / group |  |  |  |  |  |  | 0 |
| Total | 127 | 48 | 13 | 26 | 22 | 18 | 254 |

1  Includes other libraries

Table 5.  Summary of responses to data/information requests during the fourth quarter, by outcome.

| Outcome of request | CRITFC | IDFG | MFWP | ODFW | PSMFC | WDFW | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Request fully satisfied | 127 | 48 | 13 | 8 | 15 | 17 | 228 |
| Request partially satisfied |  |  |  | 5 | 3 |  | 8 |
| Referred to other sources |  |  |  | 8 | 3 | 1 | 12 |
| Could not help at all |  |  |  | 5 | 1 |  | 6 |
| Total | 127 | 48 | 13 | 26 | 22 | 18 | 254 |

Work Element:	161	Disseminate Raw & Summary Data

Work Element Title:	3	Provide data and maps to support Fish and Wildlife Program activities

Provide data and maps and related services to the Fish and Wildlife Program, as requested.  Services may include custom development of data, provision of data from the StreamNet database to support FWP activities (such as planning, monitoring and evaluation, etc.), and general advice and technical assistance with database management, data delivery, and GIS.  Work under this task will have to be based on time available, particularly for larger requests.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC support F&W 	CRITFC, on an ongoing basis, will support Fish and 	The Project Leader is a member of the PNAMP and NED steering

Program Activities [with	Wildlife Program activities such as R, M & E, 	committees.  He co-chairs the NED Subbasin Data Workgroup.  The

data and maps]	subbasin assessment, etc., by providing data and 	activities of these groups are available through other web sites.

maps and technical information management advice

or assistance as requested, within available time and

budget under base level funding.

WE No.:	161	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 39 of 56

3	MFWP support F&W 	MFWP, on an ongoing basis, will support Fish and 	We provided high resolution color aerial photographs and a layer

Program Activities [with	Wildlife Program activities such as R, M & E, 	containing updated plat maps of the Flathead and Kootenai River

data and maps]	subbasin assessment, etc., by providing data and 	watersheds (the main river corridors are top priority) to be used for a

maps of existing StreamNet data and technical 	3-way MOA (MFWP-BPA-CSKT) for land acquisitions and

information management advice or assistance as 	conservation easements to protect critical fisheries habitat in the two

requested, within available time and budget under 	watersheds for BPA mitigation staff in northwest Montana.  The

base level funding.	maps  will be used  to define criteria for parcel selection in order to

identify 10 properties to review and rank based on the criteria.  Funding

for these lands projects will be from BPA's capital investment ledger

(estimated at about $20 million for this phase) and habitats acquired

for this purpose will be credited against approved fisheries loss

statements for the construction of Hungry Horse and Libby Dams.

Losses due to dam construction are finite, so BPA could "pay off" their

obligation for mitigation with credits against the loss statement.

4	ODFW support F&W 	ODFW, on an ongoing basis, will support Fish and 	No requests were received or fulfilled during this quarter.  The draft

Program Activities [with	Wildlife Program activities such as R, M & E, sub-	NOAA RM&E data inventory proposal was reviewed this quarter, and

data and maps]	basin assessment, etc., by providing data and maps of	comments were prepared.

existing StreamNet data and technical information

management advice or assistance as requested, within

available time and budget under base level funding.

6	PSMFC support of F&W	The Region, on request, will participate in and assist	As part of cooperation with the Collaborative Systemwide Monitoring

Program Activities 	regional Monitoring and Evaluation efforts to provide	and Evaluation Project (CSMEP) of CBFWA, we wrote an overview

[with guidance and 	data management guidance, provide any relevant SN	paper describing the data management considerations that need to be

assistance]	data, and to initiate work to obtain new data types for	addressed in any large scale monitoring project and provided it to

R,M&E.  Since no specific requests or funding have	CSMEP participants.

been received for this, work may be limited to

scoping and advising.  Development of new data

types to serve R,M&E will be initiated only as current

time and funding permit, or as current work priorities

are reprioritized by regional processes.

WE No.:	161	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 40 of 56

Work Element:	161	Disseminate Raw & Summary Data

Work Element Title:	4	Maintain and post Protected Areas data

StreamNet will a) maintain and provide access to the Council's Protected Areas dataset, b) archive the official version as a historic record, c) in consultation with the Council, respond to requests for information concerning Protected Areas, and d) modernize georeferencing and make these data available through online mapping.  If the Council so directs, work with subbasin planners to record any desired changes to the protected status of individual streams.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	PSMFC maintain and 	The Region, on an ongoing basis, will maintain the 	The Protected Areas data were maintained, with access provided on

post Protected Areas 	Protected Areas database and provide access to the 	line through the tabular data query system and through the interactive

Protected Areas data through the online query system	map interface.

and through the interactive map application.  As time

allows, work to resolve the remaining unresolved

location issues from conversion of the data from

1:250,000 to the 1:100,000 regional hydrography.

Work Element:	98	Other (Library Services)

Work Element:	98	Other (Library Services)

Work Element Title:	1	Library collection development

The StreamNet Library, with input from the other project participants, will develop a collection of materials applicable to the mission of StreamNet.  We will collect, catalog and organize materials to document data sources, Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies, interested parties, and other libraries.  The project participants will submit reference documents for all data contained in the StreamNet database to the StreamNet Library.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC StreamNet 	CRITFC, on an ongoing basis, will:	The backlog of StreamNet documents has been reduced and we

Library collection 	1.  Develop a collection of materials related to the 	continue to catch up on entry of new records now that ongoing

development	Columbia Basin, including reports from other Fish 	quality control for StreamNet References has been completed.

& Wildlife Program projects, other agency documents

as they relate to the Basin, and other published and	The StreamNet Library has also been working on collection

unpublished materials as requested by clients.	development via duplicate exchange resources.  We have donated 24

2.  Coordinate, receive and incorporate source	large boxes of materials to other developing libraries.  We acquired

material submissions for data compiled by participants.	over 100 titles from other libraries for the cost of postage.  These

3.  Maintain and develop a collection of journals	materials fill in gaps in our periodicals and also provide research

related to fisheries and aquatic sciences as well as	materials for the book/document collections.

other related scientific topics.

4.  Maintain memberships in appropriate library and

subject-related associations.  Ex.  IAMSLIC, NRIC,

OFWIM, etc.

WE No.:	98	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 41 of 56

5	MFWP provide 	MFWP, on an ongoing basis, will obtain reference 	This task is ongoing.  The Fishery Division's staff has started to

references to data	documents for all data developed under WE 159 and	enter records into the library database following a physical move of

submit them to the StreamNet Library for inclusion	the library.

in the collection and catalog.

6	ODFW provide 	ODFW, on an ongoing basis, will obtain reference 	The Data Analyst submitted 32 references to the StreamNet library.

references to data	documents for all data developed under WE 159 and	Three were new and the remaining were either updates or references

submit them to the StreamNet Library for inclusion	that were submitted to the StreamNet Library, but were not in ODFW's

in the collection and catalog.	main library reference table.

7	ODFW organize ODFW 	ODFW, on an ongoing basis, will continue 	Organization of the ODFW Library continued this quarter.  The ODFW

Library documents	organization of ODFW Library documents and 	Library Technician has now entered a total of 4,489 publication

update the library bibliography with new titles as 	references into ODFW’s Library bibliography.  Documents related

they are identified.	to the Columbia, Willamette, Deschutes, and Clackamas Rivers

specifically have been included in the bibliography.  Many existing

records were also updated as needed.  Publications have been (at

least topically or geographically) organized onto shelves, labeled,

mapped and indexed.  Because the Library will be unattended for at

least the next 3 months, arrangements were made to protect the

physical library from temperature extremes over the winter.

8	WDFW provide 	WDFW, on an ongoing basis, will obtain reference 	We submitted copies of all relevant reference information during

references to data	documents for all data developed under WE 159 and	exchange of hatchery returns, barriers, and age data this quarter.

submit them to the StreamNet Library for inclusion

in the collection and catalog.

Work Element:	98	Other (Library Services)

Work Element Title:	2	Provide access to the library collection

The StreamNet Library will provide user access to the materials described in the collection development work element by providing facilities for storage of paper and electronic copies of documents, an online catalog of all documents in the collection, and staff to answer location questions and respond to requests.  They will network with other agency and regional library service providers to provide better access to other collections that will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials.  Participate in planning, development and/or coordination meetings with regional entities to provide advice in the area of data management, as requested, to support development of Fish and Wildlife Program projects and programs.  Provide input on ways StreamNet can effectively contribute to the programs and general advice about data management.  Participate in advisory groups, task forces, and other groups whose purpose is to enhance the effectiveness of the Fish and Wildlife Program relative to its data

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC provide access 	CRITFC, on an ongoing basis, will:	The StreamNet Library operated without interruption during normal

to the StreamNet 	1.  Provide and maintain appropriate facilities for the	business hours during the fourth quarter.

Library collection	storage and public use of the SN Library collections;

WE No.:	98	Title No.:	2	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 42 of 56

2.  Catalog and organize the materials for ease of	Library staff and interns cataloged approximately 600 titles during

use by clients and staff;	the fourth quarter.  Approximately 3,300 records were updated for

3.  Provide access to the catalog of materials via the	quality control purposes or additional information was added to

Internet and update the catalog at least monthly;	increase searchability.

4.  Maintain and implement a plan to place electronic

documents in the catalog and on the library website;	We are currently exploring the best way to add metadata to electronic

5.  Develop and keep a schedule of open times and	documents already in place automatically so they are searchable by

reference desk staff hours; and	regular Internet search engines rather than only having access to the

6.  Provide data regarding library materials to the	titles via the Library catalog.  This additional information and

regional Data Manager on a monthly basis.	searchability would increase traffic through the Library website.

Work Element:	98	Other (Library Services)

Work Element Title:	3	Provide library services for patrons

The StreamNet Library will provide library services to the StreamNet user community, the Council's Fish and Wildlife Program, and the general public.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC provide library 	CRITFC, on an ongoing basis, will:	The Vancouver Lake Watershed Partnership has concluded the research

services to patrons	1.  Provide information and reference services to 	phase of their process.  However, they are interested in developing

library patrons.	further documentation and working with the Library to allow access to

2.  Identify changes and new features that will 	the collection developed in support of their mission for the next phase

improve delivery of library services.	of data inventory and current status inventory.

3.  Provide interlibrary borrowing services for

library patrons to access materials not yet owned by	The Library is now hosting a database for the Johnson Creek

the StreamNet Library.	Watershed Council Resource Room.  Initially, they were developing a

4.  Provide interlibrary lending services for other 	database to post to the web, but those plans fell through and we have

libraries to access the library's unique collection.	provided electronic access to their collections.  We hope that this

5.  Provide consultations for groups and other 	example will convince other local watershed councils to also provide

agencies on library organization and services.	access to their materials so that we might facilitate information

6.  Coordinate with other StreamNet libraries, 	sharing between watershed councils.

library clients and other libraries to improve service

to clients and limit duplication of effort.	127 Interlibrary loans were made in the fourth quarter (Tables 3, 4, 5).

WE No.:	98	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 43 of 56

Work Element:	118	Coordination

Work Element:	118	Coordination

Work Element Title:	1	Support Fish and Wildlife Program development activities

Participate in planning, development and/or coordination meetings with regional entities to provide advice in the area of data management, as requested, to support development of Fish and Wildlife Program projects and programs.  Provide input on ways StreamNet can effectively contribute to the programs and general advice about data management.  Participate in advisory groups, task forces, and other groups whose purpose is to enhance the effectiveness of the Fish and Wildlife Program relative to its data

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC support F&W 	CRITFC, on an ongoing basis, will participate in 	The Regional Librarian completed the education, outreach and

Program development 	various NPCC planning and management work 	communication paper for the NED Project.  She is now participating

activities	groups to improve and coordinate regional 	on the website design team.

information management programs.

The Project Leader is an ex-officio member of the ISAB and serves on

the steering committees of the PNAMP and NED.  As co-chair of the

NED Subbasin Data Workgroup, he is leading an effort to capture the

core subbasin assessment data developed during subbasin planning.

These data will be placed on StreamNet as independent data sets.

5	ODFW support F&W 	ODFW, on an ongoing basis, will work with regional	Ongoing maintenance of the CSMEP web application continued.  The

Program development 	entities to contribute data management expertise 	CSMEP web application was modified to add the name and contact

activities	toward development of activities within the scope 	information for the data source or steward to the query option as

of the Fish and Wildlife Program, and serve as a 	requested by Washington CSMEP staff.  Currently there are 1,450

data management resource to the FWP.	records in the CSMEP web application, 174 added this quarter.

The Project Leader participated in three CSMEP meetings via phone

and provided an update on the status of the online CSMEP Inventory

Database.  Meeting notes from meetings not attended were regularly

reviewed for pertinent comments and/or assignments.  CSMEP/

StreamNet coordination meetings were attended on August 23 and 26.

Oregon StreamNet staff participated in the NED/PNAMP Data

Management Meetings on August 3rd and September 7th.

The Data Analyst and Data Technician trained with ODFW staff in

Clackamas to prepare to assume responsibility for data entry into the

CSMEP online database in the next fiscal year.  Other preparatory

work, including gathering and reviewing background on the project,

was accomplished.

The draft NOAA RM&E data inventory proposal was reviewed.

WE No.:	118	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 44 of 56

6	PSMFC support F&W 	The Region, on an opportunistic basis, will work 	The StreamNet Program Manager (steering committees) and Regional

Program development 	with regional entities to contribute data 	Fisheries Biologist (effectiveness monitoring) continued participation

activities	management expertise toward development of 	in the Northwest Environmental Data-network (NED) and Pacific

activities within the scope of the Fish and Wildlife 	Northwest Aquatic Monitoring Partnership (PNAMP) efforts.  One key

Program, and serve as a data management resource 	focus was assisting a PNAMP group investigating the need to conduct

to the FWP.  Specific activities will include:	an inventory of monitoring activities.

1.  Continued participation on the Program Team

for the Council's project to develop a Northwest

Environmental Data-network to convey

recommendations based on experience in the

development of a regional approach to data

dissemination;

2.  Continued participation in the Pacific Northwest

Aquatic Monitoring Partnership for watershed and

fishery data coordination, and other R, M & E

groups, including the Action Agencies, Federal

Caucus and CBFWA, to provide support and data

management expertise;

3.  Continued participate with CBFWA in support

of data management efforts, including work with

the Collaborative Systemwide Monitoring and

Evaluation Project; and,

4.  Provide support (expertise and guidance) to

other FWP related programs and projects as

requested and as possible under existing resources.

7	WDFW support F&W 	WDFW, on an opportunistic basis, will, work with 	The StreamNet Project Leader met with WDFW and CRITFC staff in

Program development 	regional entities to contribute data management 	Vancouver on 8/9/2005 to discuss CRITFC involvement in a project to

activities	expertise toward development of activities within 	compile and store Washington EDT spatial data for the Columbia River

the scope of the Fish and Wildlife Program, and 	Basin in a repository that would hold all Basin EDT data.  Peculiarities

serve as a data management resource to the FWP.	of the Washington data were discussed with the CRITFC project staff,

who presented a generalized work plan and study approach to the group

for review and comment.

The Vancouver data compiler entered and posted several more CSMEP

dataset inventory records reflecting sport harvest data recently received

from the Wenatchee, Methow and Okanogan basins.

WE No.:	118	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 45 of 56

Work Element:	118	Coordination

Work Element Title:	2	Support subbasin planning efforts

At the regional and cooperating agency levels, work with subbasin planners to provide needed information from the StreamNet database and to capture data developed as part of the subbasin planning process.  We will work with the TOAST group to capture subbasin planning data from Oregon, and in FY-06 will work with  others in an attempt to capture similar data in the other

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

2	MFWP support subbasin 	MFWP will work with subbasin planners to determine	Data requested by CRITFC was sent.

planning efforts	the type of data within the Montana subbasin plans

and opportunities for incorporating those data into

StreamNet and providing data on the FWP website.

3	ODFW support subbasin 	ODFW, as needed, and within existing resources, 	No subbasin planning assistance was requested, so this time was

planning efforts	will work with subbasin planners to capture data 	redirected to supporting Recovery Planning efforts as a result of the

developed as part of the subbasin planning process 	shift in agency focus.  See Work Element 118, Title 3; Milestone 4

and develop data sets outside Oregon StreamNet's 	for a description Recovery Planning support that was provided.

base efforts if requested by subbasin planners.

Work Element:	118	Coordination

Work Element Title:	3	Coordinate with related activities outside of the FWP

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities and agencies beyond the Council's Fish and Wildlife Program to identify means for collaborative data collection, storage, and dissemination.  On request or as possible, collaborative data activities will include tribal fishery programs within the Columbia Basin, federal land managers' fishery programs, state fish and wildlife agencies, and, with respect to water use and stream development, state water resource management and environmental quality agencies.  Collaboration with coast-wide and private data collection/compilation efforts will be pursued when this supports overall project goals.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

3	MFWP coordinate with 	MFWP, on an opportunistic basis, will coordinate 	The regional staff met with various USGS and state representatives

related activities outside 	with other state, federal, or tribal agencies and 	concerning the future of regional hydrography.  Steve Carson provided

of the FWP	various local inter-agency planning and management	input and follow-up discussion.  Discussion on this topic is slated for

work groups beyond the FWP to enhance the	the October 2005 steering Committee meeting.

collection and management of data related to

management of fish and wildlife resources.

4	ODFW coordinate with 	ODFW, on an opportunistic basis, will coordinate 	Oregon StreamNet coordinated with Regional StreamNet and BLM

related activities outside 	with other state, federal, or tribal agencies and 	staff in Roseburg to explore the possibility of assisting with the

of the FWP	various local inter-agency planning and management	creation, archiving, and regional sharing of freshwater mussels data in

work groups beyond the FWP to enhance the	support of the Northwest Freshwater Mussel database.

collection and management of data related to

management of fish and wildlife resources.	A lower level of support to the Oregon Plan Assessment continued

via data compilation of Oregon Watershed Council datasets, data

management, and database and web site development.

WE No.:	118	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 46 of 56

Oregon’s GIS Analyst met with Oregon State Parks and Dept of Transportation GIS Coordinators to learn their experiences with agency wide GIS initiatives, examine their structures, and review successes in organization-wide coordination and spatial information management.

Much collaboration and support took place with the Oregon Plan Monitoring Team (OPMT), including attending their July 14th and August 18th meetings to describe the data management support we provided to the Coastal Coho Assessment and discuss how that support relates to the data management needs of the Monitoring Team.  The Project Leader attended portions of the Oregon Plan Monitoring Conference to better understand data management needs of Oregon’s monitoring.  We also submitted three funding proposals to provide data and database management support to the OPMT, including: 1) updating Oregon’s distribution datasets including reconciling ODFW's various coho distribution datasets with one another, 2) creating an IMS site for Oregon Plan datasets, and 3) compiling watershed council data, and developing data standards and database templates for these data.

In response to a shift in agency priority from Subbasin Planning to Recovery Planning, Oregon StreamNet spent time designing, creating, tuning, and fine-tuning a new Recovery Planning Data Library web application.  Initially, this involved duplicating the basic infrastructure of the Coastal Coho Assessment web application, then modifying to accommodate the specific needs of Recovery Planners such as a file upload/download component that allows users to store recovery planning working files according to their team location.  As the complexity increased, we focused on creating an updated application based on SQL server and will provide enhancements including better file management capabilities, more granular security, and increased search capability of the system.  We completed the application and sent out user account information for all Mid-Columbia team members, which is where Oregon’s effort will begin.  Staff also modified existing Data Library records to include planning area designations in support of the Recovery Planning Data Library search features.

The Project Leader worked with the ODFW Monitoring Coordinator on the needs of the upcoming State of the Salmon Consortium (a joint program of Ecotrust and the Wild Salmon Center) data inventory, which is being conducted by outside consultants, and strategize how to support this effort in such a way as to realize benefits to the agency as well.  Our efforts toward this inventory will likely increase during the next quarter as the consultants engage ODFW biological staff.

WE No.:	118	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 47 of 56

5	ODFW coordinate with 	ODFW, on an ongoing basis, will coordinate and 	We coordinated with ODFW Information Systems Division (ISD)

internal ODFW staff to 	work with internal ODFW staff to improve the 	staff on metadata requirements, comparing our data management-

improve internal data 	agency data collection efforts to allow more 	related requirements to those ISD requires as part of their database

compiling	efficient compiling into internal intermediate 	reporting requirements.  We hope to get some or all of our requirements

NRIMP-Oregon StreamNet databases and/or 	included in theirs.  Balancing the need for more detailed information in

StreamNet databases at the regional scale.	metadata records with the need for the highest compliance rate possible

from ODFW staff will be a major factor in the final decision.

GIS users at the Corvallis Research Lab met to discuss GIS use by lab staff, to improve coordination between the lab and others using GIS throughout the agency, and to educate ODFW’s Chief Information Officer on the scope of GIS usage at the lab.  About a dozen GIS users from the Lab attended.  The CIO shared the agency’s motivation for wanting to better coordinate GIS in ODFW, while the GIS users described how GIS is used at the Lab, and what their concerns are about statewide coordination.  The primary concern expressed centered on maintaining the flexibility to use GIS tools, even non-standard tools, to do their job, and that coordination not become a hindrance.  Both the CIO and Lab staff expressed that NRIMP (Oregon StreamNet) is the natural place to base the agency's GIS coordination.

We helped initiate a GIS Coordination Group in ODFW, which met twice to validate the need for agency collaboration to obtain the full value, understanding, and support of GIS at ODFW.  We worked with Regional StreamNet staff to develop a ODFW GIS Forum to facilitate the capture of discussion threads related to the group’s topics.  Staff also established an on-line survey to ascertain GIS usage by agency employees.  The survey will remain open until October 21st, but responses to date provide an overview of existing GIS use across the agency and also captured a variety of issues associated with deriving maximum benefits from this technology.  To allow Group members to review survey results, a summary page has also been created.

7	WDFW coordinate with 	WDFW, on an opportunistic basis, will coordinate 	WDFW sent four representatives to a 9/15/2005 meeting between

related activities outside 	with other state, federal, or tribal agencies and 	StreamNet participants and the Pacific Northwest Hydrography

of the FWP	various local inter-agency planning and management	Framework Working Group to discuss issues with the coming NHD

work groups beyond the FWP to enhance the	hydrography linework and format standards, including migration from

collection and management of data related to	the regional 100K-based layer to the higher-resolution (24K) NHD

management of fish and wildlife resources.	product.  Key issues for Washington include dealing with the existing

Washington Framework approach, which includes conventions and

agreements that run contrary to what the national NHD standards can

support.  WDFW is committed to pursuing an approach that benefits

StreamNet data exchange and dissemination.

WE No.:	118	Title No.:	3	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 48 of 56

Work Element:	99	Outreach and Education

Work Element:	99	Outreach and Education

Work Element Title:	1	Professional and public involvement

As needed, produce public information materials and participate in various meetings and forums (public or professional) to explain the project's capabilities and purpose and to generate support and additional data sources.  Activities may include brochures, issue papers, demonstrations, posters and talks to public, policy or professional groups and organizations.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	CRITFC support 	CRITFC, on an ongoing basis and as requested, will 	The Regional Librarian attended the Natural Resources Information

professional and public 	prepare and deliver presentations to public, 	Council to discuss open source catalog software and provide

involvement	scientific and professional meetings to demonstrate 	information on the Library's electronic collections.

project capabilities, services and accomplishments

and to solicit additional data and involvement or

coordination with the project.

3	MFWP support 	MFWP, as requested, will prepare and deliver 	A presentation for the OFWIM meeting is being prepared on Montana's

professional and public 	presentations to public, scientific and professional 	Comprehensive Fish and Wildlife Conservation Strategy activities.

involvement	meetings to demonstrate project capabilities, services	StreamNet was used exclusively for the aquatic portion of the strategy.

and accomplishments and to solicit additional data

and involvement or coordination with the project.

4	ODFW support 	ODFW, on an ongoing basis, will produce public 	The visiting Restoration and Enhancement (R&E) Board was given a

professional and public 	informational documents on StreamNet data 	tour of the Corvallis Research Lab where they were introduced to the

involvement	activities for natural resource oriented publications, 	various projects and people.  A brief introduction of the R&E Web

give oral  presentations to relevant user groups, and 	application was presented to the Board on July 29th, where we were

participate in various meetings and forums in 	able to respond to the Board’s specific questions.  The Board was

support of project goals.	pleased with the progress made so far.  As an added bonus, several

ODFW staff in the audience expressed strong interest in the IMS

component of the application following the presentation.

We drafted and submitted a StreamNet Newsletter item on the work

we're doing with ODFW’s Marine Resources Program.

Our Project Leader attended the Fish Biologist Meeting on August 10

and 11 and represented the agency at the Oregon State Fair on Sept.  2.

We arranged to have Dan Haug (GIS Manager - Confederated Tribes

of the Umatilla Indian Reservation) come to Corvallis and give a

presentation on the Tribe's GIS and data management system.

Attendees were encouraged and inspired to pursue a similar system for

the Lab, and possibly the agency.

WE No.:	99	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 49 of 56

5	PSMFC support 	The Region will publish at least two editions of the 	Publication of the second newsletter for the year was postponed until

professional and public 	StreamNet Newsletter during the fiscal year, 	the next quarter.

involvement, publish 	providing readers with information about StreamNet

newsletter	activities, available data, data updates, new data

services, etc., with target dates of at least 12/31/04

and 07/1/05.

6	PSMFC support 	The Region, on an opportunistic basis, will participate	The Program Manager participated in a workshop hosted by CSMEP

professional and public 	in and prepare and deliver presentations to scientific	on regional scale monitoring.  He brought up issues related to the need

involvement, 	and professional meetings to demonstrate project	for data management consideration in developing a monitoring

professional 	capabilities and accomplishments, advertise	program and discussed how StreamNet could assist.

presentations	StreamNet services, and to solicit additional data

and coordination.

7	PSMFC support 	The Region, as needed, will develop and distribute 	Existing materials were maintained and remain available on the

professional and public 	materials to support the project and improve public 	StreamNet website.  No new materials were prepared this year

involvement, produce 	materials such as the StreamNet brochure, data

public materials	inventories, etc.  as needed.   They will maintain and

update explanatory materials such as the Query

System User Guide and documents explaining data

categories and data structures, as necessary.

8	WDFW support 	WDFW, as needed or requested, will prepare and 	The Data Manager assisted other regional office staff by working the

professional and public 	deliver presentations to public, scientific and 	WDFW information booth at the Clark County Fair.

involvement	professional meetings to demonstrate project

capabilities, services and accomplishments and to

solicit additional data and involvement or

coordination with the project.

WE No.:	99	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 50 of 56

Work Element:	119	Manage and Administer Projects

Work Element:	119	Manage and Administer Projects

Work Element Title:	1	Manage project activities

Administer all aspects of the StreamNet project at the regional and cooperating agency levels, including oversight of budget, personnel (including training and staff development), work statement / budget preparation and implementation, coordination among participating agencies, and project guidance through active participation in steering committee work.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	Project oversight and 	All StreamNet cooperators will perform project 	All cooperators conducted routine project management activities during

guidance: Project 	oversight and guidance (at both cooperator and 	the quarter.  Project guidance was preformed by all members by

management and 	Regional levels) and will participate cooperatively 	participating in the quarterly Steering Committee meeting, held July

Steering Committee	in the StreamNet Steering Committee to guide the 	26-27 at PSMFC.  The primary focus of the meeting was long term

direction of the project, coordinate among agencies 	plans for the project in light of the upcoming solicitation for FY 07-09.

and resolve policy and technical issues for the 	That lead to discussion of a long term vision for the project.  Other

Steering Committee topics included work with CSMEP, mixed scale hydrography, work on Data Exchange Formats, how to display hatchery return data, and how to deal with missing data when surveys were conducted but samplers were unable to make counts due to too many individuals.

Following the Steering Committee discussion, a formal StreamNet Vision document was drafted, with completion planned prior to submission of the next project proposal.  Project participants reviewed the draft and provided input, and further development is planned for the next Steering Committee meeting in FY-06.

Project members also provided input and guidance for a white paper written to outline data management needs for monitoring programs, which was prepared to assist the CSMEP project.

2	Project oversight and 	All StreamNet cooperators will, except for FWS, 	All cooperators, except for FWS, conducted routine staff supervision,

guidance: Supervision	supervise project staff and provide guidance and 	including performance evaluations and staff guidance.

staff development.

ODFW filled its Software Developer/Assistant Database Manager position, and recruitment began for two related positions on other funding.  One staff member attended required Advanced Driver Training.  The GIS Analyst completed all 4 modules of ESRI’s free Virtual Campus geo-database course, and the Data Analyst completed another lesson of module 3 of the web based Learning ArcGIS 8 Virtual Campus course.

WE No.:	119	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 51 of 56

For WDFW a new Human Resources initiative brought significant change to all aspects of personnel management, including collective bargaining, union representation for	 most employees, and adoption of less flexibility in work scheduling by WDFW management.  Serious challenges to morale and productivity were dealt with as employees struggled to adjust to rapid, serious change without adequate preparation time or means with which to meet the new requirements.

3	Project oversight and 	All StreamNet cooperators will manage 	All cooperators performed routine budget tracking, with particular

guidance: Budget control	expenditures to accomplish the jobs in the 	attention paid to monitoring end of fiscal year spending.  The FY-06

Statement of Work within the approved budget.	budgets were distributed to cooperators and entered into their systems.

WDFW and PSMFC completed a contract amendment to reflect work done by a PSMFC employee for WDFW StreamNet.

ODFW and PSMFC completed a contract amendment to reflect adjustments to accomplish project goals despite an unexpected staff vacancy.

5	FY-05 accrual reports, 	PSMFC, with input from the cooperating projects, 	PSMFC submitted the required accrual estimates in August.

second	will produce interim accrual reports (June and

August) and provide them to BPA.

6	FY-06 draft SOW/budget	PSMFC, with input from all project cooperators, 	The FY-06 work statement and budget, which had already been entered

package, PSMFC	will prepare and submit a Statement of Work and 	in Pisces, were adjusted to account for changes in internal PSMFC

budget to BPA 90 days prior to the end of the 	charges and to reflect commitment to supporting the CSMEP project.

FY-05 contract period.	Minor adjustments by project cooperators were accommodated.

6	FY-06 draft SOW/budget	Project cooperators will provide their respective 	All cooperators provided final review and comments for the FY-06

package, cooperators	input to the FY-06 Statement of Work and budget 	SOW and budget.  An effort to coordinate updates for annually

to PSMFC 105 days prior to the end of the FY-05 	updated data types led to some adjustments in the schedule.  The

contract period.  	ODFW Project Leader drafted a detailed description of the native

non-game fish distribution effort being planned for FY-06.

WE No.:	119	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 52 of 56

Work Element:	141	Produce Status Report

Work Element:	141	Produce Status Report

Work Element Title:	1	Quarterly reports

Produce quarterly performance reports on project activities and submit them to BPA within 15 days of the end of each quarter.  Once PISCES is fully functional, submit quarterly status reports through PISCES.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

4	April - June 2005 Status 	The StreamNet contractors will report 	All cooperators submitted input to the Third Quarter Performance

Report submitted to 	accomplishment of the work outlined in the revised 	Report to PSMFC.  They also provided review and comments for the

BPA via PISCES	FY-05 Statement of Work by Work Element, third	draft report prior to its being submitted to BPA.  ODFW also reviewed

quarter, to PSMFC.					And provided comments on its agency’s corporate quarter report.

4	April - June 2005 Status 	The Region will report accomplishment of the work	With input from all member projects, the Third Quarter Progress

Report submitted to 	 outlined in the revised FY-05 Statement of Work 	Report was prepared and submitted to BPA.  At the end of the

BPA via PISCES	by Work Element, third quarter, through a status 	quarter, project members were instructed to begin work on the Fourth

report submitted via the online PISCES system to 	Quarter Progress Report in order to meet the short deadline in the

BPA by July 15, 2005.	next fiscal year.

PSMFC will also prepare its standard format

quarterly report for the third quarter, but organized 	The Pisces performance report was not done because the Pisces report

around the Work Elements rather than the 		system was not ready.

Objectives as in past reports.

Work Element:	132	Produce Annual Report

Work Element:	132	Produce Annual Report

Work Element Title:	1	Annual report

Produce an annual report for FY-05 project activities within 30 days of the end of the fiscal year.

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	PSMFC 2004 annual 	The Region will submit the FY-04 annual progress	While the formal Annual Report for FY-05 is part of the FY-06

report submitted to BPA	report to BPA.  The format will be abbreviated due 	Statement of Work, BPA added a requirement not specifically included

to the level of detail conveyed in the quarterly		in the FY-05 SOW to require an annual performance report for FY-05

reports, with the final report also published as a	be input in Pisces by the end of the year.  Attempts to enter this report

brochure.  						were prevented by internal problems with Pisces not allowing access to

the system.  The report will be entered in the first quarter of FY-06.

WE No.:	132	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 53 of 56

Work Element:	115	Produce Inventory or Assessment

Work Element:	115	Produce Inventory or Assessment

Work Element Title:	1	Inventory of data for the CSMEP Project

Milestone Title                                   	Milestone                                                                                         	Accomplishments in the Fourth Quarter

1	IDFG conduct data 	IDFG will conduct an inventory of existing fish 	The CSMEP data inventories for the upper Salmon and Middle Fork

inventory for the CSMEP 	related data in support of the Coordinated 	Salmon basins were completed.

Project	Systemwide Monitoring and Evaluation Project

(CSMEP).

Supplemental Information

Work accomplished outside the specific work elements in the SOW

This section describes specific accomplishments during the fourth quarter that did not relate specifically to any of the Tasks / Work Elements in the annual Statement of Work.  These activities either were performed on StreamNet contract funding but related to topics that were not specifically covered by a milestone in the Statement of Work (SOW) or they were performed by staff of the various StreamNet projects but on other funding.  Work is often done by StreamNet staff on other funding because the StreamNet contract is not always sufficient to support all staff time.  Such work is reported here when it relates specifically to StreamNet objectives or is ultimately of benefit to the project.

Project     		Accomplishments, Fourth Quarter 2005

CRITFC	The CRITFC is committing substantial additional effort and funding in activities that directly and indirectly support StreamNet objectives.  Using its own funding, CRITFC funds all or most of the Project Leader and two GIS Specialist positions.  Most of the Project Leader's involvement in StreamNet is paid for with CRITFC funds.

The Project Leader is also very active in support of related regional and NPCC program activities.  Specifically, he is an ex-officio member of the ISAB, serves on the steering committees of the PNAMP and NED, and is co-chair of the NED Subbasin Data Workgroup.  Additionally, The Project Leader is a member of the CBFWA AFAC and MAG groups.  Across these groups and activities, he provides a consistent voice and advocacy for improving information management and sharing.

The GIS Specialists are developing new tools and geo databases to provide data sharing and analyses to support four major fish management processes: the U.S. v Oregon court case, Pacific Salmon Treaty, recovery planning under the ESA, and the NPCC Fish and Wildlife Program.  The GIS Specialists are leading an effort to capture and archive data used for recently developed subbasin plans in a GIS format.  This effort is supported by Power Council/BPA funding.

Supplemental Information		StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 54 of 56

These three individuals, plus a Database Programmer and the CRITFC Network Administrator, are using EPA funds to develop a collaborative tribal environmental information sharing network.  As it is tested and implemented this network will improve access to large and growing tribal environmental and fish databases.  During development of this system we will explore methods to share tribal data with other regional information systems, including StreamNet.

MFWP	Montana’s draft Fish and Wildlife Conservation Strategy was reviewed, including Information Management Unit’s (IMU) role in the monitoring of the species and the survey and inventory areas of the Strategy.  The Unit continued to play a key role in the State Wildlife Grant Technical Committee including developing options for implementation of the Strategy.  A presentation will be given at the annual OFWIM meeting on aspects of Montana’s strategy and staff have been involved with organizing a CFWCS session including discussion topics.

A major application to track Game Damage and Wildlife Incidents was developed for FWP; the application will be deployed on the FWP internal website and will be focused on game damage, bear and lion incident and urban wildlife.  The application will be deployed in November.  The agency has determined that an Information Services Division needs to be created that will centralized all IT/IM functions into one division - the division will include Network Support, Application Development, Operations Support and the Information Management Unit.  The proposal is to the governor and if approved, a division administrator will be hired by the end of the year.

The IMU staff moved into a new office area within the Montana State Library; 6 other FWP staff also moved into the area.  Steve Carson will represent FWP on the Hydrography I-Team.

ODFW	Efforts continued towards researching, designing, and developing a database to track Restoration and Enhancement funding applications that interacts with ArcIMS.  This is the first significant ArcIMS effort for ODFW, and along with Wildlife Division needs, is one of the primary reasons the necessary hardware and software was successfully acquired.  The application was released for beta testing during the quarter, and feedback was incorporated on a routine basis.

We continued to provide data management, access, dissemination, and web development support to ODFW's Marine Resources Program (MRP).  Specifically, we maintained the online groundfish harvest status tracking system, and updated the fishery quota status website through August.

Staff continued to support the Oregon Plan Review (Metadata Warehouse) site and provide technical support to numerous users of the site.  Data compilation of Oregon Watershed Council datasets continued at a lower level in support of the Oregon Plan Assessment this quarter.  This included posting statewide documents to the NRIMP Data Clearinghouse website, and creating a metadata record for each.

Oregon StreamNet staff support of the Statewide Wildlife Conservation Strategy continued throughout the quarter, mainly focused on providing GIS and analytical support.  Efforts to incorporate public feedback and streamline the final document included using fish distribution data to add specific salmon species present in each Conservation Opportunity Area to the profiles.  An ArcIMS web application (called the COA Explorer) to view the Conservation Opportunity Areas (COAs) from the Strategy along with other relevant layers is also under development.

Support of the Institute for Natural Resources’ North Coast and Willamette Web Portals continued by modifying the Open Architecture Initiative (OAI) repository service to enable the filtering of datasets by locations using keywords during data harvesting procedures by the Portals.  Because INR would like to duplicate this functionality on their system, we provided them with the source code to implement OAI repository server functionality in .NET.

Our GIS Cartographer completed a series of maps depicting cougar complaints per cougar quota hunt zone.  This included preparing the data for input into GIS and further geocoding to provide point data on a map per hunt zone.  Other hunt management mapping efforts were also completed this quarter.

Supplemental Information		StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 55 of 56

WDFW	The Data Manager completed a first aid training course, including defibrillator training, and worked on the Combined Fund Drive as the Region 5 Local Coordinator, putting together fundraisers and calling local companies to seek donations as prizes.

The Project Manager spent significant time organizing and conducting 9 of 12 planned meetings across the state to review EPA's current draft designations for water quality with WDFW and tribal regional fish biologists.  EPA used WDFW salmon, steelhead, and bull trout fish distribution and use data along with WDFW's SaSI stock-based spawning timing data and USFWS "key reaches" for bull trout in order to improve the original draft water temperature guidance issued by the Washington Department of Ecology.  The goal is to let fish use guide surface water temperature regulations for Washington state, and our input was required to help EPA use our data in proper context.  The remaining meetings will occur in October, at which time questions and recommendations from these meetings will be submitted to EPA for proposed adoption in their final set of regulations.

The Project Manager organized a meeting involving the leads of several key WDFW field sampling programs to discuss improving data capture, flow, and standardization for salmonid age data.  We hope to greatly improve the age data repository we currently struggle to maintain in several databases covering different areas in Washington state.

The Project Manager's newest developer built data capture and QA/QC routines for Chinook telemetry studies in the Upper Columbia and adult returns and research data capture for WDFW's Snake River Lab in Dayton, Washington.  In both cases, biologists were using primitive Excel spreadsheets and macros to try to manage their data, analyses, and reports.  The systems we build here will serve as templates for other areas doing similar data collection and reporting work, which will simplify our access to standardized data from our distant regional offices in the future.

Our new developer also completed a comprehensive Access-based data system for the Blocked Area Resident Fish Stock Assessment (JSAP) Project WDFW jointly participates in with the Kalispell, Colville, and Spokane Tribes.  This new system, which greatly improves the simple Excel-and-Access system currently used to manage the stream habitat and fish sampling data currently collected by WDFW on this project, will be tested on 2005 sampling data beginning in October.

PSMFC	The GIS Specialist spent most of the fourth quarter working on the Pacific Coast Marine Habitat Data Project on other funding.  This was possible because the StreamNet contract only covers ¾ of the specialist’s time.  A website and Internet map application was created to present data developed as a part of the Pacific Coast Groundfish Essential Fish Habitat Draft EIS.  Lessons learned during the course of this project will benefit   StreamNet and the potential exists for synergy between these and other GIS efforts at PSMFC.  The web site will be accessible through the PSMFC website http://www.psmfc.org/ after final review and editing.

WE No.:	999	Title No.:	1	StreamNet Fourth Quarter Performance Report, Fiscal Year 2005	Page 56 of 56