|  | StreamNet Project BPA Project No. 198810804 Fiscal Year 2005 First Quarter Progress Report October 1, 2004 through December 31, 2004 |
| --- | --- |

###### Bruce Schmidt

###### Pacific States Marine Fisheries Commission

###### Cooperators

Phil Roger, Columbia River Intertribal Fish Commission

Bart Butterfield, Idaho Department of Fish and Game

Janet Hess-Herbert, Montana Fish Wildlife and Parks

Cedric Cooney, Oregon Department of Fish and Wildlife

Steve Pastor, U. S. Fish and Wildlife Service

Dick O'Connor, Washington Department of Fish and Wildlife

##### January 15, 2005

Table of Contents                                             Pg.

Introduction………………………………………………………………	 2

Objective 1.  Data Acquisition and Development………………..…….	 7

Objective 2.  Data Management and Delivery…………………………		17

Objective 3.  Library / Reference Services…………………………….		29

Objective 4.  Services to Fish and Wildlife Program Activities………		33

Objective 5.  Project Management and Coordination…………….…..		38

## Supplemental Information: Work accomplished outside the S.O.W...		41

Introduction

StreamNet is a cooperative, multi-agency data compilation and data management project authorized by the Northwest Power and Conservation Council’s (NPCC) Fish and Wildlife Program (FWP) and is funded primarily by the Bonneville Power Administration.  The project is administered by the Pacific States Marine Fisheries Commission (PSMFC).  Three fourths of the project consists of sub-projects within the state fish and wildlife agencies, Columbia River Intertribal Fish Commission (CRITFC) and the US Fish and Wildlife Service (USFWS) to develop databases within the respective agencies and to facilitate data transfer regionally.  The remaining fourth consists of the regional staff at PSMFC, which includes project management, database management and data dissemination functions.

The StreamNet Project compiles, manages and distributes information related to fish resources in the Columbia River basin, with additional information available for the rest of the Pacific Northwest.  The state, tribal and federal fish and wildlife agencies collect and utilize data related to the region’s fish and wildlife resources to meet their own mandates.  A subset of these data, primarily the annually collected types of information that are routinely used to monitor trends within fisheries and populations and provide management information, are compiled by StreamNet into regionally standardized formats and publicly distributed.  In this manner, data common to fisheries management but collected and stored in multiple formats by the individual agencies are standardized and made uniformly available basin wide.  StreamNet also ties all data to the regional 1:100,000 scale (100K) routed hydrography (GIS stream network) so that different kinds of data can be compared on a geographic basis and mapped.  The project utilizes the Internet (www.streamnet.org) as its primary means of data distribution, but also provides custom data services to FWP participants.  The StreamNet web site provides access to information in a queriable database and also provides maps, individual data sets not contained in the queriable database, and library references.  All data in the StreamNet database are referenced to source documents that are housed in the StreamNet Library (www.fishlib.org).  Work reported herein is tied to the specific jobs contained in the Fiscal Year 2005 (FY-05) Statement of Work, available at www.streamnet.org/about-sn/project_management.html.

Introduction			StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 2 of 42

Work priorities for FY-05 include updating existing long term data sets, managing the data and infrastructure necessary to maintain and deliver data, maintaining the StreamNet Library, providing data services to regional entities associated with the FWP, and project administration.  This report documents accomplishments made by the project and its cooperators during the first quarter of FY-05.  Since the cooperating agencies work on different jobs throughout the year, and not all agencies address the same jobs in their respective portions of the Work Statement, the work accomplished in this quarter varies by cooperator.  Tasks and jobs that did not have any work addressed during the quarter are not included in this report.

Activities in the First Quarter of FY-05 included routine development and maintenance of data sets, routine administrative activities to continue project function, and data management support for components of the FWP.  The project continued supporting the Columbia Basin Fish and Wildlife Authority’s (CBFWA) Collaborative Systemwide Monitoring and Evaluation Project (CSMEP).  StreamNet has volunteered to contribute two person months per state to conduct data inventories and enter the information in the online data entry tool developed by Oregon StreamNet.  This effort is seen as a top priority by the region’s fish managers despite the fact that it alters priorities established in the StreamNet Statement of Work and will result in the delay of some planned work on existing data sets.

Key highlights of activities by all project components this quarter are presented by cooperator, as follows:

Regional StreamNet at PSMFC (Region)

Coordination with a number of regional scope efforts continued, including CSMEP, the Pacific Northwest Aquatic Monitoring Program (PNAMP) and the Northwest Environmental Data-network (NED).  StreamNet’s participation was focused on advice and services related to managing data within these programs.

Improved monitoring of the ArcIMS sites helped to optimize performance and reliability and guide future development.  New organization and layout of the IMS sites to provide additional information, clearer operations and more efficient use of space was developed and will be implemented in the near future

Regional and CRITFC personnel archived the data and other information generated during subbasin planning in Oregon subbasins.  These resources were made available on the StreamNet Internet site, and a web page (http://www.streamnet.org/subbasin/2001-subbasin-data.html) was modified to assist in finding these resources.

The web query system was modified to allow for improved data downloads.  A long-standing problem with carriage returns embedded in delimited files was corrected, and the ability to download data in xml format and as Microsoft Excel spreadsheets was added.

Introduction			StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 3 of 42

Significant database improvements occurred during the quarter.  Dozens of outdated tables were archived and removed from the database. Major data submissions from ODFW, CRITFC, IDFG, WDFW, and MFWP were incorporated into the StreamNet database.  A data submission from USFWS was received and will be processed in January.

Columbia River Intertribal Fish Commission (CRITFC)

Work during the first quarter was fairly routine.  Demands for Library services occurred at a fairly steady rate and all service requests were filled.  The scheduled upgrade of the Library server was completed and improved backup procedures were implemented.  Prior to the upgrade, the old server crashed, but all files were successfully restored.

The Project Leader continued to serve on several regional data management and monitoring groups whose activities involve data management issues.  The Project Leader also led efforts to update and improve the watershed assessment for the John Day basin.

U. S. Fish and Wildlife Service (FWS)

Activities for the FWS in the first quarter centered on routine development of data originating with the National Fish Hatchery System.

Idaho Department of Fish and Game (IDFG)

Updates of Idaho’s anadromous and bull trout generalized fish distribution database utilized the 2004 subbasin assessments and IDFG data now available in the Idaho Fish and Wildlife Information System.  This was the first major update of fish distribution since initial submission.

StreamNet staff worked with non-StreamNet staff to oversee the data compilation and preparation for the 2004 bull trout status review.  Staff worked with workshop participants and provided data proofing and updating, formatted data into final forms, produced queries for data analysis and helped write sections of the report.

Staff migrated all GIS software to the ArcGIS 9.0 level, including ArcSDE 9.0 and ArcIMS 9.0.  The improved and additional functionality has already proven useful, especially the linear referencing tools, which were used in fish distribution updates.

Introduction			StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 4 of 42

Montana Fish, Wildlife and Parks (MFWP)

Resident Fish distribution data were entered as received, completing the majority of the backlog.  2005 visits to FWP, USFS, BLM and USFWS offices to collect their 2004 data will occur in the second quarter.

A meeting was set up in January with Montana StreamNet and MFWP Fisheries Division administrators to discuss what assistance SN staff can provide to the division in developing statewide field collection standards.

Hatchery facility data was exchanged during the first quarter.  Staff worked with the genetic labs at the University of Montana and Montana State University on standardized genetic reporting.  A database front end using these standards was finalized this quarter.  Montana’s habitat restoration project database is being reviewed internally.  Additional fish passage barriers were added during the bull trout status review conducted by Montana and Idaho, further delaying data delivery to the Regional database.  This effort is near completion and data are anticipated to be exchanged in the second quarter.

Discussions were held with Montana's USGS representative concerning completion of the 1:24,000 scale (24K) hydrography for the state.  Although the USGS is interested in completing Montana, they are also interested in some financial partnerships.  The MFWP fisheries biologist responsibility area GIS layer was updated during the quarter and distributed to Fisheries Division staff.  Fifteen data and/or GIS requests were filled during this quarter.

The rating system conducted in 1998 from MFISH data was recently used to develop rules for dredge mining in Montana; meetings were held with DEQ staff on several occasions to address the draft policy.

Several staff changes were made during the quarter:  Lydia Bailey moved to Helena and was promoted to the GIS and Natural Resource Data Manager for the unit; Kim Lindstrom, GIS/Programmer Analyst, resigned and her position was rewritten to emphasize wildlife and data analysis.  The position was advertised and Adam Messer, information specialist working on the Comprehensive Fish and Wildlife Plan for the agency, was selected for the position.  Jeff Hutten will remain in Kalispell as the StreamNet western Montana representative and has reduced his hours on the StreamNet contract to a half-time basis.

Montana’s Project Manager attended the Fisheries Division Manager's meeting in September to discuss various data management projects and the Montana Angler Forum to demonstrate the "Montana Fishing Guide", the recreational version of StreamNet data.

Introduction			StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 5 of 42

Oregon Department of Fish and Wildlife (ODFW)

Progress was made on most project deliverables that were slated for attention during the quarter.

CBFWA’s request for us to conduct data inventory work and develop/maintain an online database application for the CSMEP project continued during the quarter, exhausting the 2 person-month commitment made by each StreamNet partner.  Further CSMEP participation and support will take up time that would normally go towards other planned activities and could lead to delays in or postponement of some planned activities.

Specific deliverables addressed this quarter included the submission of updated spawner / recruit data, the release of updated barrier information, and internal and external project coordination.  The other significant data related effort centered on modernizing Oregon StreamNet’s data management and dissemination capabilities through the use of SQL Server, and ArcIMS software packages.

Significant progress was made toward establishing an agreed upon approach to address 24K hydrography development and the generation of linear event data for the Basin’s 24K fish distribution.

A great deal of work was accomplished this quarter related to data and database management infrastructure improvements, including tool, website, and database development, which are described in this report.

Work on Oregon’s various data update protocols continued this quarter.  The draft Distribution Data Update Protocol was nearly completed, needing only minor edits to get it finalized.

Washington Department of Fish and Wildlife (WDFW)

The new WDFW StreamNet data compiler was hired and outfitted with an initial work plan that leverages his background in MS Access well in meeting initial WDFW-StreamNet needs.  He will initially be tasked with work related to barriers and habitat restoration project information, but his background in GIS provides us a source of additional skill to tap when unforeseen events occur.

The master escapement database has been updated with all 2003 and most 2004 fish survey records; focus now moves to incorporating data from 2002 and earlier into the new (internal) format.  This will facilitate data conversion and exchange with PSMFC in the quarters ahead.

Agreement reached on the final format of the hatchery returns database opens the doors for conversion and exchange of over 30,000 records of new-format data next quarter, including 2,500 new records.

Introduction			StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 6 of 42

The WDFW StreamNet GIS Manager started incorporating NHD line work along the WA-ID border and in Northeast Oregon (where available) into the 24K statewide hydro layer.  This is the first step toward integrating cross-border streams and creating the four-state mixed-scale hydro layer that we need in order to share recent Washington updates to fish distribution (and other spatial datasets).

Migration from ArcInfo to ArcGIS 9 continued, as the Location Data Manager created our first geodatabase files to store the Columbia River and "other Washington" 24K hydrography data.  The planning time she is putting into organizing spatial data files that will be migrated to ArcGIS will pay off in the months ahead as we attempt to continue migration without disrupting ongoing activities.

Objective	1	Data acquisition and development

Support the need for region wide fisheries data for research, monitoring, modeling, and management through acquisition and regional standardization of new information and updates to previous information for priority fishery data types.  Data types may be addressed by all data providing agencies, or for specific data types by a single cooperating agency on behalf of the entire project.  This Objective addresses both anadromous and resident fish species, although priorities may differ.  The tasks under this objective are identified as high or low priority under the constraints imposed under level base funding.  Work on the low priority types will largely be limited in scope or effort unless new funding is approved.  Primary focus this fiscal year will be to Quality Check the data in the StreamNet databases and to correct as necessary.  Data updates will be delayed during the QC.

Objective	1	Data acquisition and development

Task	1	Anadromous distribution and life history (habitat use) at the 1:100,000 scale

Document the occurrence, distribution and life history characteristics of anadromous fish species.  Project participants made major updates last fiscal year utilizing the new Data Exchange Format (DEF).  Maintenance of this data set will continue.  This is a high priority data set.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

IDFG	1	On an opportunistic basis, capture and update 100K 	We completed updates of generalized fish distribution for fall Chinook, spring

anadromous fish distributions.	Chinook, summer Chinook, steelhead and sockeye salmon.  New information from

the 2004 Salmon Subbasin Assessment and IDFG redd count database were

incorporated.  The information will be exchanged with PSMFC early next quarter.

ODFW	1	Update, maintain, correct and exchange anadromous fish 	Routine maintenance was performed on Oregon's anadromous fish

distribution and documentation information.	distribution and documentation information during the quarter.

Objective	1	Task:	1	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 7 of 42

WDFW	1	Convert newest Washington anadromous fish distribution 	WDFW GIS staff piloted data development of an "aboriginal presence" fish

data to StreamNet format (once streams layer can 	distribution layer for winter and summer run steelhead statewide.  This layer, based

accommodate 24K streams). Exchange data when completed.	on impassable natural barriers (including modeled gradient breaks) and documented

generalized presence in at least some part of the stream, was constructed in support

of WDFW's statewide Steelhead Management Plan (still under development at this

time).  If users reach consensus on the utility and proper rules for creating such a

modeled layer, the results will appear in the Plan.  Results will also be provided to

the StreamNet Steering Committee during Q3 of FY-05 for consideration as a

potential regional data layer for OR, WA and ID.

Objective	1	Data acquisition and development

Task	2	Resident fish distribution and life history (habitat use)

Document the occurrence, distribution and life history characteristics of resident fish species.  Existing resident fish distribution will be maintained, and project participants will begin expanding data for additional species.  This is high priority for Montana and Idaho, and new data will be developed by the other states as time allows.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

IDFG	1	On an opportunistic basis, capture and update 100K resident 	We completed an update of generalized fish distribution for bull trout.  Information

fish distributions.	from the 2004 5-year status review being conducted by Idaho, Montana, Nevada and

Washington were incorporated.  The information will be exchanged with PSMFC

early next quarter.

MFWP	1	Complete Distribution and Use Types data sets from data 	Data was entered as it was received and most of the 2004 backlog also was

collected from biologists, documents and reports during 	completed.

2002-2003 using LLID stream routes and Montana's lakes

coverage and water code system.  Exchange with StreamNet.

Complete distribution and use type data sets for 2003-2004.

Update entire state.  Focus on target species during the year if

opportunity arises.  Exchange the data to the regional

database in the approved DEF format.

MFWP	2	Visit MFWP, other state and federal fisheries biologists in 	Visits to FWP, USFS, BLM and USFWS offices will occur in the second quarter.

2005 to collect 2003-2004 fish distribution and supporting

survey data and references.

MFWP	3	Work with FWP Fisheries Division to assist in the 	A meeting was scheduled for January with Montana StreamNet staff and Fisheries

development of fisheries field collection survey standards.	Division Administrators to discuss what assistance SN staff can provide to the effort

of field standards as we visit the regions during the second quarter.

Objective	1	Task:	2	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 8 of 42

MFWP	4	Explore commonly used habitat fields collected on streams to	Exploration of commonly used habitat fields will be conducted during the regional

see if there is a core set related to fish distribution data.	visits.

ODFW	1	As time and funding permits update, maintain, correct and 	Routine maintenance was performed on Oregon's resident fish distribution and

exchange resident fish distribution and documentation 	documentation information during the quarter.

information.

WDFW	1	Using formal fish distribution mapping parties, organize the 	A copy of the federal west slope cutthroat data was obtained and assessed in order to

effort to update Washington west slope cutthroat distribution	plan incorporation of these data into our existing dataset.  The shapefile received

data and compile that data in concert with the existing 	was in a newer version than the one we are working in, so this work was postponed

federal data that was compiled in 2002.	until we make further progress in our conversion from ArcInfo to ArcGIS 9.

WDFW	3	Incorporate any Washington bull trout distribution data 	WDFW staff coordinating the data capture for the five-year bull trout status review

updates resulting from the regional 5-year bull trout status 	have compiled and entered dozens of updates to bull trout distribution and barriers.

review.	The distribution data that have been confirmed by area biologists have been entered

into WDFW's database.  There are still a few cases outstanding where final

confirmation was not received by the end of this quarter.

WDFW	5	Scope data availability and work to compile, convert and 	WDFW staff transferred fish distribution data for priority resident fish species

exchange distribution data for other priority resident species 	statewide (including rainbow trout, coastal cutthroat trout, and westslope cutthroat

(including coastal cutthroat and rainbow trout).	trout) from the 1985 1:100K scale dataset to the WDFW 24K hydrology layer.

These data will be available to convert and exchange once the regional mixed-scale

hydro layer is ready for data (probably in the third quarter, FY2005).

Objective	1	Data acquisition and development

Task	3	Adult abundance in the wild

Develop and maintain (update) information on adult abundance for native fish species, resident and anadromous, including escapement, redd counts, peak spawner counts, trap counts, dam and weir counts, and resident fish populations (where calculated by other agencies).  This is a high priority data type.  Also included in this data category are data gathered during spawning ground surveys regarding straying of hatchery fish onto spawning areas, i.e., marked/unmarked ratio.  These are lower priority under base funding.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Update mainstem Columbia and Snake River dam counts 	No work was performed this quarter. Dam counts are typically available in corrected

through 2003 and provide updated data to the StreamNet 	form in the second or third quarter.

database.

CRITFC	2	Update available tribal spawning ground survey data.	No work was performed this quarter. These data are typically available in corrected

form in the second or third quarter.

Objective	1	Task:	3	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 9 of 42

IDFG	1	Compile and submit the 2004 field season redd count data	Data entry for all but 2 of the 2004 redd counts were completed.  We have been

from IDFG.	unable to obtain the 2 missing counts.

Carcass data from the 2003 and 2004 spawning ground surveys was compiled.  This

completes all of our carcass data from 1960 through 2004.

We completed a wholesale update of miles surveyed in the regional database, moving the information from the comments field into the miles surveyed field.

MFWP	2	Input 2003 data into MFISH, including trend, count and references.	This task is ongoing; data will be exchanged on a scheduled basis.

ODFW	1	Maintain existing anadromous, resident, and non-game 	Routine maintenance was performed on abundance and index trend information

abundance and index trends.  Any updates will be the result of 	this quarter.  Effort this year is focused on improving the quality of existing

QA/QC efforts, and easily incorporated trend data.	information rather than updating or adding to the existing Oregon trends.  However, during QA/QC efforts  (see Objective 2; Task 3; Job 2), some new information was obtained and added to the database, particularly in the Grande Ronde and Imnaha basins.  New incidental coho and Chinook survey information in the Lower Columbia was also added.  Updated information/corrections were submitted to Regional StreamNet in late October, but work continued throughout the quarter.

WDFW	1	Update and enhance the existing natural spawner database 	Stream survey cards for the 2004 return year were entered into the survey card

(escapement estimates and/or detailed counts) for available 	database branch of the master escapement database.  A total of 1,485 records have

species. Convert and exchange data.	been entered for the Columbia River and tributary specific sites with only a few chum and coho surveys left to be made for the 2004 return year.  In the process of completing this database, past years are being entered when time permits.  The 2003 return year has been completed and attention now is focusing on the 2002 survey cards.  A total of 1,073 cards were entered this quarter, which completed the 2002 return year.  Past years have been completed for complete tributaries from1944-present.  This data has not been ported yet to the database as it needs to be proofed first.  There are approximately 10,000+ records in this dataset with another 30,000+ to be entered.

To help facilitate data collection and data needs, the Vancouver data 	compiler designed a new survey card that will be implemented in the 2005 return year.  These cards will hold more data, meet the needs of state managers and will better contain data that can be entered into the StreamNet database.

Continued efforts have been made to acquire historical steelhead spawning data that can be entered into the escapement database.  The collected data will be reflected in the July exchange that will complete the 2004 return year and age data.

WDFW	2	Continue maintaining and updating adult trap databases on all 	The Cedar Creek adult trap database was updated with 1,085 records entered.  Data

traps in Region 5 (lower Columbia River).	will continue to be entered into the adult trap database until the end of February.

Objective	1	Task:	3	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 10 of 42

Objective	1	Data acquisition and development

Task	4	Hatchery releases

Develop and maintain (update) information on the release of hatchery reared fish.  Emphasis this year will be on developing release data before release information is rolled up into PSC location codes.  Release data for resident species under base funding will be developed only where the data are readily available (primarily Montana).  Efforts will be made to complete cross references between PSC release codes and LLID stream location identifiers.  This is a high priority data set.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

FWS	1	Acquire and process hatchery release information from 	Preliminary processing of calendar year 2004 release information has occurred.

national fish hatcheries in the region.

ODFW	1	Compile and submit anadromous hatchery releases through 	Staff continued to work on cross-links to PSC codes, developing and using an

2003, and 2004 where available, in an unrolled format if 	iterative approach for following up with the liberation coordinators to finish off

possible.	this work.  During this quarter, we contacted Liberation Coordinators for the NE

and SE ODFW regions and resolved all "active" (defined as releases since 2000) NE

Region locations and assigned LLIDs as appropriate.  Work will continue until all

the unmatched codes that have actually been used are linked with LLIDs.

Objective	1	Data acquisition and development

Task	5	Hatchery returns

Develop and maintain (update) information on the return, disposition and straying (e.g., from other hatcheries) of adult fish returning to hatcheries, including information on coded wire tags.  This is an anadromous related task only.  Priority will be placed on updating total return and egg take data through 2002.  Development of disposition data is lower priority and would require additional resources.  This is a high priority data set.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

FWS	1	Complete work on the new program to convert information 	Hatchery return information from National Fish Hatcheries for the 2004 return year

from the FWS CRiS format to the new StreamNet hatchery 	has been received and added to the CRiS Returns file.

returns format.

WDFW	1	Complete the conversion of old DEF hatchery returns data to	Continued efforts have been made to convert all WDFW hatchery returns data to

the new DEF for all species and sites. Exchange data when 	the new DEF.  With the final format "finally" agreed upon by all entities, the final

complete.	conversion and exchange can take place in the second quarter.  Approximately

30,000 records will be exchanged.  Of these, approximately 2,500 records will be

new data.  The other records will be updated due to format changes, ASNID

additions or changes and fixes found in the null flag field.

Objective	1	Task:	5	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 11 of 42

WDFW	2	Work jointly with other WDFW hatchery data unit staff to 	Great effort has been made to work closely with other WDFW staff to help redesign

create a more efficient means to improve the internal 	and convert Paradox hatchery returns data to the MS Access format.  Database

WDFW hatchery returns data system and simplify data flow 	structure in the WDFW internal hatchery returns database will be similar to the

from this database into the conversion and exchange process.	StreamNet DEF for hatchery returns thus facilitating a faster and easier exchange of

data when finalized by the agency.  We expect to see gains in efficiency at the next

hatchery returns data exchange, expected in the second quarter, FY-05.

WDFW	3	Help WDFW regional biologists with run reconstruction 	Data manipulation and analysis was performed for Fish Biologist Shane Hawkins to

efforts in order to better feed the WDFW-StreamNet master 	help determine population estimates of Lewis River wild fall Chinook.  Historical

databases and meet other urgent needs of the agency.	survey counts and population estimates were queried out of the WDFW maintained

StreamNet database.  This data was used as part of the Pacific Power and Light

(PPL) re-licensing agreement and future funding.

Both Vancouver StreamNet staff assisted Regional Fish Biologist Dan Rawding with data analysis and final reporting of Cedar Creek adult and smolt data.  This effort will help to further fund this data collection effort and to continue to populate these data and information-rich databases.

Objective	1	Data acquisition and development

Task	6	Dams and Fish Passage Facilities

Develop and maintain information on dam facilities.  Update information as necessary.  This is a high priority data set.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

IDFG	1	On an opportunistic basis, capture and update dam and fish 	Some ambiguous dam Ids were updated in the regional database.

passage facility data.

MFWP	1	Update dam facilities data, as necessary	There are no new dam or fish passage data available, so no data exchange is

necessary.

WDFW	1	Update the dam database, adding records and improving field 	We questioned the keepers of the NID database why about 400 dams with unique

entries as warranted.	NID codes are now missing.  It appears we'll need to prod them for the information

a third time.

Objective	1	Data acquisition and development

Task	7	Hatchery facilities

Develop and maintain information on anadromous and resident hatchery facilities, including information on location, design, management

and authorization.  Update information as necessary.  This is a high priority data set.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

MFWP	1	Update the StreamNet hatchery database with Montana's 	The hatchery facilities data were exchanged during the first quarter of  FY-05.

public and private facilities.

Objective	1	Task:	7	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 12 of 42

WDFW	1	Update the hatchery database, adding records and improving 	We updated the internal codes grouping hatcheries under the hatchery

field entries as warranted, including record updates for related 	complex and cleaned up the storage directories.

tables (i.e. HatcheryXProduction data).  Convert and

exchange data when complete.

Objective	1	Data acquisition and development

Task	8	Harvest

Develop and maintain (update) information on sport and commercial harvest.  Higher priority is assigned to anadromous species.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Update available ocean and mainstem Columbia River harvest	No work this quarter.  This is an unfunded activity. We will see if other

numbers through 2004, as available.	StreamNet partners can pick up this task.

Objective	1	Data acquisition and development

Task	9	Hydrography

Maintain a regionally consistent routed hydrography layer at the 1:100,000 scale.  This LLID based hydrography is the basis for georeferencing and displaying locations for all other data in the StreamNet database, and as such is an essential data set.  Data will be updated as necessary.  Exploratory work will be initiated in preparation for the eventual, inevitable move to the 1:24,000 scale hydrography being developed by other entities.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

MFWP	1	Using the NHD, continue to update the routes using the 	Discussions have occurred with Montana's USGS representative concerning the

updated NHD layer, including lakes; quality check the 	completion of the 1:24 K hydro for the state.  Although the USGS is interested in

cross-reference between the LLID system and MFWP's water 	completing Montana, they are also interested in some financial partnerships.  We

code system.  Pursue any needs developed by the Steering 	will explore funding sources, including StreamNet, next quarter.

Committee for a 1:24 K product.

ODFW	1	Maintain and update, as necessary, the 1:100,000 scale 	Our GIS Analyst met with Regional and Washington StreamNet staff in Olympia to

hydrography files for Oregon.	discuss strategies for moving forward with enhancing the regional 100k hydrography

dataset with 24k stream routes. More discussion will be necessary before proceeding

with the approaches that were discussed.  As part of this effort, our GIS Analyst

assessed issues related to Framework 24k routes, and mapping our distribution event

data on top of those routes.

ODFW	2	Assist regional staff with the development of a hybrid 100k 	Our GIS Analyst compared hydrography from two different datasets along the

and 24k hydro layer that will enable display of all distribution	Oregon / California border, assessing approximately 3 dozen routes where the

data in a linear format	differences in route length were significant.  He provided comments to the regional

GIS staff person regarding the specific issues with each and recommendations about

which route to retain.

Objective	1	Task:	9	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 13 of 42

WDFW	1	Build and submit a "hybrid" layer containing 24K 	On October 5 we met in Olympia with the GIS technical team to discuss details in

representation of all 100K Washington streams PLUS 	preparing/adopting a 24K hybrid layer for StreamNet.  Following the meeting, our

24K-only streams containing StreamNet data.	Location Data Manager prepared (and shared) a work list addressing the issues and

strategies for internally QCing the conversion of existing tabular data links.

The WDFW StreamNet GIS Manager began work to replace WDFW 24K scale line work with NHD line work along the WA-ID border and in Northeast Oregon (where available). Initially, he converted the existing WDFW 24K hydro from a WRIA (state basin) basis to a HUC (USGS basin) basis.  This facilitates swapping of our line work with HUC-based line work from the NHD dataset, and represents the necessary first step toward preparing a synchronized mixed-scale hydro layer for the four-state StreamNet region.  A lot of program writing, debugging, and testing lies ahead.  We now hope to have the Washington portion completed in the second quarter, FY-05.

WDFW	2	Finalize creation and QC of a 24K spatial/tabular lakes 	Olympia StreamNet staff met twice with DNR to discuss our current lake layer and

dataset to support data compilation and exchange for resident	partially complete links to Wolcott's Lakes of Washington publication.  DNR will

fish releases and other data under Objective 1.	use our database version of Wolcott to tie to THEIR lake layer.  These meetings

and data sharing jump-started the effort to re-format our tabular lake file, create a

data dictionary, and correct some of the links.  With the cleanup, WDFW is more

prepared to finish our Wolcott links and react to the product DNR creates.

Objective	1	Data acquisition and development

Task	10	Habitat restoration / improvement projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations within the Columbia Basin, and compile and maintain them in standardized, consistent formats.  Preliminary work has been completed on this data type, but regional priority has not been assigned to developing these data.  Work continues on improving the data structure and DEF, primarily through work being done by a related project in California.  This currently remains a low priority data type under current base funding, but is ready should a higher priority be assigned by regional

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

MFWP	1	Continue to collect, centralize and maintain all stream 	Initial review of the database structure started in the first quarter; this task

restoration projects data for Montana using the "Future 	has been reassigned to Dawn Anderson.

Fisheries Interface".

WDFW	1	Complete conversion and exchange of Washington habitat 	We started converting a publication of habitat restoration and barrier terms into an

restoration project information extracted from IAC's PRISM 	electronic glossary database.

system and 2000-2002 NWIFC PCSRF data, given that a final

DEF exists for this data category.  Scope out additional content

from WDFW's LIP initiative and other sources as time permits.

Objective	1	Task:	10	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 14 of 42

Objective	1	Data acquisition and development

Task	11	Barriers

Develop and maintain data sets for barriers to fish migration.  This category is still being organized.  Existing data on adult barriers will be maintained and updated as practical.  Other sources of data will be explored.  Work on juvenile barriers and culverts may require revisions to the DEF.  The primary emphasis is on anadromous species except in non-anadromous areas.  This is a low priority data set under current base funding, and will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

IDFG	1	On an opportunistic basis, capture and update barrier data.	New barrier information was captured through our participation in the bull trout

status review.  The data have not been incorporated into our StreamNet barrier

database, yet.  As soon as the status review is completed we will capture the barrier

data in StreamNet format.

MFWP	1	Maintain barrier location, species affected and other fields on	Data exchange was delayed because additional fish passage barriers were added

stream barriers in Montana.  Information will be collected on	during the bull trout status review conducted by Montana and Idaho.  This effort is

all species regardless of life history.  Exchange Barriers data 	near completion and data are anticipated to be exchanged in the second quarter.

with the StreamNet database.

ODFW	1	Update and maintain Oregon's Barrier data and minimal Fish 	New maps reflecting Oregon's most up-to-date barrier information were posted to

Barrier data development based on new barrier information, 	the ODFW server in late November, making them available to everyone.

including information from non-ODFW sources.

WDFW	1	Scope existing Washington state barriers datasets for a pilot 	Our new Olympia Data Compiler started scoping the FPDSI fish barriers/fishways

data submission this FY.  Data sources will at least include the	database managed by WDFW's Habitat Program and building cross-references to the

Salmon and Steelhead Habitat Inventory and Assessment	newest StreamNet DEF and proposal.  Natural barriers from SSHIAP are soon to be

Project (SHIAP) and TAPPS (now renamed as the Fish Passage	integrated into the FPDSI database as well.   Through meetings with FPDSI staff and

and Diversion Screening Inventory - FPDSI) databases	reviewing a copy of the voluminous Fish Passage Database manual, he was able to

record the source field for each StreamNet Barriers DEF attribute where possible, and construct a short list of issues/questions related to this step.  That list was posted to the Forum for comment in late December.

Objective	1	Data acquisition and development

Task	12	Juvenile data (abundance and outmigration)

Develop and maintain information on smolt production (as determined from smolt traps), juvenile abundance (as determined through snorkel, electrofishing, and other surveys), and smolt density model estimates.  Primary emphasis will be on maintaining the existing smolt density model data and development of a DEF for these data.  The rest of the work for this data category is still under development and will require additional resources to accomplish.  This is a low priority data set under current base funding, and will be addressed as time and other priorities allow.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Provide tribal juvenile abundance and/or outmigration data as 	No work this quarter. These data are typically available in corrected form in the

time and availability allow.	second or third quarter.

Objective	1	Task:	12	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 15 of 42

WDFW	1	Continue maintaining and updating smolt trap databases on 	Proofing the Cedar Creek smolt trap data has been completed and 8,230 records

all traps in Region 5 (lower Columbia River).  Scope out a 	have been ported to the MS Access database.  Documentation for this database has

pilot data conversion and exchange effort for Cedar Creek 	been ongoing and is almost complete.  This database dates back to 1998 and was not

data.	maintained by the WDFW StreamNet data managers until 2002.  Great effort has

been expended to document data changes before 2002 so data is not misrepresented when compared to other years.  Vancouver Data Compiler Michelle Groesbeck has done an outstanding job in bringing this data together and into a manageable form.

The Vancouver Data Compiler also worked with the Regional Fish Biologist to complete population estimates for the tributary using collected smolt trap data.  Since this data is in MS Access and few biologists in the region understand or can manipulate data in this database, she has put together canned queries to help them with their final reports and management decisions.

Objective	1	Data acquisition and development

Task	13	Age

Develop and maintain information on age/sex composition of returning adults, primarily for anadromous species.  Emphasis on this data type will increase once the draft DEF is tested and finalized.  This is a low priority under current base funding.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

FWS	1	Finish work on the new program to transform age 	Hatchery return Age information for National Fish Hatcheries in the 2004 return

information from the CRiS format to the new StreamNet 	year has been processed and added to the CRiS Age file.

format.

IDFG	1	Compile and submit the 2004 field season age data from 	A wholesale correction and update was made to our age data in the regional

IDFG.	database.

WDFW	1	Update and exchange age data records gleaned from hatchery 	No age data work was done this quarter.  Age data from previous years return will

returns and adult abundance exchanged data.	be exchanged next quarter.  The 2004 age data cannot be entered until finalized and

released by the agency.

Objective	1	Data acquisition and development

Task	14	Production factors and run reconstruction

Develop and maintain information on survival, production factors, spawner / recruit estimates, and run reconstruction.  This is a low priority data type under current base funding, but the existing spawner / recruit estimate data will be maintained.  Current effort will focus on what aspects of this kind of data are most needed.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Provide productivity data from subbasin planning and other 	Completed.  Subbasin planning data for Oregon have been archived and delivered to

technical analyses as available.	the Regional staff.  Access is provided through the StreamNet Web page.

Objective	1	Task:	14	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 16 of 42

Objective	2	Data management and delivery

Provide high quality data management services, with specific emphasis on the creation of regionally consistent data sets and the timely delivery of data to users in formats that meet their policy, planning, monitoring, and management needs.  A primary data management effort this year will be to Quality Check the data already contained in the StreamNet databases and correct as necessary, which may delay the delivery of data updates.

Objective	2	Data management and delivery

Task	1	System Administration

Manage and maintain the computer systems (hardware and software) necessary for supporting the tabular and GIS data systems at the regional and cooperating agency levels, including system backup.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Manage, maintain and enhance the computer systems 	The Library server was scheduled for upgrade and replacement equipment was

(hardware and software) necessary for supporting the 	leased.  Prior to the upgrade, however, the old server crashed just before Christmas.

StreamNet Library, including system administration, backup 	All data and files have been recovered and placed on the new server.  We have a few

and recovery, hardware and software upgrades, and security.	remaining software configuration issues left to resolve.  These will be completed in

January.  Library services were not significantly compromised during the change to

a new server.

IDFG	1	Manage, maintain and enhance the computer systems 	Upgrades to ArcIMS 9.0 and ArcSDE 9.0 were completed.  In addition, all of our

(hardware and software) necessary for supporting the tabular 	client workstations were upgraded to ArcGIS 9.0

and GIS data systems, including system administration,

backup and recovery, hardware and software upgrades, and 	In 2004, the State of Idaho adopted a new map projection standard using the NAD83

security.	datum, referred to as IDTM83. This map projection has been added as a standard

projection to ArcGIS 9.0 with service pack 1.  We began projecting our GIS layers

to IDTM83 and rebuilding our SDE layers.  Idaho Department of Water Resources

donated 250GB of imagery in IDTM83.

Progress continued in configuring our web site and Internet access.  This will integrate our Internet, Intranet and Extranet with ArcIMS, Microsoft Reporting Services and our fisheries data applications, such as the Spawning Ground Survey and Juvenile Trap Application.  We have installed a proxy on the IDFG public web server and configured both the State of Idaho and IDFG firewalls to deliver content outside IDFG.

MFWP	1	Manage, maintain and enhance the computer systems (hardware	Ongoing system administration work continued during the quarter.

and software) necessary for supporting the tabular and GIS data

systems, including system administration, backup and recovery,

hardware and software upgrades, and security.

Objective	2	Task:	1	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 17 of 42

ODFW	1	Manage, maintain and enhance the computer systems 	Routine system administration and management continued throughout the quarter.

(hardware and software) necessary for supporting the tabular 	Significant effort was spent taking steps towards utilizing SQL Server, ArcIMS and

and GIS data systems, including system administration, 	ArcSDE, including acquiring and testing evaluation copies of the software and

backup and recovery, hardware and software upgrades, and 	reconfiguring existing hardware addressing various connectivity and configuration

security.	issues to facilitate the efficient use of these software packages.

Coordinating with other ODFW projects that utilize GIS software, our GIS Analyst initiated the purchase of updated licenses for our GIS software.

Region	1	Maintain and update, as necessary, the hardware and software,	The GIS was maintained and updated this quarter, including the installation of

including ArcView and other tools, extensions and projects, 	service packs for ArcGIS and ArcIMS.

that constitute the regional Geographic Information System.

Provide system administration, backup and recovery, and

security.

Region	2	Maintain and upgrade the StreamNet web server and software,	We maintained excellent web server up-time (99.5%+) during this quarter along

including programming, system security, etc.	with a significant reduction in overall errors reported in the logs.  The reduction in

errors is probably related to an update applied to the Apache web server that

increased stability.

Region	3	Assist with development of XML schema based options for 	An XML option was added to the download file types available for all report types.

both incoming and outgoing data.  Continue exploration of

how XML can enhance data exchange.

Region	4	Maintain database servers and SQL Server software and 	Routine maintenance of two SQL Servers was highlighted by the creation of agent

databases; installing updates, patches and service packs as 	jobs to automate daily, weekly & monthly backups of several additional databases,

they become available.  Manage logins and permissions.  	and porting of backups of the spatial data engine from disk storage to portable media

Routinely backup all databases.  Assist with system 	to free storage space for the Commission's new asset tracking software that uses a

administration and purchasing.	SQL Server database.

WDFW	1	Manage, maintain and enhance the computer systems 	New software to download, store and manipulate collected GPS coordinates was

(hardware and software) necessary for supporting the tabular 	installed on the Vancouver Data Manager's machine.  Supporting software and

and GIS data systems, including system administration, 	updates for the ArcGIS Software was installed this quarter.  All necessary software

backup and recovery, hardware and software upgrades, and 	upgrades and security patches were installed on all computers managed by

security.	Vancouver StreamNet staff.

With the Regional Programmer's effort and suggestions from our internal Information Services, we eventually resolved our StreamNet Forum access issues that came during a flurry of forum postings.

Objective	2	Task:	1	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 18 of 42

Objective	2	Data management and delivery

Task	2	Application and Interface Development

Develop computer applications and interfaces that facilitate the entry, management and dissemination of tabular and GIS data at the regional and cooperating agency levels.  This will include development of new applications and tools as well as maintenance or modification of existing applications.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Develop and/or maintain computerized databases, applications	Normal database management practices and functions were maintained.  They will

and interfaces that facilitate the entry, compilation, management	be reviewed and improved as appropriate during the data updating process in

and dissemination of tabular and GIS data.	future quarters.

IDFG	1	Develop and/or maintain computerized databases, applications	We developed XML rules and tied them to our Idaho Fish and Wildlife Information

and interfaces that facilitate the entry, compilation, management	System (IFWIS) framework.

and dissemination of tabular and GIS data.

Migration of the Reference Program to .Net has been completed.  This program is

our basic StreamNet data management application.  It contains information that is

obtained from reports, publications, etc, including redd counts, hatchery returns,

disposition, age composition and fish observations.

Work to redesign our hatchery returns database design and migrate our existing data to comply with the new StreamNet hatchery returns DEF was begun.

MFWP	1	Develop and/or maintain computerized databases, applications	Minor changes were made to the MFISH database; the restoration projects table will

and interfaces that facilitate the entry, compilation, management	be added to the MFISH website next quarter.

and dissemination of tabular and GIS data.

ODFW	1	Develop and/or maintain computerized databases, applications	Our GIS Analyst researched and installed SQL Server and ArcSDE and tested

and interfaces that facilitate the entry, compilation, management	various components of each, including the design of an integrated Distribution,

and dissemination of tabular and GIS data.	Barrier and Hydro geodatabase.

Work was done to enhance charting controls for the web application framework we use.  A generic charting control was created and other types of controls from it were specialized, such as a line plotting graph and a vertical bar graph.  Using this base control will allow us to easily propagate any fixes or enhancements that we make to the suite of charting controls, while allowing specific controls to specialize in their respective areas.

ODFW	2	Continue development of a corporate information system.	The Database Manager/Developer compiled release builds of the application framework Dynamic Link Libraries for use in past and future projects, allowing the same block of library code to be shared between several applications instead of each application having to contain copies of the routines.  He also made some changes to the framework to increase database concurrency and reduce possible errors between application and framework data.  Work performed under Objective 2; Task 2; Job 1 also aids in the development of ODFW's corporate information system.

Objective	2	Task:	2	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 19 of 42

Region	3	Develop and/or maintain computerized databases, 	No new tools were required this quarter.  Previous work was maintained.

applications and interfaces that facilitate the entry,

compilation, management and dissemination of tabular and

GIS data..  Assist cooperating agencies with tool

development, as requested.  Tools may include input

interfaces, error checking, geographic locators, etc.

WDFW	1	Develop and/or maintain computerized databases, 	WDFW's 24K hydro coverages are maintained in separate WRIAs (Washington-

applications and interfaces that facilitate the entry, 	centric watershed boundaries) and awkward to generally navigate in ArcGIS.

compilation, management and dissemination of tabular and 	Since one statewide coverage is too large for PC software, the Location Data

GIS data.	Manager created a merged geodatabase file for the Columbia River and another

for the rest of Washington.

She also started researching the best directory structure for storing files to be used with ArcGIS or the free ArcExplorer.  An initial good directory structure is vital because the paths must be re-set on any ArcGIS map or project file whenever files are moved.

Objective	2	Data management and delivery

Task	3	Data (content) Management

Manage data at the regional and cooperating agency levels to assure timely and accurate data flow from source to final

distribution.  Activities include exchange of data to PSMFC, data loading, updating data, quality assurance procedures,

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Perform comprehensive QA/QC on all datasets maintained by	No work this quarter because data were not changed during the first quarter.  This

CRITFC.	task will be completed as data sets are updated in future quarters.

MFWP	1	Manage data at the agency level, develop and maintain FGDC	A review was conducted of the current GIS levels maintained by the Information

compliant metadata for GIS data, and exchange data to 	Management Unit.  Several data layers were reassigned due to staff changes.  The

PSMFC according to deadlines specified in this work 	FWP fisheries biologist responsibility layer was updated during the quarter and

statement.	distributed to Fisheries Division staff.

ODFW	1	Manage ODFW-NRIMP and StreamNet data, including 	Our GIS Analyst reviewed a handful of distribution records from StreamNet for bull

metadata development/maintenance, QA/QC activities, and 	trout and redband trout where overlaps or other issues needed to be addressed, and

work with regional staff as necessary to assure seamless 	worked with Regional StreamNet staff to clear these up.

loading of data into the regional database.

Objective	2	Task:	3	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 20 of 42

ODFW	2	Perform comprehensive QA/QC on all Oregon Trends, Age, 	Staff documented data compilation approaches/decisions related to maintenance of

Harvest, Dams, and Barrier datasets.	the trend and reference databases.  This will assist in the QA/QC process and

development of protocol documents by documenting existing guidelines that are

followed, as well as identify and spell out new guidelines that are needed.

Significant effort was spent this quarter ensuring the data quality of Oregon's existing Trend information.  Our Data Analyst also performed QA/QC on Oregon Hatchery Return Data, working with ODFW Propagation and Regional StreamNet staff to fix any issues with data already posted on the StreamNet site.

Updated spawner/recruit data were provided to Regional StreamNet this quarter to correct errors in existing trends.

ODFW	3	Coordinate and work with internal ODFW staff to improve 	The Distribution Update Protocol Document is VERY near completion as we were

the agency data collection efforts to allow more efficient 	able to resolve all the remaining issues in the draft version.  Simple reformatting

compiling into internal intermediate NRIMP-Oregon 	remains and also a redesign of the Procedures flow chart before we release it to the

StreamNet databases and/or StreamNet databases at the 	biologists and the public.

regional scale.

Region	2	Examine the StreamNet database for errors and report any 	Summaries of data in major StreamNet tables were presented to Steering Committee

found to the appropriate entity for correction.  Continue to 	members at their Fall meeting that identified issues about consistency of data

improve error-checking capabilities.	compiled in several of the tables, such as Age (due to differences in the way fish

aging is interpreted) and Hatchery Returns (due to incomplete migration by all

agencies from the data exchange format specifications replaced in 2003).

Region	3	Whenever new tabular data with a spatial component are 	The GIS Specialist worked with the regional database administrator to address

submitted to the Region (e.g., fish distribution, hatchery 	spatial referencing issues as they arose.   He worked to improve location coding

facilities, etc.), create regional GIS layers from this 	for non-stream point events, including hatchery and dam facilities.  A focused effort

information where possible.  Verify correct format, accuracy 	is underway to QC the referencing of hatchery facilities and document the workflow

and logical consistency of spatial data sets and attributes 	involved in updating this dataset for download and use in ArcIMS.

through coordination with state GIS contacts and then load

data to the regional database in coordination with the

database manager.  Post mappable layers to the online query

system, the ArcIMS interactive mapping system, and as

downloadable layers for StreamNet GIS users.

Region	4	Maintain a library of StreamNet GIS layers for internal use 	The regional GIS library was maintained and contact information was

and as downloadable data on the web site with complete 	updated for all posted metadata.  We plan to standardize the format of all

documentation (metadata).	metadata using ArcCatalog and provide metadata to the BPA in .xml

format for use in their GIS Portal

Region	5	Obtain and refine layers such as ESUs, ecoregions, or 	Spatial data related to Critical Habitat designation were obtained from

elevations, and create cross tables for use by the query 	NOAA Fisheries.

Objective	2	Task:	3	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 21 of 42

Region	7	Coordinate efforts by the StreamNet partners to maintain 	We continued cooperation with the state GIS specialists to maintain the

and update, as necessary, the 1:100,000 scale hydrography 	1:100,00 scale hydrography.  This included discussions with ODFW and

files for the states and the PNW region.	CDFG to reconcile differences between the PNW hydrography and the

"CalHydro" (1:100,000 scale routed hydrography) dataset developed by

CDFG.  This cooperation is important to ensure the proper functioning of

the on-line query system and the compatible evolution of the two datasets.

Region	8	Coordinate efforts by the StreamNet partners to create a 	Progress continues to accommodate 1:24,000 scale data from WDFW

hybrid 1:100,000 / 1:24,000 scale hydrography for the states 	through the development of a hybrid dataset.  WDFW is currently

and the PNW region.  Implement these changes at the 	preparing their hydrography for submission to the region and is working to

Regional office.	address border issues with ODFW and IDFG.  CDFG is currently testing the

use of high-resolution (1:24,000 scale) NHD in California and will share

their experiences.

Region	9	Integrate the functioning of the GIS system with the StreamNet	The existing cross reference tables were maintained.

fisheries and habitat database in support of the query system.

Maintain up-to-date cross tables used via the StreamNet web

interface to select information by geographic area.

Region	10	Update and append data as submitted by StreamNet participants.   	Major data submissions were processed from ODFW (including new data trends,

Maintain logs of data submissions and major database changes.  	almost 2,000 new escapement data records, and over 8,100 Hatchery Disposition

Manage logins and permissions.  Produce downloadable	data records), CRITFC (including a library data exchange, escapement and Age

versions of the StreamNet databases to keep in synch with the	data), IDFG (Hatchery, Hatchery Returns and Age data), MFWP (including

updated regional databases.  Create views and stored procedures	Hatchery and Reference table updates).  Location information was updated by

for use by the web query system and in the data loading process.  	WDFW and Hatchery information was updated by USFWS.  Hatchery Returns and

Routinely backup all databases.  Create and revise database	Age data were also submitted by USFWS, but processing was not completed during

structures and indexes.  Develop and run QA/QC processes	this project period.

on new and existing data tables to Isolate missing, erroneous

or duplicative data and work with source agencies to correct	Summaries of records in major StreamNet data tables by table, compiler and the last

problems.	project year each record was updated were developed.  Feedback from data

compilers showed an interest in having such summary information available on the StreamNet website, as long as it is organized by data category instead of data table (e.g. the EscData table includes data for seven data categories).

We removed dozens of outdated StreamNet tables and then removed or modified views & stored procedures related to the deleted tables.  New stored procedures were written that search all database tables for particular field values, or check for various inconsistencies or omissions in spatial cross-reference tables used by the StreamNet web query system.

Objective	2	Task:	3	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 22 of 42

Region	11	Assist the StreamNet Librarian to export the library 	A complete StreamNet Library dump was transmitted from CRITFC to the regional

reference database of StreamNet documents for routine 	StreamNet database.  This information was reconciled with the StreamNet Reference

inclusion in the StreamNet database for use by the web query 	table that associates each data record with the source of the information, and updates

and additions were processed.  In addition, the lengthy list of new Internet URLs that

became available with this edition of the Library database were verified and URLs

having broken or invalid links were reported to the StreamNet Librarian for

investigation and correction.  A few other minor problems, such as undesirable

embedded carriage returns in text fields were also reported to the Librarian.

WDFW	1	Manage data at the agency level, develop and maintain FGDC	No exchanges occurred this quarter due to the hatchery DEF no being finalized yet

compliant metadata for GIS data, and exchange data to 	and WDFW escapement data not matching StreamNet escapement data (ASNID and

PSMFC according to deadlines specified in this work 	NullFlag).  These two will be exchanged next quarter.

statement.

The Location Data Manager finalized the metadata drafted by the StreamNet GIS

Manager for the Lakes and Facility layer.

WDFW StreamNet staff reviewed the summary of data record counts by category provided by the StreamNet Regional Data Manager at the October Steering Committee meeting and provided him with a comment and a question to help clarify what was presented.

WDFW	2	Provide and update geo-reference field data as needed for all 	We submitted a file to the StreamNet Regional Data Manager that corrected about20

StreamNet data submissions.  Improved geo-references 	streams that were miscoded as lakes.

generally contribute to multiple Objective 1 data categories.

The Location Data Manager started researching the GPS readings collected by field

staff.  Currently many of the readings don't match the field note descriptions so there

is a lot of strange data to weed through.  This pilot effort would be aborted because

of the issues, except we have learned the location for data that has been troublesome

for a long time.  She will make a last attempt to school the field compilers to

research and resolve the readings themselves before we draw any conclusions about

this pilot effort.

WDFW	3	Create standardized storage formats and protocols for area 	Work was performed on a Bull Trout trap database for WDFW biologists Steve Gray

biologists to use with data collected at various fish collection 	and Jim Byrne.

facilities.

WDFW	5	Generate a MS Access table that contains links to GPS Index 	Steve Vanderploeg was hired to create a link between the GPS index area maps and

area maps, survey card database and master escapement 	the MS Access escapement database.  This has not been finalized yet due to other

database.	priorities.

Objective	2	Task:	3	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 23 of 42

Objective	2	Data management and delivery

Task	4	Data exchange standards

Establish and maintain data exchange standards to ensure consistent content and format of data that originate from multiple data sources.  Monitor adopted and proposed data exchange formats for data categories described under Objective 1.  This task will provide coordination and technical assistance regarding interpretation of database structures and codes.  The formal process for creating new and revising old DEFs may require significant amounts of time, potentially more than a year, for

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

IDFG	1	Work cooperatively through the Steering Committee, 	The IDFG/StreamNet coordinator worked with a StreamNet technical group to

following the DEF Process document, to revise existing and 	finalize the StreamNet hatchery returns data exchange format.

develop new DEFs to assure regional data consistency and

allow for inclusion of new data types.

ODFW	1	Monitor adopted and proposed data exchange formats and 	Staff communicated with Regional StreamNet and other StreamNet partners on

provide comments, feedback, and/or recommended changes as	issues related to the Hatchery Release, Hatchery Return, Fish Passage and Barrier

necessary. Work cooperatively through the Steering 	data DEFs during the quarter.

Committee, following the DEF Process document, to revise

existing and develop new DEFs to assure regional data 	Our GIS Analyst continued efforts to refine the DEF related to the Fish Barrier table.

consistency and allow for inclusion of new data types.  New 	Agreement was reached on nearly all outstanding issues related to the proposed

or modifications to existing DEFs will be submitted as 	fishway type categories.  The one remaining issue regarding culverts and fishways

warranted.	and how to best categorize them in the database will be posted to a fish passage

listserve for further discussion.

Staff attended a Hatchery Return DEF technical meeting in Vancouver in mid-November.  Representatives from Washington, Idaho, USFWS, and Regional StreamNet were also present.  The discussion centered on the current Hatchery Return DEF and proposed new ways to organize it to better facilitate each state's varying degrees of hatchery return information.

Region	1	Work cooperatively through the Steering Committee, 	Substantial progress was made this quarter toward updating data exchange formats.

following the DEF Process document, to revise existing and 	A new DEF is due for completion early in the second quarter of the fiscal year.  DEF

develop new DEFs to assure regional data consistency and 	updates completed or nearly completed this quarter include data structures and codes

allow for inclusion of new data types.  The regional Biologist 	for location coding, fish migration barriers and fishway types, and hatchery returns

will serve as the primary coordinator of the DEF process and 	and age.

is responsible for updating and publishing the official DEF

document.	Significant research was required for the barriers update.  The new DEF will also contain changes to the data structure for habitat restoration projects, and also changes resulting from a thorough comparison of the DEF to the existing SQL tables performed by the Regional Database Manager.

Objective	2	Task:	4	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 24 of 42

WDFW	1	Work cooperatively through the Steering Committee, 	Our new Olympia Data Compiler quickly reviewed StreamNet's newest barrier DEF

following the DEF Process document, to revise existing and 	proposal and joined in the DEF Forum discussion by posting a list of his comments.

develop new DEFs to assure regional data consistency and 	WDFW feels the Barriers DEF is essentially ready for testing with live data in the

allow for inclusion of new data types.	second quarter.

Late November, the Location Data Manager and Regional Data Manager started researching and discussing the Hatchery DEF issues.  A meeting was held to work out bugs and finalize the hatchery returns DEF for all parties involved.  This resolved the data hold-up and work continues.

Objective	2	Data management and delivery

Task	5	StreamNet Internet sites

Continue to maintain and enhance the StreamNet Internet sites.  Provide access to StreamNet data products through the Internet at both the regional and cooperating project levels.  The StreamNet home page (www.streamnet.org) will continue to be utilized as the project's primary data delivery vehicle.  Priority will be given to incorporating data developed through Objective 1 and providing access to reference materials secured through Objective 3.  The site will also be used to archive data sets developed by FWP participants for data that do not fit within the StreamNet DEF, including the means to index and search

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Provide ongoing review of the StreamNet website through 	Final design modifications were implemented to make Oregon subbasin planning

routine use of the site, providing feedback to StreamNet staff 	data available through StreamNet.

at PSMFC on any problems, errors or needed improvements.

ODFW	1	Monitor and provide feedback on existing and new StreamNet	Ongoing review of the StreamNet website took place throughout the quarter.

Internet features.

ODFW	2	Manage and maintain Oregon's web-based data integration, 	Staff reviewed the entire NRIMP website and fixed/updated broken links.

communication, and data transfer systems and their links to

StreamNet.	Incorporation of the Oregon.gov website design model into our web application

framework continued throughout the quarter.  A few websites we maintain were converted to this new format, including the Reference site.  Many of our sites, or components of them, will not be converted due to the incompatibility of the Oregon.gov design to online interactivity.

For the period of October through December 2004, our web server provided an average of 21,325 page views per month to an average of 2,624 unique IP addresses.  A summary of StreamNet related Oregon website usage is summarized in Table 1.  See Supplemental Information for a usage summary of other sites maintained by NRIMP.

Objective	2	Task:	5	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 25 of 42

Table 1.  Use (page views) of the Oregon StreamNet related websites during the first quarter, FY-2005.

|  | Oct. 04 | Nov. 04 | Dec. 04 |
| --- | --- | --- | --- |
| NRIMP (OR StreamNet) | 6,488 | 6,866 | 6,438 |
| CSMEP Web App. | 5,967 | 12,268 | 2,189 |

Region	1	Maintain and improve the StreamNet Internet site, including 	The StreamNet website was maintained and minor updates made.

correcting errors, adding or fixing links, improving

performance, improving looks and usability, etc.

Region	2	Guide development and enhancement of the StreamNet web 	Regional personnel learned some of the details regarding experimental design and

query system from the perspective of data users.  Review 	data analysis of data collected following an EMAP sampling scheme.  We realized

changes to the web query system to ensure they are 	that PSMFC personnel did not appreciate, and thus we do not make clear to our

implemented appropriately and do not create unforeseen 	users, how different time series data sets in the StreamNet database relate to each

problems.	other and are intended to be used as a unit.  Research into how to analyze and interpret EMAP-format data sets began this quarter and continues into the second quarter.  We intend to make available to StreamNet users the information they will need to fully understand how to construct full data sets and interpret the results.

Region	5	Maintain the GIS Data, Map, and PNW Reach File Internet pages.	All GIS related Web sites were maintained.

Region	6	Maintain, update as necessary, and improve the Internet 	A new Critical Habitat Interactive Mapper developed in cooperation with NOAA

mapping component to the StreamNet web site to allow users	Fisheries went on-line December 13 and the new layout has received positive

to access StreamNet data through interactive map interfaces.	feedback.  StreamNet's existing interactive mappers are being redesigned to employ

Improvements might include such items as adding DRGs or 	this new layout.   Tests are also underway to develop a more efficient and robust

aerial photos to the IMS applications, and showing trend 	ArcIMS viewer based on the Active X connector and active server pages.  The

locations in the web query system.	StreamNet Interactive Mappers are being monitored for site usage and performance

to enable improved reporting and site optimization.

Region	8	Deploy new query system components and data categories 	We deployed new report download file formats for all reports including XML,

that are approved by the Steering Committee	Microsoft Excel spreadsheets and an improved text file format.

Region	9	Maintain logs of web query history and error events.  Track 	Use of the primary StreamNet website remained strong, with an average of 7,672

and report Internet site usage by month and investigate web	unique non-PSMFC visits per month from an average of 4,425 unique IP addresses,

query system errors encountered.	an increase of 4.2% and ¼%, respectively, from the previous quarter (Table 2).  Use of the tabular online data query system averaged 12.7 visits per hour on a 24 hr day basis.  New software to track use of the ArcIMS interactive map sites was instituted this quarter, and total map page requests approached the number of page requests for the main website; more page views were required to build maps than run the tabular query system.  Top users of the web query system are listed in Table 3.

Objective	2	Task:	5	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 26 of 42

Table 2.  Summary of use statistics for the StreamNet website during the first quarter of FY-05.

|  | Oct.-04 | Nov. -04 | Dec.-04 |
| --- | --- | --- | --- |
| Main Web server |  |  |  |
| Total Page Requests, tabular | 68,330 | 69,562 | 62,884 |
| Number of Visits | 7,970 | 7,763 | 7,284 |
| Unique Visitors | 4,579 | 4,526 | 4,169 |
| Data Query Page Requests | 15,076 | 19,568 | 17,404 |
| Unique Query Sessions | 6,574 | 11,738 | 9,373 |
| Unique Query Sessions / hr. | 8.8 | 16.3 | 13.0 |
| Data Reports Viewed | 1,766 | 1,644 | 1,577 |
| FTP Files Downloaded | 1,359 | 1,637 | 911 |
| ArcIMS Map server |  |  |  |
| Total IMS Page Requests | 41,552 | 42,570 | 61,828 |
| Number of IMS Visits | 778 | 999 | 1193 |
| Unique IMS Visitors | 429 | 530 | 635 |
| Mean pages/visit | 53 | 43 | 52 |

Table 3.  Top users of the StreamNet website, first quarter FY-05.

| User | Pages |  | User | Pages |
| --- | --- | --- | --- | --- |
| Unresolved IP Address | 4,848 |  | ODoT | 568 |
| Private ISPs | 3,624 |  | USDA | 362 |
| Oregon State University | 3,554 |  | USFWS | 318 |
| Private Consultants | 3,238 |  | Nez Perce Tribe | 306 |
| ODFW | 3,040 |  | Idaho Power | 292 |
| BLM | 1,094 |  | U. Cal Santa Cruz | 294 |
| Cal Dept. Fish &Game | 9,12 |  | U.S. Army | 208 |
| NOAA | 666 |  | University of Idaho | 206 |

Region	10	Maintain and enhance the functionality, look and usability of	No substantive changes were made to the look or functionality of the web query

the StreamNet web-based query system.	system this quarter besides those mentioned already.

WDFW	1	Provide ongoing review of the StreamNet website through 	The Olympia Data Compiler loaded and tested the latest StreamNet Independent

routine use of the site, providing feedback to StreamNet staff 	Dataset software system (version 1.1.1).  Initial install issues arose involving

at PSMFC on any problems, errors or needed improvements.	user-level permissions, which were set below "administrator" on his machine.

Support staff with administrator privileges were able to successfully install this

new version.  Note that WDFW Windows 2000 users only rarely are granted

administrator level rights, so tools that are built for StreamNet compiler use

must be compatible with a reduced level of rights.

Objective	2	Task:	5	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 27 of 42

Objective	2	Data management and delivery

Task	6	Respond to data / information requests

Receive and respond to requests for data and information, source materials, and custom products at the regional and cooperating agency levels.  Response to requests will be honored within the limits of available resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.  Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural resource management activities.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Respond to requests for data, maps, technical assistance, 	Library data requests are reported under Objective 3.

source materials, or custom data products at the agency level,

within the capabilities provided by base funding.  Requests

will be logged and reported.

FWS	1	Respond to requests for information.	2004 Age and Return information has been sent to cooperating agencies.

IDFG	1	Respond to requests for data, maps, technical assistance, 	We continued filling data requests on a pace typical of past years, but because of an

source materials, or custom data products at the agency level,	especially heavy work load this quarter, we did not log those requests.

within the capabilities provided by base funding.  Requests

will be logged and reported in quarterly reports.

MFWP	1	Respond to requests for data, maps, technical assistance, 	Staff handled 15 Fisheries GIS requests this quarter.  The rating system conducted

source materials, or custom data products at the agency level,	in 1998 from MFISH data was recently used to develop rules for dredge mining in

within the capabilities provided by base funding.  Requests 	Montana.  We met with DEQ staff on several occasions to address draft policy.

will be logged and reported.

ODFW	1	Respond to requests for data, maps, technical assistance, 	Staff responded to 37 information requests during the quarter (Table 4).

source materials, or custom data products at the agency level,

within the capabilities provided by base funding.	Table 4.  Type and requesting organization information for help requests

serviced by Oregon StreamNet staff during the first quarter, FY-05.

| Request Type | No. |  | Requester | No. |
| --- | --- | --- | --- | --- |
| Analysis | 3 |  | Federal Agency | 4 |
| Data | 16 |  | University | 3 |
| Document | 2 |  | State (non-ODFW) | 3 |
| Map | 9 |  | ODFW | 20 |
| Other | 6 |  | Watershed Council | 1 |
| Tech. Support | 1 |  | Local County | 1 |
|  |  |  | Consultant | 4 |
|  |  |  | Private Citizen | 1 |
| Total | 37 |  | Total | 37 |

Objective	2	Task:	6	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 28 of 42

Region	1	Respond within one business day to requests for data, information	Staff responded to 21 information requests during the quarter (Table 5).

or help.  Log and report responses to all requests received.

Table 5.  Number and types of information and help requests serviced by Regional

staff during the first quarter, FY-05.

| Requester Type | No. |  | Type of Request | No. |
| --- | --- | --- | --- | --- |
| Environmental group Federal agency General public Local government Nonprofit organization Private consultant State agency Undergraduate student Total | 3 6 3 1 1 1 3 1 19 |  | Can't find data Complex request Data currency Data interpretation Error report GIS Other Query help Total | 2 1 2 1 4 7 1 1 19 |

WDFW	1	Respond to requests for data, maps, technical assistance, 	Twenty-nine data requests involving StreamNet-related data were filled this quarter

source materials, or custom data products at the agency level,	and were logged into the WDFW-StreamNet requests database.  GIS digital data

within the capabilities provided by base funding.  Requests 	(fish distribution, hydrology) were involved in nearly half of the requests, while

will be logged and reported.	maps and fish survey data comprise the rest.  Half of the users were WDFW staff,

with the rest evenly distributed between government entities (including tribes) and

private consultants.

Objective	3	Library and reference services

Provide professional library services to the Columbia Basin's fish and wildlife decision-makers, planners, managers, and researchers by acquiring and cataloging StreamNet source documents and other related material; and by providing open and efficient access to these materials.  Provide a repository for the source documents for the data contained in the StreamNet database.

Objective	3	Library and reference services

Task	1	Collection development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document data sources, Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies, interested parties, and other libraries.  Project participants will submit reference documents for all data contained in the StreamNet database.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Coordinate source material submissions for data compiled by 	Reference documents for data submissions were received from participants

participants.	and scheduled for cataloging.

Objective	3	Task:	1	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 29 of 42

CRITFC	2	Develop a collection of materials related to the Columbia Basin,	Using print outs from the Bonneville Power Administration's report query, we began

including reports from other Fish & Wildlife Program projects,	working on verifying that we have a complete collection of documents produced by

other agency documents as they relate to the Basin, and other	the BPA Environment, Fish and Wildlife Division.

published and unpublished materials as requested by clients.

CRITFC	3	Maintain and develop a collection of journals related to fisheries	We created a prioritized list of journals for renewal for 2005.

and aquatic sciences as well as other related scientific topics.

IDFG	1	Obtain reference documents for all data developed under 	We updated some hatchery return and age references in the regional database.

Objective 1 and submit them to the StreamNet Library for

inclusion in the collection and catalog.

MFWP	1	Obtain reference documents for all data developed under 	Work continued on this ongoing task.

Objective 1 and submit them to the StreamNet Library for

inclusion in the collection and catalog.

ODFW	1	Provide originals/copies of all documents and reports 	Staff spent time researching and correcting reference issues involving the

referenced in the compilation of new StreamNet data 	Observation and Barrier databases, along with a number of other reference issues

holdings, but not already housed in the StreamNet Library.	that need to be worked out, including identifying and addressing duplicate

references.

ODFW	2	Continue organization of ODFW Library documents and 	Organization of the ODFW Library was put on hold this quarter due to the Library

update the library bibliography with new titles as they are 	Technician position being vacant.

identified.

WDFW	1	Obtain reference documents for all data developed under 	Documents describing Hanford reach aerial fall Chinook counts and upper Columbia

Objective 1 and submit them to the StreamNet Library for 	River spawning ground counts were received from Grant County PUD.  The data

inclusion in the collection and catalog.	from these documents will be added to adult abundance datasets and exchanged next

quarter, accompanied by copies of these source documents.

Objective	3	Library and reference services

Task	2	Provide access to collection

Provide user access to the materials described in Task 3.1 by providing facilities for storage of paper and electronic copies of documents, an online catalog of all documents in the collection, and staff to answer location questions and respond to

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Provide and maintain appropriate facilities for the storage 	We began working on creating an appropriate atmosphere to preserve materials in

and public use of the StreamNet Library collections.	the library.  Currently, temperature and humidity are not monitored.  We are working to monitor both.  Temperature should be 68-70 degrees and humidity should be kept at 50-55 percent to preserve paper based materials.

Objective	3	Task:	2	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 30 of 42

CRITFC	2	Catalog and organize the materials for ease of use by clients 	A large number of documents were added to the collection during the quarter (we

and staff	will update with numbers when the catalog is accessible).

CRITFC	3	Provide access to the catalog of materials via the Internet 	The catalog was updated regularly.  A new server was received to publish the

and update the online catalog on at least a monthly basis.	catalog to the Internet.

CRITFC	4	Maintain and Implement a plan to place electronic 	We prioritized documents for electronic collections.  The librarian attended training

documents in the catalog and on the library website.	for copyright management and project development for digital collections.

CRITFC	5	Develop and keep a schedule of open times and reference 	Staff were scheduled and the reference desk was handled during posted hours.

desk staff hours

Objective	3	Library and reference services

Task	3	Library services

Manage the StreamNet Library and provide library services to the StreamNet user community, the Council's Fish and Wildlife Program, and the general public.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Provide information and reference services to library clients	Library usage remains stable.

CRITFC	2	Provide information about services and hours to library 	The Library webpage was updated regularly for holidays and open hours.  When

clients via print and Internet	necessary, signs were posted at the entrance to announce openings and closings.

CRITFC	3	Provide interlibrary borrowing services for library patrons to 	Information was not compiled due to holiday and vacation schedules.  This

access materials not yet owned by the StreamNet Library.	information will be included in the next quarter's report.

CRITFC	4	Provide access to hardcopy and electronic files of draft and 	We are looking at how to best serve these materials via the Internet and catalog.

final documents related to subbasin planning and the NPPC

amendment process.

CRITFC	5	Identify changes and new features that will improve delivery 	We are considering expanding hours to the weekend.  While there has not been an

library services	overwhelming demand for these hours, there has been some interest in being able to visit the library during non-business hours.  Opening for a few hours on Saturday or Sunday seems like a good response to this demand

Objective	3	Task:	3	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 31 of 42

Objective	3	Library and reference services

Task	4	Inter-library coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other collections that will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Provide interlibrary lending services for other libraries to 	The library provided nearly 100 items to other libraries.

access the library's unique collection.

CRITFC	2	Maintain memberships in appropriate library and subject-	We renewed memberships in professional organizations.  The librarian continues to

related associations, e.g., International Association of Aquatic	be a moderator for professional email lists as well as an officer in NRIC.

and Marine Science Libraries and Information Centers,

Natural Resources Information Council, Organization of Fish

and Wildlife Information Managers, and Pacific Northwest

Library Association

CRITFC	3	Provide consultations for groups and other agencies on 	We continued to work with the Johnson Creek Watershed Council on their

library organization and services	library.   A letter of agreement was requested by the Audubon Society to

house their collections.  The Audubon collection will be transferred to the

library in the next two to five years.

CRITFC	4	Coordinate with other StreamNet libraries, library clients and 	We continued to work with other libraries that have similar collections, primarily

other libraries to improve service to clients and limit 	through providing inter-library loan services to the region.

duplication of efforts

CRITFC	5	Work with subbasin planning groups and TRTs to identify 	No further work was accomplished in this area.  Subbasin planning activities were

modifications and new uses to make information related to 	substantially completed in FY04 and we do not anticipate significant activity under

these processes easier to retrieve.	this task in FY-05.

Objective	3	Task:	4	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 32 of 42

Objective	4	Services to the Fish and Wildlife Program

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife Program projects.

Objective	4	Services to the Fish and Wildlife Program

Task	1	Data and Data Services to Support the Fish and Wildlife Program

Provide data management assistance to the Fish and Wildlife Program, as requested.  Services may include custom development of data, provision of data from the StreamNet database to support FWP activities (such as planning, monitoring and evaluation, etc.), and general advice and technical assistance with database management, data delivery, and GIS.  Work under this task will have to be based on time available, particularly for larger requests.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

IDFG	2	Provide data inventory services to the Coordinated 	The IDFG/StreamNet coordinator trained two new data technicians to enter CSMEP

Systemwide Monitoring and Evaluation Project (CSMEP).	data inventory data into the newly developed CSMEP web application.  The data

technicians entered the Selway and South Fork Salmon pilot data into the web

application, and entered data inventory information from two new basins, the

Upper Salmon and Middle Fork Salmon.

ODFW	1	At the agency level, provide tabular and/or spatial data, 	We released the CSMEP database web application for official use on October15th,

technical advice/assistance and data services to Fish and 	and continued to manage and maintain the application, incorporating requested

Wildlife Program participants, as requested.  Support F&W 	changes as needed.  Also, we created a summary of the updates that have been made

Program activities, such as R, M & E, subbasin assessment, 	to the application as requested by one of the CSMEP biologists.

etc., within available time and budget under base level funding.

Our Data Technician entered all data records from the Imnaha and Lower Columbia pilot subbasins into the CSMEP web application, at the request of Oregon's CSMEP Biologist.  She also spent time on the harvest data, making it more complete and accurate.

Our Data Technician reviewed the Fifteenmile Subbasin plan looking at the status of focal species and for data sources, in response to Tom Iverson's (CBFWA) request for an at-a-glance approach to comparing species status across subbasins within the Columbia Basin.

Objective	4	Task:	1	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 33 of 42

Objective	4	Services to the Fish and Wildlife Program

Task	2	Participate in Fish and Wildlife Program Development Activities

Participate in planning, development and/or coordination meetings with regional entities to provide assistance in the area of data management, as requested, to support development of Fish and Wildlife Program projects and programs.  Provide input on ways StreamNet can effectively contribute to the programs and general advice about data management.  Participate in advisory groups, task forces, and other groups whose purpose is to enhance the effectiveness of the Fish and Wildlife Program relative to its data development activities.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Participate in various NPCC planning and management 	The Project Leader serves on the steering committees of the Pacific Northwest

work groups to improve and coordinate regional information 	Aquatic Monitoring Partnership and the Northwest Environmental Data-network

management programs.	and participates in the John Day Analytical Framework Group.  Data management

and sharing issues are regularly discussed in these groups.  We will be providing

revised John Day watershed assessment data and limiting factors data to the latter

group in the second quarter.

CRITFC	2	Develop strategies for ESA recovery planning and NWPPC 	Base level funds are not available for this task.

subbasin planning efforts to ensure data and technical

literature are captured and made regionally accessible. This

will be done "as possible"' under base level funding.

MFWP	1	At the agency level, work with regional entities to contribute 	We met with CBFWA staff during the Steering Committee meeting in Vancouver

data management expertise toward development of activities 	to discuss the use of subbasin plans and their content in upcoming regional efforts.

within the scope of the Fish and Wildlife Program.  Serve as a

data management resource to the FWP.

ODFW	1	At the agency level, work with regional entities to contribute 	Oregon StreamNet staff participated in regularly scheduled CSMEP meetings and

data management expertise toward development of activities 	conference calls throughout the quarter.

within the scope of the Fish and Wildlife Program.  Serve as a

data management resource to the FWP.	The Oregon StreamNet Project Leader participated in the joint PNAMP / NED

meeting  on December 7th, and the Joint PNAMP/CSMEP meeting on Dec. 15th.

Region	2	Continue participation on the Program Team for the 	The Program Manager continued participation in the NED program group.

Council's project to develop a Northwest Environmental 	Ultimately, regional scope data management approaches are being explored, but it

Data-network to convey recommendations based on 	is clear that under nearly any scenario, regional scale data management will be based

experience in the development of a regional approach to data	on existing data management efforts until significantly greater resources are brought

to the effort.

Region	3	Continue participation in the Pacific Northwest Aquatic 	The Program Manager continued serving on the PNAMP Steering Committee, and

Monitoring Partnership for watershed and fishery data 	also provided time of the Regional Fisheries Biologist to assist with database

coordination.  Participate in other R, M & E groups, 	development for project tracking to the PNAMP Effectiveness Monitoring group.

including the Action Agencies, Federal Caucus and CBFWA,

to provide support and data management expertise.

Objective	4	Task:	2	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 34 of 42

Region	4	Participate with CBFWA in support of data management 	The Program Manager continued participating with the CSMEP project.  StreamNet

efforts, including work with the Collaborative Systemwide 	has volunteered to provide two person-months of data technician help per state per

Monitoring and Evaluation Project.	year to assist the fish and wildlife agencies conduct data inventories.

Objective	4	Services to the Fish and Wildlife Program

Task	3	Support to Subbasin Planning

At the regional and cooperating agency levels, work with subbasin planners to provide needed information from the StreamNet database and to capture data developed as part of the subbasin planning process.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Continue to provide data and analytic support to Oregon 	The Project Leader is leading a group to update and revise the watershed assessment

subbasin planners as needed, and as base funding resources 	for the John Day subbasin.  These data will be added to the StreamNet website

allow.	when completed.

MFWP	1	Work with subbasin planners to determine type of data within	No assistance was necessary or requested during this quarter.

the Montana subbasin plans and opportunities for

incorporating those data into StreamNet.  Assist in providing

data on the FWP website.

Region	1	At the regional level, and within existing resources, work with	The Regional Fisheries Biologist worked with CRITFC personnel to archive and

subbasin planning groups to provide needed information 	make available the subbasin planning data and information for Oregon subbasins

from the StreamNet database.  Work with regional entities 	that CRITFC helped capture during the TOAST (Technical Outreach and Assistance

and subbasin planning groups to provide data management 	Team) effort.  CRITFC personnel modified the web page that StreamNet had

expertise and services related to capturing data developed 	previously created to help subbasin planners find data on the StreamNet website

during the subbasin planning process and making them readily	(http://www.streamnet.org/subbasin/2001-subbasin-data.html).  Originally this page

available.  Assist with archiving subbasin planning data, and 	contained links to materials provided by StreamNet for use by subbasin planners.

means of publicly distributing them, as requested.  This effort 	CRITFC added information and links about data and materials produced by the

will have to be scaled to fit within existing resources and 	subbasin planners.  The existing and new files were rearranged on the StreamNet

available time.	Internet site for clearer navigation.  Data from most Oregon subbasins is included in the archive, and we hope to eventually get data and other materials from all subbasins.  The Regional Fisheries Biologist met with Phil Roger (CRITFC), Peter Paquet (NPCC), and Chip McConnaha of Mobrand Biometrics to discuss strategies for capturing these data from all subbasins.

Objective	4	Task:	3	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 35 of 42

Objective	4	Services to the Fish and Wildlife Program

Task	4	Archive and deliver independent data sets, as requested

Work with participants to aid in the capture and distribution of data generated through Fish and Wildlife Program activities and to help determine the most appropriate means of storing and disseminating them.  Where data do not fit in existing StreamNet data sets, post data in the archive as independent data sets in their native formats.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	Continue efforts to capture and archive subbasin planning 	Oregon subbasin planning data were added to the StreamNet website in the first

data and literature, as base funding allows.	quarter.

MFWP	1	Work with FWP supported projects in the state to assist 	No assistance was necessary or requested during this quarter.

them with submission of their data sets to StreamNet for

archiving and dissemination as part of the formal DEF or as

Independent Data Sets.

Region	1	Coordinate with BPA and BPA contractors, StreamNet 	As of the end of the first quarter the ability to archive data sets on the StreamNet

cooperators, and others to capture data sets, reports, and 	Independent Data Sets page has not been advertised.  Early this quarter the Nez

other electronic materials for inclusion on the StreamNet 	Perce Soil & Water Conservation District (Nez Perce County, Idaho) found the

Independent Data Sets Internet page.  Post these items on 	independent data sets page and tool and submitted a stream temperature data set.

the Independent Data Sets page.	This was the first actual use of the data submission tool by an entity outside of

StreamNet, and data capture went fairly smoothly.  The submission, in addition to the temperature data, included a spreadsheet program that allows users to analyze and graph temperature data relative to water quality standards.  Unfortunately, the data file sent got corrupted in transfer.  The data that did come through were posted, and late in the quarter the NPSWCD submitted additional stream temperature data, which were added to the existing data set.

A review of the on-line Independent Data Sets page resulted in the discovery that the search function was not querying the correct set of fields.  Adjustments were made and the correct fields are being searched as of late November.

Region	2	Review StreamNet Links web pages.  For Internet sites that 	This task has not begun in earnest.  However, the data set for the pesticide ruling

provide on-line data, add the sites to the Independent Data 	was added to the Independent Data Sets page to make another area where users

Sets page.	can find this information.

Region	3	Solicit feedback on the use of the Independent Data Sets 	The Nez Perce Soil & Water Conservation District needed minor assistance for the

submission tool.  Make changes to the tool and IDS web page 	installation of the independent data sets tool.  A shortcoming of the computer

as appropriate.  Assist users with the IDS page and the IDS 	program is that it must be installed to a user's hard disk.  This can cause difficulties

submission tool.	for agencies that restrict privileges on users' computers.  After telling NPSWCD

of the need for administrative rights to install the software no other problems were

encountered in the installation.

Objective	4	Task:	4	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 36 of 42

A minor change to the program was needed this quarter due to a change in network security at PSMFC.  Passive FTP transfers became required, but the FTP object from Microsoft that was used in the Independent Data Sets tool cannot perform passive transfers.  An Internet search resulted in a free FTP ActiveX component from Chilkat Software that let this problem be overcome.  For long term planning we intend to follow different paths based on how extensively the Independent Data Sets archival function is used.  If extensive use is anticipated then the Programmer will create a better, web-based tool that does not require installation.  However, we wish to ensure that this effort will be worth it before committing his time to this task.  In the near term, we have begun creation of a spreadsheet to capture the information.  This will not be as fool-proof as a program designed for the task, but if use proves to be small this may be a better alternative than expending the limited time of the programmer.

Objective	4	Services to the Fish and Wildlife Program

Task	5	Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas dataset, b) archive the official version as a

historic record, c) in consultation with the Council, respond to requests for information concerning Protected Areas, and d)

modernize georeferencing and make these data available through online mapping.  If the Council so directs, work with

subbasin planners to record any desired changes to the protected status of individual streams.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

Region	1	Maintain the Protected Areas database.  Provide access to the	The Protected Areas database was maintained.

Protected Areas data through the online database and

through the interactive map application.  As time allows,

work to resolve the remaining unresolved location issues that

resulted from conversion of the data from the 1:250,000

scale to the 1:100,000 regional hydrography.

Objective	4	Task:	5	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 37 of 42

Objective	5	Project management and coordination

Provide effective leadership that ensures the production of high quality information products targeted at critical applications and the development of these products in a timely, cost-effective manner.

Objective	5	Project management and coordination

Task	1	Manage Project Activities

Administer all aspects of the StreamNet project at the regional and cooperating agency levels, including oversight of budget, personnel (including training and staff development), work statement preparation and implementation, coordination among participating agencies, active participation in steering committee work, and project reporting.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

All	1	Project oversight and guidance.  Participate cooperatively in 	The fall meeting of the Steering Committee was held Oct. 28-29, hosted by FWS

Cooperators	the StreamNet Steering Committee to guide the direction of 	at their new USFWS office in Vancouver, WA.  Topics included the CSMEP

the project, coordinate within respective agencies and resolve	project, the bull trout status review, consideration of a request for a means to provide

policy and technical issues for the project.	overview tracking of salmon status, handling EMAP format randomized data, and

potential data types for future work.  Internal issues discussed included unrolled hatchery release data, archiving changes in fish distribution and progress toward a 24K hydrography.  All cooperators prepared for and participated in the meeting.

All	2	Supervise project staff at the cooperator level to provide 	All cooperators except FWS performed routine supervisory functions during the

Cooperators	guidance and staff development	Quarter.   MT moved two positions to Helena to consolidate the personnel and activities associated with the Information Management Unit.  Lydia Bailey was promoted to the manager level in charge of GIS and Natural Resource data for the agency.  Adam Messer was hired to a redefined position emphasizing wildlife and data analysis.  Jeff Hutten will remain in Kalispell as the StreamNet western Montana representative, half time on StreamNet.  OR StreamNet staff in Corvallis attended Medic First aid/CPR training as required for all ODFW employees.  The hiring process for a new Library Technician and a Cartographer was initiated this quarter.  WA hired Greg Lippert as the new Olympia Data Compiler.  The Vancouver Data Manager and Data Compiler met to facilitate data flow and direct work.  The Location Data Manager directed the new compiler and established his initial work plan.  She also assisted interviewing for an internal Biological Data Systems compiler/programmer.

All	3	Manage expenditures to accomplish the jobs in the Statement	All cooperators exercised routine budget controls during the quarter.  Subcontractors

Cooperators	of Work within the approved budget.	were encouraged to ensure their agencies submitted final FY-04 invoices to PSMFC within the shortened timeframe required by BPA this year.  PSMFC submitted the final invoice billing to BPA.

Objective	5	Task:	1	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 38 of 42

Region	4	Develop the annual project proposal and budget within 	The draft FY05 project proposal was finalized and submitted to BPA this quarter.

submission deadlines.	This task included a full assessment of the inventory.  Regional personnel worked

with PSMFC administrative staff to straighten out the inventory listing so that future

inventories go more quickly.

All	5	Report accomplishment of the work outlined in the annual 	All cooperators developed and submitted input to the FY-04 fourth quarter

Cooperators	Statement of Work through quarterly progress reports	performance report.  In addition, the subcontractors began work on the FY-05 first

submitted to PSMFC within 20 days of the end of each	quarter performance report at the end of the quarter as a result of the impossibly

shortened report deadline in the new FY-05 contract with BPA.  WA submitted its

input to the first quarter report on the last day of the quarter.

Region	5	Report accomplishment of the work outlined in the annual 	The Fourth Quarter report for FY-04 was completed and submitted to BPA. Staff

Statement of Work through quarterly progress reports 	members began work on input to the FY-05 First Quarter report in order to meet the

submitted to BPA within 30 days of the end of each quarter.	impossibly shortened deadline for submission to BPA.

All	6	Submit the draft FY-04 annual progress report for the sub 	All cooperators provided input for the FY-04 Annual Report.  They also reviewed

Cooperators	project to PSMFC within 50 days of the end of the fiscal year,	and provided feedback on the draft report.

Region	6	Submit the FY-04 annual progress report to BPA within 60 	Input for the FY-04 Annual Report was received from the cooperators and a draft

days of the end of the fiscal year.	report was prepared and sent out for review and editing.  The Program Manager was

hampered in completing the report on time by a family medical emergency.  The

report will be submitted early in the second quarter.

Objective	5	Project management and coordination

Task	2	Coordinate with Related Activities Beyond the FWP

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities and agencies beyond the Council's Fish and Wildlife Program to identify means for collaborative data collection, storage, and dissemination.  Collaborative data activities will include tribal fishery programs within the Columbia Basin, federal land managers’ fishery programs, state fish and wildlife agencies, and, with respect to water use and stream development, state water resource management and environmental quality agencies. Collaboration with coast-wide and private data collection/compilation efforts will be pursued when this supports overall project goals.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

IDFG	1	On an opportunistic basis, coordinate with other state, 	The IDFG/StreamNet coordinator participated on the IDFG Standard Stream Survey

federal, or tribal agencies and various local inter-agency 	(SSS) committee.  This committee is responsible for developing a standard stream

planning and management work groups beyond the FWP to 	survey database and application to be used by all IDFG fish biologists that conduct

enhance the collection and management of data related to 	stream surveys.  Due to much of the work of IDFG/StreamNet to build a

management of fish and wildlife resources.	comprehensive fish information system, the SSS incorporated many StreamNet

standards and will be highly compatible with StreamNet.  The SSS should prove to be an effective, electronic source of information for StreamNet.

Objective	5	Task:	2	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 39 of 42

StreamNet staff worked with non-StreamNet staff to oversee the data compilation and preparation for the 2004 bull trout status review.  We worked with workshop participants to provide data proofing and updating, formatted data into final forms, produced queries for data analysis and helped write sections of the report.

MFWP	1	Coordinate with other state, federal, or tribal agencies and 	We worked with staff from the genetic labs at the University of Montana and

various local inter-agency planning and management work 	Montana State University on standardized genetic reporting.  A database front end

groups beyond the FWP to enhance the collection and 	using these standards was finalized this quarter.

management of data related to management of fish and

wildlife resources.

ODFW	1	On an opportunistic basis, coordinate with other state, 	We attended the User Workshops for the OWEB North Coast Prototype Web Portal

federal, or tribal agencies and various local inter-agency 	on Oct. 6th and Nov. 12th.  Our data management staff continued to work with

planning and management work groups beyond the FWP to 	North Coast Web Portal staff regarding the interoperability of their upcoming portal

enhance the collection and management of data related to 	system to the OPSW metadata site.

management of fish and wildlife resources.

Staff coordinated with ODFW's Fish Screen and Passage Program to craft a funding

proposal for the development of a statewide barrier restoration prioritization system.

Staff met with ODFW Propagation and Information Systems Division staff to discuss issues and potential redevelopment of ODFW's Hatchery Management Information System.

Our GIS Analyst attended the GIS Project Leaders meeting in Portland in early November and reported on ODFW GIS activities.  He also coordinated with staff from the Geospatial Enterprise Office in regards to fish passage barrier GIS data standards.

Our Data Analyst attended a Pacific Northwest Water Quality Data Exchange presentation in Salem to determine if any data was applicable to StreamNet.

WDFW	1	On an opportunistic basis, coordinate with other state, 	WDFW StreamNet GIS staff worked with Habitat Program staff and The Nature

federal, or tribal agencies and various local inter-agency 	Conservancy to construct a standard geospatial database for EDT reach data and

planning and management work groups beyond the FWP to 	analytical results for Washington state provinces of current interest to TNC.  WDFW

enhance the collection and management of data related to 	StreamNet staff were responsible for creation of EDT reach points in the Upper

management of fish and wildlife resources.	Columbia (WRIAs 45, 46, 48 and 49) and the Klickitat basin (WRIA 30).

Objective	5	Task:	2	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 40 of 42

Objective	5	Project management and coordination

Task	3	Professional and Public Involvement

As needed, produce public information materials and participate in various meetings and forums (public or professional) to

explain the project's capabilities and purpose and to generate support and additional data sources.  Activities may include

brochures, issue papers, demonstrations, posters and talks to public, policy or professional groups and organizations.

Project	Job	Planned work elements                                                                                        	Accomplishments, First Quarter 2005

CRITFC	1	As requested, prepare and deliver presentations to public, 	We reported to the North Pacific/International chapter of AFS on the tribal

scientific and professional meetings to demonstrate project 	perspectives on the Subbasin Planning and ESA Recovery Planning efforts.  The

capabilities, services and accomplishments and to solicit 	presentation described the success and problems of data management during these

additional data and involvement or coordination with the 	processes.

project.

MFWP	1	As requested, prepare and deliver presentations to public, 	The Manager attended the Fisheries Division Manager's meeting in September to

scientific and professional meetings to demonstrate project 	discuss various data management projects and the Montana Angler Forum to

capabilities, services and accomplishments and to solicit 	demonstrate the "Montana Fishing Guide", the recreational version of StreamNet

additional data and involvement or coordination with the 	data.

project.

ODFW	1	Produce public informational documents on StreamNet data 	Our Data Technician presented information on various fish runs, salmon life history,

activities for natural resource oriented publications, give oral 	Celilo Falls, what Lewis and Clark would have seen at the falls, and what that area

presentations to relevant user groups, and participate in 	of the Columbia is like now, at Outdoor School for the Corvallis School District.

various meetings and forums in support of project goals.

Region	1	Publish at least two editions of the StreamNet Newsletter 	Some additional preparations for a StreamNet newsletter were conducted this

during the fiscal year, providing readers with information 	quarter, but a newsletter was not sent.  We anticipate issuing the first newsletter

about StreamNet activities, available data, data updates, new 	for FY-05 in January.

data services, etc.

Supplemental Information

Work accomplished outside the specific work elements in the SOW

This section describes specific accomplishments during the first quarter that did not relate specifically to any of the Tasks / Work Elements in the annual Statement of Work.  These activities either were performed on StreamNet contract funding but related to topics that were not specifically covered by a task or job in the Statement of Work (SOW) or they were performed by staff of the various StreamNet projects but on other funding.  Work is often done by StreamNet staff on other funding because the StreamNet contract is not always sufficient to support all staff time.  Such work is reported here when it relates specifically to StreamNet objectives or is ultimately of benefit to the project.

Project		Accomplishments, First Quarter 2005

CRITFC  	Many of the activities reported above by the Project Leader were supported in part or in full by CRITFC or other funding sources.

Supplemental Information	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 41 of 42

MFWP		Discussions continued between FWP and the Montana Natural Heritage Program with respect to integrating that program into FWP.  Integrating data activities between the two agencies continues and determination of how NHP will fit into the Comprehensive Fish and Wildlife Plan (CFWP) is still under discussion.  IMU staff continued to provide information management services to the CFWP including refinement of the species, habitat and survey/inventory portions of the plan.  Considerable time has been devoted to developing a new agency level approach to information services requests.  The electronic request tracker continued to refined and its use required by FWP staff; the first round of large requests were reviewed by a joint IMU/IT Bureau group, recommendations were made to the Information Services Steering Committee and work will now begin on these 40 larger requests.

ODFW		We continued to provide data management, access, dissemination, and web development support to ODFW's Marine Resources Program (MRP).  Specifically, we are designing and developing a website to provide fishery quota status information to the public.  We are also web enabling MRP's nearshore projection application.

Staff continued to support the Oregon Plan Review (Metadata Warehouse) site and provide technical support to numerous users of the site.  We also ramped up our support of the Oregon Plan Assessment via data compilation of Oregon Watershed Council datasets, data management, database and web site development.

Oregon StreamNet staff support of the Statewide Wildlife Conservation Strategy continued throughout the quarter, mainly focused on providing GIS and analytical support.

Web use statistics for the various web sites maintained by or related to Oregon StreamNet are provided in Table 6.

Table 6.  Page views recorded in the first quarter, FY-05 for the web pages maintained by or related to Oregon StreamNet.

|  | Oct. -04 | Nov. -04 | Dec. -04 | Distinct IP’s (monthly mean) |
| --- | --- | --- | --- | --- |
| Oregon Plan Metadata Warehouse | 278 | 191 | 1644 | 19 |
| Or. Plan Review | 417 | 281 | 840 | 18 |
| Oregon Fish Finder | 2534 | 2398 | 1959 | 327 |
| Marine Resources Program | 54 | 25 | 4018 | 11 |
| Fish Screening and Passage | 84 | 12 | 206 | 4 |

Region		The GIS Specialist completed and published the Critical Habitat Interactive Mapper in cooperation with NOAA Fisheries.  This new application went on-line December 13, 2004 and includes links to spatial data and metadata for download from StreamNet and NOAA Fisheries.  Improved base data layers were acquired and the improved layout and functionality are being used to update the other existing StreamNet IMS applications.

WDFW		Vancouver StreamNet staff finished reviewing all the data and making appropriate corrections to dataset inventory work being performed for CSMEP.   A total of 303 inventory records were entered into the CSMEP web application, with each one being reviewed for accuracy.  A CSMEP planning session for Upper Columbia basins (Methow, Okanogan) was held on December 8 in Wenatchee.  The WDFW StreamNet Lead built a list of data contacts from multiple agencies in the area and sent out information packets and invitations to share their expertise on any relevant M&E datasets.  These activities were performed on funding outside the StreamNet contract.

WDFW filled a vacant programmer/database manager position in the Biological Data Systems (BDS) Unit (which houses WDFW StreamNet) to regain full-time support for statewide spawning ground survey data, age data, and escapement data.  While this person will work out of Headquarters in Olympia, we foresee over time that this extra support will help reduce some of the workload on our Vancouver StreamNet staff, allowing them to expand their data compiling into other needed data categories.

Supplemental Information	StreamNet First Quarter Performance Report, Fiscal Year 2005	Page 42 of 42