DRAFT

StreamNet FY 1998 Work Plan

Oregon Department of Fish and Wildlife

Product deliverables by ODFW are as follows.  Objective and task numbers correspond to the umbrella work statement (Attachment I).  Tasks are not referenced where no deliverables are expected to be completed by ODFW in FY98.

Objective 1 	Data Acquisition:

Task 1.1.	Prepare and maintain standardized data on anadromous fish.

a) 	Ocean range and distribution

Tabular data:  Ocean distribution patterns from CWT and landings data. (by stock and recovery zone for all Pacific Salmon Commission index stocks from the Columbia basin).

b) 	Freshwater distribution, life history, and barriers

GIS data: Chum salmon distribution in OR (presence by type & reach).

c) 	Adult abundance

Tabular data:  Abundance and indices (escapement, redd counts, trap counts, etc.) for OR populations. (updated for 1997 surveys).

Tabular data:  Hatchery-wild fractions in OR portions of the Columbia basin.  (Annual for spring chinook and fall chinook).

e) 	Harvest (ocean, in-river, terminal)

Tabular data:  Tributary sport harvest from angler harvest cards (update for 1996, OR statewide).

f) 	Natural production (survival, etc.)

Tabular data:  Spawner-recruit numbers (updated for spring chinook surveys in 1997, available time series for fall chinook and coho returns).

g) 	Hatchery production

Tabular data:  Returns to ODFW facilities (updated for 1996 and part of 97 returns).

Tabular data:  Historic releases, returns, and return rates (pre-1980 time series by facility, basin, and species/run).

Tabular data:  Exploitation, return, and maturation rates from cohort analyses of CWT and PIT groups (incorporate where available from other sources).

h) 	Age

Tabular data:  Age frequency (updated for natural spring chinook in 1997, available time series for natural steelhead in OR portion of Columbia basin).

i)	Genetic origin, production type, stock, and population identification)

Tabular data:  List of ODFW gene conservation groups by subbasin.

j) 	Historic and potential range.

GIS data:  Historic OR distribution of spring chinook, fall chinook, and coho salmon (spawning areas by reach in OR portions of Columbia basin circa 1950)

Task 1.2.	Prepare and maintain standardized data on resident fish and other aquatic species.

a)	Distribution for native salmonids, sensitive fish and  aquatic vertebrate and invertebrate species, and key competitor/predator species.

Tabular data:  Bull trout distribution in OR (presence by type & reach).

GIS data: Rainbow/redband trout distribution in the Hood and Malhuer River basins (presence by type & reach).

GIS data: Cutthroat trout distribution in OR (presence by type & reach).

GIS data: Sensitive fish species occurrence (point observations statewide as available such as Oregon Chub).

b) 	Hatchery production

Tabular Data: Trout releases (1997 by sp., location, facility).

Tabular Data: Trout releases (Pre-1980 by yr., sp., location, facility).

Task 1.3.	Prepare and maintain fish and aquatic habitat data.

a) stream habitat data.

GIS data: ODFW aquatic inventory surveys sites and data for 1995 and 1996.

c) critical habitat designations.

GIS data:  Update key stream management area designations for OR including FEMAT key watersheds, AFS aquatic diversity areas, ODFW coho source river reaches, ODSL essential salmon habitat.

Task 1.4.	Prepare and maintain facilities data affecting fish and aquatic habitat.

c) Man-made blockages and facilities data.

GIS data:  Update the locations of blockages and incorporate fishways data from ORIS that affect anadromous species in OR.

GIS data:  Point coverage of all ODFW fixed stations.

Tabular data:  Summary descriptions for all OR hatchery facilities including LLid-IBM Code cross-reference.

Task 1.5.	Prepare and maintain data related to tracking aquatic mitigation and restoration projects.

c)  Compile state project tracking data.

Tabular data:  Compile tracking data for ODFW mitigation and restoration projects in the Columbia basin.

Task 1.6.	Document data sources, collect documents, and provide to StreamNet library.

Documents:  Originals/copies of all referenced in Objective 1 datasets and reports but not already included in the StreamNet/CRITFC library.

Objective 2	Data Management:

Task 2.1	Design, develop, and maintain codes and data exchange formats and provide technical assistance for state agency data activities.

Data Management Activities:  Provide or contribute input to new and existing data exchange formats.

Task 2.3	Provide state-level database management and administration.

Data Management Activities:  Maintain state-level StreamNet data sets.

Data Management Activities:  Engage in activities that enhance StreamNet database structure and capabilities.

Task 2.4	Designate and maintain metadata format.

Spatial data:  Participate in metadata format development processes.

Objective 3	Library/Referencing System:

Task 3.1	Continue to develop a collection of appropriate materials.

Documents: Update the set of historic Oregon Fish Commission and Game Commission reports to StreamNet library as available.

Tabular data: Bibliography of ODFW, Fish Commission, and Game Commission reports (updated for 1997 publications by ODFW).

Photographic data:  Identify needs and provide photo library on CD’s.

Services:  Forward external (non-ODFW) service requests to the StreamNet Library or respond to external service requests according to the cooperative work agreement with the StreamNet Library.

Objective 4	River Reach System / Hydrologic Referencing:

Task 4.4	Maintain the 100K river reach system, including making corrections per the FY-97 white paper.

List:  Corrections to 100K stream coverage as identified during other data compilation activities.

Objective 5	Data Delivery / Information Systems:

Task 5.1	Receive and respond to requests for data, source materials, and custom products.

Services:  As requested and consistent with other deliverables under this contract.

Task 5.5	Provide training for state-level users of the StreamNet data delivery systems.

Services:  As requested, provide training and instruction on the use of the StreamNet website data delivery system.

Task 5.7	Prepare map products depicting fish distribution.

Data report:  Atlas of spawning and rearing distribution for fall chinook in Oregon  (color maps by HUC with summary of methods and sources - includes barriers, survey sites, & key production areas where available).

Task 5.8	Prepare topical reports that describe content, compilation methods, and sources of large datasets.

Data report:  Review of historic salmon and steelhead sport catch statistics for Oregon (summary of methods, sources, and data)

Data report: Spawner-recruit data for fall chinook populations in ID, OR, and WA. (summary of methods, sources, and data)

Objective 6	Project Management / Coordination:

Task 6.1	Administer all aspects of project coordination.

Coordination activities:  Oversee and monitor personnel, budget, and other project activities.

Statement of work and budget for ODFW.

Task 6.2	Essential coordination meetings.

Attend steering committee meetings (4).

Task 6.3	Project administrative reports.

a)	Contribute Oregon portion of the Quarterly report.

b)	Contribute Oregon portion of the Annual report for products completed in FY-97.

Task 6.4	Public information materials.

Written comments upon review of submitted and/or selected materials.

Task 6.5	Conference participation.

Copies of conference agendas, proceedings, and presentations.

Task 6.7	Participate in Fish and Wildlife Program advisory groups and applicable regional policy, planning, and management forums.

Written summary of activities in quarterly progress reports.

Task 6.8	Update the StreamNet data and strategic plans.

Written comments upon review of draft plans.

StreamNet FY 1998 Budget - Oregon Department of Fish and Wildlife

NOTE:  This budget reflects an 9% reduction from FY-97 when the training costs (which were left out in FY-97) and salary increases are factored out.

| StreamNet budget (FY-98) |
| --- |
| (Oct. 97 - Sept. 98) |
| A. PERSONNEL |
|  | Months | Rate | Total |
| 1. NRS-3 | TBA | 4 | $3,010 | 12,040 |
| 2. NRS-3 | Forsberg | 12 | $3,472 | 41,664 |
| 3. NRS-3 (Proj. Coor.) | Cooney | 12 | $3,155 | 37,860 |
| 4. NRS 1 | Tinus | 6 | $2,487 | 14,922 |
| 5. EBA 1 | Bourne ** | 10 | $1,790 | 17,900 |
| 6. NRS-2 | Hupperts | 12 | $2,374 | 28,488 |
|  | * | 7. Clerical | Smith | 0 | $2,587 | 0 |
| * | 8. NRS-3 | Hill | 0 | $3,309 | 0 |
|  | Total Salary |
| 152,874 |
| Fringe Benefits @ | 41% |  |
| 62,678 |
| Total Personnel |
| 215,552 |
| Salary increases during FY-98 | 3.75% |
| 223,636 |
| B. TRAVEL |
|  | Airfare - Steering Meet. |
| 3 trips | $500 | 1,500 |
| PerDiem/Lodging |
| 30 days | $60 | 1,800 |
| Mileage |
| 6000 miles | $0.25 | 1,500 |
| Vehicle Rent |
| 3 months | $200 | 600 |
| Total Travel |
|  | 5,400 |
| C. SERVICES AND SUPPLIES |
|  | Office Supplies |
| 2,700 |
| Software misc |
| 2,000 |
| Training |
| 1,000 |
|  | * | GIS license annual fee |
| 0 |
| * | Corvallis GIS lic. fee |
| 0 |
|  | Computer maintenance |
| 1,000 |
| Telephone |
| 12 months | $200 | 2,400 |
| Fax Machine |
| 9 months | $80 | 720 |
| Copy Machine |
| 9 months | $250 | 2,250 |
| Duplication Charges |
| 3,000 |
| Total Services and Supplies |
|  | 15,070 |
| D. NONEXPENDABLE EQUIPMENT |
| * | New Computer |
| 0 |
|  | Total equipment |
| 0 |
|  | E. DIRECT COST |
| 244,106 |
| F. INDIRECT COST |
| 0.229 | of A through C |
|  | 55,900 |
| G. TOTAL COST |
| 300,006 |
|  | FY-97 Budget total = | $325,094 |
|  | Estimated FY 97 carryover = $0 |

*  Denotes FY-98 costs paid in FY-97 using carryover.

** 2 months of Gloria's time paid by ODFW in FY 98. 1 month was paid by ODFW in Fy-97 which contributed to the FY 97 carryover

Staff Time Allocations

|  | Name |
| --- | --- |

Obj. 1

(Data Acq.)

Obj. 2

(Data Mgmt)

Obj. 3

| (Library) | Obj.4 (RRF/Hyd) |
| --- | --- |

Obj. 5

(Data Deliv)

Obj. 6

| (Mgt/Coor) | Total Months |
| --- | --- |
|  | FWB3 - TBA | 2.5 | 0.5 |
|  | 1.0 |
| 4 |
| Brent Forsberg | 5.4 | 1.0 |
| 0.6 | 5.0 |
| 12 |
| Cedric Cooney | 6.0 | 0.5 | 0.5 |
| 3.0 | 2.0 | 12 |
| Eric Tinus | 4.0 | 0.5 |
|  | 1.5 |
| 6 |
| Keith Hupperts | 7.0 | 1.4 |
| 2.4 | 1.2 |
| 12 |
| Gloria Bourne | 3.0 |
| 1.2 |
| 5.8 |
| 10 |
| Clerical |
|  | 1.0 | 2.0 | 3 |
| Milt Hill | 0.5 | 0.1 |
|  | 0.9 |
| 1.5 |
|  | TOTALS: | 47% | 7% | 3% | 5% | 32% | 7% | 60.5 |