StreamNet Project

FY 2001 Work Statement

And

FY 2001 Budget Request

November 17, 2000 (Budget Revised)

# The purpose of the StreamNet project is to compile, manage and distribute information related to the fish, and

secondarily wildlife, resources in the Columbia River basin, with additional information available for the Pacific

Northwest.  The project utilizes the Internet as its primary means of data distribution, but also provides custom data

services.  The StreamNet web site provides access to its queriable database, maps and library references.

StreamNet is a multi-agency project authorized by the Northwest Power Planning Council’s Fish and Wildlife Program.

The project is funded primarily by the Bonneville Power Administration as part of its program to protect, mitigate,

and enhance fish and wildlife affected by the development and operation of hydroelectric facilities on the Columbia

River and its tributaries.  Other funding in the past has been obtained from agencies include the Environmental

Protection Agency (EPA) and the National Marine Fisheries Service (NMFS).  The Pacific States Marine Fisheries

Commission (PSMFC) administers the StreamNet project.  The project includes project participants in four state fish

and wildlife agencies, two tribal agencies and the US Fish and Wildlife Service.  Federal, state and tribal fish and

wildlife agencies collect, manage and distribute data related to the region’s fish and wildlife resources.  A subset of

these data are compiled into standard formats and publicly distributed by the StreamNet project.

Each year StreamNet develops a project-wide Work Statement.  Not all tasks identified in the Work Statement apply

to all participating agencies.  Each participating agency contributes work to a sub set of the project tasks, with their

responsibilities detailed individually for each task.  The intent of this format is to provide clarity concerning the total

activities addressing each project task and the role of each project participant.  This combined Statement of Work

covers Federal Fiscal Year 2001, from October 1, 2000 through September 30, 2001.

Objective	1	Data Development

Increase the knowledge base concerning the region’s fish and wildlife resources through the

acquisition of new information that responds to emerging needs as well as the updating and

enhancement of production and survival trends and other existing information.

Objective	1	Data Development

Task	1	Anadromous Fish

Acquire data sets related to salmon, steelhead and, where data are readily available, other anadromous fish populations from the

multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent

formats for the following categories:

Objective	1	Data Development	Task   1        Anadromous Fish

Task	1.a	Distribution, Life History (use type), and Barriers

Document the occurrence, distribution and habitat use of anadromous species, related barriers to migration, and life history

characteristics

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Identify and update missing data in anadromous barrier data.	Updated 	Database	Brown

periodically

ODFW	1	Update, maintain, correct and exchange anadromous fish distribution 	As needed	Updated event data	Bowers	Particular effort will focus on NE Oregon

information (DistUse and DistPresence tables).	basins but any new information will be

submitted as it becomes available.

ODFW	2	Update, maintain, correct and exchange barrier information.	As needed	Updated Barrier 	Brodeur

database

ODFW	3	Modify / refine the automated approach to populating the FishBarrier 	As needed	Updated 	Bowers

table (as needed) and rectify any new anadromous distribution 	FishBarrier table

information with the barriers database.

ODFW	4	Design and develop a database to capture carcass placement data.	6/30/01	Database	Database 	This will be a lower priority item unless Basin

Manager	 needs dictate otherwise.

ODFW	5	Update (and modify if needed) the Fish Presence Survey database 	As data are 	Updated Database	Database 	Modifications will be necessary as the

which helps populate the DistPresence table.	submitted 	Manager	database is used in the field

from field staff.

ODFW	6	Update (and modify if needed) the Incidental Fish Observation 	As data are 	Updated Database	Data Assistant	Modifications will be necessary as the

database, which captures incidental species observations not 	submitted 	database is used in the field

routinely reported in agency documents, which helps populate the 	from field staff.

DistPresence table.

ODFW	7	Identify appropriate documents/references for anadromous fish 	Ongoing	Updated table.	Data Assistant, 	This will be done opportunistically during

distribution data in order to populate the DistPresence table.	Bourne	conduct of other tasks.

ODFW	8	Update, maintain, correct and exchange photographic information 	Ongoing	Updated table.	Brodeur, Data

(MapCat and related tables).	Assistant

Objective:	1	Task:	1.a	10/01/00	Page 2 of 41

ODFW	9	Populate the genetic origin and production origin fields in StreamNet 	7/31/01	Event data	Bowers	Only when and if ODFW agrees on criteria for

distribution exchange format for all anadromous fish distribution data 	making designations and criteria agree w/

in the Columbia basin.	StreamNet DEF formats.

Region	1	Compile distribution updates (tabular events) as they arrive.  Create 	Ongoing	GIS coverages	Graves

anadromous fish distribution GIS coverages from these event tables,

and post the shape files to the StreamNet website as downloadable

GIS coverages.

Region	2	Compile barriers data from the states and maintain a GIS coverage of 	Ongoing	GIS data coverages	Graves

barriers data on the StreamNet web site.

Region	3	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	staff

and submission of data.

WDFW	1	Review barriers in the anadromous fish distribution layer, based on 	As needed	Updated regional 	Hudson, Burns

SSHIAP information and indicators in the Stream Catalog. Update and

exchange the data with the regional database.

Objective	1	Data Development	Task   1        Anadromous Fish

Task	1.b	Adult Abundance

Escapement, redd counts, trap counts, dam counts, hatchery returns

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

FWS	1	Compile FWS hatchery return data for FWS hatcheries	Ongoing	Compiled data	Pastor

FWS	2	Submit data updated through 2000 to PSMFC	9/30/01	Updated database	Pastor

IDFG	1	Compile 2000-field season redd count data and 2000 field season 	6/30/01	Database	Elms-Cockrum

hatchery return data and submit to the regional database.

ODFW	1	Update existing abundance and index trends (escapement, redd counts,	1/30/01, 	Updated database	Hurn

trap counts, peak/other spawning counts, etc.) for anadromous species	4/30/01,

through 1999 and modify as needed to adhere to the 2000.2 Data 	7/31/01,

Exchange Format.  Four data submissions are planned.	&9/20/01

ODFW	2	Compile data on returns to ODFW hatchery facilities (updated for 	7/31/01	Updated db	Database 	Will be done if SN adopts an exchange format.

1997, 1998,  and part of 1999 returns).	Manager

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	staff

and submission of data.

SBT	1	Update adult abundance data gathered by SBT personnel through 	10/15/00	Updated db	Taki

2000 and provide to IDFG.

WDFW	1	Update and exchange hatchery returns through 1999 in StreamNet 	7/1/01	Updated regional 	Woodard

data exchange format.

WDFW	2	Update and exchange natural spawner data (returns and/or redd 	7/1/01	Updated regional 	Woodard

counts) through 1999 for available species (CR, PS)

Objective:	1	Task:	1.b	10/01/00	Page 3 of 41

Objective	1	Data Development				Task    1        Anadromous Fish

Task	1.c	Juvenile Data

Sample records, abundance indices (as available)

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Finalize the incorporation of the IDFG General Parr Monitoring 	3/30/01	Database	Murdock

(juvenile) data into StreamNet.

ODFW	1	Prepare and submit recommended modifications of the draft Juvenile 	6/30/01	DEF proposal	Cooney

abundance portion of the DEF.

ODFW	2	Update Oregon's 10 existing juvenile abundance records to approved 	9/20/01	Updated records	Hurn	Will be done if SN adopts an exchange format.

DEF standards.

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	staff

and submission of data.

SBT	1	Update to IDFG juvenile data gathered by SBT personnel.	10/15/00	Updated db	Taki

Objective	1	Data Development	Task   1        Anadromous Fish

Task	1.d	Harvest

In-river, terminal, and other harvest, as available

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

ODFW	1	Provide remaining 1997 & statewide 1998 tributary sport harvest 	9/20/01	Updated sport 	Frazier

from angler harvest cards.	harvest

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	staff

and submission of data.

WDFW	1	Update and exchange salmon harvest data through 1999, beginning 	9/1/01	Updated db	Woodard

with Columbia River commercial, sport and treaty harvest.

WDFW	2	Update and exchange steelhead harvest through 1998.	5/1/01	Updated db	Sikora

Objective:	1	Task:	1.d	10/01/00	Page 4 of 41

Objective	1	Data Development	Task   1        Anadromous Fish

Task	1.e	Hatchery Production

Releases and disposition

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

FWS	1	Compile FWS hatchery release data, w/ added CWT information	Ongoing	Compiled data	Pastor

FWS	2	Transform data to format 032	1/31/01	Transformed data	Pastor

FWS	3	Submit 2000 data to PSMFC via USFWS WWFRO	1/31/01	PSCrel00.dbf	Pastor

IDFG	1	Compile 2000-field season hatchery returns data.	6/30/01	Database	Elms-Cockrum

ODFW	1	Develop the ability to remotely access the Portland mainframe 	5/31/01	Remote access	Database

hatchery database and download hatchery return data consistent with 	Manager

the StreamNet contract.

ODFW	2	Compile egg-take data into StreamNet format and submit to PSMFC.	7/31/01	Updated db	Database 	Will be done if SN adopts an exchange format.

Manager

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Updated db	staff

and submission of data.

Region	2	Develop a new data import procedure to upload data from the revised 	3/30/01	Updated db	Kinney	Will try to do this sooner

RMIS data structure and incorporate backlogged production data into

the StreamNet database

Region	3	Acquire hatchery production data through 2000 from the RMIS 	7/15/01	Updated db	Kinney

database and incorporate into the StreamNet on-line database.

SBT	1	Update SBT anadromous release information and provide to the IDFG.	uncertain	Updated db	Taki

WDFW	1	Update and exchange juvenile release data to PSMFC through 2000.	6/1/01	Updated regional 	Sikora

WDFW	2	Explore providing "unrolled" release data directly to StreamNet.	uncertain	Decision on use of 	O'Connor	Unrolled data is reported by individual

unrolled data	release Rolled data often cannot be assigned

to a single location code (LLID).

Objective	1	Data Development	Task   1        Anadromous Fish

Task	1.f	Natural Production

Survival, production factors, spawner recruit

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Coordinate with IDFG personnel to determine the feasibility of 	12/30/00	Summarized in 	Butterfield

incorporating survival/recruitment data.	progress reports

ODFW	1	Compile hatchery-wild fractions in OR portions of the Columbia basin	9/20/01	Updated database	Frazier

for spring chinook and fall chinook.

Objective:	1	Task:	1.f	10/01/00	Page 5 of 41

ODFW	2	Compile spawner-recruit data (updated for spring chinook surveys in 	9/20/01	Updated database	Frazier

1998 and 1999, and available time series for fall chinook and coho

returns)

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

Objective	1	Data Development	Task   1        Anadromous Fish

Task	1.g	Age

Age/sex composition for returning adults

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

FWS	1	Update age and sex data through 2000	6/29/01	Updated db	Pastor

IDFG	1	Compile 2000-field season age and sex composition data.	6/30/01	Database	Elms-Cockrum

ODFW	1	Compile age frequency data (updated for natural spring chinook in 	4/30/01	Updated age data	Frazier

1998, available time series for natural steelhead in OR portion of

Columbia basin).

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	staff

and submission of data.

WDFW	1	Provide age/sex data associated with exchanged CRB natural returns 	8/1/01	Updated db	Woodard

data.

Objective	1	Data Development	Task   1        Anadromous Fish

Task	1.h	Genetics

Areas where genetics data exists and the sources of these data

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Develop, with SC input, standardized database format and DEF for 	3/01/01	DEF for allozyme 	Forrest

existing regional genetic data	data

CRITFC	2	Provide allozyme and genetic data developed by CRITFC in standard 	4/01/01	Database	Forrest

format

IDFG	1	Participate in decisions regarding genetic data	12/31/00	Decision	Butterfield

ODFW	1	Participate in decisions regarding genetic data	12/31/00	Decision	Cooney

Region	1	Request that the Steering Committee  decide whether genetics data are 	10/27/00	Decision	Schmidt

available and needed in the StreamNet database

Region	2	If approved, draft and submit a DEF proposal to Steering Committee.	TBD	DEF	Banach

WDFW	1	Participate in decisions regarding genetic data	12/31/00	Decision	O'Connor

Objective:	1	Task:	1.h	10/01/00	Page 6 of 41

Objective	1	Data Development	Task   1        Anadromous Fish

Task	1.i	Populations

Population delineation, as determined by others

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

ODFW	1	Produce a cross-reference table of ODFW designated Gene 	7/31/01	Table	Cooney	This task will only be done if subbasin

Conservation Groups (GCG) by subbasin.	delineations are modified to line up with

ODFW GCGs.

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

WDFW	1	Compile and exchange updated Washington SaSI stock status data for 	3/1/01	Updated regional 	Burns, O'Connor	The Salmonid Stock Inventory for WA assigns

anadromous fish using newly developed 2000.1 Data Exchange 	 wild salmonids to stocks and rates the health

Format (see Task 2.3).	of each

Objective	1	Data Development	Task   1        Anadromous Fish

Task	1.j	Historic Range

As available at the watershed-level.  Compilation at the reach level is an option if these data are available

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

ODFW	1	Work with the Steering Committee to define the term "historic" in the 	11/30/00	Definition	Cooney

DEF.

Objective:	1	Task:    1j	10/01/00	Page 7 of 41

Objective	1	Data Development

Task	2	Resident Fish and Other Aquatic Species

Acquire data sets related to resident fish species, and where specifically identified other aquatic species, from the multiple agencies,

tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   2        Resident Fish and Other Aquatic Species

Task	2.a	Distribution and Life History

Document species occurrence and distribution and life history characteristics

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Add additional distribution information from references, collecting 	Updated 	Database	Brown

permits and stream and lake surveys for resident fish.	periodically

MFWP	1	Complete conversion of distribution data for all fish species to 	04/01/01	Updated db	Carson	Conversion of routed hydrography for eastern

measures using the routed hydrography in western Montana and 	Montana will occur when the NHD is

eastern Montana when it becomes available.  These data were collected	available.

from biologists in FY2000.

MFWP	2	Provide distribution data in DEF to StreamNet when completed.	06/01/01	Updated db	Carson

MFWP	3	Determine a schedule for updating data in the future and at what 	6/30/01	Schedule	Carson

frequency data needs to be collected from field biologists, also

addressing species of special concern.

MFWP	4	Collect and catalog supporting references to document distribution 	8/01/01	Cataloged 	Carson

and connect distribution to reference.	references

MFWP	5	Explore the development of a standard field survey form to be used by 	4/01/01	Decision on form	Carson,

state and federal biologists to record occurrence information.	Hess-Herbert

MFWP	6	Continue to work with regional StreamNet staff and SC to 	ongoing	Improved DEF	Carson,

develop/modify/add to a resident fish data exchange format if not 	Hess-Herbert

completed in FY2000.

ODFW	1	Update, maintain, correct and exchange resident fish distribution 	As needed	Updated event data	Bowers	Only if ODFW staff provide the information

information (DistUse and DistPresence tables).	during anadromous distribution update work.

Region	1	Compile distribution updates (tabular events) as they arrive.  Create 	Ongoing	GIS Data 	Graves

and maintain distribution GIS coverages from these event tables and

distribute these via the StreamNet web site.

Region	2	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

WDFW	1	Update and exchange statewide updated bull char distribution data at 	11/1/00	Updated db	Burns	New presence/use categories and criteria

100K resolution (see Task 2.3).	applied: summer, 2000

Objective:	1	Task:	2.a	10/01/00	Page 8 of 41

Objective	1	Data Development	Task   2        Resident Fish and Other Aquatic Species

Task	2.b	Adult Abundance

Escapement, redd counts, trap counts, dam counts

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Coordinate with IDFG personnel to determine the feasibility of 	12/30/00	Summarized in 	Butterfield

incorporating resident adult abundance.	progress reports

MFWP	1	Enter 2000-2001 stream fisheries survey data collected for population 	6/30/01	Updated db	Carson

trends; genetics and escapement, redd counts, trap count and other

counts during visits to biologists.

MFWP	2	Collect reference for each survey.	8/01/01	References	Carson

MFWP	3	Provide data in data exchange format to regional StreamNet staff.	6/30/01	Updated db	Carson

ODFW	1	Update existing abundance and indices trends (escapement, redd 	1/30/01, 	Updated database	Hurn

counts, trap counts, peak/other spawning counts, etc.) for resident 	4/30/01,

species through 1999 and modify as needed to adhere to the 2000.2 	7/31/01,

data exchange standards.  Four data submissions planned.	&9/20/01

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing 	Assistance	Staff

and submission of data.

WDFW	1	Explore opportunities to compile, convert, and exchange portions of 	9/1/01	Updated db	Sikora

the Yakima Basin juvenile and adult abundance data from Ken Ham.

Objective	1	Data Development	Task   2        Resident Fish and Other Aquatic Species

Task	2.c	Angler Use

Fishing pressure, creel census

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Add FWP 1999 angler survey data collected by MFWP mail survey to	12/01/00	Updated db	Carson

MRIS.

MFWP	2	Review available creel census data on Montana's waters and determine	9/30/01	Data/or 	Carson

value and availability.	recommendation

ODFW	1	Evaluate available creel data for appropriateness and fit into the 	3/30/01	Report of data 	Cooney	Some test data may be submitted depending on

StreamNet format.	availability	 availability.

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

WDFW	1	Explore conversion of Angler Fish Database harvest information from 	7/1/01	Updated db	Burns	Depends on recruitment of a game fish data

the Columbia Basin into either "harvest" or a new "census" format for 	systems manager for WDFW.

exchange.

Objective:	1	Task:	2.c	10/01/00	Page 9 of 41

Objective	1	Data Development	Task   2        Resident Fish and Other Aquatic Species

Task	2.d	Hatchery Production

Hatchery production (releases and outplants) for salmonids

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

FWS	1	Explore availability of resident fish data relative to FWS facilities.  	Ongoing	Data submitted	Pastor	Provide data when DEF is complete.

Provide resident fish production and release data to PSMFC

IDFG	1	Complete cross reference of IDFG Catalog Number to LLID	3/30/01	Database	Butterfield

IDFG	2	Migrate the IDFG stocking data into StreamNet.	6/30/01	Database	Murdock

MFWP	1	Update StreamNet hatchery outplant data in the data exchange format 	6/1/01	Updated db	Hess-Herbert

with 1999 data from the FWP Information Services Unit Hatchery

Database, if changes are made.

ODFW	1	Acquire trout release data from 1997 through 2000 (by species, 	8/31/01	Updated db	Database

location, and facility) and compile into SN exchange format.	Manager

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

WDFW	1	Complete conversion and exchange resident fish stocking data from 	3/1/01	Partial regional db	Sikora

1930-1981, once location coding has been standardized and verified.

WDFW	2	Add stocking data from 1981-2000.	9/1/01	Updated db	Sikora

Objective	1	Data Development	Task   2        Resident Fish and Other Aquatic Species

Task	2.e	Genetics

Areas where genetics data exists and the sources of these data

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Update genetic spatial and tabular databases that contain the results 	Ongoing	Update db	Carson

of genetic analysis of populations of Montana's species of special

concern

MFWP	2	Update fish distribution table when new samples affect fields.	Ongoing	Update db	Carson

MFWP	3	Exchange data.	8/30/01	Decision	Carson

MFWP	4	Work with University of Montana Genetics Lab staff to develop a 	4/01/01	Edit/entry program	Corbin

more efficient method of data entry/delivery.

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

Objective:     1	Task:	2.e						10/01/00								Page 10 of 41

Objective	1	Data Development	Task   2        Resident Fish and Other Aquatic Species

Task	2.f	Population

Population delineation, as determined by others

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Maintain spatial delineation of bull trout populations, core and nodal 	7/1/01	Coverage	Hutten

habitat.  Enhance layer with population risk field.

MFWP	2	Finalize westslope cutthroat trout priority areas as part Westslope 	11/01/00	Coverage	Carson

Cutthroat Conservation Agreement and provide to StreamNet.

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

WDFW	1	Compile and exchange Washington SaSI stock status data for resident 	3/1/01	Updated regional 	Burns, O'Connor	The Salmonid Stock Inventory for WA assigns

fish using newly developed exchange format (see Task 2.3).	 wild salmonids to stocks and rates the health

Objective	1	Data Development	Task   2        Resident Fish and Other Aquatic Species

Task	2.g	Historic Range

As available at the watershed-level

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Complete the review of the historic distribution of Montana's native 	11/01/00	Available 	Carson

species developed by The Nature Conservancy.

MFWP	2	Coordinate the development of a Data Exchange Format for StreamNet 	11/01/00	Coverage	Hess-Herbert

by working with a Steering Committee subcommittee.

Region	1	Compile distribution updates (tabular events) as they arrive.  Create 	Ongoing	GIS Data 	Graves

and maintain distribution GIS coverages from these event tables and

distribute these via the StreamNet web site.

Region	2	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

Objective	1	Data Development	Task   2        Resident Fish and Other Aquatic Species

Task	2.h	Status

Population stability index

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Assist regional and state data managers in developing data exchange 	TBA	Advice	Hess-Herbert

format.

MFWP	2	If DEF adopted, submit bull trout, arctic grayling and westslope and 	When DEF 	Data	Carson

Yellowstone cutthroat trout data.	avail.

Region	1	Work with partners to determine data formats for this category	As needed	Formats	Banach

Objective:	1	Task:   2.h	10/01/00	Page 11 of 41

Objective	1	Data Development

Task	3	Habitat

Acquire data sets related to fish habitat from the multiple agencies, tribes and organizations within the Columbia Basin and compile

and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development				Task   3        Habitat

Task	3.a	Stream / Watershed Habitat

Incorporate applicable stream and watershed level habitat and stream survey data, as these become available

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Incorporate the IDFG General Parr Monitoring habitat data into 	9/30/01	Database	Murdock

StreamNet.

IDFG	2	Compile additional habitat data from stream surveys.	Updated 	Database	Brown

periodically

MFWP	1	Develop a statewide stream survey form based on information 	6/30/01	Survey	Carson

provided by Montana state and federal fisheries biologists in FY2000.

MFWP	2	Work with regional StreamNet staff on data exchange format, if 	8/31/01	DEF if developed	Carson

sufficient interest and/or data.

Region	1	Work with Steering Committee to decide whether a format for Aquatic 	12/31/00	Decision	Schmidt, staff	The Oregon Aquatic Inventory Project data

Inventory Project data should be developed and incorporated into the	are currently linked to the StreamNet web site.

StreamNet database.	  Should be adopt the AIP format as a regional

standard, or wait until other states develop

their own formats?

Region	2	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

SBT	1	Update data collected by the SBT to IDFG GPM data coordinator.	Ongoing	Updated db	Taki

WDFW	1	Transfer and exchange spatial layers of SSHIAP habitat characteristics 	2/1/01 first 	Database	Burns, Hudson	Depends on progress of parallel SSHIAP

and segmentation (based on gradient, confinement, and substrate).	test ready

Objective	1	Data Development	Task   3        Habitat

Task	3.b	Water Quality

Incorporate existing Clean Water Act 303(d) data and other water quality data as applicable

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Integrate 303(d) (TMDL)  data into the sub-basin planning effort if 	12/01/00	Sub-basin 	Hess-Herbert

opportunity arises during the fiscal year.

MFWP	2	Link the Army Corps of Engineer stream permitting database to MRIS	01/01/01	Link to StreamNet	Hess-Herbert

Region	1	Complete development of the 303d event table as soon as data is 	12/31/00	303d Coverage	Graves	The data is expected from DOE in October,

available from WA Dept. of Ecology	2000

Region	2	Maintain GIS water quality data event tables from the 303(d) data on 	Ongoing	GIS Data	Graves

the StreamNet web site.

Objective:	1	Task:	3.b	10/01/00	Page 12 of 41

Region	3	Incorporate the stream nutrient and temperature data into the 	3/31/01	Queriable data	programmer

StreamNet query system and make available via the web site.

Region	4	Assist SN partners with data acquisition, development, formatting 	Ongoing	Assistance	Staff

submission.

Objective	1	Data Development	Task   3        Habitat

Task	3.c	Miscellaneous Habitat Data

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Meet with Montana GIS community concerning the Montana GAP 	11/01/00	Discussion	Hess-Herbert

data to determine layer usability particularly in riparian and wetland

areas.

MFWP	2	Work with NRCS staff to determine usability of derived slope, aspect, 	12/01/00	Progress report	Hess-Herbert

gradient, sinuosity data in MRIS.

ODFW	1	Update key stream management area designations for OR including 	7/31/01	Updated coverages	Bowers	This task will be done only if changes have

FEMAT key watersheds, AFS aquatic diversity areas, ODFW coho 	been made.

source river reaches, ODSL essential salmon habitat and Priority

Areas.

ODFW	2	Track the progress of ODFW aquatic habitat prioritization model and 	7/31/01	URL link and 	Cooney

provide a URL for StreamNet to link to model results when they are 	status report

available.	quarterly.

Region	1	Assist partners with acquisition, development, formatting and 	Ongoing	Assistance	Graves

submitting data

WDFW	1	Explore Cosentino's model to assess habitat suitability for 	8/1/01	Paper	O'Connor

anadromous and resident fish by comparing predictions to actual.

Write paper on techniques and findings.

Objective:	1	Task:  3.c	10/01/00	Page 13 of 41

Objective	1	Data Development

Task	4	Facilities

Acquire data sets related to fishery-related facilities and structures from the multiple agencies, tribes and organizations within the

Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   4        Facilities

Task	4.a	Dams and Fish Passage Facilities

Enhance the existing StreamNet dams data set by updating relevant data from the Pacific Northwest Hydropower Database and

Analysis System (NWHS) and the National Inventory of Dams

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Incorporate enhanced dams data into StreamNet.	12/30/00	Database	Murdock

MFWP	1	Combine the StreamNet dams dataset with dams named in the GNIS 	01/01/01	Update db	Hess-Herbert

and the National Inventory of Dams, and exchange Montana's data.

ODFW	1	Update, maintain, correct and exchange dam information (as part of the 	As needed	Updated Barrier 	Brodeur	Data could be submitted up to 4 times during

Barrier database).	database	the year if significant updates are made.

Region	1	Maintain spatial aspect of dams table including location of dams and 	Ongoing	GIS Data Coverage	Graves

GIS data.  Assist states in tying dams to LLID-based stream locations

when requested.

Region	2	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

WDFW	1	Review, update, and exchange any new Washington state dams 	9/30/01	Updated db	Burns

information.

Objective	1	Data Development	Task   4        Facilities

Task	4.b	Hatchery Facilities

Update and maintain a dataset on anadromous and resident hatchery facilities containing information on location, design,

management and authorization

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

FWS	1	Update hatchery facility records as needed	As needed	Updated 	Pastor

Hatchery.dbf

FWS	2	Update hatchery water records as needed	As needed	Updated 	Pastor

HatchWat.dbf

IDFG	1	Incorporate supporting hatchery structures, such as weirs and traps, 	3/30/01	Database	Elms-Cockrum

into StreamNet.

MFWP	1	Provide update of these data if changes have occurred in Montana's 	9/30/01	Updated db	Hutten

facilities.

ODFW	1	Locate at least one public domain photo of each hatchery in Oregon 	8/31/01	Photographs in the	Brodeur

and provide to PSMFC.	 MapCat table

ODFW	2	Review and update Oregon hatchery facilities data and submit to 	8/31/01	Updated hatchery 	Brodeur, Bourne

PSMFC.	facilities table

Objective:   1	Task:   4.b					10/01/00									Page 14 of 41

Region	1	Maintain spatial aspect of hatcheries table including location of 	Ongoing	GIS Data Coverage	Graves

hatcheries and GIS data.  Assist states in tying hatcheries to

LLID-based stream locations when requested.

Region	2	Finalize the structure of the Hatchery Facilities table with input from 	10/30/00	Table structure	Kinney

the Steering Committee

Region	3	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

WDFW	1	Provide standard geo-spatial coordinates (Longitude-Latitude) for 	As available	Updated db	Burns

each facility.

WDFW	2	Compile similar coordinates for fish releases that occur away from 	As available	Updated db	Burns

these facilities, in order to develop a spatial layer of fish release sites

(including streams, lakes, and marine areas).

WDFW	3	Complete, convert, and exchange tabular and spatial data tables of 	12/1/00	Updated regional 	Sikora

Washington state hatchery facilities, including federal and tribal

stations.

Objective	1	Data Development	Task   4        Facilities

Task	4.c	Diversion/screening

Develop a data set for water diversions and screening

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Review regional data exchange format.	TBA	Review	Hess-Herbert

MFWP	2	Provide input and data to watershed planning projects.	TBA	Input	Hess-Herbert

ODFW	1	Develop a database structure and compile Oregon's fish screening data	TBD	DEF proposal	Brodeur,

and submit a draft data exchange format to SC for review and adoption.	Database

Manager

ODFW	2	Identify fish screening data that is appropriate for the StreamNet site 	TBD	Test records	Brodeur, 	Will do if an exchange format is adopted.

and submit test records once an exchange format has been adopted.	Database

Manager

Region	1	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

Objective:	1	Task:  4.c	10/01/00		Page 15 of 41

Objective	1	Data Development

Task	5	Habitat Restoration/Improvement Projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations within

the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective	1	Data Development	Task   5        Habitat Restoration/Improvement Projects

Task	5.a	Fish and Wildlife Program Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects related to the Fish and

Wildlife Program

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Data will be updated for FWP Projects during FY-01; the spatial data 	8/1/01	Update db	Hutten

layer of project location will be updated.

Region	1	Update Habitat Restoration/Improvement project GIS data (including 	Ongoing	GIS data	Graves

a polygon coverage to illustrate true extent of projects) and make this

available via the StreamNet website as downloadable GIS coverages

as new data are received.

Region	2	Develop Habitat Restoration/Improvement project GIS data 	As data are 	GIS Data	Graves

(including a polygon coverage to illustrate true extent of projects) 	received

based on state submissions and make this available via the StreamNet

website as downloadable GIS coverages.

Region	3	Assist StreamNet partners with acquisition, development, formatting 	Ongoing	Assistance	Staff

and submission of data.

WDFW	1	Follow-up from FY2000 habitat restoration project compilation 	 	 	 	Work is dependent on outside funds

Objective	1	Data Development	Task   5        Habitat Restoration/Improvement Projects

Task	5.b	Other Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects other than related to the

Fish and Wildlife Program

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Compile additional information from non-FWP restoration projects 	Updated 	Database	Brown

into StreamNet.	periodically

MFWP	1	Update Montana's Fish and Wildlife habitat restoration projects into 	8/1/01	Updated db	Hutten

StreamNet's Restoration and Mitigation database and submit in data

exchange format.

MFWP	2	Exchange Montana data in data exchange format.	8/1/01	Update db	Hutten

ODFW	1	Assist PSMFC with the creation and development of the map 	as needed	TBD	Bowers, Cooney

presentation of Oregon GWEB restoration data.

ODFW	2	Design and develop a database to capture carcass placement data for 	6/30/01	Database	Hurn, Database

Columbia Basin activities.	Manager

ODFW	3	Provide technical assistance to GWEB and StreamNet staff as needed 	as needed	Assistance	Database

to make compilation of ODFW habitat restoration/improvement 	Manager

projects in the Columbia basin more efficient.

Region	1	Assist StreamNet partners with submission of data.	Ongoing	Assistance	staff

Objective	1	Data Development

Task	6	Sub-basin Planning

Develop consistent data sets and information that are particularly suitable and useful for regional sub-basin planning and make them

readily available for planners

Objective	1	Data Development	Task   6        Sub-basin Planning

Task	6.a	Provide data for Sub-basin Planning

Organize and distribute the available fish, wildlife and habitat data in a standardized format for use in Sub-basin Planning or other

regional planning efforts

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Develop tools and applications to make regional watershed 	quarterly	various Internet 	Forrest, Roger

assessment and other planning information available to subbasin 	applications

planners

IDFG	1	Coordinate with sub-basin planning efforts to supply data.	As requested	Data exports, maps 	Butterfield

and other services

MFWP	1	Provide data to planners on request	On request	Provided 	Hess-Herbert

information

ODFW	1	Participate in discussions concerning data needs to support 	As needed	Updated project 	Cooney

sub-basin planning or other processes adopted by the amended Fish &	workplan

Wildlife Program. Modify data plan and priorities as needed to be

responsive.

ODFW	2	Provide consultation services and assistance to ODFW data managers	Ongoing	Assistance	All staff

to assist them in meeting Subbasin Planning needs.

Region	1	Meet with sub-basin planners to discuss data types that may be 	As requested	Assistance	staff

needed, data sources, and to plan integration methods of the various

data sets.  Assist planners acquire needed fisheries data.

Region	2	Provide available tabular data described under tasks 1.1 through 1.5 	On request	Data to planners	Banach

to entities conducting sub-basin planning.

Region	3	Provide StreamNet GIS coverages or other data (on request) to the 	On request	GIS data to 	Graves

entities conducting sub-basin planning.  Assist subbasin planners

with use of this data as needed.

SBT	1	Assist StreamNet cooperators with data needs as they are developed 	Ongoing	Id. of data needs	Taki

by Fish and Wildlife Program managers from sub-basin planning

WDFW	1	Continue to participate in discussions concerning data needs to 	Ongoing	Technical Advice	O'Connor

support sub-basin assessment coordinated by the Regional

Assessment Advisory Committee or other processes adopted by the

amended Fish & Wildlife Program. Modify data plan and priorities as

needed to be responsive.

WDFW	2	Coordinate data compilation from other WDFW Units as needed to 	Ongoing	Assistance	O'Connor,

respond to the above needs, using StreamNet data exchange

experience.

WDFW	3	Provide consultation services for WDFW wildlife and habitat data 	Ongoing	Assistance	Sikora, Hudson

managers to assist them in meeting the above needs.

Objective:   1	Task:   6.a					10/01/00									Page 17 of 41

Objective	1	Data Development				Task   6        Sub-basin Planning

Task	6.b	Capture information from Sub-basin Planning

Acquire information developed during subbasin planning to update anadromous fish, resident fish, and wildlife data sets

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Develop applications and procedures to update watershed assessment 	9/30/01	updated databases	Forrest, Roger	Regional schedule has been delayed.

data during subbasin planning	Activities will continue into FY01

IDFG	1	Coordinate with sub-basin planning efforts to capture outputs.	As requested	Databases	Butterfield

MFWP	1	Collaborate with regional staff and Montana CBFWA representative 	As needed	Determine when 	Hess-Herbert

when data become available	available

ODFW	1	Evaluate Subbasin Summaries and other Subbasin Planning related 	As needed	Work plan 	Cooney

documents related to Oregon, identify data which are not contained in 	adjustments

StreamNet and adjust staff work plans to capture new data if

appropriate and applicable.

Region	1	In collaboration with CRITFC staff, provide subbasin planners with 	As possible	Application	Regional staff

computer applications to enter and edit information developed during

subbasin planning as described in Tasks 1.1 through 1.5, above.

SBT	1	See 1.6.a

WDFW	1	Provide data compilation, conversion, and analytical services in 	Ongoing	TBD	O'Connor	HIGH PRIORITY WORK; specifics will be

support of the subbasin assessment process, the NMFS Viable Salmon 	determined during the first few months of

Populations model, and related NWPPC needs.	FY2001.

Objective:      1	Task:    6.b	10/01/00	Page 18 of 41

Objective	2	Data Management and Delivery

Provide high quality data management services, with specific emphasis on the creation of regionally

consistent data sets and the timely delivery of data to users in formats that meets their policy, planning, and

management needs

Objective	2	Data Management and Delivery

Task	1	Database Management

Maintain functional database programs at the state and regional levels to make consistent data sets for anadromous fish, resident

fish and to a lesser extent wildlife available through the StreamNet online database system.  At both the regional and state levels,

provide database management and administration necessary for accomplishing StreamNet objectives, to include: 1) maintaining

regional and state-level StreamNet data sets, 2) processing exchange data into the regional database, 3) transporting data to the

SQL environment, 4) enhancing StreamNet database structures and capabilities, and 5) providing programming services to project

participants to allow for efficient data entry and transfer.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

FWS	1	Update FWS data sets with 2000 data and submit to PSMFC	9/31/01	Updated database	Pastor

IDFG	1	After beta testing, implement Fish Information System in IDFG 	12/30/00	Functional 	Butterfield, 	This system will allow us to more efficiently

StreamNet and IDFG Fishery Bureau	Information System	Murdock	capture and manage data for StreamNet

IDFG	2	Continue development and improvements to Fish Information System.	Ongoing	Improved system	Murdock

MFWP	1	Provide state-level data management services, emphasizing 	Ongoing	Coordination, 	Hess-Herbert

coordination with StreamNet regional staff, MFWP and other state and	Summary in Q and

federal natural resource agencies and encourage the use of consistent 	A reports.

data attributes and data sets among all agencies.

MFWP	2	Provide high quality data management services with specific emphasis	Ongoing	Consistent data	Hess-Herbert,

on creation of regionally consistent data sets and the timely delivery 	staff

of data to users in formats that meet their policy, planning, and

management needs.

MFWP 	3	Update existing data sets as described in Task 1 and provide data to 	Ongoing	Updated regional 	Carson

the regional StreamNet office in DEF.  Provide data as sub-sets are

updated rather than waiting for entire data to be complete.

ODFW	1	Provide state-level StreamNet database management / administration / 	Ongoing	Functional 	All staff

development.  Enhance StreamNet and ODFW database structures, 	databases

interfaces, tools, and capabilities as needed.

ODFW	2	Develop custom GIS products and database structures that help 	as needed	Improved database 	Bowers,Brodeur,

improve data management and transfer with ODFW staff.	function	DatabaseManager

Region	1	Maintain and manage the StreamNet database so information / data are 	Ongoing	Updated  databases	Kinney

available internally to project participants and externally via Internet.

Region	2	Add data submitted to the StreamNet regional office into the SN 	Ongoing	Updated  databases	Kinney

database within ~30 days of receipt from the project partners.

Objective:   2	Task:	1					10/01/00									Page 19 of 41

Region	3	Assist data-providing agencies with error checking of data sets.	Ongoing	Updated  databases	Kinney, Banach

Region	4	Coordinate database compilation between agencies, helping to ensure 	Ongoing	Consistent data	Banach, Schmidt

that data submitted are usable, scientifically sound, and consistent.

Region	5	Update the database structure as new data categories are added or 	Ongoing	Updated db	Banach

categories are changed.

Region	6	Publish a procedure manual to define procedures and protocols for 	6/30/01	Manual	Kinney

data submission.

Region	7	Document all additions/changes to data structure, exchange formats, 	Ongoing	documentation	Staff

interface tools, etc.

Region	8	Develop metadata for all spatial data sets posted to the SN GIS web 	Ongoing	Metadata	Graves

page.

Region	9	Begin developing metadata for StreamNet's tabular data holdings.	Ongoing	Metadata	Staff

Region	10	Provide programming services to project participants to assist with 	Ongoing	Assistance	Staff

efficient data entry and data transfer

Region	11	Based on direction from the Steering Committee, develop 	7/31/01	SDE-format 	Graves, Kinney

recommendations on the means to move the StreamNet database into an	database structure

SDE-compatible format to provide enhanced interactive mapping and 	recommendation

to develop necessary structures to serve data through SDE.

Region	12	Write documentation detailing use and maintenance of new SDE table 	9/30/01	Documentation	Graves, Kinney

structures and functions for regional staff, if approved by Steering

Committee.

Region	13	Ensure georeferencing of data is accurate and complete.	Ongoing	Updated  databases	Kinney, Graves,

Banach

WDFW	1	Washington state data maintenance and exchange support services, 	Ongoing	Support services 	Brown, Hudson

including updated exchange format system, support for MS Access 97,

and support for new data categories and fields.

WDFW	2	Update existing data sets as described in Task 1 and provide data to 	Ongoing	Updated regional 	Sikora

the regional StreamNet office in Data Exchange Format (DEF).

Provide data as subsets are updated, rather than waiting for entire data

to be complete.

Objective	2	Data Management and Delivery

Task	2	Data Plan

Update and maintain a project data plan that identifies 1) current data holdings at the regional level, 2) data items to be

incorporated in the current contract period and in future years, and 3) expectations for data development and delivery from

participating organizations within the current contract period

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Provide input to the data plan to keep it responsive to subbasin 	Ongoing	comments	Roger

planning and Framework needs and schedules.

IDFG	1	Work jointly with other participants to modify elements of data plan 	Ongoing	Updated data plan	Butterfield

or priorities based on needs arising out of sub-basin planning or other

processes that drive Basin data needs through the amended Fish

&Wildlife Program.

Objective:   2	Task:   2					10/01/00									Page 20 of 41

MFWP	1	Provide input into plan when requested.	Ongoing	Updated data plan	Hess-Herbert

ODFW	1	Work jointly with other participants to modify elements of data plan 	Ongoing, as 	Cooney

or priorities based on needs arising out of sub-basin planning or other	needed

processes that drive Basin data needs through the amended Fish

&Wildlife Program.

Region	1	Explore creating a consolidated data plan format that outlines current 	5/1/01	Decision on future 	Schmidt

data holdings.  Beginning in FY 2000, the Statement of Work now 	plan format

provides more information on planned data incorporation.

Region	2	Based on input from the BPA COTR and project participants, modify 	Ongoing, as 	Updated data plan	Schmidt

and update the Data Plan as needed.	needed

WDFW	1	Work jointly with other participants to modify elements of data plan 	Ongoing	Updated data plan	O'Connor

or priorities based on needs arising out of subbasin assessments or

other processes stemming from the amended Fish & Wildlife Program.

Objective	2	Data Management and Delivery

Task	3	Data Exchange Standards

Establish and maintain data exchange standards that ensure consistent format and content of data that originated from the multiple

agencies and data sources in the basin.  Included will be proposed and adopted data exchange formats, metadata and location

look-up tables for specific data items as described under Objective 1.  At the regional level, this task will provide technical

assistance regarding standard codes and exchange formats for Fish and Wildlife Program and ESA- related projects, and for

applicable tribal data compilation activities.  At the state level, this task will provide similar technical assistance for state agency

data activities applicable to StreamNet.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Participate in the design, development and maintenance of standard 	Ongoing	Updated DEF	Forrest

codes and data exchange formats. This will occur through involvement

on the Steering Committee and technical work groups.

IDFG	1	Participate in the design, development and maintenance of standard 	Ongoing	Updated data 	Butterfield,

codes and data exchange formats. This will occur through involvement	exchange formats 	Murdock

on the Steering Committee and technical work groups. There is no set 	(DEF)

schedule for this task, because it is highly dependent on issues facing

the Steering Committee. Potential new data exchange standards may

include juvenile abundance, genetics, stream habitat, stream

temperature and resident fish releases.

MFWP	1	MFWP StreamNet will participate in the design, development and 	Ongoing	Updated DEF	Hess-Herbert,

maintenance of standard codes and data exchange formats through 	Carson

involvement on the Steering Committee and technical work groups.

ODFW	1	Participate in the design, development and maintenance of standard 	Ongoing	Updated DEF	All staff

codes and data exchange formats. This will occur through involvement

on the Steering Committee and technical work groups. There is no set

schedule for this task, because it is highly dependent on issues facing

the Steering Committee. Potential new data exchange standards may

include juvenile abundance, genetics, stream habitat, stream

temperature and resident fish releases.

Objective:	2	Task:	3	10/01/00		Page 21 of 41

Region	1	Work with the project database managers to identify needed 	Ongoing	Proposed DEF	Banach

modifications to the Data Exchange Format (DEF) to accommodate

changing data needs

Region	2	Formally adopt changes to the DEF through the SN Steering 	quarterly	Meeting report	Banach

Region	3	Document all adopted changes to the DEF	Ongoing	Report	Banach

Region	4	Lead or work with partners to develop data exchange formats for new 	various dates 	DEFs	Banach

data categories, including:  population delineation (anadromous and 	during fiscal

resident); carcass placement; resident fish hatchery releases; juvenile 	year

abundance; stream habitat.  As time permits and need dictates, data

exchange formats may also be created for macroinvertebrate samples,

and water quality parameters.

WDFW	1	Compile and review the specific criteria used by participating 	1/1/01	DEF proposal	Hudson,

agencies in describing fish distribution, use, or extent information, in 	O'Connor

order to find and adopt common standards among data providers.

WDFW	2	Analyze Hatchery Returns exchange format and explore whether a 	11/1/00	DEF proposal	O'Connor

second table (covering Spawning and Disposition data fields) is

needed to more accurately meet the needs of the Artificial Production

Committee.

WDFW	3	Finalize and distribute for adoption an exchange format for State Risk 	11/1/00	DEF proposal	O'Connor

status (stock status) to provide information on sensitive salmonid

stocks.

WDFW	4	Move toward complete adoption of LLIDs as the standard stream 	Ongoing	LLID cross 	Sikora, Woodard

referencing code by reviewing and completing the RRN-to-LLID 	reference table

conversion, addressing supercode issues, and assuring that LLIDs are

assigned to all locations where StreamNet data exist.

WDFW	5	Provide metadata for tabular and spatial datasets according to 	with data	Metadata in DEF.	Hudson, Sikora

guidelines adopted by the Steering Committee.

WDFW	6	Construct a new data compilation and conversion system to provide 	1/1/01	New compiler 	Brown,

data in MS Access according to the most recently adopted exchange 	system.	Woodard, Sikora

format. Begin exchanging data in MS Access form by winter, 2001

Objective	2	Data Management and Delivery

Task	4	GIS Data System

Establish and implement procedures for coordination of StreamNet-related spatial data activities among participating

organizations, to include regular meetings and or other communication links among participating GIS specialists. Designate and

maintain metadata format for spatial data to be used by StreamNet participants. Prepare map products in hardcopy and/or

electronic format for use in Program-related aquatic resource policy, planning, and management.  Provide for distribution of spatial

data in GIS and tabular format and as GIS products.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Maintain and enhance a geographic information system (GIS) related 	Ongoing	Functional system	Butterfield

to regional and state-level StreamNet goals and objectives.

IDFG	2	Prepare data and map products from StreamNet data on request	Ongoing	Data and map 	Butterfield,

products.	Graham

Objective:	2	Task:	4	10/01/00		Page 22 of 41

MFWP	1	Maintain a state- level GIS program (state and StreamNet funded)	Ongoing	Summary in Q. and 	staff

An. reports

MFWP	2	Prepare map products in hardcopy and/or electronic format for use in 	Ongoing	GIS products	staff

Program-related aquatic resource policy, planning, and management.

ODFW	1	Participate in planning and coordination meetings for state-level 24k 	as needed	update SC 	Bowers

hydrography layer to ensure compatibility with the StreamNet's

adopted hydrography.

ODFW	2	Maintain and enhance a geographic information system (GIS) related 	Ongoing	Functional System	Bowers

to regional StreamNet goals and objectives (general maintenance,

metadata development and maintenance, planning and coordination

activities, etc.).

ODFW	3	Prepare spatial data and map products in hardcopy and/or electronic 	as needed	Products	Bowers

format for use in Program-related aquatic resource policy, planning,

and management.

Region	1	Maintain and enhance a geographic information system (GIS) related 	Ongoing	Functional GIS	Graves

to regional StreamNet goals and objectives.

Region	2	Prepare GIS data and map products from StreamNet data.	On request	Maps	Graves

Region	3	Integrate the functioning of the GIS system with the StreamNet 	As needed	Shape files, X-ref. 	Graves

fisheries and habitat database, in support of the query system.  Create 	tables

cross tables and queriable maps used via the StreamNet web interface.

Region	4	Direct users to other GIS resources when requests exceed SN 	As needed	Assistance	Graves

WDFW	1	Create approved reference documents for all exchanged spatial data 	Ongoing	Reference 	Burns

sets. (See also Task 2.3, work component 5)	documents

Objective	2	Data Management and Delivery

Task	5	StreamNet Internet Site

Continue to maintain and enhance the existing client-server system to provide access to StreamNet data products through the

Internet.  The StreamNet home page will continue to be recognized as the project's primary data delivery vehicle.  Priority will be

given to incorporating data developed through Objective 1 and providing access to reference materials secured through Objective 3.

Appropriate training on the use of the system will be provided through a combination of on-line help and in-person training

sessions.

Objective	2	Data Management and Delivery	Task   5        StreamNet Internet Site

Task	5.a	Maintain the StreamNet Client Server system

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

Region	1	Maintain, upgrade as needed, and administer the StreamNet web 	Ongoing	Functional website	Kinney

site and data system

Objective:	2	Task:	5.a	10/01/00	Page 23 of 41

Objective    2        Data Management and Delivery                                                      Task   5        StreamNet Internet Site

Task	5.b	Enhance and improve the StreamNet website

Maintain and enhance components of the StreamNet home page and incorporate new features that complement existing

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Work with subbasin planners to identify modifications and new uses 	Ongoing	Recommendations	Oftedahl

which will make the website more useful to them

CRITFC	2	Identify changes and new features which will improve delivery of 	Ongoing	Recommendations	Oftedahl, Nock,

Library services	Liberty

CRITFC	3	Work with regional staff to implement changes identified above.	Ongoing	Improved services	Oftedahl, Nock,

Liberty

IDFG	1	Recommend and/or take part in review of new products and features.  	Ongoing	Recommendations	All staff

Provide feedback on content, suitability, navigability and data

currency issues.

MFWP	1	Montana will review and comment when necessary.	Ongoing	Advice	Hess-Herbert

ODFW	1	Recommend and/or take part in review of new products and features.  	Ongoing	Recommendations	All staff

Provide feedback on content, suitability, navigability and data

currency issues.

ODFW	2	Provide a link from the StreamNet website to available Columbia 	4/30/01	URL's & text to 	Frazier

River fisheries information (including Columbia River Compact 	PSMFC

Action Notices, In-Season Updates, and Joint Columbia River

Management Staff Reports and possibly in-season catch estimates)

along with informational text to describe each link.

Region	1	Summarize results from the StreamNet online user survey.  Compile a 	12/29/00	Report	Schmidt

list of recommended changes and improvements to the online data

system

Region	2	Continue to review the StreamNet website for clarity, organization 	Ongoing	Improved web site	Schmidt, McGill,

and ease of use.  Recommend and implement changes to maximize 	 staff

utility for people accessing the site to obtain information.  Changes

will include updating, replacing, and retirement of existing web pages,

and archiving of all existing pages.

Region	3	Plan to enhance the website content by adding additional kinds of 	Ongoing	Expanded content	Schmidt, staff

information that will support the Fish and Wildlife Program.  Develop

concept for increasing information by coordinating with regional data

users

Region	4	Investigate the latest internet technology in order to improve/add 	Ongoing	Updated web plan	Staff

interactive features to our site.

Region	5	Identify and provide links to other web sites that provide data 	Ongoing	Improved website	Staff

complimentary to but not contained in StreamNet.

Objective:	2	Task:	5.b	10/01/00	Page 24 of 41

Region	6	As the DEF is revised and new data sets are added to the database, 	Ongoing	Revised queries	Schmidt,

modify the query system to function with the revisions.  Test and 	programmer

debug these changes.  Continue to check to the existing functioning of

the query system and address any shortcomings as they are identified.

Region	7	Develop an on-line mapping application which may be used over the 	2/28/01	Internet mapping 	Graves

internet by the public to view StreamNet data "layers" through 	application

interactive maps.  This application will allow users to view and query

StreamNet data spatially, generate reports and tabular or GIS data

based on spatial queries, and create their own custom maps.

Region	8	Once the internet mapping application is created and implemented, it 	Ongoing	Enhancements to 	Graves

will be enhanced on an ongoing basis to improve speed, add new 	internet mapping

features and capabilities, and to incorporate additional data layers.	application

Region	9	Write documentation on access, use, editing, and maintenance of the 	4/30/01	Documentation	Graves

internet mapping application.

Region	10	Integrate new SDE database structure and Internet Mapping 	8/31/01	Enhanced internet 	Graves

Application for high-level speed and performance.	mapping capability

WDFW	1	Take part in review of new products and features. Provide feedback on 	Ongoing	Improved website	All staff

content, suitability, navigability and data currency issues, especially

issues related to providing static or dynamic map capabilities.

Objective	2	Data Management and Delivery

Task	6	1:100,000-scale Hydrography

Maintain the 1:100,000-scale PNW hydrography for purposes of attaching StreamNet data.  Coordinate with efforts to prepare a

National Hydrographic Dataset (NHD). Develop a standardized method for incorporating lake hydrography and attribute

information.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Maintain the Idaho portion of the 1:100,000-scale PNW hydrography	Ongoing	Any modifications 	Butterfield

for purposes of attaching StreamNet data.	to hydro.

IDFG	2	Participate in coordination of the National Hydrographic Dataset 	Ongoing	Coordination with 	Butterfield

other agencies

MFWP	1	Support the efforts of the NHD and convert Montana hydrography to 	Depends on 	Converted 	Hutten

NHD upon receipt.	NHD data 	hydrography

delivery

MFWP	2	Enhance layer with LLID and stream level routing.	LLID routing	Hutten

MFWP	3	Coordinate with NRIS in the QA/QC of the NHD for Montana 	Ongoing	Assistance	Hutten

including the development of a lakes layer (funding provided by the

BOR for lakes).

ODFW	1	Continue to maintain the Oregon portion of the 1:100,000-scale PNW	as needed	Updated 	Bowers

hydrography for purposes of attaching StreamNet data and for use in 	hydrography

ODFW information management systems. Submit all modified PNW

hydrography to PSMFC for inclusion in the regional PNW

hydrography data.

Objective:	2	Task:	6	10/01/00	Page 25 of 41

ODFW	2	Participate in technical and policy discussions concerning efforts and 	Ongoing	Input to 	Cooney, Bowers

activities that relate to or impact the PNW hydrography (NHD, 	discussions and

OR/WA state framework physical data model, clearinghouse issues, 	decisions

data dictionary development, etc.)

ODFW	3	Provide technical advice on hydrology routing and other issues 	As needed	Advice provided 	Bowers

including those related to working with higher resolution 	(and summarized in

hydrography.	quart. Reports)

Region	1	Continue to maintain the regional 1:100,000-scale PNW 	Ongoing	Updated 	Graves

hydrography

Region	2	Implement updates to the 1:100,000-scale PNW hydrography from 	Ongoing	Updated 	Graves

state cooperators.	hydrography

Region	3	Update and serve a regional web version of the 1:100,000-scale PNW 	Ongoing	Hydrography 	Graves

hydrographic set from the StreamNet website.	available

Region	4	Assess future uses of the National Hydrography Dataset (NHD) and if 	TBD	TBD	Graves

adopted, coordinate the replacement of the PNW Reach files with the

NHD as the StreamNet hydrography layer.

Region	5	Update Montana hydrography with LLID routing as updates are 	Ongoing	LLID assignments 	Graves

received from MFWP.	and stream routes

Region	6	Work with developers of 1:24,000 hydrography at BLM and USFS to 	Ongoing	Updated 	Graves

ensure that the 1:100,000 stream-based routing system remains 	hydrography

consistent with the new 1:24,000 system.

Region	7	Develop a complete cross-reference application between all streams in 	11/30/00	Cross-reference 	Graves

the PNW Reach Files and the NHD (National Hydrography Dataset)  	table

for Washington, Oregon, and Idaho to allow collection and

distribution of stream-based data in both LLID and NHD formats.

WDFW	1	Complete Steering Committee discussion about lake attributes useful 	12/1/00	DEF proposal	O'Connor

to share in a regional database; determine support for a new data

format.

WDFW	2	Compile, standardize, and exchange point, line, and polygon 	6/1/01	Updated 	Hudson

information for lakes stocked with fish that appear at 100K (or higher) 	hydrography

resolution.

WDFW	3	Participate in technical and policy discussions concerning adoption 	Ongoing	Decisions re. NHD	O'Connor,

of the NHD 100K framework for the Northwest. Review Washington 	Hudson

state NHD datasets if funding is available.

WDFW	4	Maintain Washington 100K HUCs by performing error fixes, 	Ongoing	Updated 	Hudson

addressing cross-border and cross-HUC incompatibilities, and related	hydrography

duties.

WDFW	5	Provide technical advice on hydrology routing and other issues 	Ongoing	Improved 	Hudson

related to working with higher resolution hydrography as needed.	hydrography

Objective:	2	Task:	6	10/01/00	Page 26 of 41

Objective	2	Data Management and Delivery

Task	7	Data Requests

Receive and respond to requests for data, source materials, and custom products.  Response to requests will be honored within the

limits of available resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.

Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural resource

management activities.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	See Tasks 1.1h, 1.6, and Objective 3	Ongoing	Improved services	Oftedahl, Roger,

staff

IDFG	1	Continue to respond to requests for information from StreamNet 	Ongoing	Filled requests, 	Elms-Cockrum,

database, including requests for fishery information that comes into 	summary in qu. 	Graham, Brown

the Idaho Conservation Data Center (Natural Heritage Program), other	Report

IDFG programs and personnel, and outside agencies and consultants.

MFWP	1	Receive and respond to requests for data, source materials, and custom 	Ongoing	Summary in Q. & A.	staff	Other priorities = ESA, federal, state, and

products.  Respond to requests within the limits of available 	 reports	tribal natural resource management

resources, with priority given to information requests having direct

relevance to the FWP.

ODFW	1	As requested, consistent with other deliverables in this contract, 	Ongoing	Summaries in 	All staff

receive and respond to requests for data, source materials, technical 	quarterly reports

training, and custom products.

Region	1	Respond within one day whenever possible to all user requests 	Ongoing	Rapid assistance	Banach

received via email, phone, or other medium.  Typical requests received

include help using the query system, complex data requests not easily

done with the query system, and requests for GIS coverages and maps.

Region	2	Fill requests for data not available via the web in an expeditious 	Ongoing	Filled requests	Banach, Graves

manner, with highest priority for people working for the NPPC's Fish

and Wildlife Program.  Requests from outside the Fish and Wildlife

Program or participating agencies will be addressed on an 'as

possible' basis.

Region	3	Modify the web site to inform of all ways data can be obtained, 	12/31/00	Updated web site	McGill

including custom requests made directly to the project

WDFW	1	Generate maps, data reports, and electronic copies of datasets as 	Ongoing	Requests	All staff

requested.

WDFW	2	Provide PRIORITY data support for subbasin assessments and other 	Ongoing	Requests	All staff

new elements of the NWPPC Fish & Wildlife Program.

Objective:   2		Task:   7	10/01/00	Page 27 of 41

Objective	3	Library / Reference Services

Provide a full service regional library for fish (and to some degree wildlife) literature (published and

gray), including documentation of all data in the StreamNet database.

Objective	3	Library / Reference Services

Task	1	Collection Development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document data

source materials, Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists,

agencies, interested parties, and other libraries.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Coordinate source material submissions for data compiled under 	Ongoing	Updated, expanded,	Oftedahl, staff

Objective 1. Develop standards for document submissions	 fully cataloged

collection

CRITFC	2	Collect and catalog documents prepared by contractors (including 	6/30/01	Updated, expanded,	Oftedahl, staff

final products published by BPA and draft documents suitable for 	 fully cataloged

public release) under the Fish and Wildlife Program. Work with 	collection

Publications distribution for better publication notification and

deposit system.

CRITFC	3	Collect and catalog documents from the Council's Fish and Wildlife 	4/30/01	Updated, expanded,	Oftedahl, staff

Program-related collection.	 fully cataloged

collection

CRITFC	4	Collect and catalog additional books, journals, agency reports, gray 	Ongoing	Updated, expanded,	Oftedahl, staff

literature, research reports, and documents that are applicable to 	 fully cataloged

management of the region's aquatic resources.	collection

IDFG	1	Continue to collect documents used as source materials for data in 	Ongoing	Submission to 	Elms-Cockrum,

Objectives 1 and 2.  Documents will be assigned reference numbers 	library	Brown

and forwarded to the StreamNet library as per established guidelines.

MFWP	1	Provide an update to the electronic version of documents used as 	9/1/01	Submission to 	Hess-Herbert

source materials for data compiled in Objective 1. 	library

ODFW	1	Provide originals/copies of all documents and reports referenced in 	Ongoing	Documents	All staff

the compilation of new StreamNet data holdings, but not already

housed in the StreamNet Library.

ODFW	2	Update the set of historic (pre-1975) Oregon Fish Commission and 	Ongoing	Documents	Bourne

Game Commission reports and provide to the SN library as available.

ODFW	3	Update library bibliography of ODFW, Fish Commission, and Game 	Ongoing	Updated 	Bourne

Commission reports with historic and current publications and make 	bibliography

the bibliography available for reference via SN and ODFW websites.

Region	1	Coordinate with the StreamNet librarian to maintain, update and 	Ongoing	Current collection	staff

improve the StreamNet reference database and query system.

WDFW	1	Continue to collect documents used as source materials for data in	Ongoing	Submission to 	Sikora

Objectives 1 and 2. Documents will be assigned reference numbers	library

and forwarded to the StreamNet library as per established SN guidelines

Objective:  3	Task:	1					10/01/00									Page 28 of 41

Objective	3	Library / Reference Services

Task	2	Provide Access to Collection

Provide user access to the materials described in Task 3.1 by providing facilities for storage of paper and electronic copies of

documents, an online catalog of all documents in collections, and staff to answer location questions and respond to requests.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Maintain an appropriate facility for the storage and public use of the 	Ongoing	Library open to 	Oftedahl, staff

physical collection.	public

CRITFC	2	Catalog, organize and maintain the collection for appropriate on-site 	Ongoing	Current catalog	Oftedahl, staff

CRITFC	3	Provide access to the StreamNet Library Catalog.	Ongoing	Website	PSMFC

CRITFC	4	Develop a schedule for regular updates of the reference table.	9/30/01	Schedule	Oftedahl

ODFW	1	Enhance, maintain, and update ODFW Library software and 	8/31/01	Updated Library 	Database

procedures to ensure adequate tracking of information requests, key 	information system	Manager, Bourne

word searches, and easy comparison to the StreamNet Library

holdings.

Region	1	Work with CRITFC librarian to make electronic library resources 	Ongoing	Reference  	Staff

available on the StreamNet website.	information

Objective	3	Library / Reference Services

Task	3	Improve Electronic Access

Enhance the online capabilities of the StreamNet Library, including catalog access via the internet and an electronic archive of key

Columbia Basin documents.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Manage and maintain the Library catalog server	4/1/00	Library server 	Oftedahl, Forrest

linked to

StreamNet

CRITFC	2	Integrate the library catalogs into a single web application using 	7/1/01	All holding 	Oftedahl, Forrest

TextWorks Web Publisher	available through a

single catalog

CRITFC	3	Develop an electronic archive of key Columbia Basin documents.	7/1/01	Document archive	Oftedahl, Nock

CRITFC	4	Make electronic documents available through the Library web page.	9/30/01	Electronic 	Oftedahl, Nock

documents

available online

Objective:	3	Task:	3	10/01/00	Page 29 of 41

Objective	3	Library / Reference Services

Task	4	Library Services

Manage the StreamNet Library and provide library services to the StreamNet user community and the general public.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Provide access guide to outline services for patrons. 	3/31/01	Pamphlet	Oftedahl, staff

CRITFC	2	Assist users to locate information by providing reference, referral, and 	Ongoing	Service	Oftedahl, staff

computer based search services.

CRITFC	3	Provide document delivery services, including inter-library lending 	On request	Service	Oftedahl, staff

and borrowing.

CRITFC	4	Maintain hardcopy files of draft and final documents related to the 	Ongoing	Current collection	Oftedahl, staff

NPPC amendment process, subbasin planning, and Columbia

River/Portland harbor dredging

ODFW	1	Respond to requests for ODFW documents and other source materials.	@request	Filled requests	Bourne

Objective	3	Library / Reference Services

Task	5	Inter-library Coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other

collections that will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Collect information about other regional fish and wildlife library 	Ongoing	Database	Oftedahl, staff

collections and access policies.

CRITFC	2	Provide consultations for agencies and groups on ways to coordinate 	Ongoing	Services as 	Oftedahl, staff

catalogs and services.	requested

CRITFC	3	Coordinate with users, agencies, and regional libraries to improve 	9/30/01	Needs assessment	Oftedahl, staff

services and avoid unnecessary duplication.  Perform a needs

assessment for the Library.

CRITFC	4	Facilitate communications between subject related library service 	9/30/01	Host meeting	Oftedahl, staff

providers. Coordinate concurrent Library Needs workshop with Data

Needs workshop (Task 4.7).

CRITFC	5	Maintain presence in related Library groups (i.e. IAMSLIC, NRIC) to 	Ongoing	Presentations, 	Oftedahl,  staff

provide access to knowledge on Best Management Practices for 	reports

libraries and current awareness of subject-related materials.

ODFW	1	Coordinate with the Oregon State Library system to enhance access to	Ongoing	Regular 	Bourne

published periodicals, journals, and other documents for StreamNet 	communication &

users.	coordination

Objective:	3	Task:	5	10/01/00	Page 30 of 41

Objective	4	Services to Fish and Wildlife Program Activities

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and

Wildlife Program projects

Objective	4	Services to Fish and Wildlife Program Activities

Task	1	Monitoring and Evaluation

Assist in the development of products that contribute to the monitoring and evaluating (M&E) of Fish and Wildlife Program

effectiveness.  Specific area of involvement will include:

Objective	4	Services to Fish and Wildlife Program Activities	Task   1        Monitoring and Evaluation

Task	1.a	M&E Participation

Participate in Program-related monitoring and evaluation work groups

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Assist basin wide efforts to develop an R/M/E plan consistent with 	7/1/01	R/M/E guidelines 	Roger, Forrest

the regional Framework	for subbasin

planners

IDFG	1	Participate in discussions concerning data needs to support processes	As needed	Butterfield

adopted by the amended Fish & Wildlife Program for Monitoring and

Evaluation.

MFWP	1	Participate in discussions concerning data needs to support processes	As needed	Participation	Hess-Herbert

adopted by the amended Fish & Wildlife Program for Monitoring and

Evaluation.

ODFW	1	Participate in discussions concerning data needs to support processes	As needed	M&R related 	Cooney

adopted by the amended Fish & Wildlife Program for Monitoring and 	activities to

Evaluation.	address data needs

(TBD)

Region	1	Participate in Monitoring and Evaluation work groups to provide 	On request	Participation	Schmidt

assistance in locating, acquiring and providing data needed for R/M/E

activities.

WDFW	1	Participate in discussions concerning data needs to support processes	As needed	O'Connor

adopted by the amended Fish & Wildlife Program for Monitoring and

Evaluation.

Objective:	4	Task:	1.a	10/01/00	Page 31 of 41

Objective	4	Services to Fish and Wildlife Program Activities	Task   1        Monitoring and Evaluation

Task	1.b	Evaluation

Periodically re-evaluate the StreamNet data plan to ensure consistency with M&E needs

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Keep Steering Committee apprised of regional R/M/E plans and needs	Ongoing	Reports to SC	Roger

MFWP	1	Assist as needed.	As needed

ODFW	1	Participate in discussions concerning the StreamNet data plan to 	As needed	M&E support 	Cooney

ensure it supports processes adopted by the amended Fish & Wildlife 	activities (TBD)

Program for Monitoring and Evaluation.

Region	1	Keep abreast of regional data needs related to Fish and Wildlife 	Ongoing	Improved relevance	Schmidt, Banach

Program Monitoring and Evaluation and plan for StreamNet 	 to M&E

database's ability to fulfill these needs.

Objective	4	Services to Fish and Wildlife Program Activities	Task   1        Monitoring and Evaluation

Task	1.c	M & E Reporting

Prepare reports and data products that illustrate key M&E topics

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Assist Steering Committee to identify useful M&E products which 	4/01/01	Reports to SC	Roger, Forrest

StreamNet can produce at regular intervals

MFWP	1	Respond to requests from the Fish and Wildlife Program.	On request	Completed request	Staff

ODFW	1	No work planned but we are willing to adjust work plans to address 	TBD	Cooney

amended Fish and Wildlife Program needs.

Region	1	Participate in and/or monitor FWP monitoring and evaluation work 	Ongoing	Participation	Schmidt

groups.

Region	2	Respond to M&E needs for information and provide data reports and 	On request	Data, reports	Banach

other products in support of M&E activities.

WDFW	1	Respond to requests from the Fish and Wildlife Program	On request	Completed request	Staff

Objective:	4	Task:   1.c	10/01/00	Page 32 of 41

Objective	4	Services to Fish and Wildlife Program Activities

Task	2	Watershed Projects

Provide data and data services to Fish and Wildlife Program-sponsored watershed planning and assessment projects

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Assist subbasin planners to develop monitoring and evaluation 	6/01/01	R/M/E guidelines	Roger, Forrest

activities for watershed projects that will integrate smoothly with

StreamNet databases (cost sharing)

MFWP	1	Participate in watershed and, sub-basin planning to the extent 	As scheduled	Products as 	Hess-Herbert

requested by the Council and other regional participants.  Coordinate 	requested

with Montana CBFWA representatives in the process and assure a

valuable product.  Volunteer to complete a pilot sub-basin in the

process within Montana.

ODFW	1	Participate in watershed planning and assessment activities to the 	As needed	TBD	Cooney

extent requested by the Council and other regional participants.

Coordinate with Oregon CBFWA representatives to ensure

applicability to F&W Program needs.

Region	1	Receive information on watershed restoration and improvement 	Ongoing	Updated db	Kinney

projects and make available via the StreamNet website

WDFW	1	No work planned. (Related F&WP work under Tasks 1.6, 2.2, 2.7, and

4.2a)

Objective	4	Services to Fish and Wildlife Program Activities

Task	3	Stock Assessment Projects

Provide technical assistance to the Upper Columbia Basin and Upper Snake River Basin resident fish stock assessment projects,

including a) identification of regionally consistent data exchange standards and b) Internet access to project data and other

information. Specific actions will be defined in consultation with stock assessment project managers

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

IDFG	1	Coordinate with the Upper Snake River Basin Resident Fish Stock 	Ongoing	Summarized in 	Brown

Assessment project in order to incorporate that data into StreamNet 	progress reports

and to provide technical assistance.

MFWP	1	Provide input as needed	As needed	Input	Hess-Herbert

ODFW	1	Provide assistance as needed.	As needed	TBD	Cooney

Region	1	Assist state partners as needed.	As needed	Assistance	Banach

WDFW	1	Provide spatial, tabular data standardization and exchange 	9/30/01	JSAP data forms, 	O'Connor, Burns

consultation and assistance to participants in the BPA-funded Joint 	structures.

Stock Assessment Project (JSAP).

Objective:	4	Task:   3	10/01/00	Page 33 of 41

Objective	4	Services to Fish and Wildlife Program Activities

Task	4	Service to Other Fish and Wildlife Program Projects and Activities

In consultation with CBFWA, the Council, and BPA StreamNet will provide technical assistance and data services to select

Program projects

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Collaborate with CBFWA, NPPC, and other fish and wildlife 	ongoing	Recommendations 	Roger, Forrest

programs in the Columbia Basin to identify and provide technical and 	for SN products

other services to the Fish and Wildlife Program

IDFG	1	Provide technical and other services to other FWP projects occurring 	Ongoing	Summarized in 	Brown

in IDFG. 	progress reports

MFWP	1	Provide technical assistance and data services to Program projects 	As needed	Summary in Q 	staff

upon request.	reports

ODFW	1	Provide technical assistance and data services to F&W Program 	As needed	TBD	Cooney

projects as needed and adjust work plan priorities accordingly.

ODFW	2	Produce pre- and post-season harvest and stock status reports for 	On going	Reports completed 	Frazier

Columbia River fish runs and fisheries and make reports available via 	and on the web.

either via the StreamNet site directly or via the ODFW Columbia

River Management site with a link from StreamNet.

ODFW	3	Draft a summary of real-time data services that can be provided as well 	4/30/01	Summary submitted	Frazier

as a description of how these services differ from current data services 	 to PSMFC

provided in the Basin.

Region	1	Work with Fish and Wildlife Program projects throughout the basin 	As needed	Assistance	Staff

to assist with providing information needed by the projects and

acquiring and distributing information generated by the projects.

WDFW	1	No work planned; available as needed and as prioritized.

Objective	4	Services to Fish and Wildlife Program Activities

Task	5	Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas dataset, b) archive the official version as a historic

record, and c) in consultation with the Council, respond to requests for information concerning Protected Areas

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

MFWP	1	Participate at whatever level is requested by StreamNet regional staff 	As needed	Participation	staff

and/or the Council.

Region	1	Maintain the existing Protected Areas database.	Ongoing	Static db	Kinney

Objective:	4	Task:   5	10/01/00	Page 34 of 41

Objective	4	Services to Fish and Wildlife Program Activities

Task	6	Basin Data Needs

StreamNet will provide information and assistance to regional reviews of data management projects and data management needs

conducted by the PPC, ISRP, ISAB and other regional entities

Objective	4	Services to Fish and Wildlife Program Activities	Task   6        Basin Data Needs

Task	6.a	Data Management Needs

Work with regional entities to develop an analysis of regional data management needs, challenges and capabilities

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Participate on Council advisory committees to identify data needs and	4/1/01	Report	Roger, Oftedahl

data gaps

IDFG	1	Participate in discussions and coordination of basin data management 	Ongoing	Summarized in 	Butterfield

needs.	progress reports

MFWP	1	Provide review of any and all regional data management issues	ongoing	Report	Hess-Herbert

ODFW	1	Assist as needed with identifying data needs of the amended Fish and 	As needed	Cooney

Wildlife Program

Region	1	Encourage and work with regional entities to respond to the 	Ongoing	Participation and 	Schmidt

recommendations made by the ISRP database project review.  Assist 	assistance

with efforts to standardize data collection methods and develop

regional data priorities.

Region	2	Meet with regional data using agencies (state and tribal managers, 	11/30/00	Report	Schmidt

NMFS, USFWS, EPA, FS, BLM, etc.) to determine data and

information needs

SBT	1	Participate with steering committee in regional analysis of data needs	as requested	participation	Taki

WDFW	1	Participate in regional discussions of data needs and data management	Ongoing	O'Connor

strategies in support of the amended Fish and Wildlife Program.

Objective	4	Services to Fish and Wildlife Program Activities	Task   6        Basin Data Needs

Task	6.b	Data Needs Workshop

Promote organization of a regional 'data needs workshop' to establish regional data / information needs and priorities and to

develop recommendations for roles and responsibilities for acquiring and providing the needed data / information

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Assist in planning and conducting the workshop.	TBD	Workshop	Roger

MFWP	1	Participate if requested.	TBD	Workshop	Hess-Herbert

ODFW	1	Participate if requested.	TBD	Workshop	Cooney

Region	1	Organize and hold a meeting of the regional data management projects 	2/28/01	Meeting report	Schmidt

to discuss current activities and capabilities, investigate potential

duplication of effort, and develop a plan for coordinated activities to

meet regional data and information needs.

Objective:	4	Task:	6.b	10/01/00	Page 35 of 41

Region	2	Call for, and if successful, participate in, a regional workshop 	TBD	Workshop, 	Schmidt

designed to bring together regional, state and tribal agencies to 	followed by report

establish data and information needs, determine data and information

priorities, and determine a coordinated regional approach to

developing and providing the priority data and information.

SBT	1	Participate if requested.	TBD	Workshop	Taki

WDFW	1	Assist Regional staff as needed.	TBD	Workshop	O'Connor

Objective	5	Project Management / Coordination

Provide effective leadership that ensures the production of high quality products targeted at critical

applications and the development of these products in a timely, cost-effective manner.

Objective	5	Project Management / Coordination

Task	1	Manage Project Activities

Administer all aspects of the project at the regional and sub-contractor levels, including oversight of budget, personnel, work

statement preparation and implementation, coordination among participating agencies, active participation in steering committee

work, and project reporting

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Provide normal supervision of StreamNet Library staff and the CRITFC	Ongoing	Supervision	Roger

database Programmer.

CRITFC	2	Produce quarterly reports within 1 month after the end of each quarter	Quarterly	Reports	Roger

CRITFC	3	Produce final report within 2 months of the end of the contract period	11/31/00	Report	Roger

CRITFC	4	Participate in Steering Committee meetings	Ongoing	Participation	Roger

CRITFC	5	Collaborate on developing a final detailed Statement of Work for the 	6/30/01	Statements of Work	Roger

current contract and for the coming year	 and budgets

FWS	1	Represent FWS in Steering Committee meetings	Quarterly	Participation	Pastor

FWS	2	Produce quarterly reports w/in 30 days of quarter end	Oct., Jan., 	Quarterly report	Pastor

Apr., July

FWS	3	Produce FWS component of FY2000 final report	10/31/00	Final report	Pastor

FWS	4	Create FWS StreamNet budget & statement of work for FY2002	8/31/01	Annual Budget	Pastor

FWS	5	Contribute FWS portion of Project Renewal documents	5/30/01	Project renewal 	Pastor

documents

Objective:	5	Task:	1	10/01/00	Page 36 of 41

IDFG	1	Participate in Steering Committee activities. Manage all aspects of 	Ongoing	SOW, Q and A 	Butterfield

StreamNet in IDFG, including budget, personnel, and work 	reports, Budgets

management. Products will include:  Annual IDFG StreamNet work

statement; Quarterly and annual reports of progress; and,

Participation in Steering Committee activities.

MFWP	1	Administer all aspects of the project for Montana, including oversight 	Ongoing	Meetings, Q. 	Hess-Herbert,

of budget, personnel, work statement preparation and implementation, 	reports, 	staff

coordination, and project reporting. Participate in Steering 	participation

Committee.

ODFW	1	Administer all aspects of the project for Oregon, including budget 	Ongoing	Meetings, & 	Cooney

oversight, personnel, staff work plans, project implementation and 	project oversight

coordination, Steering Committee and technical issues meeting

attendance.

ODFW	2	Participate/attend appropriate training and conferences in order to 	As needed	Attendance & in 	All staff

enhance technical skills which are relevant to StreamNet's mission.	quarterly report

ODFW	3	Produce and provide a Statement of Work, budget proposal, quarterly 	Upon request	Documents and 	Cooney, Frazier

reports, and annual report for Oregon.	Reports

Region	1	Provide oversight for the StreamNet Program	Ongoing	Oversight	Schmidt

Region	2	Supervise StreamNet regional staff.  Provide training opportunities for	Ongoing	Training	Schmidt

project staff to further their technical development and capabilities.

Region	3	Develop program budgets and manage / monitor expenditures	Ongoing	Budget	Schmidt

Region	4	Coordinate with other regional data management projects to 	Ongoing	Coordination	Schmidt

coordinate and cooperate to maximize data and information flow,

maximize complementary aspects, and to avoid duplication of effort.

Region	5	Coordinate with data collecting agencies and organizations to 	Ongoing	Coordination	Schmidt

determine data availability and encourage data and information being

made public.

Region	6	Coordinate with regional management agencies / entities and data 	Ongoing	Coordination	Schmidt

using entities to determine information and data service needs and to

assure rapid response to reasonable data and information needs.

Region	7	Produce quarterly reports within 1 month after the end of each quarter	Quarterly	Q. reports	Schmidt

Region	8	Produce final report within 2 months of the end of the contract period	11/31/00	A. report	Schmidt

Region	9	Manage and serve the StreamNet Steering Committee through:  	Quarterly, and	Meetings, meeting 	Schmidt

Organizing and conducting committee meetings at least quarterly; 	 ongoing	notes, consultation

Calling additional meetings as needed to address timely issues; and,

Actively consulting with Steering Committee on program activities

Region	10	Prepare a project proposal and Statement of Work for FY2002.	5/31/01	Proposal	Schmidt

SBT	1	Produce quarterly reports within 1 month after the end of each quarter	Quarterly	Report	Taki

SBT	2	Produce final report within 2 months of the end of the contract period	11/31/01	Report	Taki

SBT	3	Participate in Steering Committee meetings	quarterly	meeting	Taki

Objective:	5	Task:	1	10/01/00	Page 37 of 41

WDFW	1	The WDFW StreamNet state coordinator will participate in all 	9/30/01	Q & Ann reports, 	O'Connor,

Steering Committee and StreamNet Project management activities. The 	meeting notes,

state coordinator and the state data manager will jointly manage all 	budgets, SOW,

aspects of StreamNet in WDFW, including budget, personnel, work 	data

scheduling, and product delivery.

Objective	5	Project Management / Coordination

Task	2	Participate in Fish and Wildlife Program Development Activities

Organize, facilitate, and/or participate in appropriate coordination meetings with BPA, CBFWA, the Council, ESA officials,

ISAB/ISRP, and/or staff and management of participating organizations aimed at identifying ways that StreamNet might more

effectively contribute to the Fish and Wildlife Program (FWP). Participate in advisory groups, task forces, and other groups whose

purpose is enhancing the effectiveness of the Fish and Wildlife Program and its data development activities.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Participate in appropriate coordination meetings with BPA, CBFWA, 	As needed	Identify SN 	Roger, Forrest

the Council, ESA officials, ISAB/ISRP, and/or staff and management of

participating organizations aimed at identifying ways that StreamNet

might more effectively contribute to the Fish and Wildlife Program.

CRITFC	2	Where appropriate, participate in advisory groups, task forces, and 	As needed	Improved SN 	Roger, Forrest

other groups whose purpose is enhancing the effectiveness of the Fish 	services

and Wildlife Program and its data development activities, with

particular emphasis on subbasin planning and R/M/E issues.

IDFG	1	Participate in appropriate coordination meetings with BPA, CBFWA, 	Ongoing	Summarized in 	Butterfield

the Council, ESA officials, ISAB/ISRP, and/or staff and management of 	progress reports

participating organizations aimed at identifying ways that StreamNet

might more effectively contribute to the Fish and Wildlife Program.

IDFG	2	Where appropriate, participate in advisory groups, task forces, and 	Ongoing	Summarized in 	Butterfield

other groups whose purpose is enhancing the effectiveness of the Fish 	progress reports

and Wildlife Program and its data development activities.

MFWP	1	Participate in appropriate coordination meetings with BPA, CBFWA, 	As needed	Participation, 	Hess-Herbert

the Council, ESA officials, ISAB/ISRP, and/or staff and management of 	assistance

participating organizations aimed at identifying ways that StreamNet

might more effectively contribute to the Fish and Wildlife Program.

ODFW	1	Participate in activities aimed at identifying ways that StreamNet 	As needed	Details in quarterly	Cooney

might more effectively contribute to the Fish and Wildlife Program, 	 report

including participation in Fish and Wildlife Program advisory groups

and applicable regional policy, planning, and management forums.

Region	1	Participate in appropriate coordination meetings with BPA, CBFWA, 	As needed	Participation	Schmidt

the Council, ESA officials, ISAB / ISRP, and/or staff and management

of participating organizations aimed at identifying ways that

StreamNet might most effectively contribute data / information and

support to the FWP.

Objective:	5	Task:	2	10/01/00	Page 38 of 41

Region	2	Where appropriate, participate in advisory groups, task forces, and 	As needed	Participation	Schmidt

other groups whose purpose is enhancing the effectiveness of the Fish

and Wildlife Program and its data development activities.  Areas of

particular emphasis are a) participation in FWP monitoring and

evaluation activities, and b) exploring opportunities for integration of

StreamNet data exchange formats into Fish and Wildlife Program

contract terms and conditions.

SBT	1	Participate in appropriate coordination meetings with BPA, CBFWA, 	As needed	Participation	Taki

the Council, ESA officials, ISAB/ISRP, and/or staff and management of

participating organizations aimed at identifying ways that StreamNet

might more effectively contribute to the Fish and Wildlife Program.

SBT	2	Where appropriate, participate in advisory groups, task forces, and 	As needed	Participation	Taki

other groups whose purpose is enhancing the effectiveness of the Fish

and Wildlife Program and its data development activities.

WDFW	1	No specific work planned; available as needed for coordination (see 	As needed	O'Connor

related work under Tasks 1.6, 2.2, 2.7, 4.2a, 4.7a).

Objective	5	Project Management / Coordination

Task	3	Coordinate with Other Related Activities

As needed, produce public information materials including updated versions of the project brochure, computer demonstration

materials, and/or other appropriate materials

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Seek closer cooperation, coordination, and consistency of information 	Ongoing	Coordination	Roger, Forrest

management practices and standards between salmon restoration

programs in the Columbia Basin (e.g. Mid-Columbia PUD's, LSRCP)

by participating on appropriate work groups.

CRITFC	2	Promote greater regional and national coordination of information 	Ongoing	Coordination	Roger, Forrest

management applications at appropriate professional meetings.

IDFG	1	Coordinate with regional and state-level fish and wildlife activities 	Ongoing	Summarized in 	Butterfield

that have relevance to the goals and objectives of StreamNet.	progress reports

MFWP	1	Maintain communication, help coordinate activities with Montana 	Ongoing	Activities 	Hess-Herbert

Department of Natural Resources, Department of Environmental 	summarized in

Quality and the Natural Resource Information System as they relate to 	quarterly reports.

StreamNet activities.  Participate in appropriate conferences by

preparing papers and giving presentations.

ODFW	1	Establish / maintain working relationships with data collection 	As needed	Enhanced data flow	Cooney

projects within and outside ODFW to promote efficient and beneficial 	 into StreamNet

data sharing.

Region	1	Coordinate the efforts of the StreamNet project with other data 	Ongoing	Complimentary 	Schmidt

compilation projects occurring in the region.  Address issues of data 	programs

gaps, duplication of effort, data set integration, georeferencing

standardization, scientific rigor, management needs, etc.

Region	2	Organize an annual meeting of regional data compilation projects to 	7/1/01	Meeting	Schmidt

facilitate coordination and communication.  See Task 4.7.b.

Objective:	5	Task:	3	10/01/00	Page 39 of 41

WDFW	1	Maintain working contact with Washington Hydro Framework 	Ongoing	Updated 	Hudson,

partners and USGS Regional Ecosystem Office staff to promote 	hydrology and db	O'Connor

effective sharing of hydrology base layers and attached fish and

habitat data.

Objective	5	Project Management / Coordination

Task	4	Prepare Public Information Materials.

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities to identify

means for collaborative data collection, storage, and dissemination. Collaborative data activities will target tribal fishery programs

within the Columbia Basin, federal land managers’ fishery programs, state fish and wildlife agencies, and, with respect to water use

and stream development, state water resource management agencies. Collaboration with coast-wide and private data

collection/compilation efforts will be pursued when this supports overall project goals. Areas of particular emphasis are 1)

participation in Fish and Wildlife Program monitoring and evaluation activities, and 2) exploring opportunities for integration of

StreamNet data exchange formats into Fish and Wildlife Program contract terms and conditions.

Objective	5	Project Management / Coordination	Task   4        Prepare Public Information Materials.

Task	4.a	Prepare Public Information Materials

As needed, produce public information materials including updated versions of the project brochure, computer demonstration

materials, and/or other appropriate materials

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	Produce and update a Library brochure and Access guide listing 	9/30/01	Library brochure, 	Oftedahl

services, hours and cost recovery fees.	Access guide

MFWP	1	Montana will participate in review and recommendations.	As needed	Participation	Hess-Herbert

ODFW	1	Write informational articles on StreamNet data activities for natural 	As needed	Published articles, 	All staff

resource oriented publications and give oral presentations to relevant 	and presentations

user groups.

ODFW	2	Develop an informational PowerPoint presentation about the SN 	7/31/01	PowerPoint	Cooney

Region	1	Update the existing StreamNet brochure	7/31/01	Brochure	Schmidt

Region	2	Create improved web page help files to assist users in understanding 	9/30/01	Updated help files	Staff

and making better use of StreamNet information.

Region	3	Create a demonstration of the data and services available by 	12/1/00	Demonstration 	Banach, Graves,

StreamNet.  Update this presentation as necessary.  Materials 	materials	Schmidt

developed will be for presentations covering the data and services

provided by StreamNet, and how to use the StreamNet web site to

obtain data.

Objective:	5	Task:	4.a	10/01/00	Page 40 of 41

Objective	5	Project Management / Coordination	Task   4        Prepare Public Information Materials.

Task	4.b	Participate in informational meetings/conferences

Participate in appropriate state, regional, and national educational and professional conferences, including, where applicable, giving

presentations, preparing poster session materials, and contributing to conference proceedings.

Project      	Planned work elements                                                 	Date Due	Deliverable     	Lead              	Comments

CRITFC	1	See task 3.5

IDFG	1	Participate in state, regional, or national educational or professional 	Ongoing	Summarized in 	ID Staff

conferences. 	progress reports

IDFG	2	Serve as chairman and organizer for the 2001 ArcInfo User's Group 	Ongoing	Summarized in 	Butterfield

Conference scheduled for October 2001.	progress reports

MFWP	1	Participate as opportunities arise to highlight StreamNet programs & 	As needed	Participation	Hess-Herbert

ODFW	1	Participate in appropriate meetings & conferences as opportunities 	As needed	Participation 	Cooney

arise to highlight StreamNet programs & data

Region	1	Participate in appropriate meetings to explain the StreamNet project, 	As 	Participation	Schmidt

solicit new data and information, or to present relevant data from the 	opportunities

SN database.	arise

Region	2	Represent StreamNet in relevant state, regional and national meetings 	Ongoing	Participation	Schmidt

and conferences.

WDFW	1	Participate as opportunities arise to highlight StreamNet programs & 	As needed	Participation	O'Connor

Objective:	5	Task:	4.b	10/01/00	Page 41 of 41