StreamNet Quarterly Progress Report

(October - December 1997)

Submitted to:

Bonneville Power Administration

Submitted by:

Pacific States Marine Fisheries Commission

Contents

I.	Columbia River Inter-Tribal Fish Commission

II.	Idaho Department of Fish and Game

III.	Montana Department of Fish, Wildlife & Parks

IV.	Oregon Department of Fish and Wildlife

V.	Pacific States Marine Fisheries Commission

VI.	Shoshone-Bannock Tribes

VII.	U.S. Fish and Wildlife Service

VIII.	Washington Department of Fish and Wildlife

I.  Columbia River Inter-Tribal Fish Commission

PERIOD HIGHLIGHTS

Cataloging

StreamNet Library References Module:  Cataloged 127 new StreamNet documents.

Textworks catalog: 477  records were cataloged on OCLC and added to the library catalog; 115 maps were cataloged directly onto DBTextWorks.

Collection Management

IAMSLIC duplicate exchange program: received 45 needed journal issues and technical reports.

Other exchanges: donated 236 journal issues to NRIC libraries and 5 boxes of materials to Yakama/Klickitat Fisheries Project library.

Created space for the NWPPC collection and made further plans for receiving these materials.

Processed and shelved cataloged materials; completed routine shelf-reads.

Services

Continued to provide reference, online search,  and interlibrary loan services (see statistics).

Meetings/Training

Attended October StreamNet steering committee meeting (Gretta, Phil).

Participated in OCLC Interlibrary Loan workshop in October (Krista).

Continued to meet with CRITFC ESU committee to enable improved library support in this area (Krista).

Met with fisheries staff at Yakama and Warm Springs (Hilary, Phil).

Data Compilation

Compiled and delivered 24 new trends from Yakama Fisheries Program.

Miscellaneous

Wrote quarterly project report.

Advertised for Assistant Librarian Position and reviewed applications.

Evaluated potential for increasing watershed support in FY98 as per NPPC recommendation; deferred for scoping in 1998 for implementation in FY99.

Revised library web page

Worked with Duane and Doug on re-vamping library query system.

Selected, purchased, framed and installed new artwork for StreamNet Library (funded outside of StreamNet).

LIBRARY STATISTICS

Reference requests:  conservative estimate: 134  liberal estimate: 178

(note: approximately 1/3 - 1/2 of reference requests do not get logged in detail)

Interlibrary loan requests: 62

Circulation:  journals - 8,   books, videos, maps and technical reports - 115

Photocopy usage: 1051 - CRITFC staff;  53 - NMFS staff;  194 - public/other

INFORMATION REQUEST LOG   (note: does not include most ILL requests)

| Requestor | Affiliation | Nature of Request | Action |
| --- | --- | --- | --- |
| Lance Kruzic | NMFS | streamnet document and journal articles | assisted on site |
| Starla Dill | CRITFC | Federal Register Contents, week of 9/29 |

provided

| Starla Dill | CRITFC | 2 documents from Federal Register | provided |
| --- | --- | --- | --- |
| Irene Voigt | USFS Library-Ogden, UT | specialized literature search | provided |
| Scherri Sotomish | CRITFC | locations for newspapers from small Co. River. towns | Referred to Multnomah Co. Lib.Newspaper room |
| Inez Hopkins | BioAnalysts - lib | ODFW doc. | referred to ODFW library |
| Inez Hopkins | BioAnalysts - lib | zone 6 tribal salmon prices 1975-1995 | provided |
| Nan Murch | PSU | financial info re: Col. Basin fisheries expenditures | referred to BPA |
| David Johnson | Nez Perce | Chapman document | had Inez send him a copy |
| John Hawksworth | S.P. Cramer | ODFW document | referred to ODFW |
| Starla Dill | CRITFC | Federal Register Contents 10/6-16 | provided |
| Starla Dill | CRITFC | 4 documents from Fed Reg. | provided |
| Bob Ellis | Consultant | documents and articles | assisted on site |
| Sean ? | public | info on Grande Ronde tribe | provided guidance |
| Ted Gresch | Interrain Pacific | assistance with catalog searching | provided |
| Starla Dill/Laurie Jordan | CRITFC | training on GPO Wais client | provided |
| Bob Ringo | CRITFC | EPA water quality criteria | provided |
| Dale McCullough | CRITFC | Keizer flood info | assisted with use of Oregon Index |
| Bob Ringo | CRITFC | Juvenile fish transport docs. | provided |
| Bob Ringo | CRITFC | SOR - anadromous volume | provided |
| M. McClure | CRITFC | citation verification | provided |
| Ken Collis | CRITFC | NW Fishletter | provided via WWW |
| Stephanie Fiereck | attorney/NWF | training on research strategies | provided |
| Stephanie Fiereck | attorney/NWF | 11 documents | assisted on site |
| Stephanie Fiereck | attorney/NWF | 5 documents | 1 provided, 4 referred |
| Jen Bayer | USGS-BRD | library orientation | provided |
| Rob Laird | David Brown & Assoc. | habitat quality at specific reaches | refereed to Duane, CBFWA for copy if Sandy R. sub-basin plan |
| Al Evans | CRITFC | citation verification | provided |
| Mara Scantlebury | BPA library | document for Kalispells | advised of holdings |
| Blaine Parker | CRITFC | Federal Register document | provided |
| Inez Hopkins | BioAnalysts | info on Brownlee/Oxbow/Hells Canyon Dams | advised of holdings |
| Jim Turner | NMFS | library orientation | provided |
| Steve Cramer | Consultant | 4 documents | 2 held and provided; 2 requested from elsewhere and provided |
| Rosemary Siefried | National Park Service, Seattle | Idaho document | left message that we had it, patron did not request further |
| Kevin Ford | NMFS, Seattle | CRFMP | left message, patron did not request further |
| student | Linfield College | cultural info and videotapes | referred to Linfield ILL |
| Heather Shaw | Warm Springs | 'everything on the Deschutes' | assisted on site |
| Wade Myers | BPA (purpose was private) | May '97 Fishing Rights doc. from CRITFC | not provided, discretionary document (as per policy dept); gave alternatives |
| Darren Brumbaugh | BLM, Prineville | 2 library docs, 2 CRITFC docs | sent 2, referred to authors for others |
| John Fenker | BPA Library | PNRS documentation | supplied what we could and referred |
| Skip ? | public | etymology question re: coho | answered |
| Mark Yoshinaka | USFWS | document request and access to IDFG pubs listing | provided |
| Leslie Bach | Oregon Water Trust | document | not held - gave referral info |
| Jim Welter | Port of Brookings Salmon Advisory Committee | data query | assisted and referred to Duane |
| Alan Ruger | BPA | WWW full text NMFS document | not available this way |
| Inez Hopkins | BioAnalysts- Lib | consultation | provided |
| Nina Rabin | Harvard University | orientation, use of library, tribal materials re:hatcheries | assisted |
| Ken Thompson | NMFS Seattle | document request | lent |
| Jon Rhodes | CRITFC | reference question re: journal | answered |
| Shelly Espeland | CRITFC | search assistance | provided |
| Sandra Peterson | CRITFC | procurement question | answered |
| Gary Morishima | Quinault Nation | CRITFC document | referred to authors |

PLANS FOR NEXT QUARTER

Library:

Hold an open house in (January).

Hire new assistant librarian (January).

Receive NWPPC collection.

Provide normal library services.

Data Management:

Continue to work with the Yakama Indian Nation to compile trend data.

Coordinate with WDFW in integrating WDFW-managed data from the Yakima Basin into StreamNet.

Coordinate with the Yakama Indian Nation in integrating non-standard data into StreamNet home page.

Begin the process of integrating Warm Springs Reservation data into StreamNet system.

Initiate discussions with Nez Perce and Umatilla tribes regarding initiation of data activities during the 3rd quarter.

II.  Idaho Department of Fish and Game

PERIOD HIGHLIGHTS

Completed 1997 draft spawning ground report

Completed and uploaded 1997 steelhead redd count information.

Completed data entry for 1997 spring and summer chinook updates.  Verification and editing nearing completion.

Completed lower Snake River area and began the mid-Snake sections of the SR3 Program for waterfowl data. Includes: compilation, analysis, verification, data entry and editing.

Completed resident fish distribution reference verification from IRIS.

Attended steering committee meeting.

Recruited and hired new Sr. Programmer Analyst.

Translated the anadromous distribution data into Arc/Info dynamic segmentation events.  Included a thorough update of the data using Fisheries official reach by reach smolt density notebook.  We need only two additional pieces of information, including: 1) distribution of fall chinook in Clearwater River from the Nezperce Tribe, and 2) information on portions of the Lemhi drainage with blocked but suitable habitat.  The anadromous distribution event tables have been formatted for uploading into the Department’s Oracle system, and will be uploaded with completion of the final pieces of information.

Beginning the process to convert bull trout distribution information to Arc/Info dynamic segmentation event tables.  Editting the preliminary events and to make sure they match the original source documents.

Developing a barriers layer by using the anadromous distribution event table.  Every event that stops short of a stream’s headwaters will be converted into a barrier point.  Each point will be attributed by LLID, measure, species, and barrier type as recorded in Fisheries smolt density notebook.

PLANS FOR NEXT QUARTER

Provide StreamNet update to IDFG anadromous fish managers.

Meet with GPM personnel to review and finalize Stream Survey database and entry program.

Continue work on barriers database.

In conjunction with SR3, begin development of lakes database system.

In conjunction with SR3, continue entry of waterfowl information.

Continue conversion of bull trout distribution to dynamic segmentation.

DATA REQUESTS

Record #  	date 		organization        	supplier          	data_type

204  	10/06/97 	IDEQ                     	E Brown      	GPM and Resdist. data

205  	10/16/97 	IDEQ                     	E Brown        	All GPM data for SALEFS

218  	10/02/97 	US BOR                	Butterfield      	CDC and fish dist data

219  	10/02/97 	Nezperce NF          	Butterfield     	streams for SF Clearwater

220  	10/02/97 	IDFG Region2       	Butterfield     	bull trout maps -digital

221  	10/15/97 	IDFG Fisheries      	Hartpence     	map of dams in CRB

222  	10/28/97 	IDFG CDC            	Hartpence      	map of EOs and Bailey ER

223  	12/1997  	USFS			Butterfield	bull trout maps - digital

III.  Montana Department of Fish, Wildlife & Parks

PERIOD HIGHLIGHTS

Objective 1 - Data Acquisition

Resident Fish

The culmination of a 10 year update to the MRIS resident fish database occurred with the rating of all stream reaches with fish species present and their reclassification by sport fisheries and species and habitat values (redo of Montana Rivers Study).  Materials for review were sent to all MFWP biologists included a map displaying the 1987 classification and the preliminary 1997 classification, a report explaining the fish species present and other fields used in the rating process and a new Assessment Guidelines.  Packets were sent in November.  Extensive data cleanup occurred in preparation for rating of stream reaches and review of data and ratings by biologists is providing further data correction and documentation.  Continued on bull trout update; received all edit maps back from USFS and MFWP fisheries biologists.

Created metadata for many of the coverages we have created and sent to the Natural Resource Information System (NRIS).  Historic distribution data table is completed until conversion to LLID when new data sources will be entered.  Updated MRIS Protected Areas database to insure all river reaches where splits had occurred in the last 5 years were included.  Began clean up work on the MRIS barriers database and discovered  that the spatial and tabular files were poorly related.

Aquatic Mitigation and Restoration Projects

Added this table to MRIS restructure design; will determine how it will be incorporated.

Data Reference

Continuing to search for library technician to begin work on referencing of documents in MFWP Fisheries Library in Helena.

Objective 2 - Data Management

Continued work on the restructure of MRIS databases to Access and using PSMFC data exchange formats. Met with software developer in Helena and sent him data structures and other support documents to begin estimating cost of new edit/entry program (MFWP will pay for software development).  Data collection will be by LLID.

As part of restructure, related FISHSPEC.DBF (fish species distribution database for Montana) to the databases containing survey data (genetic analysis, natural production counts, and population trend data);  new system will make survey records mandatory for each species distribution record.  Will also convert FISHSPEC to a trend database similar to PSMFC for tracking a species in a reach over time.

Objective 4 - River Reach System

Kept abreast of NHD activities through StreamNet website.  Discovered that USFS Region 1 had completed routing and assigning LLIDs to several forests in western Montana using all the named streams in the 1:24000 hydrography.  Received sample HUC (17010202, Rock and Flint Creek) from Brian Sanborn, USFS contact, and compared to 1:100 000 line work,  the number assigned and stream name given.  Work looks good and involved PSMFC regional data and GIS coordinators in discussion as to how to proceed.  Will defer entering new fisheries data into MRIS until conversion to LLID is completed.

Objective 5 - Data Delivery

Sent shape files of  Montana’s species of special concern to PSMFC Regional data coordinator to include on the website.

Continued to work on developing a web-based version of the MRIS database.

Successfully tested using simple html forms to retrieve data from Microsoft Access databases.

Objective 6 - Project Management/Coordination

Have been asked to give a presentation on StreamNet at the Annual Montana/Idaho GIS User’s Conference in Butte on April  27-29.  Have been given the responsibility for GIS Coordination for MFWP; duties (which are funded by the department) have included inventorying current use/hardware/software; assessing needs that can be met with current budget and needs that will require expansion of budget; and representing the department on the NRIS Advisory Committee and the GIS Technical Working Group.  Position will also elevate the work of StreamNet. Using MFWP funding, have completed the spatial coverage of our Wildlife Management Areas and completing hard copy atlases; digital files for MFWP brochure of Fishing Access Sites; and map production for a Roads Assessment of State Parks.  All of these products carry the StreamNet logo!

PLANS FOR NEXT QUARTER

Complete Fisheries stream rating process and provide to PSMFC for posting on web site.

Begin update of barriers database, clean up resident fish hatchery facilities database, and begin exploring a prototype test of data on irrigation diversions.

Begin work on restoration database coordinating with MFWP Future Fisheries Coordinator, Mark Lere;  create edit/entry or wait for regional product.

Complete bull trout edit and send to USFWS in Portland and update maps distributed around state in the past.

Link Dams database from PSMFC to MRIS. Attend Region 1 USFS meeting in Missoula with all Fisheries Program Managers to discuss LLID issue at different scales.

Continue discussions with PSMFC regional data and GIS coordinators to insure conversion process of LLIDs between scales has no problems.

Begin routing 1:100 K hydrography for western Montana.

Attend Montana Chapter American Fisheries Society and meet with USFS fisheries biologist to discuss 1:24000 hydrography and LLID issues.

Attend MFWP Fisheries Division meeting and discuss data standards and habitat variables with MFWP biologists.

Explore interactive mapping of fisheries ratings system using NRIS staff.  Complete metadata for all data layers created here and send to NRIS and PSMFC.

DATA REQUESTS / RESPONSE LOG

General Data Requests

Request for fisheries information on the Middle Clark Fork and Ninemile.

Request for fisheries and wildlife information on Cedar Creek and Smith, Sun, and the

Bitterroot Rivers.  Also wanting information on Swamp Creek.

Request for all information on Clark Fork and St. Regis for proposed pipeline.

Request for fisheries and wildlife information for Swamp Creek-2590000 and Wise River.

Request for all information on the Smith River above Eagle - River Reach # 06077200.

GIS Log (services mostly funded through MFWP)

Date	By	For	Agency	Hours

10/13/97	Lydia Bailey	Bruce Sterling	MFWP - Region 1	0.25

Provided technical assistance for using township, range, and section values to generate spatial data.  Instruction for setting up tabular database necessary to generate spatial database.

10/14/97	Lydia Bailey	Kevin Chappell	DNRC	5

Statewide map of big horn sheep overall distribution, winter core areas, summer core areas with land ownership (Nat'l Forests labeled), hydrography, highways, cities.  To be used in review of grazing leases.  Sent large and small copies.

10/16/97	Lydia Bailey	Wildlfe Managers	MFWP - All Regions	2

Updated mule deer and white-tailed deer monitoring location maps.  Maps also include special mgmnt districts, population mgmnt units, hydrography, hunting districts, cities, highways, Indian Reservations, National Parks.

10/16/97	Lydia Bailey	Tony Jewett	MT Wildlife Fed.

Sent copies of statewide big horn sheep distribution maps.

10/20/97	Angie Schmidt	Kathy Jewel	BLM

Sent her the latest copy of our statewide hydrography,  MRIS database files, and metadata files.

10/21/97	Angie Schmidt	Bill Schultz	DNRC	4.5

Produced Three maps for Bill displaying the Upper Missouri drainage Westslope Cutthroat Trout Genetic Distribution with public land ownership, cities,  and roads.

10/22/97	Lydia Bailey	Ray Heagney	MFWP - Region 3	0.5

Provided ArcView shape files for Missouri Headwaters State Park.

10/23/97	Lydia Bailey	Brian Richards	MFWP - Region 4	3

Wall maps of Brinkham Game Preserve.  One with public land ownership and  the other with shaded relief.  Both maps also included hydrography, roads, and preserve boundary.

10/24/97	Angie Schmidt	Gael Bissell	MFWP - Region 1	44

Digitized game preseves withing Deer/Elk Hunting District 170.  Produced 2- 8.5x11 black and white maps of HD 170 displaying the landownership,roads, cities, hunting district boundaries, game preserves, and hunting closures.

10/27/97	Angie Schmidt	Brian Peck	MT Wild Forever	0.3

Requested a wall size map of the Swan River Drainage displaying public land ownership, and Westslope Cutthroat Trout Genetic Distribution.

10/27/97	Angie Schmidt	Val Jaffe	Maxim Technologies	2

Requested  State Fishing Access Sites and non-state Fishing Access Sites, State Parks, Wildlife Management Area Points,  and the recreation database for  portions of the Middle Clark Fork Drainage,  Lower Clark Fork Drainage, and L. Flathead Drainage

10/30/97	Lydia Bailey	Marty Watkins/Darlene Edge	MFWP

Wall map of Thompson Chain of Lakes area with public land ownership, Plum Creek lands,  detailed roads, hydrography, and Plum Creek  lands FWP would like to acquire, FWP lands available for trade, and FWP lands Plum Creek would acquire.

10/31/97	Lydia Bailey	Eric Atkinson	OEA Research Inc	0.5

Sent copies of 8.5 x 11 maps of Treasure Mountain proposed  ski area vicinity with shaded relief, big game winter ranges, hydrography, roads, and cities.

10/31/97	Lydia Bailey	Dale Carlsen and Lee Bastian	MFWP - Region 2	0.25

Used GIS to determine square miles of Parks' administrative regions.

11/5/97	Lydia Bailey	Brad Shepard	MFWP - Region 3	2

Used Arc/Info GRID to generate elevation, slope, and aspect by short_rrn for streams within  the Flint-Rock, Boxelder, and Upper Clark Fork drainages.

11/5/97	Jeff Hutten	Jim Vashro	MFWP - Region 1	1

Bull trout spawning map for the Kootenai drainage.

11/12/97	Lydia Bailey	Paul Valle	MFWP - Helena	0.25

Generated latitude and longitude for the section corner of sections 8, 9, 17, 16 in Township 04 North, Range 23 East.

11/12/97	Lydia Bailey	Jim McGowan	Damschen & Associates	5

Converted Arc/Info data to .dxf format.  Seven sets of data - one for each FWP region.  Each set contained the following data:  regional boundary, counties, roads, streams, cities.

11/12/97	Jeff Hutten	Jeff Copeland	MFWP - Helena	1

WordPerfect 6.1 file of full output of Parks Report on diskette.

11/12/97	Jeff Hutten	Ron Rhew	USFWS	0.5

Bull trout data (mt_bull.tar.Z) ftp:164.159.7.175  ron_rhew@fws.gov

11/17/97	Angie Schmidt	Donna Leeper	DNRC	24

Requested the statewide hydrography layers along with the MRIS databases.  FTP'd the data to : flathead.dnrc.mt.gov.

11/17/97	Angie Schmidt	Leanne Hennessy	Montana State Univ

Requested the Upper Yellowstone Drainage hydrography layers (10070001, 10070002) in a shapfile format for use in ArcView 3.0.   email:  glh3334@montana.edu.

11/17/97	Angie Schmidt	Carol Fisher		1

Sent Carol MRIS stream list for the Upper Yellowstone, Stillwater, Clarks Fork of the Yellowstone,  Flint Rock, Powder River Drainages, and Fishing access site maps for  Regions 1, 2, 3, 5, 7.

11/20/97	Jeff Hutten	Duane Anderson	PSMFC	5

Species distribution coverages for western Montana: species 001, 003, 004, 005, 012, 090, 122, and 133.

11/20/97	Lydia Bailey	James Colegrove	Maxim Technology	0.5

Sent copies of my comments on the Backes Game Farm EA and Maxim Technology's use of FWP's big game GIS data.  Also sent metadata for big game GIS data and verbally explained the process for correctly querying and displaying the data.

11/25/97	Lydia Bailey	Don Childress	MFWP - Helena	3

Provided acres, square miles, and percent of types of land ownership by deer/elk hunting district.  Analysis was performed in the Arc module of Arc/Info.

11/25/97	Lydia Bailey	Chris Lorentz	MFWP - Region 7	6

Maps of 1996 and 1997 noxious weed infestations collected using GPS in Makoshika State Park.  Maps also included public land ownership, Makoshika park boundary, hydrography and detailed roads.

11/25/97	Angie Schmidt	Jon Winkelried	Private Consultant	1

Provided a full stream report of  Deep Creek in the Teton Drainage.

12/1/97	Lydia Bailey	Ross Baty	DNRC	1

Provided two copies of statewide big horn sheep distribution map (one small, one large) with herd names, public land ownership, hydrography, highways,  and cities.

12/2/97	Lydia Bailey	Brian Giddings	MFWP - Helena	12

Generated spatial data of lynx locations based on township, range, and section locations.  Produced map depicting lynx locations using a range graded scaling method to illustrate locations with more than one lynx occurence.

12/3/97	Angie Schmidt	Rick Malta	MFWP - Region 1	1.5

Black and white, 8.5"x11" map of the Hungry Horse Reservoir revegetation sites.

12/3/97	Lydia Bailey	Ross Campbell	DNRC	1

Provided electronic copy of statewide big horn sheep distribution and public land ownership map in Adobe Illustrator format.

12/4/97	Lydia Bailey	Jon Schulman	USDA Forest Service	0.5

Sent copy of metadata for big game GIS layers.  Data will be used for the Yellowstone Pipeline EIS.

12/8/97	Angie Schmidt	Kevin Redmond	MFWP - Helena	1

Provided a statewide copy of  black and white 17"x11" maps displaying roads, cities, hydrography, and counties.

12/8/97	Angie Schmidt	Jim Darling	MFWP - Region 5	8

Provided a wall size map of the high moutain lakes within MFWP Region 5.  The map displayed public land ownership, plss,  lake watercode, and lake name.

12/10/97	Lydia Bailey	Glenn Erickson	MFWP - Helena	12

8.5 x 11 black and white maps of mule deer and white-tailed deer monitoring locations with special management units, population units, hunting districts, hydrography, counties, and cities.  One map for each species.

12/16/97	Jeff Hutten	John Woods	Plum Creek	1.5

Tabular data (ASCII delimited) for species 122 and 012 for western Montana and   hydrography.

12/17/97	Lydia Bailey	Brian Peck	MT Wilderness Assoc	16

One with USFS grizzly bear linkage zones, grizzly bear subunits, and roadless security areas.  One map with bull trout core areas and USFS old growth areas. One map depicting areas of overlap of at least 4 out of the 5 layers named above.

12/18/97	Lydia Bailey	Melissa Hart	MFWP Lab	0.5

Sent updated version of State Parks GIS layer and metadata.

12/19/97	Lydia Bailey	Gael Bissell	MFWP - Region 1	4

Wall map of proposed interest areas in the Thompson and Fisher drainages with land ownership, hydrography, highways, cities, and public land survey system.

12/21/97	Angie Schmidt	Gael Bissell	MFWP - Region 1	5

Two color  8.5"x11" maps of the Ray Kuhns Wildlife Management Area vicinity.  One map displays White-tailed deer density along with roads, hydrography, and plss.  The other displays White-tailed deer winter range and public  land ownership.

12/29/97	Lydia Bailey	Glenn Erickson	MFWP - Helena	2

Updated mule deer monitoring location GIS data and sent maps to all regional wildlife managers reflecting the changes.

12/30/97	Lydia Bailey	Tom Reilly	MFWP - Helena	10

Modified regional state fishing access site maps for brochure.  Converted to Adobe Illustrator format.   Worked with pre-press technical staff in layout for 4 color process negatives for printer.

12/30/97	Lydia Bailey	Ray Heagney	MFWP - Region 3	1

Provide UTM 12 projected Arc/View shape files for Bannack, Parker Homestead, and Lewis & Clark Caverns state parks.  Also sent hard copy maps for reference.

12/30/97	Lydia Bailey	Kathy Jewell	BLM	1

Sent fishing access site point GIS data and metadata.

12/31/97	Angie Schmidt	Bill Viste	MFWP - Region 6	3

Two black and white, 8.5"x11" maps. One of Fresno Reservoir and the other of Nelson Reservoir.  Each map displays  the surrounding Bureau of Reclamation land ownership.

IV.  Oregon Department of Fish and Wildlife

PERIOD HIGHLIGHTS

Delivered several directories of event tables to PSMFC (Forsberg; Task 1.1).

Completed process of developing dbase programs to convert coastal coho distribution files into StreamNet format, combining them into one info file and distributed them to PSMFC (Forsberg; Task 1.1).

Completed final rectification Coho maps for Upper Rogue, Mid-Rogue, Illinois, and Applegate Basins and sent them to Steve Jacobs for final review (Forsberg; Task 1.1).

Compiled information on hatchery returns of adult and jack fall chinook by stock for Columbia Basin hatcheries upstream of Bonneville Dam. (Tinus; Task 1.1)

Compiled monthly Columbia Basin tributary sport harvest of fall chinook salmon by stock from monthly punch card estimates prior to 1970 in Oregon and 1964 to 1996 for Washington for fall chinook run reconstruction. (Tinus; Task 1.1)

Compiled information on natural spawning escapement by stock of fall chinook salmon adults and jacks for Columbia Basin tributaries in Washington upstream of Bonneville Dam. (Tinus; Task 1.1)

Compiled age composition data on early fall commercial fishery harvest, 1960 to present. (Tinus; Task 1.1)

Compiled Indian dip net harvest of fall chinook salmon in the Klickitat River (Tinus; Task 1.1)

Compiled spawner/recruit information for spring chinook salmon populations in Idaho, Oregon, and Washington (Tinus; Task 1.1)

Delivered two Map Gallery examples for web page  to PSMFC (Forsberg; Task 1.1).

A total of 8 data, 49 document, 3 map/GIS related, and 5 other requests were answered during this quarter.  (All staff; Task 5.1)

Assisted StreamNet’s efforts to post a new Oregon Plan web page on the Internet by acquiring the necessary pieces of information.  (Cooney)

Prepared the remaining prototype species distribution atlas pages for the Northeast Region and solicited/received comments from several staff members. (Forsberg, Cooney; Task 5.7)

Continued to negotiate with Human Resources on the Information Systems Specialist reclass appeal for ODFW StreamNet GIS Specialist. (Cooney; Task 6.0)

One or more staff members attended 4 Oregon Plan coordination meetings. (Forsberg, Cooney; Task 6.1)

One or more staff members attended 3 essential project coordination meetings. (Forsberg, Cooney, Bourne; Task 6.1)

Developed quarterly report for Oregon. (Cooney; Task 6.2)

Reviewed and commented on new StreamNet Internet query tools. (Cooney, Tinus; Task 6.8)

Provided StreamNet Library with a list of journals and publications that should be made available on the Library website. (Cooney)

PLANS FOR NEXT QUARTER

Complete hiring process for ODFW StreamNet GIS Specialist. (Cooney, Schmidt)

Complete the hiring process for the ODFW tabular data specialist (Cooney)

Complete the coho distribution reconciliation for the Siltcoos, North Umpqua, and Chetco HUC’s. (Forsberg)

Modify and improve electronic Library request data entry system and continue to catalog pending and completed Library requests. (Cooney/Anderson/Bourne)

Provide updated adult abundance estimates and indices for anadromous species with available 1996 data. (Cooney)

Provide updated spawner-recruit data for PATH spring chinook run reconstructions. (Tinus, Cooney)

Provide 1996 age frequency data for natural spring chinook. (Tinus, Cooney).

Continue to answer information requests as received. (All).

DATA REQUEST/RESPONSE LOG

| DATE | REQUESTER | ORGANIZATION | REQUEST | Who Responded |
| --- | --- | --- | --- | --- |
| 10/1/97 | Don Bennett & Rob Laird | ODFW & David Brown and Associates | Aquatic Inventory data for Sandy River (Messinger Bottom area) | Cedric |
| 10/3/97 | Marv Yoshinaka | ?? | Lower Snake River data | Cedric |
| 10/9/97 | Leslie Sikora | WDFW | Oregon conventions for distinguishing steelhead vs. rainbow | CC/Barry McPherson |
| 10/16/97 | Susan Payne | Metro | Questions about finding/reporting fish streams in ORIS | Forsberg |
| 10/28/97 | Duane Anderson | PSMFC | Barriers data documentation, via fax | Forsberg |
| 10/30/97 | Rick Sheppard | Applied Ecosystem Services | ORIS download instructions | Forsberg |
| 11/3/97 | Holly Michael | ODFW-Clackamas | ORIS download instructions | Forsberg |
| 11/4/97 | Keith Hupperts | Defenders of Wildlife | Management coverages | Forsberg |
| 11/14/97 | Jerry Winterbothem | Private citizen | Tenmile Creek survey data | Cedric |
| 11/18/97 | Jennifer Budhabhatti | Metro Parks & Green Spaces | Fish Questions in the Metro area | Forsberg |
| 11/20/97 | Ted Williams | Steve Cramer & Assoc. | ORIS smolt carrying capacity questions | Forsberg |
| 11/25/97 | Nick Beer | Univ. of Washington | Oregon GIS data | Cedric |
| 12/9/97 | Pat Keeley | ODFW-Clackamas | Simple Sandy Basin Stream Map examples | Forsberg |
| 12/18/97 | June Johnson | Idaho Department of Fish and Game | 1996 returns to Imnaha & Looking Glass hatchery | Cedric |
| 12/18/97 | Jeff Peterson | EMCON (consulting firm) | Info on fish distribution data for contamination risks project study | Forsberg |
| 12/19/97 | Don Bennett | ODFW-Clackamas | Finalized 11x17 Sandy Basin map for watershed group | Forsberg |
| 10/9/98 | Scott Chitwood | Quinault Fisheries Division | document | Gloria |
| 10/15/98 | Kurt Reidinger | CompuServe | 2 documents | Gloria |
| 10/15/98 | Krista Shauer | CRITFC | 2 documents | Gloria |
| 10/16/98 | Dick Ewing | BioTech | 2 documents | Gloria |
| 10/20/98 | Inez Hopkins | BioAnalysts, Boise | document | Gloria/Cedric |
| 10/20/98 | Erling Westlien | Foster Wheeler Environmental | document | Gloria |
| 10/20/98 | Tom Harder | Max McGraw Wildlife Foundation | document | Gloria |
| 10/20/98 | Steven Shepard | Gomez & Sullivan Engineers, P.C. | document | Gloria |
| 10/20/98 | Erling Westlien | Foster Wheeler Environmental | document | Gloria |
| 10/20/98 | Jin-Won Seo | private | 5 documents | Gloria |
| 10/20/98 | Ann Garrett | private | 2 documents | Gloria |
| 10/20/98 | Brent Edwards | private | document | referred to CRITFC |
| 10/21/98 | Jon Bowers | Interrain Pacific | document | Gloria |
| 10/21/98 | John Hawksworth | SP Cramer & Assoc. | 2 documents | Gloria |
| 10/21/98 | Patricia Arentz | BLM/FWS Interagency Library | document | Gloria |
| 10/28/98 | Mary Barczak | Hebo Ranger District | 2 documents | Gloria |
| 10/31/98 | Kathy Hemtill | Davis & Evans Assoc. | 3 documents | Gloria |
| 10/31/98 | Krista Shauer | CRITFC | 3 documents | Gloria |
| 11/5/98 | Ken Witty | SP Cramer & Assoc. | document | Gloria |
| 11/5/98 | Ralph Browning | NOAA, Idaho | document | Gloria |
| 11/7/98 | Eleanor MacLean | Blacker-Wood Library of Biology, McGill University | 2 documents | Gloria |
| 11/7/98 | Tiffany ? | Accents Publications | document | Gloria |
| 11/7/98 | Judy | Library Acquisitions, Willamette University | document | Gloria |
| 11/7/98 | Eric Dahler | Historical Multimedia Productions, Inc. | 3 documents | Gloria |
| 11/10/98 | Inez Hopkins | BioAnalysts | document | Gloria |
| 11/10/98 | John Hawksworth | S.P. Cramer & Assoc. | document | referred to CRITFC, back to Gloria |
| 11/11/98 | Ann Garrett | Graduate student | 3 documents | Gloria |
| 11/14/98 | Sam Stephenson | Ontario Ministry of Natural Resources | document | Gloria |
| 11/17/98 | Steve Vigg | S.P. Cramer & Assoc. | document | referred to CRITFC & Eric Olsen@ Hood River |
| 11/18/98 | Allen Byrne | IDFG | document | Gloria |
| 11/18/98 | Dennis Rogers | student | 8 documents | Gloria |
| 11/18/98 | Ms. Amanda McClaire | John Smith & Son (Glasgow) Ltd. | document | Gloria |
| 11/18/98 | Steve Cramer | S.P. Cramer & Assoc. | 6 documents | referred part to CRITFC |
| 11/21/98 | Steve Cramer | S.P. Cramer & Assoc. | 8 documents | Gloria |
| 11/24/98 | Michael Jones | Cascade Geographics Society | document | Gloria |
| 11/26/98 | Steve Cramer | S.P. Cramer & Assoc. | 4 documents | Gloria |
| 11/26/98 | Steve Cramer | S.P. Cramer & Assoc. | 3 documents | Gloria |
| 11/26/98 | David Saiget | USFS, Alaska | 3 documents | Gloria |
| 11/28/98 | Paul Winkle | Chadwick Ecological Consultants | 2 documents | Gloria |
| 11/28/98 | Dr. Andrea Buffagni | Instituto di Ricerca sulle Acque, Italy | document | Gloria |
| 11/28/98 | Dr. M.S.M. Siddeck, Ph.D. | Sultan Qaboos University | document | Gloria |
| 12/4/98 | Prof. Ana Beatriz Prieto | Dept de Cap y Trans del C.E.A.N., Argentina | document | Gloria |
| 12/10/98 | Gretta Siegel | CRITFC | document | Gloria |
| 12/13/98 | Mike Sanchez | PEAK | 5 documents | Gloria |
| 12/16/98 | Andrew Murdock | WDF, Wenatche, WA | document | Gloria |
| 12/29/98 | Beth Sanches | USFW, Crescent R.D. | 5 documents | Gloria |
| 12/29/98 | Chris Brennan | CTWSF, Dept. F & W Natural Resources | 3 documents | Gloria |
| 12/30/98 | ? | AQUAPROGRAM S.R.S, Italy | document | Gloria |

StreamNet GIS Data Downloads off the ODFW FTP Server

| GIS Coverages | Number of Files Downloaded | Number of Different Users Downloading Files |
| --- | --- | --- |
| Routed Streams | 229 | 19 |
| Fall Chinook | 29 | 6 |
| Spring Chinook | 29 | 3 |
| Chum | 8 | 2 |
| Coho | 36 | 6 |
| Winter Steelhead | 28 | 6 |
| Summer Steelhead | 27 | 5 |
| Coastal Salmon Plan Core Areas | 741 | 324 |
| Oregon Rivers Information System | 367 | 63 |

V.  Pacific States Marine Fisheries Commission

PERIOD HIGHLIGHTS

Data Development

Reviewed the status of all data development tasks with project participants.

Prepared a data plan for FY 99, including the identification of targets for each data type and participating organization.

Prepared an online version of the Fish and Wildlife Program Annual Implementation Work Plan.

Data Management

Completed data porting, application development, and testing for 3 all new Internet query systems; Data, Reference, and Map

Continued update and maintenance for the StreamNet web site.

Incorporated major data updates from Idaho.

Completed preliminary work on regional anadromous distribution coverages.

Prepared an updated description of StreamNet data holdings and an updated data dictionary.

Ported existing StreamNet data to the NT server for use on the StreamNet web site.

Revised the StreamNet data holdings document.

Revised the StreamNet data exchange format document.

Library/Reference System

Assisted CRITFC in preparing for the library open house, including editing of the library brochure and policy guidelines.

Worked with CRITFC to create a n updated version of the library query system.

River Reach System

Error checked and revised the 100K river reach system for the state of Washington.   Reviewed progress in other states, including supplying directions to state teams on protocol for completing their tasks.

Maintained contact with regional river reach system users including the USFS, BLM, and states, in order to ensure compatibility of efforts.

Maintained frequent contact with the national NHD team.

Monitored progress of ODFW’s efforts on conducting the visual pass of 100K hydrography for the state of Montana.

Maintained and revised the StreamNet 100K web site feature.

Data Delivery

Introduced a new graphic interface for the StreamNet home page, including new visuals, new button bar, and new layout.

Updated the StreamNet map catalog by deleting unnecessary or redundant maps and adding new ones.

Prepared and refined a test version of a new data query system, having data, map, and library reference components.

Added 6 sites to the related links section of the home page.

Edited the text of the StreamNet home page.

Enhanced the education portion of the StreamNet home page, including the addition of virtual photo tours, a kids pics feature, an ocean conditions links page, and an interactive life history feature.

Added approximately 20 terms to the fish resource glossary.

Maintained and revised the project management section to the home page.

Monitored use of the StreamNet web site (summary attached).

Responded to all web site “feedback” comments within 24 hours of receipt.

Prepared a list of StreamNet home page enhancement ideas and identified priorities for future home page improvements.

Responded to data requests (attached)

Project Management

Prepared and submitted a final version of the FY 98 work statement.

Prepared an updated version of the StreamNet brochure.

Met individually with the following sub-contractors to monitor progress in both data development and expenditure of funds: ODFW, IDFG, WDFW and CRITFC.

Held coordination meetings with NWPPC staff and the IRRIC hydro/fish team.

Scheduled and held the October Steering Committee meeting.

Made contact with project coordinators via telephone on at least a weekly basis.

Reviewed sub-contractor invoices and prepared BPA invoices.

Coordinated with BPA on administrative matters relevant to StreamNet.

PLANS FOR NEXT QUARTER

Data Development

Coordinate data development by participating agencies.

Data Management

Incorporate new data as received from participating agencies.

Library

Provide direction to library staff regarding library use policies and other appropriate issues.

Cooperate with library staff in updating source references.

Assist library staff in completing transfer of the NWPPC collection.

River Reach System

Consolidate Idaho and Oregon PNW files, error check and integrate into the regional system.

Data Delivery

Release the new online data query system.

Respond to requests for data and data services as needed.

Project Management

Prepare for a winter steering committee meeting.

Continue to monitor project progress, including overseeing work of subcontractors.

Continue to monitor Fish and Wildlife Program-related activities and reports in order to identify links with these activities.

Prepare the FY 98 project description.

DATA REQUESTS / RESPONSE LOG

Data Requests

| Name | Organization | Request | Date Requested | Data Delivered |
| --- | --- | --- | --- | --- |

Hileman

| Jim | Environmental Protection Agency | Temperature data from Aspen Database (jim.zip) | 10/28/97 | 10/28/97 |
| --- | --- | --- | --- | --- |

Frasier

| Pat | Oregon Department of Fish and Wildlife | Upwelling Data Request | 11/17/97 | 11/14/97 |
| --- | --- | --- | --- | --- |

Becker

| Westin | Water Resources Department | steelhead images | 11/18/97 | 11/18/97 |
| --- | --- | --- | --- | --- |

Williams

| Ted | S.P. Cramer & Associates, Inc. | SDM data for Steelhead in lower columbia - Williams.DB | 11/20/97 | 11/20/97 |
| --- | --- | --- | --- | --- |

Sasser

| Stephen | Northwest Power Planning Council | hard copy maps of subbasins used in project prioritization | 11/25/97 | 12/3/97 |
| --- | --- | --- | --- | --- |

Malin

| Debra | Bonneville Power Administration |
| --- | --- |

Anadromous presence at selected dams, and status of fish passage facilities - file

|  | 11/26/97 | 12/5/97 |
| --- | --- | --- |

Harrison

| John | Northwest Power Planning Council | Total hatchery releases for Mitchell Act Hatcheries | 12/15/97 | 12/15/97 |
| --- | --- | --- | --- | --- |

Welter

| Jim | Oregon South Coast Fishermen | Total coastal coho hatchery releases from ODFW hatcheries | 12/15/97 | 12/15/97 |
| --- | --- | --- | --- | --- |

Arthaud

| David | Unknown | Smolt production values for various drainages in the Salmon Basin | 12/29/97 | 12/30/97 |
| --- | --- | --- | --- | --- |

StreamNet Online Query System Access

| Month | Web Page - Avg Files Delivered Daily | Web Page - Avg mb Delivered Daily | Query System Requests | Reference System Requests | Map System Requests |
| --- | --- | --- | --- | --- | --- |
|  | Oct | 2,408 | 16.2 | 1,859 | 351 | 1,425 |
| Nov | 1,787 | 14.5 | 2,377 | 553 | 2,202 |
| Dec | 1,316 | 11.1 | 2,988 | 405 | 1,298 |

Technical Summary of Web Site Use

Month 		Category			MB 			# of Files

10 		Fish Facts 			70.996493 		3

10 		Maps 				205.784442 		448

10 		NWPPC Project Data 		21.297539 		15

10 		Project Management Files 	13.058571 		92

10 		Reach Files 			668.079761 		192

11 		Fish Facts 			45.668994 		56

11 		Maps 				206.633638 		483

11 		NWPPC Project Data 		4.245115 		4

11 		Project Management Files 	8.917413 		42

11 		Reach Files 			671.7357729 		963

12 		Fish Facts 			47.147621 		79

12 		Maps 				268.386345 		760

12 		NWPPC Project Data 		0.40046 		5

12 		Project Management Files 	25.253393 		37

12 		Reach Files 			367.65086 		402

VI.  Shoshone-Bannock Tribes

PERIOD HIGHLIGHTS

Reviewed and commented on new additions that are planned for release on the StreamNet web site.

Interviewed University of Idaho geneticists about incorporating their data with ours.

PLANS FOR NEXT QUARTER

Continue pursuing genetic information.  My goal for this sub-project is to recommend what types of data we will be able to use with members at the next Steering Committee in order to discuss how we can devise a data transfer protocol to incorporate available genetic information.

DATA REQUESTS / RESPONSE LOG

No requests were received during this quarter.  However, I assisted other biologist in retrieving information from our web site.

VII.  U.S. Fish and Wildlife Service

PERIOD HIGHLIGHTS

Coordinated delivery of hatchery data from federal hatcheries to StreamNet, including cooperating with IDFG in reviewing data delivery issues concerning hatcheries in that state.

Attended StreamNet steering committee meeting in Boise.

PLANS FOR NEXT QUARTER

Attend Steering Committee meeting in Gladstone.

DATA REQUESTS / RESPONSE LOG

There were no data requests filled by the USFWS during the quarter.

VIII.  Washington Department of Fish and Wildlife

PERIOD HIGHLIGHTS

General

At the start of this new year, we had some personnel and work assignment changes. Bill Kinney joins Dick O’Connor in a management role over day-to-day StreamNet activities at WDFW. Brodie Cox and Holly Ballantyne have left the project for other assignments and school, respectively. Responsibility for statewide hatchery returns data was re-assigned to headquarters staff (Leslie Sikora and Sarah Nielsen), while statewide natural spawner data will now be handled by Region 5 staff (Bob Woodard).

Leslie joined Dick at the kick-off Steering Committee meeting in Boise October 14-15 where we shared progress on various data and coordination tasks. Dick later met with project staff from the Joint Kalispell Stock Assessment project in Spokane, in order to assist them in their plans so that the data they collect will be easy to exchange with StreamNet. We held several telephone discussions aimed at coordinating work on the regional 100K river reach files and routes, based on differences between the Washington layers currently used by WDFW and PSMFC. Martin Hudson and his PSMFC counterpart Matt Fried have gotten together to discuss differences and are pursuing ways to merge their products into a single layer for the region to use.

Some WDFW biologists working in Region 3 (Yakima area) discovered the StreamNet project and sent Leslie some historical steelhead returns and harvest information. Some of these data are maintained by Yakama tribal staff, so we have a coordination challenge to address as we try to determine the most appropriate division of labor here between WDFW data compilers, Yakama tribal data compilers, and CRITFC compilers who coordinate work by individual tribes. Initial contacts have been positive, and we’re confident a plan can be set in place during this project period.

Database Development

Tabular.

Columbia Basin salmon hatchery returns data are now complete through 1996, as are Columbia Basin salmon and steelhead natural spawner data. Columbia Basin steelhead returns need to be converted to version 11 of our internal format before exchange, and the rest of the returns (statewide) need to be compared to the NMFS statewide historical file before conversion. Work continued on expanding the redd count database to allow exchange of raw adult survey data from the Columbia Basin, with eventual addition of the coastal Washington and Puget Sound survey data. Gamefish hatchery release data prior to 1983 is being entered to complement the work on truthing and converting the 1983-1994 historical release file. Initial assessment indicates that 25% of the steelhead release records in the 1983-1994 file do not match corresponding records in the PSMFC historical CWT release database, so we are turning to paper records to identify and fix the incorrect data. This part of compiling has taken much longer than anticipated due to the extent of the discrepancies and no clear official version to use as a benchmark for comparison.

Spatial.

Work to reconcile the spawning extent of SaSI stocks with recently updated spawning data compiled by species continues, as we can arrange time for fish biologists to review the maps. Older resident fish data compiled under the old NED project have been converted to modern format and have been transferred into the newer event tables to allow for display of both resident and anadromous fish data on the same 100K layer. Design and construction of a database for lakes began, in order to be able to identify all water bodies linked to the route of anadromous fish, as well as provide useful features to link resident fish data to in the future, if that becomes a project priority.

Systems Development

Tabular.

A pilot system for allowing local area network-based review and reporting of summary data destined for StreamNet exchange was developed and testing began. It is hoped that this will develop into a tool to ease interaction with the fish data experts in our Program so that the quality of data we compile for exchange can be reviewed before we convert and send it out. It also will provide access to Washington StreamNet data for those who do not yet have adequate hardware to browse the StreamNet Online Web site. A good deal of time was spent mapping internal (PSC-format) codes for locations, hatchery sites, and stocks to codes used in older historical databases to support StreamNet data conversion across all data categories. Cross-reference tables have been updated for this purpose. A small tool to convert hatchery returns data from WDFW new Form5" format to exchange format was built and shared with all data compilers.

Spatial.

Data dictionaries and data tracking tables were built for the StreamNet spatial data tables in order to assist users who need to know about the new organization of data. The programs that build tabular datasets from point coverages were improved to increase quality in the data locations captured. Tools were built to check and correct routes in the 100K reach files. By the end of this quarter, all HUC files had been checked and corrected, and data transfer to the corrected reach files had begun. Martin also built a series of routines to allow easy display, entry, and transfer of data related to lakes of Washington, in order to complete a task begun a few years ago under the NED project.

PLANS FOR NEXT QUARTER

Complete compilation of steelhead hatchery release/return data.

Complete digital coverage for bull trout.

Prepare StreamNet display for WDFW conference.

Prepare 100K coverage for shipment to region.

Participate in state-level river reach system activities (state framework group, USFS 24K development, etc.)

Visual pass of 100K will be postponed pending release of necessary materials by NHD.

DATA REQUEST/RESPONSE LOG

WDFW StreamNet staff record both spatial data and tabular data requests in a similar format. The cooperation of Habitat Management Program staff was instrumental to both compilation and standardization of information concerning spatial data requests, or "data releases". The table on the following pages (Appendix A) summarizes the people who requested data, the type of information they needed, and the date the information was delivered as part of the StreamNet project during this project reporting period. There were 156 data requests fulfilled during this time period, most of which were spatial data requests (generally maps and digital data).

We note that ftp provision of data continues to increase, as users find electronic transmission of data quicker and more convenient than the standard method of exchanging tape cartridges.

Requestor

Organization

Data Requested

Date Delivered

Marty Garman

WA Dept Of Transportation Olympic

Project no mc5420 SR 109 milepost 10.36 - 10.74

10/01/1997

Melissa Chaun

Michael P. Williams Consulting

Dickman Mill and Pritchard Reserve projects

10/01/1997

Wendy Schmidt

Okanogan County Dept Of Public Works

Proposed county road project in T33 R22E in Okanogan County

10/01/1997

Adam Escalona

Adapt Engineering Inc.

Proposed bridge construction T24N R07E Sec 6

10/07/1997

Ed Sewall

B-Twelve Associates Inc.

Proposed short plat-Erwin short plat #97-145

10/07/1997

John Hawksworth

SP Cramer and Associates

Development of a steelhead restoration plan for the Lower Ccolumbia ESU

10/07/1997

Nancy M. Thompson

WA Dept Of Transportation North

Proposed hwy construction project l-3119 Ruby Cr. vicinity

10/07/1997

Nancy M. Thompson

WA Dept Of Transportation North

Proposed hwy construction projects on SR 90 and SR 97

10/07/1997

Stephanie Allen

Pentec Environmental

PSE pipeline construction project # 333-002

10/07/1997

Ed Sewall

B-Twelve Associates Inc.

Proposed short plat-Finkbeiner/Keller 97-106

10/08/1997

Marti Louther

Adolfson Associates Inc.

Habitat study for a residential development in King County

10/08/1997

Bradford Shea

Westech Co.

To prepare environmental documents for US Navy contract

10/09/1997

Gregory M. Poels

Shannon & Wilson Inc.

United Homes of Renton proposed purchase of 12-acres site near Lk. Sammamish

10/09/1997

Kent Lien

Golder Associates Ltd.

Assessment of watercourses crossed by the Yellowstone Pipeline Company

10/09/1997

Nathan Pate

Whitman County Dept Of Public Works

Proposed residential development by Carl Quist within T15N R46E Section 6

10/10/1997

Thomas J. Cammarata

ATC Environmental Inc.

IAC wetlands delineation and rating

10/10/1997

Jim Dougherty

FEMA Region 10 Hazard Mitigation

Proposed Glenwood flood diversion project

10/13/1997

Michelle Dewey

Seattle City Light

Preparation of SEPA

10/14/1997

Marty Garman

WA Dept Of Transportation Olympic

State route 167 mp 9.06 - 10.19 project no ol-2082

10/15/1997

Matt Bennett

The Coot Company

Proposed city-owned stormwater detention facility

10/15/1997

Michael J. Rickel

Pacific International Engineer

SEPA for construction of a marina in Douglas County T20 R22E Section 13

10/15/1997

Nathan Pate

Whitman County Dept Of Public Works

Delbert Moore short plat T18N R44E Section 32

10/15/1997

Marty Garman

WA Dept Of Transportation Olympic

Coo583a, SR5 Pacific Ave i/c seismic retrofit mp 133.33 - 134.11

10/16/1997

Regina Simon

Public Request

Move homestead house to new location T18 R42E Section 36

10/16/1997

Scott Sissons

Apex Engineering

Bald Hill large lot file#25581/1

10/16/1997

Ed Bowlby

Olympic Coast Natl Marine Sanctuary

Use digital data to monitor coastal resources and management purposes

10/20/1997

Mike Marshall

Gibbs & Olson Inc.

Pe Ell and Toutle general sewer plans

10/20/1997

Peter C. Blansett

SA Newman Forest Engineers Inc.

Appraisal services

10/20/1997

Crilly R. Ritz

Snohomish County Public Works

SEPA/EIS for road corridor study in Granite Falls area in Snohomish County

10/22/1997

Kathleen Stephanick

Anchor Environmental

Simpson timber SEPA for the Goldsborough Cr. restoration project

10/22/1997

Kirsten Krueger

The ERC Group

City of Issaquah Pickering Reach improvements

10/22/1997

Randy Edwards

Pacific Groundwater Group

Stream/groundwater studies for Clark Public Utilities

10/22/1997

John S. Fleming

Polaris Engineering & Surveying

To evaluate property for potential purchaser within T29N R4W Sec 3,4,5,9,10

10/23/1997

Keitlyn Watson

Stevens County Conservation Div.

Provide PHS data to local school children in Stevens County

10/23/1997

Kathleen Neely

NOAA National Marine Fisheries Service

Statewide StreamNet digital data for mapping essential fish habitat

10/24/1997

Katie Walter

Shannon & Wilson Inc.

Yakima Training Center clean up site project # t-4118-05

10/24/1997

Laura Techico

WA Dept Of Transportation South

SR 90 Cabin Creek vic unstable slope

10/24/1997

Suzanne Dolberg

Ecology & Environment

Site assessments for EPA at four locations in the Port Angeles area

10/24/1997

Frederick L. Huston Jr.

Beak Consultants Inc.

Water right SEPA for Snohomish River Regional Water Authority

10/30/1997

Gary R. Beeman

WA Dept Of Transportation South

WR 970 Teanaway Tiver vicinity bridge 970/10

10/31/1997

John Gold

John Gold & Company Consulting

Preparing forest land management plans for land owners

11/04/1997

Theresa Henson

Natural Resource Consulting

Potential development of property by owner within T23 R07E Section 23

11/04/1997

Theresa Henson

Natural Resource Consulting

Potential development of property by owner within T23N R08E Sections 13, 24

11/04/1997

Gary R. Beeman

WA Dept Of Transportation South

SR 90 Cabin Creek vic. unstable slope-project revision

11/05/1997

Jack Dinniene

Northwest Valuation Services

Property appraisal for WDFW

11/05/1997

Jim Dougherty

FEMA Region 10 Hazard Mitigation

Glenwood flood diversion project-revised

11/05/1997

Marty Garman

WA Dept Of Transportation Olympic

SR16 road widening at Anderson Hill Road project no ol-3212

11/05/1997

Marty Garman

WA Dept Of Transportation Olympic

SR3 mp 3.65 to mp 8.96 Shelton ECL to Agate Road project no ol-3181

11/05/1997

Michael J. Rickel

Pacific International Engineer

Blair Waterway channel deepening

11/05/1997

Steven Yach

WA Dept Of Transportation East

SR20/SR395 to Laundry Road

11/05/1997

Calvin Kelly Douglas

Shapiro And Associates Inc.

SEPA EIS for a proposed new arterial called the North Spar

11/12/1997

Chris Snapp

Green Crow

SEPA within T21 R14E Section 34

11/12/1997

Dale Morimoto

WA Dept Of Transportation North

SR 525 Maxwelton Road to Honeymood Road

11/12/1997

John Altmann

Talasaea Consultants

Land owner proposed development within T28N R04E Section 24

11/12/1997

Linda Foster

Ecology And Environment Inc.

EPA Region X CERCLA

11/12/1997

Rich Schumaker

Stevens County Conservation Div.

Jumpoff Joe watershed management plan

11/12/1997

Tim Young

US Fish And Wildlife Service

StreamNet digital data base

11/12/1997

William Kombel

Palmer Coking Coal Company

Permits for a gravel extraction operation within T21N R07E Section 30

11/12/1997

Debra Bouchard

Envirovision

Integrated aquatic vegetation mgt plan for Lake McMurray in Skagit County

11/14/1997

Joetta Zablotney

R2 Resource Consultants

Environmental studies for land owner

11/14/1997

Tom Angus

Ecology And Environment Inc.

Oeser Cedar site risk assessment for EPA

11/14/1997

Lynn Sharp

Woodward-Clyde Consultants

Skagit Co PUD No. 1 Judy Reservoir proposed dam raise

11/17/1997

Melissa K. Cohen

Wetland rating for property within Golden Gardens park

11/17/1997

Rick Spaulding

Ogden Environmental And Energy

EA for the WA Air National Guard at Fairchild AFB in Spokane

11/17/1997

Stacey M. Wenger

Adolfson Associates Inc.

Proposed Cowlitz Co. road widening along old Pacific Hwy

11/17/1997

Susan M. Callan

FEMA Region 10 Hazard Mitigation

Mineral Cr hazard mitigation project in Lewis Co.

11/17/1997

Andrea Escame-Hedger

King County Road Services Div.

SEPA for various projects

11/19/1997

Bertie Weddell

Draba

Proposed replacement of elevator scale within T18 R43E Section 15

11/19/1997

Marty Garman

WA Dept Of Transportation Olympic

Ol 2759 SR 510 Bingo Hall vicinity

11/19/1997

Marty Garman

WA Dept Of Transportation Olympic

Ol 3196 SR 101/107 intersection

11/19/1997

Nathan Pate

Whitman County Dept Of Public Works

Residence construction by Roger and Robert McKirnan within T14N R44E Sec 16

11/19/1997

Peter C. Blansett

SA Newman Forest Engineers Inc.

Land appraisal for Crown Pacific and others

11/19/1997

Steven Yach

WA Dept Of Transportation East

Lords Valley Cr. rechannelization within T22 R37 Section 26

11/19/1997

Sue Burgermeister

B-Twelve Associates Inc.

Permitting of residential development South Corp. job # 97-130

11/19/1997

Theresa R. Henson

Natural Resource Consulting

Wildlife survey for property owner prior to potential development

11/19/1997

Will Keller

US Natural Resources Conservancy

Jobs for the environment grant application for sites in Okanogan/Methow

11/19/1997

David Rolph

The Nature Conservancy

PHS, Heritage and Marbled Murrelet digital data

11/21/1997

Ed Sewall

B-Twelve Associates Inc.

Parking lot expansion within T21 R04E Section 28

11/21/1997

Greg Poels

Shannon & Wilson Inc.

BA for clean up of contaminants on site for Ft. Lewis training facility

11/21/1997

John Altmann

Talasaea Consultants

Proposed land owner development within T27 R05E Sec 29

11/21/1997

Victoria Luiting

Raedeke Associates Inc.

Lonestar Quarry at Maury Is. # 97059

11/21/1997

Ben Klein

WA Dept Of Transportation Room

Planning for pile driving projects

11/26/1997

Dan Wiren

Green River Community College

PHS and HRTG digital data for Kittitas County

11/26/1997

Dr Frank Westerlund

UW Dept Of Urban Design And Planning

HRTG and StreamNet digital data for Spokane County coop project

11/26/1997

Jessica Escow

Champion Pacific Timberlands Inc.

PHS, HRTG digital data for Champion Pacific Timberlands

11/26/1997

Mark Mower

Green River Community College

Old growth digital data for Mt. Rainier National Park

11/26/1997

Matthew Boyle

Parametrix Inc.

Hazard waste cleanup environmental reports for City of Seattle

11/26/1997

W. Nicholas Beer

UW Columbia Basin Research

Statewide StreamNet digital data

11/26/1997

Catherine Conolly

Adolfson Associates Inc.

Port of Tacoma environmental documentation

12/01/1997

Dana Heller

Michael P. Williams Consulting

Pierce Co. Parks and Rec. proposed multi-use trail in the Carbon R. drainage

12/01/1997

David Lee

National Park Service Denver

Management plan and EIS for Ft. Vancouver Nat. Historic Reserve

12/01/1997

John Gold

John Gold & Company Consulting

Appraisals and management plans for property owners

12/01/1997

Marti Louther

Adolfson Associates Inc.

Habitat survey for proposed development

12/01/1997

Melanie Carpenter

ENSR Consulting And Engineering

SEPA review for Puget Sound Energy within T24N R07E

12/01/1997

Nancy M. Thompson

WA Dept Of Transportation North

Icicle Spillway slide repair l-3243 SR2 mp 101 T24N R18E Section 7

12/01/1997

Joseph Arnett

Foster Wheeler Environmental

SEPA review for proposed golf resort at Bear Mtn. Ranch

12/02/1997

Adam E. Escalona

Adapt Engineering Inc.

NEPA checklist for proposed cellular tower within T21N R05W Sect 8

12/04/1997

Bruce Maclearnsberry

Maclearnsberry Engineers

Short plat within T25 R02E Section 29

12/04/1997

Cliff Palmer

Wetlands Resources Inc.

Wildlife study for proposed land owner development site

12/04/1997

Darrel Erfle

Jefferson County Dept Of Public Works

Jobs for the environment grant application

12/04/1997

Don E. Wyll

ERM-West Inc.

Wetlands rating information for potential land owner

12/04/1997

Joseph Arnett

Foster Wheeler Environmental

Environmental Assessment for the Makah Tribe Forest Mgt. Plan

12/04/1997

Micheleen O=Neill

Evergreen State College

Research project for college within T16N R04W Section 30 and 31

12/04/1997

Nathan Pate

Whitman County Dept Of Public Works

Short plat for land owners Don and Cheryl Smith within T14N R46E Section 17

12/04/1997

Priscilla Zieber

Emcom

Proj# 40358-016.004 remedial investigation for site within T09N R28E Sect 11

12/04/1997

Sarah Cassatt

Jones & Stokes Associates Inc.

Environmental reviews for the city of Sultan Sewer Ltd project

12/04/1997

Steve Yarbrough

CC Johnson & Malhofra PC

Environmental site assessment for US BLM

12/04/1997

Linda Krippner

Dames & Moore

Olympic pipeline project HRTG and PHS digital data

12/09/1997

James Hirsch

Pacificorp

Updated PHS, HRTG and spotted owl digital data for Lewis River watershed

12/10/1997

John Keates

City Of Enumclaw

PHS map for city of Enumclaw

12/10/1997

Marty Garman

WA Dept Of Transportation Olympic

Widening of SR510 between I5 and Pacific Avenue project ol-2497

12/10/1997

Matthew Boyle

Parametrix Inc.

Environmental reports for the RTA Everett to Seattle commuter rail project

12/10/1997

Nikolina Yonkow

Adolfson Associates Inc.

PHS data for government agency

12/10/1997

Peter C. Blansett

SA Newman Forest Engineers Inc.

Appraisial for WDFW

12/10/1997

Eric Doyle

NOAA National Marine Fisheries

Digital HUC, WRIA and state boundaries

12/11/1997

Dale Morimoto

WA Dept Of Transportation North

SR525, SR99 to SR526 132nd to Paine Field Blvd widening

12/12/1997

Donald K. Wills II

WA Dept Of Transportation North

SR 161 Jovita Blvd to S 369th St widening project mp 32.09 to mp 34.12

12/12/1997

Gail S. Brooks

Berger/Abam Engineers Inc.

Treemont residential subdivision EIS

12/12/1997

Margaret Spence

Parametrix Inc.

Proposed aerial tramway within the Olympic National Forest

12/12/1997

Nikolina Yonkow

Adolfson Associates Inc.

PHS data for government agency

12/12/1997

Steven Yach

WA Dept Of Transportation East

SR 31 bridge 31/36 and bridge 31/42 painting

12/12/1997

Steven Yach

WA Dept Of Transportation East

SR 395 north corridor channelization

12/12/1997

Tom Ehrlichman

Law Offices Of Tom Ehrlichman

Map of N. Lake Washington

12/12/1997

Heidi Reynolds

Snohomish County Public Works

Aquatic plant management plan for Lake Shoecraft

12/15/1997

Jerry Erickson

Beak Consultants Inc.

Proposed barge loading facility on the Duwamish waterway

12/15/1997

Marty Garman

WA Dept Of Transportation Olympic

Project ol-3198 paving SR307 between SR305 (Bond Rd) and SR104

12/15/1997

Peter Carr

Edaw Inc.

Feasibility study for the Calvinwood/Square Lake/McCormick Lake project

12/15/1997

Jessica Roque

WA Wetlands And Mitigation Co.

David Moore property within T36N R04E Sec 27

12/16/1997

Jessica Roque

WA Wetlands And Mitigation Co.

Wetland delineation for Murray property within T34N R05E Sec 30

12/16/1997

Alana Hess

WA State Parks And Recreation

Sequim Bay State Park project

12/18/1997

Debby Howe

Howe Consulting Inc.

Proposed Okanogan Co. PUD transmission line between Twisp and Pateros

12/18/1997

Janel London

King County Road Services Div.

SEPA review for Juanita Drive NE at NE 122nd Pl and 76th Pl NE

12/18/1997

Linda Newberry

Jamestown S'Klallam Tribe

Application for state IAC riparian protection grant with Clallam Cons. Dist.

12/18/1997

Pat Bahor

King County Road Services Div.

SEPA review for temporary storage and permanent fill site - Krain

12/18/1997

Thomas R. Strong Ph.D.

Terra Associates Inc.

Proposed residential development on the Sammamish plateau

12/18/1997

Tyler Patterson

USDA Forest Service

Watershed analysis in Puyallup basin

12/18/1997

Bill Wettengel

USFS Olympic National Forest

Digital StreamNet for Washington

12/23/1997

Chad H. Phillips

WA Dept Of Agriculture Lab

Three proposed treatment areas for gypsy moth eradication projects

12/23/1997

Holly Barnard

Trust For Public Land

Aid in identification of land with high conservation priority

12/23/1997

Jim Stephenson

Yakima Indian Nation

Digital data for ceded lands as well as the land under contract in TFW

12/23/1997

Liz Kriewald

WA Dept Of Transportation North

SR 530 mp 21.78 to mp 29.43 Stillaguamish River Br. 530/120 to 170th Ave.

12/23/1997

Margaret Clark

UXB International Inc.

Assessment and remediation at Camp Bonneville for US Army Corps of Eng.

12/23/1997

Michael M. Pollock

10,000 Years Institute

Digital StreamNet for the Willapa basin

12/23/1997

Teresa Vanderburg

Adolfson Associates Inc.

Proposed expansion of Cedar Creek Corrections Center

12/23/1997

Brady Engvall

Friends Of Grays Harbor

Permit review for Stafford Creek Correctional Center

12/25/1997

Ann Blakley

WDFW

Columbia River map of the four states

10/15/1997

Chris Mendoza

Aquatic Restoration Consultant

Anad. fish in Chehalis River basin

10/15/1997

Clark County

Clark County

Digital Tape of Statewide Steelhead info

10/15/1997

David Johnson

WDFW

general selection of available maps

10/15/1997

Steve Phelps

WDFW

Ringold Pond releases, returns & sport catch in the area

10/22/1997

Mike Malone

Private citizen

November Steelhead catch - Grande Ronde R.

10/28/1997

Betsy Reynolds

Northwest Renewable Resource

Three County maps of Fall Chinook

11/15/1997